## Budget Tower-E (hidden)
OMAXE AANANDA, ALLAHABAD
SUMMARY OF COST OF CIVIL WORK
S.No. | Description of Items | Amount (Rs.) | COST PER SQFT
|  |  | 259280 | Salable Area
A | BUILDING WORK
I. | EARTH WORK & P.C.C. | 4667040 | 18
II. | R.C.C. | 53152400 | 205
III. | SHUTTERING | 16075360 | 62
IV. | STEEL REINFORCEMENT | 84266000 | 325
V. | BRICK WORK | 29817200 | 115
VI | WOOD WORK | 32410000 | 125
VII. | STEEL WORK | 4634291.3217 | 17.8737
VIII. | FLOORING | 30595040 | 118
IX. | ROOFING | 1555680 | 6
X. | FINISHING | 45374000 | 175
XI | SPECIAL FEATURES (AC, Gyser, RO, Modular Kitchen, Dish Washer, Cup board, Home Theater) | 66327503.424 | 255.8142
XII. | MISCELLANEOUS | 2312777.6 | 8.92
XIII. | ENTRY AND ELEVATION | 7778400 | 30
| TOTAL OF CIVIL WORK Rs. = | 378965692.3457 | 1461.6079
B | OTHER WORK
I. | INTERNAL ELECTRICAL | 18149600 | 70
II. | PLUMBING WORK | 18149600 | 70
III. | LIFT | 12964000 | 50
IV. | EXTERNAL DEVELOPMENT | 12964000 | 50
V. | FIRE FIGHTING | 7778400 | 30
VI. | MECHANICAL VENT | 0 | 0
VII. | CLUB | 12964000 | 50
| TOTAL AMOUNT | 82969600 | 320
C | EXTERNAL DEVELOPMENT
a | ROAD WORK |  | 0
0
b | SEWER AND STORM LINE WORK |  | 0
0
c | UGT |  | 0
0
d | STP |  | 0
0
e | BOUNDARY WALL |  | 0
0
f | DG/LT/PANEL ROOM |  | 0
0
g | MAIN GATE |  | 0
0
h | WATER BODY/PATHWAYS/GUARD WALL/HARVESTING/HORTICULTURE/INTERNAL BOUNDARY/MISCELLANEOUS WORK |  | 0
0
i | WATER SUPPLY WORK |  | 0
0
j | EXTERNAL ELECTRIFICATION |  | 0
| TOATL AMOUNT (EXTERNAL DEVELOPMENT) | 0 | 0
| TOTAL(A+B) = (WITH OUT ESCALATION) | 461935292.3457
C | EXTRA PARKINGS FOR ANANDA(Basement+Ground) | 92610518
| GROSS TOTAL(A+B+C) | 554545810.3457 | 2138.7913 | Per sqft

## Schedule-Tower-E (hidden)
Tower-E Estimated Budget |  |  | Schedule of Work
S.No. | Description | Amount | Months
A | Building Work | time axis 2024-11-23 to 2028-07-23
1 | Earthwork & PCC (including other works over existing structure) | 4667040 | 2024-11-23: 933408; 2024-12-23: 933408; 2025-01-23: 933408; 2025-02-23: 933408; 2025-03-23: 933408 | 4667040
2 | RCC | 53152400 | 2025-01-23: 3126611.7647; 2025-02-23: 3126611.7647; 2025-03-23: 3126611.7647; 2025-04-23: 3126611.7647; 2025-05-23: 3126611.7647; 2025-06-23: 3126611.7647; 2025-07-23: 3126611.7647; 2025-08-23: 3126611.7647; 2025-09-23: 3126611.7647; 2025-10-23: 3126611.7647; 2025-11-23: 3126611.7647; 2025-12-23: 3126611.7647; 2026-01-23: 3126611.7647; 2026-02-23: 3126611.7647; 2026-03-23: 3126611.7647; 2026-04-23: 3126611.7647; 2026-05-23: 3126611.7647 | 53152400
3 | Shuttering | 16075360 | 2025-01-23: 945609.4118; 2025-02-23: 945609.4118; 2025-03-23: 945609.4118; 2025-04-23: 945609.4118; 2025-05-23: 945609.4118; 2025-06-23: 945609.4118; 2025-07-23: 945609.4118; 2025-08-23: 945609.4118; 2025-09-23: 945609.4118; 2025-10-23: 945609.4118; 2025-11-23: 945609.4118; 2025-12-23: 945609.4118; 2026-01-23: 945609.4118; 2026-02-23: 945609.4118; 2026-03-23: 945609.4118; 2026-04-23: 945609.4118; 2026-05-23: 945609.4118 | 16075360
4 | Steel | 84266000 | 2025-01-23: 4956823.5294; 2025-02-23: 4956823.5294; 2025-03-23: 4956823.5294; 2025-04-23: 4956823.5294; 2025-05-23: 4956823.5294; 2025-06-23: 4956823.5294; 2025-07-23: 4956823.5294; 2025-08-23: 4956823.5294; 2025-09-23: 4956823.5294; 2025-10-23: 4956823.5294; 2025-11-23: 4956823.5294; 2025-12-23: 4956823.5294; 2026-01-23: 4956823.5294; 2026-02-23: 4956823.5294; 2026-03-23: 4956823.5294; 2026-04-23: 4956823.5294; 2026-05-23: 4956823.5294 | 84266000
5 | Brickwork | 29817200 | 2025-08-23: 1490860; 2025-09-23: 1490860; 2025-10-23: 1490860; 2025-11-23: 1490860; 2025-12-23: 1490860; 2026-01-23: 1490860; 2026-02-23: 1490860; 2026-03-23: 1490860; 2026-04-23: 1490860; 2026-05-23: 1490860; 2026-06-23: 1490860; 2026-07-23: 1490860; 2026-08-23: 1490860; 2026-09-23: 1490860; 2026-10-23: 1490860; 2026-11-23: 1490860; 2026-12-23: 1490860; 2027-01-23: 1490860; 2027-02-23: 1490860; 2027-03-23: 1490860 | 29817200
6 | UPVC & Woodwork etc. | 32410000 | 2026-09-23: 1543333.3333; 2026-10-23: 1543333.3333; 2026-11-23: 1543333.3333; 2026-12-23: 1543333.3333; 2027-01-23: 1543333.3333; 2027-02-23: 1543333.3333; 2027-03-23: 1543333.3333; 2027-04-23: 1543333.3333; 2027-05-23: 1543333.3333; 2027-06-23: 1543333.3333; 2027-07-23: 1543333.3333; 2027-08-23: 1543333.3333; 2027-09-23: 1543333.3333; 2027-10-23: 1543333.3333; 2027-11-23: 1543333.3333; 2027-12-23: 1543333.3333; 2028-01-23: 1543333.3333; 2028-02-23: 1543333.3333; 2028-03-23: 1543333.3333; 2028-04-23: 1543333.3333; 2028-05-23: 1543333.3333 | 32410000
7 | MS Work | 4634291.3217 | 2026-04-23: 231714.5661; 2026-05-23: 231714.5661; 2026-06-23: 231714.5661; 2026-07-23: 231714.5661; 2026-08-23: 231714.5661; 2026-09-23: 231714.5661; 2026-10-23: 231714.5661; 2026-11-23: 231714.5661; 2026-12-23: 231714.5661; 2027-01-23: 231714.5661; 2027-02-23: 231714.5661; 2027-03-23: 231714.5661; 2027-04-23: 231714.5661; 2027-05-23: 231714.5661; 2027-06-23: 231714.5661; 2027-07-23: 231714.5661; 2027-08-23: 231714.5661; 2027-09-23: 231714.5661; 2027-10-23: 231714.5661; 2027-11-23: 231714.5661 | 4634291.3217
8 | Flooring Work | 30595040 | 2026-07-23: 1223801.6; 2026-08-23: 1223801.6; 2026-09-23: 1223801.6; 2026-10-23: 1223801.6; 2026-11-23: 1223801.6; 2026-12-23: 1223801.6; 2027-01-23: 1223801.6; 2027-02-23: 1223801.6; 2027-03-23: 1223801.6; 2027-04-23: 1223801.6; 2027-05-23: 1223801.6; 2027-06-23: 1223801.6; 2027-07-23: 1223801.6; 2027-08-23: 1223801.6; 2027-09-23: 1223801.6; 2027-10-23: 1223801.6; 2027-11-23: 1223801.6; 2027-12-23: 1223801.6; 2028-01-23: 1223801.6; 2028-02-23: 1223801.6; 2028-03-23: 1223801.6; 2028-04-23: 1223801.6; 2028-05-23: 1223801.6; 2028-06-23: 1223801.6; 2028-07-23: 1223801.6 | 30595040
9 | Roofing Work | 1555680 | 2027-10-23: 388920; 2027-11-23: 388920; 2027-12-23: 388920; 2028-01-23: 388920 | 1555680
10 | Finishing Work | 45374000 | 2026-03-23: 1814960; 2026-04-23: 1814960; 2026-05-23: 1814960; 2026-06-23: 1814960; 2026-07-23: 1814960; 2026-08-23: 1814960; 2026-09-23: 1814960; 2026-10-23: 1814960; 2026-11-23: 1814960; 2026-12-23: 1814960; 2027-01-23: 1814960; 2027-02-23: 1814960; 2027-03-23: 1814960; 2027-04-23: 1814960; 2027-05-23: 1814960; 2027-06-23: 1814960; 2027-07-23: 1814960; 2027-08-23: 1814960; 2027-09-23: 1814960; 2027-10-23: 1814960; 2027-11-23: 1814960; 2027-12-23: 1814960; 2028-01-23: 1814960; 2028-02-23: 1814960; 2028-03-23: 1814960 | 45374000
11 | SPECIAL FEATURES (AC, Gyser, RO, Modular Kitchen, Dish Washer, Cup board, Home Theater) | 66327503.424 | 2026-12-23: 3316375.1712; 2027-01-23: 3316375.1712; 2027-02-23: 3316375.1712; 2027-03-23: 3316375.1712; 2027-04-23: 3316375.1712; 2027-05-23: 3316375.1712; 2027-06-23: 3316375.1712; 2027-07-23: 3316375.1712; 2027-08-23: 3316375.1712; 2027-09-23: 3316375.1712; 2027-10-23: 3316375.1712; 2027-11-23: 3316375.1712; 2027-12-23: 3316375.1712; 2028-01-23: 3316375.1712; 2028-02-23: 3316375.1712; 2028-03-23: 3316375.1712; 2028-04-23: 3316375.1712; 2028-05-23: 3316375.1712; 2028-06-23: 3316375.1712; 2028-07-23: 3316375.1712 | 66327503.424
12 | Miscellaneous | 2312777.6 | 2026-11-23: 289097.2; 2026-12-23: 289097.2; 2027-01-23: 289097.2; 2027-02-23: 289097.2; 2027-03-23: 289097.2; 2027-04-23: 289097.2; 2027-05-23: 289097.2; 2027-06-23: 289097.2; 2028-07-23: 0 | 2312777.6
13 | ENTRY AND ELEVATION | 7778400 | 2026-03-23: 972300; 2026-04-23: 972300; 2026-05-23: 972300; 2026-06-23: 972300; 2026-07-23: 972300; 2026-08-23: 972300; 2026-09-23: 972300; 2026-10-23: 972300 | 7778400
| Total of Civil Work(i) | 378965692.3457 | 933408 | 933408 | 9962452.7059 | 9962452.7059 | 9962452.7059 | 9029044.7059 | 9029044.7059 | 9029044.7059 | 9029044.7059 | 10519904.7059 | 10519904.7059 | 10519904.7059 | 10519904.7059 | 10519904.7059 | 10519904.7059 | 10519904.7059 | 13307164.7059 | 13538879.272 | 13538879.272 | 4509834.5661 | 5733636.1661 | 5733636.1661 | 7276969.4994 | 7276969.4994 | 6593766.6994 | 9910141.8706 | 9910141.8706 | 9910141.8706 | 9910141.8706 | 8419281.8706 | 8419281.8706 | 8419281.8706 | 8130184.6706 | 8130184.6706 | 8130184.6706 | 8519104.6706 | 8519104.6706 | 8287390.1045 | 8287390.1045 | 7898470.1045 | 7898470.1045 | 6083510.1045 | 6083510.1045 | 4540176.7712 | 4540176.7712 | 378965692.3457
|  | 37.8966 | 0.093341 | 0.093341 | 0.99625 | 0.99625 | 0.99625 | 0.9029 | 0.9029 | 0.9029 | 0.9029 | 1.052 | 1.052 | 1.052 | 1.052 | 1.052 | 1.052 | 1.052 | 1.3307 | 1.3539 | 1.3539 | 0.45098 | 0.57336 | 0.57336 | 0.7277 | 0.7277 | 0.65938 | 0.99101 | 0.99101 | 0.99101 | 0.99101 | 0.84193 | 0.84193 | 0.84193 | 0.81302 | 0.81302 | 0.81302 | 0.85191 | 0.85191 | 0.82874 | 0.82874 | 0.78985 | 0.78985 | 0.60835 | 0.60835 | 0.45402 | 0.45402 | 37.8966
B | Other Work
1 | Electrical Work-Internal | 18149600 | 2026-01-23: 725984; 2026-02-23: 725984; 2026-03-23: 725984; 2026-04-23: 725984; 2026-05-23: 725984; 2026-06-23: 725984; 2026-07-23: 725984; 2026-08-23: 725984; 2026-09-23: 725984; 2026-10-23: 725984; 2026-11-23: 725984; 2026-12-23: 725984; 2027-01-23: 725984; 2027-02-23: 725984; 2027-03-23: 725984; 2027-04-23: 725984; 2027-05-23: 725984; 2027-06-23: 725984; 2027-07-23: 725984; 2027-08-23: 725984; 2027-09-23: 725984; 2027-10-23: 725984; 2027-11-23: 725984; 2027-12-23: 725984; 2028-01-23: 725984 | 18149600
2 | Plumbing work- Internal | 18149600 | 2026-06-23: 1209973.3333; 2026-07-23: 1209973.3333; 2026-08-23: 1209973.3333; 2026-09-23: 1209973.3333; 2026-10-23: 1209973.3333; 2026-11-23: 1209973.3333; 2026-12-23: 1209973.3333; 2027-01-23: 1209973.3333; 2027-02-23: 1209973.3333; 2027-03-23: 1209973.3333; 2027-04-23: 1209973.3333; 2027-05-23: 1209973.3333; 2027-06-23: 1209973.3333; 2027-07-23: 1209973.3333; 2027-08-23: 1209973.3333 | 18149600
3 | Fire fighting | 7778400 | 2027-04-23: 972300; 2027-05-23: 972300; 2027-06-23: 972300; 2027-07-23: 972300; 2027-08-23: 972300; 2027-09-23: 972300; 2027-10-23: 972300; 2027-11-23: 972300 | 7778400
4 | Lift | 12964000 | 2027-04-23: 1620500; 2027-05-23: 1620500; 2027-06-23: 1620500; 2027-07-23: 1620500; 2027-08-23: 1620500; 2027-09-23: 1620500; 2027-10-23: 1620500; 2027-11-23: 1620500 | 12964000
5 | External Development | 12964000 | 2026-06-23: 864266.6667; 2026-07-23: 864266.6667; 2026-08-23: 864266.6667; 2026-09-23: 864266.6667; 2026-10-23: 864266.6667; 2026-11-23: 864266.6667; 2026-12-23: 864266.6667; 2027-01-23: 864266.6667; 2027-02-23: 864266.6667; 2027-03-23: 864266.6667; 2027-04-23: 864266.6667; 2027-05-23: 864266.6667; 2027-06-23: 864266.6667; 2027-07-23: 864266.6667; 2027-08-23: 864266.6667 | 12964000
6 | CLUB | 12964000 | 2027-07-23: 1296400; 2027-08-23: 1296400; 2027-09-23: 1296400; 2027-10-23: 1296400; 2027-11-23: 1296400; 2027-12-23: 1296400; 2028-01-23: 1296400; 2028-02-23: 1296400; 2028-03-23: 1296400; 2028-04-23: 1296400
| Total of Other works(ii) | 82969600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 725984 | 725984 | 725984 | 725984 | 725984 | 2800224 | 2800224 | 2800224 | 2800224 | 2800224 | 2800224 | 2800224 | 2800224 | 2800224 | 2800224 | 5393024 | 5393024 | 5393024 | 6689424 | 6689424 | 4615184 | 4615184 | 4615184 | 2022384 | 2022384 | 1296400 | 1296400 | 1296400 | 0 | 0 | 0 | 82969600
|  | 8.297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.072598 | 0.072598 | 0.072598 | 0.072598 | 0.072598 | 0.28002 | 0.28002 | 0.28002 | 0.28002 | 0.28002 | 0.28002 | 0.28002 | 0.28002 | 0.28002 | 0.28002 | 0.5393 | 0.5393 | 0.5393 | 0.66894 | 0.66894 | 0.46152 | 0.46152 | 0.46152 | 0.20224 | 0.20224 | 0.12964 | 0.12964 | 0.12964 | 0 | 0 | 0 | 8.297
C | Extra Parking work(Basement+Ground) | 92610518 | 2025-01-23: 11576314.75; 2025-02-23: 11576314.75; 2025-03-23: 11576314.75; 2025-04-23: 11576314.75; 2025-05-23: 11576314.75; 2025-06-23: 11576314.75; 2025-07-23: 11576314.75; 2025-08-23: 11576314.75 | 92610518
|  | 9.2611 | 2025-01-23: 0.77938; 2025-02-23: 0.77938; 2025-03-23: 0.77938; 2025-04-23: 0.77938; 2025-05-23: 0.77938; 2025-06-23: 0.77938; 2025-07-23: 0.77938; 2025-08-23: 0.77938
| Total of Civil,Other Works & Parkings(A+B+C) | 554545810.3457 | 933408 | 933408 | 21538767.4559 | 21538767.4559 | 21538767.4559 | 20605359.4559 | 20605359.4559 | 20605359.4559 | 20605359.4559 | 22096219.4559 | 10519904.7059 | 10519904.7059 | 10519904.7059 | 10519904.7059 | 11245888.7059 | 11245888.7059 | 14033148.7059 | 14264863.272 | 14264863.272 | 7310058.5661 | 8533860.1661 | 8533860.1661 | 10077193.4994 | 10077193.4994 | 9393990.6994 | 12710365.8706 | 12710365.8706 | 12710365.8706 | 12710365.8706 | 13812305.8706 | 13812305.8706 | 13812305.8706 | 14819608.6706 | 14819608.6706 | 12745368.6706 | 13134288.6706 | 13134288.6706 | 10309774.1045 | 10309774.1045 | 9194870.1045 | 9194870.1045 | 7379910.1045 | 6083510.1045 | 4540176.7712 | 4540176.7712 | 554545810.3457
| Gross Total --(Rs.) | 554545810.3457 | 933408 | 933408 | 21538767.4559 | 21538767.4559 | 21538767.4559 | 20605359.4559 | 20605359.4559 | 20605359.4559 | 20605359.4559 | 22096219.4559 | 10519904.7059 | 10519904.7059 | 10519904.7059 | 10519904.7059 | 11245888.7059 | 11245888.7059 | 14033148.7059 | 14264863.272 | 14264863.272 | 7310058.5661 | 8533860.1661 | 8533860.1661 | 10077193.4994 | 10077193.4994 | 9393990.6994 | 12710365.8706 | 12710365.8706 | 12710365.8706 | 12710365.8706 | 13812305.8706 | 13812305.8706 | 13812305.8706 | 14819608.6706 | 14819608.6706 | 12745368.6706 | 13134288.6706 | 13134288.6706 | 10309774.1045 | 10309774.1045 | 9194870.1045 | 9194870.1045 | 7379910.1045 | 6083510.1045 | 4540176.7712 | 4540176.7712 | 554545810.3457
| Gross Total --(Cr.) | 55.4546 | 0.093341 | 0.093341 | 2.1539 | 2.1539 | 2.1539 | 2.0605 | 2.0605 | 2.0605 | 2.0605 | 2.2096 | 1.052 | 1.052 | 1.052 | 1.052 | 1.1246 | 1.1246 | 1.4033 | 1.4265 | 1.4265 | 0.73101 | 0.85339 | 0.85339 | 1.0077 | 1.0077 | 0.9394 | 1.271 | 1.271 | 1.271 | 1.271 | 1.3812 | 1.3812 | 1.3812 | 1.482 | 1.482 | 1.2745 | 1.3134 | 1.3134 | 1.031 | 1.031 | 0.91949 | 0.91949 | 0.73799 | 0.60835 | 0.45402 | 0.45402 | 55.4546

## BOQ
BOQ of Civil & Structure Works (Stilt + 14) Tower-E - Prayagraj
S.No. | Description | Unit | Qty | Rate | Amount
General Notes - The following notes shall apply to all Sections and Bills contained in this Bill of Quantities:
1 | The quantities, classes and kinds of work set out in this Bill of Quantities are provisional. They do not purport to or represent the final quantities, classes or kinds of work eventually required to be done.
2 | This Bill of Quantities is not intended for and shall not be used for ordering purposes.
3 | This Bill of Quantities is to be read in conjunction with the Drawings, Specifications & Preambles to Work Sections which shall be construed as being complementary to one another. Any discrepancy shall be dealt in accordance with the Conditions of Contract.
4 | Works shall be executed at all heights / depths, levels, floors and locations all complete as per Drawings, Specifications and to the complete satisfaction of the Engineer-In-Charge.
5 | Unless otherwise specified, mode and method of measurement shall be in accordance with IS:1200.
6 | Contractor should strictly follow the Site Safety Manual and provide & install all the safety measures required as per Manual.
7 | The description of an item shall be deemed to include all preambles, headings, sub-headings and references to other documents. The detailed description of work and materials, given in the Specification are not necessarily repeated in the Bill of Quantities.
8 | The Preamble to the Bills of Quantities must be read with the Drawings, Conditions of Contract and the Specification and the tenderer shall be deemed to have examined the Drawings, Specifications, Conditions of Contract and to have acquainted himself with the Works to be done and the way in which they are to be carried out. This preamble to the Bills of Quantities shall form part of the Contract.
9 | Providing and maintaining Field Laboratory in a satisfactory manner till the completion of work to ensure site control on quality of materials and the works and shall strictly comply with provision of Indian/ International Standards at no extra cost. All other regular tests including requisite materials shall be carried out as directed either at approved laboratory or at site at no extra cost.
10 | The Tenderers are requested to inspect the site and obtain for themselves at their own expense all necessary information and particulars to enable them to submit the tender.
11 | The dimensions shown in the drawings shall have to be verified by the contractor at site before execution of the items and necessary allowance's have to be made as per the actual dimensions available at site.
12 | For the items of works having Basic rate of material, price adjustment will be made only on the actual quantity measured. Wastage shall be to Contractors account. Basic rate indicates landed cost at site including transportation charges, loading-unloading as applicable.
13 | The contractor should refer to the detailed drawings for details. All the rates so quoted should be inclusive of all hardware. In case of discrepancy between drawing and Bill of Quantity the drawing supersedes, unless specifically mentioned in the BOQ.
14 | The work shall be carried out as per drawings, specifications, the description of the items in the schedule and / or engineer’s instructions.
15 | All pre-fabrication works wherever possible shall be carried outside the client's premises, only assembling and finishing work will be allowed within the Site.
16 | Items of work provided in this schedule but not covered in the specifications shall be executed strictly as per instructions of the engineer.
17 | Unless otherwise mentioned in the contract, the tenderer shall quote for the finished items and shall provide for the complete cost towards labour, materials, plant and machinery, operational costs, levies, taxes, transport, repairs, rectification, maintenance till handing over, revenue expenses, contingencies, overheads, profits and all incidental items not specifically mentioned but reasonably implied and necessary to complete the works according to the contract.
18 | The quantities of the various items mentioned in the schedule of items are approximate and may vary up to any extent or be deleted altogether. The contractor, in his own interest, should get an indication of the probable extent of the work to be executed under any particular item in this schedule, before undertaking any preliminary and enabling work or purchasing bought out components related to the work.
19 | The Engineer-in-charge's decision shall be final and binding on the contractor regarding clarifications of items in this schedule with respect to the other sections of the Contract.
20 | It may be noted that the total work or any part / parts of the same may be awarded as mentioned in this schedule of items.
21 | The rates quoted shall be inclusive of all mock-ups, associated samples prior to any mass production or procurement as per complete satisfaction of the Client and Architect. Inclusive of dismantling, demolishing and carting the material and making good of the surface.
22 | Any debris generated out of the said work may please be cleared on priority basis from the Site. The contractor to allow for work to be executed on the upper Floors, temporary storage of material on the Ground Floor, for hoisting material to the upper floors, for bringing debris and waste down, for co-ordinating and scheduling movement of material with facilities available on site. The disposal of debris will be the sole responsibility of the Contractor.
23 | Any fault that occurs during the time of production, shifting or installation of finished materials should be replaced with good one as per the instruction from Engineer-in-charge.
24 | Maintaining the barricade and repair if required by the contractor.
25 | Making lay out with help of professional/In house survey agency, establishing bench marks, permanent grid lines on permanent objects and checking verticality of entire structure floor wise at regular intervals, and producing drawings, and all survey works related to project, using Total Station, laser beam device. Laser beam range of minimum 200 metres to be used for checking of verticality of entire structure.
26 | Protection- Cover up and protect from damage, including inclement weather including all works and materials but not limited to , all finished works, unfixed materials, to the satisfaction of the Project Manager.
27 | Keeping the site clear, clean, and meeting the hygiene standards- Cost of providing and maintaining the workers toilets shall be covered in the scope of contractor. As per safety norms mentioned elsewhere.
EARTH WORK
1.1. | Earth work in excavation in foundation trenches, column pits, plinth beam, under grade/ raft slab etc. by mechanical and/or manual means up to a depth of 1.5 mtr in soil from existing excavated soil level, stacking/spreading the excavated material within site premises (within a stretch of 1500 M) as per direction of Project Manager including dressing of bottom, sides strutting, timbering, shoring, trimming of sides, all leads and lifts, bailing or pumping out the water from the excavated areas collected from any source including subsoil water and keeping the excavated surface dry for subsequent works incidentals, etc. complete with ramming of bottom, surface preparation as per specifications to receive the PCC. | CUM | 1000 |  | 0
Excavation shall be payable only for vertical cut up to the outer edge of foundation lean concrete as indicated in drawings for all depths. Cost of extra excavation required for working space, supporting side shuttering of foundations and retaining walls, planking, dewatering, strutting etc. and that required for making slopes for stability of excavation shall be deemed to be included in the rate quoted. This item is not for Mass Excavation.
1.2. | Prepare the surface for PCC by manual excavation upto 30 cm depth including dressing the surface, ramming the bottom, disposal and spreading of the surplus earth at the specified location within premises including proper levelling, watering and consolidation complete as directed by E I C. (The item shall be measured as per plan area of PCC, Working space shall not be taken into measurement, deemed to be included into rates) (This item is only applicable if excavation item is not being executed by contractor and excavation already done by client for the location) | SQM | 1500 |  | 0
1.3. | Filling available excavated earth in trenches, plinth, sides of foundations etc. in layers not exceeding 20cm in depth: consolidating each deposited layer by ramming and watering, lead within the premises and upto any depth. (Compacted Volume shall be payable as per drawing) - Actual volume shall be paid incase excavation is done by Client. | CUM | 2400 |  | 0
| Total of Earthwork |  |  |  | 0
2 | CONCRETE WORK
Rates for all cement concrete items plain and reinforced described below shall include work from Basement Level to top of last roof including roof of machine room, mumty, over head water tanks and parapets above at all floors and for all heights. The contractor should provide full time sufficient pipes with accessories and pumps based on the site requirement for pumping and laying of concrete as directed by the EIC. The rate inclusive of standard rigid pipe line and its supports, lifting, laying charges, etc., at all heights and levels. No additional payment shall be payable to the contractor on account of using or change in any size of coarse aggregate in PCC/ RCC work at any stage during currency of works. (This section covers cast in situ structural and architectural as well.)
2.1 | Plain Cement Concrete: Providing and laying plain cement concrete of specified grade as bed concrete under foundation, bases for rafts, underground water tank, building machine equipments, column footing, under floor landings, below road and pathways, cill, coping, screeding at roof to required slope and other locations as called for laid, consolidated and cured etc. complete including finishing the top surface to receive the next course / layer as per specification and drawing. (Shuttering shall be paid in Item No.3.1.1) M10 Grade (Basic Rate of PCC - Rs. 4200/cum) without pump | CUM | 100 |  | 0
2.2. | Providing and laying cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) for ledge wall below balcony railings, band, mullion, lintel etc. (Shuttering shall be paid separately in respective item) as per drawing and as directed by the Project Manager. | CUM | 50 |  | 0
2.3. | Providing and laying damp proof course 40mm thick including shttering with cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) including mixing of water proofing compound @ 2% of cement content and applying two layers of bitumen @ 1.70 Kg/Sqm of grade 85/25 and as directed by the Project Manager. | SQM | 200 |  | 0
2.4. | RCC WORK
Providing & Laying RMC M-25 Grade as per approved design mix concrete (strictly controlled conditions) with flyash (as per approved design mix) with automatic batching plant machine mixed and machine vibrated RCC with melamine based plasticisers etc., upto any level, including finishing the exposed surface, fixing/ removal of pockets, fixing of sleeves and inserts (sleeves provided by client), curing etc complete, as per drawing (including all size and shape like circular, semi-circular, oval etc.) and as directed for all lead and lift, excluding cost of centering, shuttering and steel reinforcement but including cost of making shear keys and provision of construction / contraction / control joints in various locations. Checking from Client should not be considered as final and any defects arising during or after casting should be borne & bear by contractor at his own cost. This is inclusive of leaving shuttering & centring for pour strip, slab in slope, RCC members in curved, etc., nothing is payable extra on this account. RMC (M-25) Basic Rate - Rs. 5200/cum without pump excluding GST
2.4.1. | Foundation, column footings, raft slab, raft beams, plinth beam, lift pits, sump pits, pedestals / bases of column, column upto plinth, swimming pool, Retaining wall foundations, grade slab etc. | CUM | 2080 |  | 0
2.4.2. | Suspended floors, roofs, balconies, shelves/ counters, stair waist slabs, folded plate stairs and landings, swimming pool slab, lintel and floor beams, landing beams, girders (deep beams), RCC bands, swimming pool beam, cantilever projections, coping, cills, slab of tank etc at all levels.
2.4.2.1. | Stilt Floor level to 7th Floor level | CUM | 2200 |  | 0
2.4.2.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | CUM | 2440 |  | 0
2.4.2.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | CUM | 70 |  | 0
2.5. | Columns, Wall, pillars, piers, abutments, posts and struts, offset and projection of columns, water tank walls, lift walls, Retaining Wall, swimming pool, Parapets, planters, vertical projection of pergolas, wall and ramp walls etc. at all levels.
2.5.1. | Stilt Floor level to 7th Floor level | CUM | 860 |  | 0
2.5.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | CUM | 950 |  | 0
2.5.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | CUM | 30 |  | 0
2.5.4. | Finishing vaccum dewatering continuous concrete flooring 100-150 mm thick with specified grade concrete including necessary formwork in required level, vibrating concrete both by poker vibrators / leveling vaccum processing of the concrete and planning the surface by skin powered floater trowels with broom/plain finish including groove cutting & filling etc. complete. (Concrete shall be paid in the respective items above). | SQM | 1625 |  | 0
| Total of RCC Work |  |  |  | 0
3 | CENTRING AND SHUTTERING
Providing and fixing plywood or steel plate shuttering and centring for structural concrete work in locations called for including strutting, propping, bracing, bolting, wedging, casing, striking, removal etc. complete for any size, section, thickness. Props shall consist of well designed steel pipes adequately braced (wooden ballies as props shall not be permitted). The item to include centering and shuttering at all heights and levels. Allow for forming grooves, drip course, chamfers, cut-outs, openings etc. where called for and for dressing with approved shuttering oil to prevent adhesion. Unexposed concrete surfaces subsequently left untreated (in the condition obtained on removal of form work) shall not constitute exposed concrete work and shall be measured under this item only Irregular shapes with sides (like circular, semi-circular, oval etc.) which may not be perpendicular to each other for shapes not conforming to rectangle or square, and circular shuttering shall not be paid separately. Joints of soffits of the slab shall be made clean after concreting and de-shuttering. (quoted rate to include all staging upto 3.50 mtr height). Note:- Contractor shall take necessary precautions such as watertight shuttering. This is inclusive of RCC members, leaving shuttering & centring for pour strip, slab in slope, RCC members in curved (in plan), etc., nothing is payable extra on this account.
3.1.1. | Foundation, column footings, raft slab, raft beams, plinth beam, lift pits, sump pits, pedestals / bases of column, column up to plinth, swimming pool, Retaining wall foundations, grade slab etc. | SQM | 2150 |  | 0
3.1.2. | Suspended floors, roofs, balconies, shelves/ counters, stair waist slabs, folded plate stairs and landings, swimming pool slab, lintel and floor beams, landing beams, girders (deep beams), RCC bands, swimming pool beam, cantilever projections, coping, cills, slab of tank etc at all levels.
3.1.2.1. | Stilt Floor level to 7th Floor level | SQM | 17600 |  | 0
3.1.2.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | 18800 |  | 0
3.1.2..3 | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | SQM | 400 |  | 0
3.2. | Columns, Wall, pillars, piers, abutments, posts and struts, offset and projection of columns, water tank walls, lift walls, Retaining Wall, swimming pool, Parapets, planters, vertical projection of pergolas, wall and ramp walls etc. at all levels.
3.2.1. | Stilt Floor level to 7th Floor level | SQM | 7825 |  | 0
3.2.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | 8200 |  | 0
3.2.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | SQM | 150 |  | 0
3.3. | Extra for additional height in centring, shuttering where ever required with adequate bracing, propping etc. including cost of de-shuttering and decentring at all levels, over and above height of 3.50 mtr (Plan area to be measured and shall be paid proportionately on actual height) – for every 1.0 mtr. height | SQM | 1000 |  | 0
| Total of Shuttering |  |  |  | 0
4 | REINFORCEMENT
Receiving, laying and fixing in position steel reinforcement in all reinforced concrete work, including straightening, cutting, removal of loose rust by wire brush and coating with cement slurry, bending, hoisting, laying in position to the shape and profile required at all levels and heights as per drawing and design and/ or as directed, binding with double folded steel wire as approved by EIC etc. complete. (Contractor shall prepare BBS and submit to EIC for approval prior to cutting, bending & laying of steel bars and payments shall be released as per approved BBS complete in all respect as per direction and approval of EIC Rate shall include cost of 18 gauge GI binding wire, cover blocks as per Indian Standards, unloading the steel & moving to the steel yard, moving site to site within project etc) (Only Steel reinforcement shall be provided by the owner free of cost at one point)
4.1. | Thermomechanically Treated Reinforcement (TMT) or High yield strength Deformed (Tor steel) bars of all size & grades.
4.1.1. | Up to Stilt Floor Level | MT | 150 |  | 0
4.1.2. | Stilt Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet) | MT | 805 |  | 0
4.1.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | MT | 10 |  | 0
| Total of Reinforcement |  |  |  | 0
5 | MASONARY WORK
(Quoted Rates are for all heights, all depths, all levels, including basement to roof (mumty) & all leads and lifts, including curved or circular including elevation masonary work) (Basic Rate of Brick @ Rs. 7/No. FOR at site without GST)
5.1. | Brick work in Sub Structure (Up to Stilt Floor level):
| Providing and laying 230mm thick brick masonry using 1st quality burnt clay FPS bricks in Sub-Structure laid in cement mortar 1:6 (1 cement : 6 coarse sand) mix, joints finished, flush/ raked to 6mm depth including scaffolding, curing complete as per specification and drawing or as directed by Project Manager. | CUM | 100 |  | 0
5.2. | Brick work in Sub Structure (Up to Stilt Floor level):
| Providing and laying of 115 mm thick brick work with 1st quality burnt clay FPS bricks in sub-superstructure laid in cement mortar 1:4 (1 cement : 4 coarse sand) mix, joints finished, including placing hoop iron as per specification at every third course, scaffolding, curing complete in all respect as per direction of EIC. (Hoop iron shall be provided by client free of cost) (Items of RCC bands like shuttering, concrete and reinforcement to be paid in respective items). | SQM | 1000 |  | 0
5.3. | Brick work in Super Structure (Above Stilt FLoor level)
5.3.1 | Providing and laying 230mm thick brick masonry using 1st quality burnt clay FPS bricks in Super-Structure laid in cement mortar 1:6 (1 cement : 6 coarse sand) mix, joints finished, flush/ raked to 6mm depth including scaffolding, curing complete as per specification and drawing or as directed by Project Manager.
(a) | Stilt Floor level to 7th Floor level | CUM | 1185 |  | 0
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | CUM | 1355 |  | 0
5.4. | Brick work in Super Structure (Above Stilt FLoor level)
5.4.1 | Providing and laying of 115 mm thick brick work with 1st quality burnt clay FPS bricks in Super-Superstructure laid in cement mortar 1:4 (1 cement : 4 coarse sand) mix, joints finished, including placing hoop iron as per specification at every third course, scaffolding, curing complete in all respect as per direction of EIC. (Hoop iron shall be provided by client free of cost) (Items of RCC bands like shuttering, concrete and reinforcement to be paid in respective items).
(a) | Stilt Floor level to 7th Floor level | SQM | 7100 |  | 0
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | 8155 |  | 0
5.8. | Brick work in staircase steps:
| Providing and laying and constructing brickwork in staircase steps using 1st quality burnt clay FPS bricks in cement mortar 1:3 (1 cement : 3 coarse sand) at all heights and levels including cutting, chamfering scaffolding, curing, complete as per specification. | CUM | 40 |  | 0
| Total of Masonary Work |  |  |  | 0
6 | FINISHING WORKS (PLASTER)
(Quoted Rate shall be for all heights, depths, levels, leads and lifts and to include providing and fixing chicken wire mesh in junction RCC and brick / AAC Block walls and at all chased for electrical conduits & plumbing pipes etc. for internal and external plaster works including minor chipping of RCC, brickwork surface).
6.1. | Internal Plaster Super-Structure:
Wall Plaster: Providing and applying 12 to 15mm thick plaster to masonry and RCC walls, columns etc. in cement mortar 1:5 (1 cement : 5 screened coarse sand) finished smooth including hacking the surfaces, steel scaffolding, curing, making grooves at desired location etc. complete for all levels as per approved drawing.
(a) | Stilt Floor level to 7th Floor level | SQM | 19970 |  | 0
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | 22825 |  | 0
6.2. | Internal Plaster Super-Structure:
Ceiling Plaster: Providing and applying 6-10mm thick plaster to RCC slab, beam in cement mortar 1:4 (1 cement : 4 screened coarse sand) finished smooth including hacking the surfaces, steel scaffolding, curing, making grooves at desired location etc. complete for all levels as per approved drawing.
(a) | Stilt Floor level to 7th Floor level | SQM | 9135 |  | 0
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | 10440 |  | 0
6.3 | Double Layer External Plaster: Providing and applying 20 mm thick external cement plaster in two coats under layer 12 mm thick cement plaster 1:5 (1 cement : 5 screened coarse sand) finished with a top layer 8mm thick cement plaster 1:4 (1 cement : 4 screened coarse sand) including making of grooves, bands, drip coarse, design etc. as shown in drawing, steel scaffolding, curing, providing & mixing water proofing compound (CICO) in both layers as per manufacturer specification etc. complete as per approved drawing. | SQM | 19200 |  | 0
6.4 | Single Layer (Shaft Plaster): Providing and applying 12-15 mm thick external cement plaster in single coat finished with cement plaster 1:4 (1 cement : 4 screened coarse sand) including making of grooves, bands, drip coarse as shown in drawing, steel scaffolding, curing, providing & mixing water proofing compound (CICO) as per manufacturer specification etc. complete as per approved drawing. | SQM | 1000 |  | 0
| Total of Finishing Work (Plaster) |  |  |  | 0
7 | STRUCTURE STEEL
NOTES: The rates quoted by contractor for items under this head shall be inclusive of the following:-
(i) | Fabrication, cutting, bending to required size and shape, drilling, punching, counter-sinking, welding, grinding, filling etc. finishing, erecting and fixing in position at all heights and depths with all leads and lift.
(ii) | M.S. ladders and MS Railings in staircases, balconies and at any other place etc shall be fixed by welding the railing to steel reinforcement of slabs/beams/columns/staircase etc to make it absolutely rigid. The rate includes cutting of RCC required if any and making good the same after welding of the railing. Subsequently, the same shall be embedded in cement concrete of specified grade.
(iii) | M.S. grills/weld mesh etc. shall be fixed to masonry/concrete jambs of floor by means of required size and number of M.S. lugs grouted/ embeded in cement concrete block 1:2:4 or fixed by means of suitable counter sunk screw with rawal plugs or fixed by dash fastener of required dia and depth.
(iv) | The accessories such as M.S. hold-fasts / dash fasteners, lugs screws, rawal plug, G.I. pipe pieces, grouting in C.C. block 1:2:4 etc. shall not be paid separately. This shall be included in rate of items.
(v) | All steel work shall be painted with one coat of red oxide primer of approved make.
(vi) | No extra shall be paid for transport of fabricated items from one place to another place.
(vii) | Cost of all erection fasteners shall be borne by the contractor.
(viii) | All Welding work should be done as per IS:814.
(ix) | Domestic LPG cylinder shall not be used for any cutting of steel members.
(x) | All holes shall be drilled and no gas cutting shall be Allowed.
(xi) | Localized 'earthing' to be provided while welding to avoid any damage to electronic equipments in the running plant.
7.1. | Structural steel work with solid/hollow sections: Providing and fixing M.S. work in built-up section such as staircase railing, balcony railing, grating, MS drain cover, MS mumty door including hold fast/fastener etc. with square/round MS Pipes, MS flats, MS Hollow section etc., as per design electrically welded and fixing in RCC/brick masonry or/and treads of steps with cement concrete 1:2:4 (1 cement : 2 corse sand : 4 grades stone aggregate 20 mm nominal sie), complete in all respect as per drawing & direction of EIC, including a coat of red oxide steel primer. (Basic Rate of Str. Steel - Rs. 60/- Per Kg. F.O.R excluding GST) | KG | 39665 | 118 | 4680470
| Total of Strutural Steel Work |  |  |  | 4680470
8 | WOOD WORK
NOTES: The rates quoted by contractor for items under this head shall be inclusive of the following:-
i | All labour, materials, use of tools and equipment to complete the Wood works with all leads and lift.
ii | The rate shall be inclusive for applying water proof wood primer and two coats of termite proof paint on concelled surfaces on the wooden frame.
iii | Nails, Glue, Screws, Dash Fastener, lipping, Door hardware i.e. Mortice Lock, Handle, Tower bolt, Door Stopper, Door Buffer, Magic eye etc. are included in the rate.
iv | All joints shall be approved by the Client and according to the best practice. All joinery work shall be glued with best quality synthetic waterproof adhesive Fevicol or equivalent make as approved.
v | All screws shall be driven with screwdriver and shall not be hammered.
vi | Quoted rates are applicable for all depths, heights, lead & lift unless specified explicitly.
1 | Providing and Fixing seasoned Red Meranti door frame including painting the portion in contact with masonary / R.C.C. with 2 or more coats of Antitermite treatment paint and fixng the frames with suitable 3 Nos. M.S. holdfasts each side made out of 40 x 5 mm flat iron 230 mm long with bolts and nuts/ dash fasteners for RCC surfaces, duly embedded in C.C. Blocks of required size in (1:2:4 ) 1 cement : 2 coarse sand : 4 stone aggregate 20 mm nominal size) including tarring the hold fast etc.all complete as per direction of EIC. (Finished size to be confirmed by client before procurement) (Sample of wood shall be get approved by client before procurement) | CUM | 50 | 85000 | 4250000
| Total of Wood Work |  |  |  | 4250000
9 | WATERPROOFING
1 | The waterproofing treatment shall be got executed only through a specialized agency to be approved by the owner, under the supervision of the main contractor. Specialized agency, through which the contractor intends to get the water proofing work done, sholud have completed at least three similar works with satisfactory completion certificates and performance. At least one of these three works should have been completed by the specialized agency, at least five years prior to the date of the tender.
2 | Signing guarantee bond as per approved performa for waterproofing treatment for 10 years from the date of final completion on non judicial stamp paper. The guarantee bond shall be executed & extended by the contractor to the client and not by the water proofing agency.The guarantee bond enclosed with tender paper shall be signed by waterproofing agency and the main civil contractor.
3 | The rate shall be inclusive of the work in narrow widths, junctions Including leads and lift upto terrace level unless explicitly specified otherwise.
4 | Terrace - Providing 50x50mm, size chase in wall, parapets etc. at 300mm height from floor level for tucking ends of vertical layers of the treatment, filling up the chase with cement mortar 1:4 (1 Cement : 4 Course sand ) and preparing a drip mould as per detailed drawing just above the chase.
5 | The contractor shall get water tanks tested against any leakage/seepage by filling all the water tanks with water for a minimum period of 15 days, including cost of water, all necessary arrangements required for filling and emptying the tank after testing. The testing, rectification of leakage and seepage if any shall be completed to the entire satisfaction of the owner, who may desire the retesting as detailed above, till satisfactory results are obtained, to the entire satisfaction of the client.
6 | For measurements, the actual treated area shall be measured.
7 | Quoted rates are applicable for all depths, heights, lead & lift unless specified explicitly.
8 | Contractor to deposit all the water proofing material(s) in owner's stores and a copy of the bill(s) of such materials to be submitted to the owner. Empty bags/drums/containers of waterproofing material shall be removed only after the written permission of the owner.
9 | The Contractor shall submit the daily report of the status of waterproofing material received/consumed and the balance at site, to the client.
TERRACE WATERPROOFING:
1 | Providing and laying 120 mm average thickness of brick bat Coba and 65 mm at Khurra on Terrace through an approved agency, approved by the Architect as per steps given. (a) Surface Preparation, Cleaning the mother slab, reapir of joints, Providing and applying URP with cement slurry as primer to fill all the pores etc on mother slab over primer Providing and applying two coats of Fast Flex @ 2kg/Sqm including sandwiching the layer with fiber mesh of 45 GSM between two layers. (It shall also be execute up to 300 mm height of wall) (b) laying cement concrete using broken bricks/ brick bats of size 25 mm to 100 mm size with 50 % of cement mortar 1:5 ( 1 cement : 5 coarse sand) admixed with proprietary water proofing compound conforming to IS:2645 over 20 mm thick layer of cement mortar of mix 1:5 ( 1 cement : 5 coarse sand) admixed with admixed with proprietary water proofing compound conforming to IS:2645 to required slope and treating similarly the adjoining wall upto 300 mm height including rounding of junctions of wall and slabs. (c) After two days of proper curing applying a second coat of cement slurry admixed with proprietary water proofing compound conforming to IS:2645 (d) Finishing the surface with 20 mm thick jointless cement mortar of mix 1:4 (1 cement : 4 coarse sand) admixed with proprietary water proofing compound conforming to IS:2645 and finally finishing the surface with trowel with neat cement slurry and making 300X300 mm square. (e) The whole terrace so finished sshall be looded with water for a minimum period of two weeks for curing and for final test. All above operations to be done in order and as directed and specified by the engineer in charge. With average thickness of 100 mm thickness and minimum thickness at khurra as 65 mm. | SQM | 1000 | 1150 | 1150000
Providing gola in 1: 2: 4 cement concrete with 12 mm nominal size stone ballast, finished with cement plaster 1:2 (1 cement: 2 medium sand) laid, cured complete as per design. (Approx. Size 100mm x 100mm) Making khurras 450 x 450 mm with average min. thk. Of 50 mm over PVCsheet of 1m x 1m x 400 micron with cement concrete 1:2:4 (1 cement: 2 coarse sand: 4 graded stone aggregate of 12 mm nominal size) finished with 12 mm cement plaster 1:3 (1 cement: 3 coarse sand) and a coat of neat cement, rounding the edges, making and finishing complete. (Only plan area shall be paid).
| Total of Waterproofing Work |  |  |  | 1150000
| Grand Total (Excluding GST) |  |  |  | 10080470
Basic Rate of PCC (M10 Grade) @ Rs. 4200/- per cum without Pump
Basic Rate of RMC (M25 Grade) @ Rs. 5000/- per cum without Pump
Basic Rate of Bricks - Rs. 7/- per No.
Basic Rate of Structure Steel - Rs. 60/- per Kg
All Basic Rates are F.O.R at site excluding GST
Further only difference shall be paid/recovered subject to prior approval and with the consent of Client Purchase Department.
Basic rate shall be considered only for items as mentioned above. Nothing shall be considered for any hike in price for any other material except mentioned above.
Any variation (upward/ downward, both cases) in basic rate versus purchase rates shall be paid / recovered, only if prior approval taken by contractor through client's procurement department.
Contractor shall submit monthly/ fortnightly or as per requirement of material at site (well in advance) to site team for approval of material purchase rates through client's procurement department before procurement of materials, this is applicable for which base rate is mentioned in work order.
Design mix approval of RMC shall be obtained by contractor from client.
For higher grade of RMC including SCC only basic rate difference shall be paid/recovered
NOTE:-
Steel reinforcement shall be provided by the owner free of cost. Maximum Permissible wastage for steel reinforcement is 2%. If wastage of reinforcement exceeded the specified limit, Cost of the excess wastage quantity shall be recovered from the Contractor on the basis of 1.5 times of actual cost to client.
Only space shall be provided by Client for labour hutment, further construction of labour hutment, sanitation, house keeping, water, electricity arrangement shall be made by contractor at his own cost.
Electricity for construction and labour colony shall be in the scope of contractor including perimeter lighting. Electricity shall be provided at one point on chargeable basis further distribution is in the scope of contractor. Nothing extra shall be paid on this account whatsoever.
Construction as well as Drinking water shall be in the scope of contractor inluding its further distribution and storage.
Functional QA/QC lab shall be established by the contractor to maintain the required quality at the project for meeting the quality standards and contractor shall depute a proper Q.A. Engineer from the beginning and submit a quality assurance plan for the same.
1 No. Mobile crane is in the scope of contractor.
1 No. Material Hoist is in the scope of contractor.
DG of required capacity for Mobile Crane and Material Hoist is in the scope of contractor.
Survey work is in the scope of contractor. Client personnel will verify it.
Safety net minimum at 2 level shall be provided by contractor.
HDPE Debris chute is in contractor scope
Surface water, rainy water pumping out is in contractor scope.
Contractor shall submit the PF and ESI deposit challan, if the same is not deposited, shall be deducted from contractor's bill.
Make List
RMC - Prism/Shubham
Structural Steel - Tata/JSW/Jindal/Apollo
Cement - Ultratech/ACC/JK/Wonder

## Sheet6 (hidden)
S. No. | DESCRIPTION OF ITEMS | UNIT | BOQ DETAIL
|  |  | QUANTITY | RATE | AMOUNT
S.H.-I | MAIN WORK
1 | EARTH WORK IN EXCAVATION
1.1 | A) ALL KINDS OF SOIL, LIFT UPTO 3 M | CUM
1.3 | FILLING OF EARTH | CUM
2 | REINFORCED CEMENT CONCRETE
PROVIDING & LAYING RMC DESIGN MIX CONCRETE
2.1 | FOUNDATION, RAFTS, FOOTINGS, BASES OF COLUMNS, IN M-25 GRADE | CUM
2.2 | IN SUSPENDED FLOORS, ROOFS,BEAMS, LANDING, CHAJJAS, CANTILEVERS, BALCONIES,
| M25 GRADE | CUM
2.3 | IN PLINTH BEAMS, LANDING BEAM CANTILEVERS BEAM ETC ON PLINTH LVL.
| M25 GRADE | CUM
2.4 | IN GRADE SLAB FOR FLOORING AT GROUND FLOOR LVL.
| M25 GRADE | CUM
2.5 | IN STAIRCASE ETC. IN M-25 GRADE CONCRETE ALL WORK .
| M25 GRADE | CUM
2.6 | IN SHEAR WALLS, LIFT WALLS, RETAINING WALL | CUM
| M25 GRADE | CUM
| M30 GRADE | CUM
2.7 | IN COLUMNS, PILLARS & PIERS, POSTS, STRUTS
| M25 GRADE | CUM
| M30 GRADE | CUM
2.8 | IN WALLS (ANY THICKNESS) AND BASE SLAB AND COVER SLAB OF OVERHEAD TANKS ETC., IN M-25 GRADE | CUM
2.9 | EXTRA OVER 5TH FLOOR LEVEL TO 8TH FLOOR | CUM
2.1 | EXTRA OVER 9TH FLOOR LEVEL TO 12TH FLOOR | CUM
2.11 | EXTRA OVER 13TH FLOOR LEVEL TO 16TH FLOOR | CUM
2.12 | RCC IN KITCHEN COUNTER INCLUDING SHUTTERING REINFORCEMENT COMPLETE IN FLAT | NOS
2.13 | RCC IN LINTEL OF AVG SIZE 100X125X1200MM INCLUDING SHUTTERING REINFORCEMENT COMPLETE | NOS
2.14 | RCC IN LEDGE WALL/CONCRET BLOCK OF COMPLETE | CUM
3 | P/F SHUTTERING WORK
3.1 | FOUNDATIONS, RAFT, FOOTINGS, | Sqm
3.2 | OUTER SHEAR WALLS, LIFT WALLS, | Sqm
3.3 | PLINTH BEAM, LANDING BEAM, AT PLINTH LVL. | Sqm
3.4 | STAIRCASE, TIE-BEAMS, ETC UP TO ANY HEIGHT. | Sqm
3.5 | SUSPENDED/FLAT FLOOR, ROOFS AND BEAM, LANDINGS, CANTILEVER SLABS, CHAJJAS, | Sqm
3.6 | COLUMNS, PILLARS, PIERS, POSTS, STRUTS | Sqm
3.7 | ABOVE TERRACE WORK WALLS | Sqm
3.7 | ABOVE TERRACE WORK WALLS | Sqm
4 | P/F REINFORCEMENT WORK
4.1 | LAYING OF REINFORCEMENT STEEL OF HIGH YEILD STRENGTH . ( BASIC RATE RS. 40/- PER KGS. ) | MT
4.2 | ADJUSTMENT UPTO MONTH OF JAN 19. ( INSTRUCTED BY C.GUPTA SIR)
4.3 | June-19 Closing as per ERP was 14 MT BUT PHY Balance at site found 75 mt, So same qty reverse from ERP as well as in Client also. ( INSTRUCTED BY SK PANDEY SIR)
5 | BRICK MASONRY
5.1 | P/L 230 MM THICK BRICK WORK WITH FIRST QUALITY FLY ASH BRICKS IN SUPER STRUCTURE ABOVE PLINTH | Cum
5.2 | P/L 115 MM TH. MASONRY WITH FIRST QUALITY FLY ASH BRICKS IN SUPER STRUCTURE ABOVE PLINTH LVL | Sqm
5.3 | P/L 200 MM THICK WORK WITH FIRST QUALITY AAC BLOCK IN SUPER STRUCTURE ABOVE PLINTH LVL | Cum
5.4 | P/L 100 MM TH. MASONRY WITH FIRST QUALITY AAC BLOCK BRICKS IN SUPER STRUCTURE ABOVE PLINTH LVL | Sqm
5.5 | BRICK WORK IN STAIRCASE FOR STAIRCASE STEP MAKING IN THE RATIO 1:6 | Nos.
5.6 | FOR 230MM THICK BRICK WORK
5.6a | EXTRA OVER 5TH FLOOR LVL TO 8TH FLOOR LVL | CUM
5.6b | EXTRA OVER 9TH FLOOR LVL TO 12TH FLOOR LVL | CUM
5.6c | EXTRA OVER 13TH FLOOR LVL AND ABOVE LVL | CUM
5.7 | FOR 115MM THICK BRICK WORK
5.7a | EXTRA OVER 5TH FLOOR LVL TO 8TH FLOOR LVL | SQM
5.7b | EXTRA OVER 9TH FLOOR LVL TO 12TH FLOOR LVL | SQM
5.7c | EXTRA OVER 13TH FLOOR LVL AND ABOVE LVL | SQM
5.8 | P/L VERTICAL/HORIZONTAL BAND I/C SHUTTEING WORK. | CUM
5.9 | P/L REINFORCEMENT WORK IN RCC BAND AS PER SPECIFICATION. | MT
| CC BLOCK CASTING | CUM
6 | WOOD WORK & ALUMINIUM WORK
6.1 | PROVIDING WOOD WORK IN FRAMES OF DOORS, WINDOWS AND OTHER FRAMES,
| A) USING RED MIRANDI WOOD. | Rmt
6.2 | PROVIDING AND FIXING 35 MM THICK SKIN MOULDED DOORS SHUTTER, | Sqm
6.3 | PROVIDING AND FIXING 35 MM THICK WELL SEASONED HARDWOOD FRAME WOODEN PANELLED SHUTTER POLISH, | Sqm
6.4 | PROVIDING AND FIXING TAPERED HARD WOOD MOULDING 35 MM WIDE AND 12 MM ON ONE SIDE AND 6 MM ON OTHER SIDE THICKNESS | Mtrs.
6.5 | PROVIDING AND FIXING OF STRUCTURE GLAZZING IN ELEVATION OF TOWER AS PER APPROVED DETAIL. | Sqm
6.6 | PROVIDING AND FIXING OF FIRE HYDRANT CABINATE DOOR IN SHAFT AREA AS PER APPROVED DESIGN. | Nos
6.7 | SUPPLYING & FIXING UPVC DOOR AND WINDOWS WITH ALL ACCESORIESA AS PER DRAWINGS (BASIC RATE - RS 400 PER SQFT. ) | Sqm
6.8 | SUPPLYING & FIXING ALUMINIUM WINDOWS WITH ALL ACCESORIES AS PER DRAWINGS IN MAIN STAIRCASE (TOWER -A) | Sft
6.9 | SUPPLYING & FIXING ALUMINIUM WINDOWS WITH ALL ACCESORIESS AS PER DRAWINGS IN FIRE STAIRCASE (TOWER -A) | Sft
7 | STEEL WORK
7.1 | PROVIDING AND FIXING M.S. STAIRCASE RAILING WITH M S HANDRAIL, BALCONY RAILING | Kg.
8 | FLOORING
8.1 | PROVIDING AND LAYING VITRIFIED TILES OF MINIMUM THICKNESS 10 MM IN FLOORING & SKIRTING.(BASIC RATE OF VITRIFIED TILES @ RS. 400/- PER SQM INCLUDING FREIGHT BUT EXCLUDING TAXES) | Sqm
8.2 | PROVIDING AND LAYING FIRST CLASS CERAMIC TILES OF REQUIRED SIZE THICKNESS 8 MM IN FLOORING ON 20 MM AVERAGE THICK. (BASIC RATE OF CEREMIC TILES @ RS. 320 /- PER SQM INCLUDING FREIGHT BUT EXCLUDING TAXES) | Sqm
8.3 | PROVIDING AND LAYING FIRST CLASS GLAZED/ CERAMIC TILES OF REQUIRED SIZE OF MINIMUM THICKNESS 5 MM IN SKIRTING AND DADO ON 12 MM THICK CEMENT PLASTER. (BASIC RATE OF CEREMIC TILES @ RS.320/- PER SQM INCLUDING FREIGHT BUT EXCLUDING TAXES) | Sqm
8.4 | PROVIDING AND FIXING PRE POLISHED GRANITE 18 - 20 M M THICK IN STAIR CASE ON RISER AND TREADS AND SKIRTING . (BASIC RATE OF STONE @ RS. 1000/ - PER SQM INCLUDING FREIGHT BUT EXCLUDING TAXES.) | SQM
8.5 | PROVIDING AND FIXING GRANITE 18 - 20 M M THICK IN LIFT FACIA AS PER APPROVED DESIGN, . (BASIC RATE OF STONE @ RS. 1500/ - PER SQM INCLUDING FREIGHT BUT EXCLUDING TAXES.) | SQM
8.6 | PROVIDING AND FIXING 18 MM THICK GRANITE STONE SLABS AS APPROVED ON KITCHEN PLATFORM COUNTER (BASIC RATE OF STONE @ RS. 1600/- PER SQM INCLUDING FREIGHT BUT EXCLUDING TAXES.) | Sqm
8.7 | IPS FLOORING 1:2:4 OF THICKNESS 100MM FOR CUP BOARD | Sqm
8.8 | PROVIDING AND LAYING FIRST CLASS GLAZED TILE FOR WATER TANK INCLUDING REQUIRED WATERPROOFING PLASTER | Sqm
8.9 | WATER PROOFING OF WATER TANK WITH INJECTION GROUTING INCLUDING TWO OR MORE COAT WATER PROOFING | Sqm
8.1 | SAND FILLING UNDER FLAT VITRIFIED FLOOR TILES | CUM
8.11 | PCC (1:4:8) (FOR BELOW TOILET & BALCONY FL TILES) | CUM
8.12 | GRANITE IN CORIDOR-18MM THICK | SQMT
9 | ROOFING
9.1 | PROVIDING AND LAYING BRICK COBA WATER PROOFING TREATMENT ON TERRACE 120 MM THICK (AVERAGE) | SQM
9.2 | MAKING KHURRAS 45 X 45 CM WITH AVERAGE MINIMUM THICKNESS OF 5 CM CEMENT CONCRETE 1:2:4 | NOS
10 | FINISHING WORK
10.1 | P/L 12 MM THICK CEMENT PLASTER IN CEMENT MORTAR 1:6 (1 CEMENT : 0 FINE SAND AND 6 COARSE SAND) . | Sqm
10.2 | P/L 20 MM CEMENT PLASTER IN TWO COATS, UNDER LAYER 12MM TH.IN CEMENT MORTAR 1:6 | Sqm
10.3 | POP CORNICE | Rmt
10.4 | DISTEMPERING WITH OIL BOUND WASHABLE DISTEMPER OF APPROVED BRAND AND MANUFACTURER | Sqm
10.5 | Texture Paint with Primer | Sqmt
| Superfine with Primer | Sqmt
10.6 | POLISH ON INTERNAL DOOR SHUTTERS | Sqm
10.7 | ENAMEL PAINT | Sqm
10.8 | P/L UPTO 50 MM THICK CEMENT ROUGH PLASTER IN CEMENT MORTAR 1:6 (1 CEMENT : 0 FINE SAND AND 6 COARSE SAND) . | Sqm
11 | MISCELLANEOUS
11.1 | MAKING PLINTH PROTECTION 50 MM THICK OF CEMENT CONCRETE 1:3:6 | Sqm
11.2 | PROVIDING AND LAYING 6 MM THICK E-BOARD FALSE CEILING OF APPROVED QUALITY | Sqm
11.3 | PROVIDING AND LAYING WATER PROOFING TREATMENT TO SUNKEN PORTION OF TOILETS | Sqm
11.4 | Providing & Fixing of Modular Kitchen | NO
12 | ENTRY & ELEVATION IN TOWER
12.1 | FOR ENTRY AND ARCH ETC | NOS
12.2 | DESIGNER PLASTER ON TAPPERED ROOF I/C BASE PLASTER APX 60MM THICK IN AVG. | Sqm
12.3 | P/F OF GUMMAD ON TERRACE COMPLETE IN ALL RESPECT. | NOS
12.4 | DESIGNER PAINT ON TAPPERED SLAB | Sqm
12.5 | STONE WORK AT ENTRANCE | Rmt
13 | HANDING OVER
13 | Handover of Flat (Labour & Houskeeping Material) | Nos
15.3 | HORTICULTURE WORK

## Summary (hidden)
S. No. | Description | Unit | QTY
1 | Excavation upto 3 Mtr. | CUM | 3832.075 | 4000 | 2400
2 | PCC | CUM | #REF!
3 | RCC M-25 | CUM | #REF!
4 | RCC M-30 | CUM | #REF!
5 | RCC in Ladge Wall | CUM | #REF!
6 | Shuttering | SQM
6.1 | RAFT | SQM | #REF!
6.2 | COLUMN | SQM | #REF!
6.3 | SHEAR WALL | SQM | #REF!
6.4 | STAIR CASE | SQM | #REF!
6.5 | PLINTH BEAM | SQM | #REF!
6.6 | Slab | SQM | #REF!
7 | Steel | MT | #REF!
8 | DPC | CUM | #REF!
9 | Brick Work 115mm | SQM | #REF!
10 | Brick Work 230mm | CUM | #REF!
11 | Internal Wall Plaster | SQM | #REF!
12 | Internal Ceiling Plaster | SQM | #REF!
13 | External Plaster | SQM | #REF!

## Sheet2 (hidden)
259280 |  | 23970 | 22500
24087.6997 |  | 258013.08 | 242190
1605.8466 |  | 258336
259143.3
136.7566 | 9.1171
123080.958 | 8205.3972 | 233228970
23.3229
230mm Wall
Flat No.2
|  |  |  | Bed Room-1 | 6 | 1 | 3.165 | 2.5 | 47.475
[5 empty] | 6 | -1 | 2.065 | 2.5 | -30.975
[5 empty] | 6 | 1 | 0.985 | 2.5 | 14.775
|  |  |  | Bed Room-2 | 6 | 1 | 2.165 | 2.5 | 32.475
[5 empty] | 6 | -1 | 2.065 | 2.5 | -30.975
|  |  |  | Bed Room-3 | 6 | 1 | 3.55 | 2.5 | 53.25
[5 empty] | 6 | 1 | 1.92 | 2.5 | 28.8
[5 empty] | 6 | -1 | 1.5 | 1.5 | -13.5
|  |  |  | Toilet Wall | 6 | 1 | 2.58 | 2.5 | 38.7
[5 empty] | 6 | -2 | 0.55 | 1 | -6.6
[5 empty] | 6 | 1 | 2.3 | 2.65 | 36.57
|  |  |  | Drawing Room | 6 | 1 | 3.19 | 2.5 | 47.85
[5 empty] | 6 | -1 | 2.45 | 2.5 | -36.75
|  |  |  | Kitchen | 6 | 1 | 0.415 | 2.65 | 6.5985
|  |  |  | Entry Wall | 6 | 1 | 1.515 | 2.875 | 26.1337
[5 empty] | 6 | -1 | 1.2 | 2.4 | -17.28
|  |  |  | Toilet Wall | 6 | 1 | 0.515 | 2.5 | 7.725
|  |  |  | Toilet Wall | 6 | 1 | 1.81 | 2.5 | 27.15
|  |  |  | Kitchen Common Wall for Flat 2 & 3 | 2 | 1 | 4.735 | 2.65 | 25.0955
|  |  |  | Drawing Room Common Wall for Flat 1 & 2 | 2 | 1 | 1.5 | 2.55 | 7.65
[5 empty] | 2 | 1 | 5.245 | 2.55 | 26.7495
[5 empty] | 2 | 1 | 1.075 | 2.875 | 6.1812
|  |  |  | Drawing Room Common Wall for Flat 3 | 2 | 1 | 2.57 | 2.5 | 12.85
Flat No.4
|  |  |  | Bed Room-1 | 2 | 1 | 3.025 | 2.5 | 15.125
[5 empty] | 2 | -1 | 2.065 | 2.5 | -10.325
[5 empty] | 2 | 1 | 3.8 | 2.5 | 19
[5 empty] | 2 | -1 | 0.55 | 1 | -1.1
|  |  |  | Bed Room-2 | 2 | 1 | 2.8 | 2.5 | 14
[5 empty] | 2 | -1 | 2.065 | 2.5 | -10.325
|  |  |  | Living Room | 2 | 1 | 3.3 | 2.5 | 16.5
[5 empty] | 2 | -1 | 2.45 | 2.5 | -12.25
[5 empty] | 2 | 1 | 1.99 | 2.55 | 10.149
[5 empty] | 2 | 1 | 3.43 | 2.55 | 17.493
|  |  |  | Entry Wall | 2 | 1 | 1.5 | 2.55 | 7.65
[5 empty] | 2 | -1 | 1.2 | 2.4 | -5.76
|  |  |  | Bed Room-3 | 2 | 1 | 3.115 | 2.5 | 15.575
[5 empty] | 2 | 1 | 1.785 | 2.5 | 8.925
[5 empty] | 2 | -1 | 1.5 | 1.5 | -4.5
|  |  |  | Toilet Wall | 2 | 1 | 1.915 | 2.55 | 9.7665
[5 empty] | 2 | 1 | 2.04 | 2.65 | 10.812
Flat No.5
|  |  |  | Living Room | 4 | 1 | 2.93 | 2.5 | 29.3
[5 empty] | 4 | -1 | 2.05 | 2.5 | -20.5
[5 empty] | 4 | 1 | 0.415 | 2.5 | 4.15
|  |  |  | Kitchen cum Bed Room-2 | 4 | 1 | 4.69 | 2.5 | 46.9
|  |  |  | Bed Room-3 | 4 | 1 | 3.05 | 2.5 | 30.5
[5 empty] | 4 | -1 | 2.45 | 2.5 | -24.5
|  |  |  | Toilet Wall | 4 | 1 | 1.6 | 2.5 | 16
[5 empty] | 4 | -1 | 0.55 | 1 | -2.2
|  |  |  | Open to Sky Wall | 4 | 1 | 3.35 | 2.5 | 33.5
[5 empty] | 4 | 1 | 0.6 | 2.5 | 6
[5 empty] | 4 | 1 | 1.385 | 2.5 | 13.85
[5 empty] | 4 | -1 | 0.55 | 1 | -2.2
|  |  |  | Entry Wall | 4 | 1 | 1.57 | 2.55 | 16.014
[5 empty] | 4 | -1 | 1.2 | 2.4 | -11.52
|  |  |  | Common Wall of Flat 5 & 8 | 2 | 1 | 5.28 | 2.5 | 26.4
|  |  |  | Common Wall of Flat 5 & 6 | 2 | 1 | 2.41 | 2.5 | 12.05
|  |  |  | Common Wall of Flat 5 & 6 | 2 | 1 | 6.79 | 2.5 | 33.95
Flat No.11 & 12
|  |  |  | Bed Room-1 | 2 | 1 | 3.43 | 2.5 | 17.15
|  |  |  | Main Staircase | 2 | 1 | 2.55 | 2.5 | 12.75
[5 empty] | 2 | 1 | 3.53 | 2.5 | 17.65
[5 empty] | 2 | -1 | 1.55 | 1 | -3.1
|  |  |  | Fire Staircase | 2 | 1 | 3.2 | 2.5 | 16
[5 empty] | 2 | 1 | 2.76 | 2.5 | 13.8
[5 empty] | 2 | 1 | 3.2 | 2.5 | 16
[5 empty] | 2 | -1 | 1.8 | 1 | -3.6
|  |  |  | Lift | 4 | 2 | 1.9 | 2.5 | 38
[5 empty] | 4 | -1 | 0.9 | 2.1 | -7.56
735.468