## TOP SHEET
OMAXE LTD. |  |  |  |  | Tracker NO | Office NO
NAME OF PROJECT : OMAXE ANANDA TOWER-E (Location: Tower-E STILT + 14 FLOORS) |  |  |  | CONTRACT VALUE ; |  | 162331805
NATURE OF WORK : CIVIL STRUCTURE WORK |  |  |  | PROGRESS OF WORK: |  | 15.11%
NAME OF THE CONTRACTOR :- M/s MARCO-ENTERPRISES |  |  |  | VENDOR CODE:
WORK ORDER NO. & DATE : OPRL/ATE/11094106758 (14 FEB, 2025) |  |  |  | DATE OF START: 01.MAY.2025
THIS R/A BILL NO. & DATE : 11TH RA BILL, DATE 16-03-2026 |  |  |  | COMPLETION PERIOD : Upto 31-Aug-2026 (18 Months)
PERIOD OF BILL :- FROM 05-03-2026 TO 16-03-2026 |  |  |  | GST No. : 09BLDPK5228HIZ2
ERP PROJECT CODE : 127018 |  |  |  | PAN NO. : BLDPK5228H
DATE OF BILL REC. AT SITE :- |  | DATE OF BILL RECEIVED AT H.O. :- |  | DATE OF BILL CHECKING AT H.O. :-
S.NO. | PARTICULARS | CLAIMED BY CONTRACTOR | GROSS AMT | PREVIOUS AMT. | THIS BILL AMT | REMARKS
1 | WORK DONE(CIVIL) |  | 24526278.4581 | 21337062.4041 | 3189216.054
2 | WORK DONE(ELECT/ PLUMBING)
3 | DIFF. OF CEMENT
4 | RATE DIFF OF TILES
| TOTAL (A) |  | 24526278.4581 | 21337062.4041 | 3189216.054
5 | Add GST 18% On (A) |  | 4414730.1225 | 3840671.2327 | 574058.8897
| TOTAL (B) |  | 28941008.5806 | 25177733.6368 | 3763274.9438
ADVANCES
7.1 | Add Mobilization Advance |  | 6000000 | 6000000
7.2 | Recover Mobilization Advance |  | -1133154.9504 | -985807.8522 | -147347.0982
| TOTAL (C) |  | 33807853.6302 | 30191925.7846 | 3615927.8456
DEDUCTIONS
8 | SECURITY @ 5 % (ON TOTAL A) |  | 1226314 | 1066853 | 159461
9 | TDS @ 1% (ON TOTAL A) |  | 293931 | 263513 | 30419
| TOTAL DEDUCTION (C) |  | 1520245 | 1330366 | 189880
11 | NET PAYABLE AMOUNT (D) |  | 32287608.6302 | 28861559.7846 | 3426047.8456
| NOW PAYABLE |  |  |  | 3426047.8456 |  | 2851988.9559
| PREPARED BY | [5 empty] | 1996392.2691
PRIYANK BARANWAL
MANAGER (BILLING)
9988294677
| ACCOUNT (SITE) |  |  | PREVIOUS RA BILL NO:-
|  | ANUP SINGH |  | PREVIOUS RA GROSS AMOUNT:-
DY. MANAGER
9315403180
PROJECT INCHARGE {CPC/PC/ASST V.P./SR GM /GM}
S K PANDEY
G.M. - PROJECT
9711800470
HO BILL MONITORING
|  | UPENDER SINGH |  | GAURAV MAHESHWARI
|  | CHIEF MANAGER |  | G.M.-HO BILLING

## ABSTRACT
OMAXE PANCHAM REALCON PVT. LTD.
| WORK ORDER NO. & DATE : OPRL/ATE/11094106758 (14 FEB, 2025) | [7 empty] | ERP PROJECT CODE : 127018
| THIS R/A BILL NO. & DATE : 11TH RA BILL, DATE 16-03-2026 | [7 empty] | DATE OF BILL REC. AT SITE :-
| NATURE OF WORK : CIVIL STRUCTURE WORK | [7 empty] | PERIOD OF BILL :- FROM 05-03-2026 TO 16-03-2026
ABSTRACT OF COST
S.No. | DESCRIPTION OF ITEM | Unit | AS PER W.O. (R0) |  |  |  | Qty |  |  | Amount |  |  | Executed %
|  |  | Qty | Rate | Amount | Part Rate | Prev. Bill | This Bill | UpTo Date | Prev. Bill | This Bill | UpTo Date
1 | EARTH WORK
1.1. | Earth work in excavation in foundation trenches, column pits, plinth beam, under grade/ raft slab etc. by mechanical and/or manual means up to a depth of 1.5 mtr in soil from existing excavated soil level, stacking/spreading the excavated material within site premises (within a stretch of 1500 M) as per direction of Project Manager including dressing of bottom, sides strutting, timbering, shoring, trimming of sides, all leads and lifts, bailing or pumping out the water from the excavated areas collected from any source including subsoil water and keeping the excavated surface dry for subsequent works incidentals, etc. complete with ramming of bottom, surface preparation as per specifications to receive the PCC. | CUM | 1000 | 120 | 120000 |  |  | 0 |  | 0 | 0 | 0 | 0% | 0
| Excavation shall be payable only for vertical cut up to the outer edge of foundation lean concrete as indicated in drawings for all depths. Cost of extra excavation required for working space, supporting side shuttering of foundations and retaining walls, planking, dewatering, strutting etc. and that required for making slopes for stability of excavation shall be deemed to be included in the rate quoted. This item is not for Mass Excavation. | [8 empty] | 0 | 0 | 0 |  | 0
1.2. | Prepare the surface for PCC by manual excavation upto 30 cm depth including dressing the surface, ramming the bottom, disposal and spreading of the surplus earth at the specified location within premises including proper levelling, watering and consolidation complete as directed by E I C. (The item shall be measured as per plan area of PCC, Working space shall not be taken into measurement, deemed to be included into rates) (This item is only applicable if excavation item is not being executed by contractor and excavation already done by client for the location) | SQM | 1882 | 65 | 122330 | 65 | 1881.385 | 0 | 1881.385 | 122290.0218 | 0 | 122290.0218 | 99.97% | 0
1.3. | Filling available excavated earth in trenches, plinth, sides of foundations etc. in layers not exceeding 20cm in depth: consolidating each deposited layer by ramming and watering, lead within the premises and upto any depth. (Compacted Volume shall be payable as per drawing) - Actual volume shall be paid incase excavation is done by Client. | CUM | 4726 | 100 | 472600 | 100 | 4725.3991 | 0 | 4725.3991 | 472539.9141 | 0 | 472539.9141 | 99.99% | 0
| Total of Earthwork |  |  |  | 714930
2 | CONCRETE WORK
Rates for all cement concrete items plain and reinforced described below shall include work from Basement Level to top of last roof including roof of machine room, mumty, over head water tanks and parapets above at all floors and for all heights. The contractor should provide full time sufficient pipes with accessories and pumps based on the site requirement for pumping and laying of concrete as directed by the EIC. The rate inclusive of standard rigid pipe line and its supports, lifting, laying charges, etc., at all heights and levels. No additional payment shall be payable to the contractor on account of using or change in any size of coarse aggregate in PCC/ RCC work at any stage during currency of works. (This section covers cast in situ structural and architectural as well.)
2.1 | Plain Cement Concrete: Providing and laying plain cement concrete of specified grade as bed concrete under foundation, bases for rafts, underground water tank, building machine equipments, column footing, under floor landings, below road and pathways, cill, coping, screeding at roof to required slope and other locations as called for laid, consolidated and cured etc. complete including finishing the top surface to receive the next course / layer as per specification and drawing. (Shuttering shall be paid in Item No.3.1.1) M10 Grade (Basic Rate of PCC - Rs. 4200/cum) without pump | CUM | 100 | 5550 | 555000 | 5550 | 78.9267 | 0.54 | 79.4667 | 438042.9353 | 2997 | 441039.9353 | 79.47% | 0
2.2. | Providing and laying cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) for ledge wall below balcony railings, band, mullion, lintel etc. (Shuttering shall be paid separately in respective item) as per drawing and as directed by the Project Manager. | CUM | 50 | 5750 | 287500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
2.3. | Providing and laying damp proof course 40mm thick including shttering with cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) including mixing of water proofing compound @ 2% of cement content and applying two layers of bitumen @ 1.70 Kg/Sqm of grade 85/25 and as directed by the Project Manager. | SQM | 200 | 480 | 96000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
2.4. | RCC WORK
Providing & Laying RMC M-25 Grade as per approved design mix concrete (strictly controlled conditions) with flyash (as per approved design mix) with automatic batching plant machine mixed and machine vibrated RCC with melamine based plasticisers etc., upto any level, including finishing the exposed surface, fixing/ removal of pockets, fixing of sleeves and inserts (sleeves provided by client), curing etc complete, as per drawing (including all size and shape like circular, semi-circular, oval etc.) and as directed for all lead and lift, excluding cost of centering, shuttering and steel reinforcement but including cost of making shear keys and provision of construction / contraction / control joints in various locations. Checking from Client should not be considered as final and any defects arising during or after casting should be borne & bear by contractor at his own cost. This is inclusive of leaving shuttering & centring for pour strip, slab in slope, RCC members in curved, etc., nothing is payable extra on this account. RMC (M-25) Basic Rate - Rs. 5200/cum without pump excluding GST
2.4.1. | Foundation, column footings, raft slab, raft beams, plinth beam, lift pits, sump pits, pedestals / bases of column, column upto plinth, swimming pool, Retaining wall foundations, grade slab etc. | CUM | 2080 | 6600 | 13728000 | 6600 | 1686.5471 | 0 | 1686.5471 | 11131211.0679 | 0 | 11131211.0679 | 81.08% | 0
2.4.2. | Suspended floors, roofs, balconies, shelves/ counters, stair waist slabs, folded plate stairs and landings, swimming pool slab, lintel and floor beams, landing beams, girders (deep beams), RCC bands, swimming pool beam, cantilever projections, coping, cills, slab of tank etc at all levels.
2.4.2.1. | Stilt Floor level to 7th Floor level | CUM | 2200 | 6550 | 14410000 | 6550 | 445.8329 | 168.9677 | 614.8006 | 2920205.5829 | 1106738.4683 | 4026944.0512 | 27.95% | 1007346.1453
2.4.2.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | CUM | 2440 | 6750 | 16470000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
2.4.2.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | CUM | 70 | 7300 | 511000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
2.5. | Columns, Wall, pillars, piers, abutments, posts and struts, offset and projection of columns, water tank walls, lift walls, Retaining Wall, swimming pool, Parapets, planters, vertical projection of pergolas, wall and ramp walls etc. at all levels.
2.5.1. | Stilt Floor level to 7th Floor level | CUM | 860 | 6850 | 5891000 | 6850 | 183.5854 | 85.5721 | 269.1575 | 1257559.853 | 586169.0905 | 1843728.9435 | 31.3% | 776703.553
2.5.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | CUM | 950 | 7050 | 6697500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
2.5.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | CUM | 30 | 7650 | 229500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
2.5.4. | Finishing vaccum dewatering continuous concrete flooring 100-150 mm thick with specified grade concrete including necessary formwork in required level, vibrating concrete both by poker vibrators / leveling vaccum processing of the concrete and planning the surface by skin powered floater trowels with broom/plain finish including groove cutting & filling etc. complete. (Concrete shall be paid in the respective items above). | SQM | 1625 | 100 | 162500 |  | 0 |  | 0
| Total of RCC Work |  |  |  | 59038000
3 | CENTRING AND SHUTTERING
Providing and fixing plywood or steel plate shuttering and centring for structural concrete work in locations called for including strutting, propping, bracing, bolting, wedging, casing, striking, removal etc. complete for any size, section, thickness. Props shall consist of well designed steel pipes adequately braced (wooden ballies as props shall not be permitted). The item to include centering and shuttering at all heights and levels. Allow for forming grooves, drip course, chamfers, cut-outs, openings etc. where called for and for dressing with approved shuttering oil to prevent adhesion. Unexposed concrete surfaces subsequently left untreated (in the condition obtained on removal of form work) shall not constitute exposed concrete work and shall be measured under this item only Irregular shapes with sides (like circular, semi-circular, oval etc.) which may not be perpendicular to each other for shapes not conforming to rectangle or square, and circular shuttering shall not be paid separately. Joints of soffits of the slab shall be made clean after concreting and de-shuttering. (quoted rate to include all staging upto 3.50 mtr height). Note:- Contractor shall take necessary precautions such as watertight shuttering. This is inclusive of RCC members, leaving shuttering & centring for pour strip, slab in slope, RCC members in curved (in plan), etc., nothing is payable extra on this account.
3.1.1. | Foundation, column footings, raft slab, raft beams, plinth beam, lift pits, sump pits, pedestals / bases of column, column up to plinth, swimming pool, Retaining wall foundations, grade slab etc. | SQM | 2150 | 360 | 774000 | 360 | 1645.4974 | 0 | 1645.4974 | 592379.046 | 0 | 592379.046 | 76.53% | 0
3.1.2. | Suspended floors, roofs, balconies, shelves/ counters, stair waist slabs, folded plate stairs and landings, swimming pool slab, lintel and floor beams, landing beams, girders (deep beams), RCC bands, swimming pool beam, cantilever projections, coping, cills, slab of tank etc at all levels.
3.1.2.1. | Stilt Floor level to 7th Floor level | SQM | 17600 | 465 | 8184000 | 465 | 2869.9559 | 2066.5063 | 4936.4622 | 1334529.4842 | 960925.4388 | 2295454.923 | 28.05% | 556053.9517
3.1.2.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | 18800 | 485 | 9118000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
3.1.2..3 | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | SQM | 400 | 550 | 220000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[10 empty] | 0 | 0 | 0 |  | 0
3.2. | Columns, Wall, pillars, piers, abutments, posts and struts, offset and projection of columns, water tank walls, lift walls, Retaining Wall, swimming pool, Parapets, planters, vertical projection of pergolas, wall and ramp walls etc. at all levels.
3.2.1. | Stilt Floor level to 7th Floor level | SQM | 7825 | 465 | 3638625 | 465 | 1947.104 | 474.5 | 2421.604 | 905403.36 | 220642.5 | 1126045.86 | 30.95% | 464118.36
3.2.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | 8200 | 485 | 3977000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
3.2.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | SQM | 150 | 550 | 82500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
3.3. | Extra for additional height in centring, shuttering where ever required with adequate bracing, propping etc. including cost of de-shuttering and decentring at all levels, over and above height of 3.50 mtr (Plan area to be measured and shall be paid proportionately on actual height) – for every 1.0 mtr. height | SQM | 1000 | 115 | 115000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Total of Shuttering |  |  |  | 26109125
4 | REINFORCEMENT
Receiving, laying and fixing in position steel reinforcement in all reinforced concrete work, including straightening, cutting, removal of loose rust by wire brush and coating with cement slurry, bending, hoisting, laying in position to the shape and profile required at all levels and heights as per drawing and design and/ or as directed, binding with double folded steel wire as approved by EIC etc. complete. (Contractor shall prepare BBS and submit to EIC for approval prior to cutting, bending & laying of steel bars and payments shall be released as per approved BBS complete in all respect as per direction and approval of EIC Rate shall include cost of 18 gauge GI binding wire, cover blocks as per Indian Standards, unloading the steel & moving to the steel yard, moving site to site within project etc) (Only Steel reinforcement shall be provided by the owner free of cost at one point)
4.1. | Thermomechanically Treated Reinforcement (TMT) or High yield strength Deformed (Tor steel) bars of all size & grades.
4.1.1. | Up to Stilt Floor Level | MT | 150 | 8500 | 1275000 | 8500 | 136.9855 | 0 | 136.9855 | 1164376.4535 | 0 | 1164376.4535 | 91.32% | 40943.3676
4.1.2. | Stilt Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet) | MT | 805 | 9400 | 7567000 | 9400 | 100.9749 | 29.2078 | 130.1828 | 949164.3256 | 274553.5564 | 1223717.882 | 16.17% | 371226.5583
4.1.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | MT | 10 | 11000 | 110000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Total of Reinforcement |  |  |  | 8952000
5 | MASONARY WORK
(Quoted Rates are for all heights, all depths, all levels, including basement to roof (mumty) & all leads and lifts, including curved or circular including elevation masonary work) (Basic Rate of Brick @ Rs. 7/No. FOR at site without GST)
5.1. | Brick work in Sub Structure (Up to Stilt Floor level):
| Providing and laying 230mm thick brick masonry using 1st quality burnt clay FPS bricks in Sub-Structure laid in cement mortar 1:6 (1 cement : 6 coarse sand) mix, joints finished, flush/ raked to 6mm depth including scaffolding, curing complete as per specification and drawing or as directed by Project Manager. | CUM | 100 | 6000 | 600000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
5.2. | Brick work in Sub Structure (Up to Stilt Floor level):
| Providing and laying of 115 mm thick brick work with 1st quality burnt clay FPS bricks in sub-superstructure laid in cement mortar 1:4 (1 cement : 4 coarse sand) mix, joints finished, including placing hoop iron as per specification at every third course, scaffolding, curing complete in all respect as per direction of EIC. (Hoop iron shall be provided by client free of cost) (Items of RCC bands like shuttering, concrete and reinforcement to be paid in respective items). | SQM | 1000 | 800 | 800000 | 560 | 88.1435 | 0 | 88.1435 | 49360.36 | 0 | 49360.36 | 8.814% | 0
5.3. | Brick work in Super Structure (Above Stilt FLoor level)
5.3.1 | Providing and laying 230mm thick brick masonry using 1st quality burnt clay FPS bricks in Super-Structure laid in cement mortar 1:6 (1 cement : 6 coarse sand) mix, joints finished, flush/ raked to 6mm depth including scaffolding, curing complete as per specification and drawing or as directed by Project Manager. | [8 empty] | 0 | 0 | 0 |  | 0
(a) | Stilt Floor level to 7th Floor level | CUM | 1185 | 6300 | 7465500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | CUM | 1355 | 6500 | 8807500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
5.4. | Brick work in Super Structure (Above Stilt FLoor level)
5.4.1 | Providing and laying of 115 mm thick brick work with 1st quality burnt clay FPS bricks in Super-Superstructure laid in cement mortar 1:4 (1 cement : 4 coarse sand) mix, joints finished, including placing hoop iron as per specification at every third course, scaffolding, curing complete in all respect as per direction of EIC. (Hoop iron shall be provided by client free of cost) (Items of RCC bands like shuttering, concrete and reinforcement to be paid in respective items).
(a) | Stilt Floor level to 7th Floor level | SQM | 7100 | 875 | 6212500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | 8155 | 915 | 7461825 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
5.8. | Brick work in staircase steps:
| Providing and laying and constructing brickwork in staircase steps using 1st quality burnt clay FPS bricks in cement mortar 1:3 (1 cement : 3 coarse sand) at all heights and levels including cutting, chamfering scaffolding, curing, complete as per specification. | CUM | 40 | 7000 | 280000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Total of Masonary Work |  |  |  | 31627325
6 | FINISHING WORKS (PLASTER)
(Quoted Rate shall be for all heights, depths, levels, leads and lifts and to include providing and fixing chicken wire mesh in junction RCC and brick / AAC Block walls and at all chased for electrical conduits & plumbing pipes etc. for internal and external plaster works including minor chipping of RCC, brickwork surface).
6.1. | Internal Plaster Super-Structure:
Wall Plaster: Providing and applying 12 to 15mm thick plaster to masonry and RCC walls, columns etc. in cement mortar 1:5 (1 cement : 5 screened coarse sand) finished smooth including hacking the surfaces, steel scaffolding, curing, making grooves at desired location etc. complete for all levels as per approved drawing.
(a) | Stilt Floor level to 7th Floor level | SQM | 19970 | 265 | 5292050 |  |  | 0 |  | 0 | 0 | 0 | 0% | 0
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | 22825 | 280 | 6391000 |  |  | 0 |  | 0 | 0 | 0 | 0% | 0
6.2. | Internal Plaster Super-Structure:
Ceiling Plaster: Providing and applying 6-10mm thick plaster to RCC slab, beam in cement mortar 1:4 (1 cement : 4 screened coarse sand) finished smooth including hacking the surfaces, steel scaffolding, curing, making grooves at desired location etc. complete for all levels as per approved drawing.
(a) | Stilt Floor level to 7th Floor level | SQM | 9135 | 255 | 2329425 |  |  | 0 |  | 0 | 0 | 0 | 0% | 0
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | 10440 | 270 | 2818800 |  |  | 0 |  | 0 | 0 | 0 | 0% | 0
6.3 | Double Layer External Plaster: Providing and applying 20 mm thick external cement plaster in two coats under layer 12 mm thick cement plaster 1:5 (1 cement : 5 screened coarse sand) finished with a top layer 8mm thick cement plaster 1:4 (1 cement : 4 screened coarse sand) including making of grooves, bands, drip coarse, design etc. as shown in drawing, steel scaffolding, curing, providing & mixing water proofing compound (CICO) in both layers as per manufacturer specification etc. complete as per approved drawing. | SQM | 19200 | 480 | 9216000 |  |  | 0 |  |  |  |  | 0%
6.4 | Single Layer (Shaft Plaster): Providing and applying 12-15 mm thick external cement plaster in single coat finished with cement plaster 1:4 (1 cement : 4 screened coarse sand) including making of grooves, bands, drip coarse as shown in drawing, steel scaffolding, curing, providing & mixing water proofing compound (CICO) as per manufacturer specification etc. complete as per approved drawing. | SQM | 1000 | 380 | 380000 |  |  | 0 |  | 0 | 0 | 0 | 0% | 0
| Total of Finishing Work (Plaster) |  |  |  | 26427275
7 | STRUCTURE STEEL
7.1. | Structural steel work with solid/hollow sections: Providing and fixing M.S. work in built-up section such as staircase railing, balcony railing, grating, MS drain cover, MS mumty door including hold fast/fastener etc. with square/round MS Pipes, MS flats, MS Hollow section etc., as per design electrically welded and fixing in RCC/brick masonry or/and treads of steps with cement concrete 1:2:4 (1 cement : 2 corse sand : 4 grades stone aggregate 20 mm nominal sie), complete in all respect as per drawing & direction of EIC, including a coat of red oxide steel primer. (Basic Rate of Str. Steel - Rs. 60/- Per Kg. F.O.R excluding GST) | KG | 39665 | 110 | 4363150 |  |  | 0 |  | 0 | 0 | 0 | 0% | 0
| Total of Strutural Steel Work |  |  |  | 4363150
8 | WOOD WORK
1 | Providing and Fixing seasoned Red Meranti door frame including painting the portion in contact with masonary / R.C.C. with 2 or more coats of Antitermite treatment paint and fixng the frames with suitable 3 Nos. M.S. holdfasts each side made out of 40 x 5 mm flat iron 230 mm long with bolts and nuts/ dash fasteners for RCC surfaces, duly embedded in C.C. Blocks of required size in (1:2:4 ) 1 cement : 2 coarse sand : 4 stone aggregate 20 mm nominal size) including tarring the hold fast etc.all complete as per direction of EIC. (Finished size to be confirmed by client before procurement) (Sample of wood shall be get approved by client before procurement) | CUM | 50 | 79000 | 3950000 |  |  | 0 |  | 0 | 0 | 0 | 0% | 0
| Total of Wood Work |  |  |  | 3950000
9 | WATERPROOFING
TERRACE WATERPROOFING:
1 | Providing and laying 120 mm average thickness of brick bat Coba and 65 mm at Khurra on Terrace through an approved agency, approved by the Architect as per steps given. (a) Surface Preparation, Cleaning the mother slab, reapir of joints, Providing and applying URP with cement slurry as primer to fill all the pores etc on mother slab over primer Providing and applying two coats of Fast Flex @ 2kg/Sqm including sandwiching the layer with fiber mesh of 45 GSM between two layers. (It shall also be execute up to 300 mm height of wall) (b) laying cement concrete using broken bricks/ brick bats of size 25 mm to 100 mm size with 50 % of cement mortar 1:5 ( 1 cement : 5 coarse sand) admixed with proprietary water proofing compound conforming to IS:2645 over 20 mm thick layer of cement mortar of mix 1:5 ( 1 cement : 5 coarse sand) admixed with admixed with proprietary water proofing compound conforming to IS:2645 to required slope and treating similarly the adjoining wall upto 300 mm height including rounding of junctions of wall and slabs. (c) After two days of proper curing applying a second coat of cement slurry admixed with proprietary water proofing compound conforming to IS:2645 (d) Finishing the surface with 20 mm thick jointless cement mortar of mix 1:4 (1 cement : 4 coarse sand) admixed with proprietary water proofing compound conforming to IS:2645 and finally finishing the surface with trowel with neat cement slurry and making 300X300 mm square. (e) The whole terrace so finished sshall be looded with water for a minimum period of two weeks for curing and for final test. All above operations to be done in order and as directed and specified by the engineer in charge. With average thickness of 100 mm thickness and minimum thickness at khurra as 65 mm. | SQM | 1000 | 1150 | 1150000 |  |  | 0 |  | 0 | 0 | 0 | 0% | 0
Providing gola in 1: 2: 4 cement concrete with 12 mm nominal size stone ballast, finished with cement plaster 1:2 (1 cement: 2 medium sand) laid, cured complete as per design. (Approx. Size 100mm x 100mm) Making khurras 450 x 450 mm with average min. thk. Of 50 mm over PVCsheet of 1m x 1m x 400 micron with cement concrete 1:2:4 (1 cement: 2 coarse sand: 4 graded stone aggregate of 12 mm nominal size) finished with 12 mm cement plaster 1:3 (1 cement: 3 coarse sand) and a coat of neat cement, rounding the edges, making and finishing complete. (Only plan area shall be paid).
| Total of Waterproofing Work |  |  |  | 1150000
| RMC BASIC RATE DIFF. | CUM | [7 empty] | 0 | 37190 | 37190
| Grand Total (Excluding GST) |  |  |  | 162331805 |  | 15790.3373 | 2825.294 | 18615.6313 | 21337062.4041 | 3189216.054 | 24526278.4581 |  | 3216391.9359
[11 empty] | 2300494.2774 | 12640000
37166278.4581
3.7166

## APP. BASIC RATE
TOWER-E RMC APPROVED RATE LIST
S.NO. | DATE | RMC PLANT NAME | UNIT | GRADE OF CONCRTE WITH CEMENT |  |  |  |  | GRADE OF CONCRTE WITHOUT CEMENT |  |  |  |  | REMARKS
|  |  |  | M10 | M25 | M30 | M35 | M40 | M10 | M25 | M30 | M35 | M40
1 | 2025-05-19 | SHUBHAM RMC | CUM | 4400 | 5100 | 5300 | 5500 |  | 3300 | 3300 | 3300 | 3300
2 |  | SRIJAN INFRA | CUM | 4600 | 5300 | 5550 | 5700 |  | 3450 | 3450 | 3400 | 3400
1 | 2025-11-03 | SHUBHAM RMC | CUM |  |  |  | 5200 | 5300
2 |  | ULTRATECH | CUM |  |  |  | 5300 | 5500
1 | 2025-11-17 | SHUBHAM RMC | CUM | 4400 | 4950
2 |  | ULTRATECH | CUM | 4500 | 5100

## RMC BASIC RATE DIFF
M/s. MARCO ENTERPRISES : RMC BASIC RATE DIFF. AT OMAXE ANANDA TOWER-E -PRAYAGRAJ
SN | DATE | RMC SUPPLIER | MATERIAL GRADE | UNIT | QTY | BASIC RATE | APPROVED RATE | DIFF. IN RATE | DIFF. AMOUNT | REMARKS
1 | 2025-05-14 | ELSA | M10 | CUM | 3.3 | 4200 | 4400 | 200 | 660
2 | 2025-05-20 | ELSA | M10 | CUM | 5.4 | 4200 | 4400 | 200 | 1080
3 | 2025-05-09 | SHUBHAM | M10 | CUM | 40 | 4200 | 4400 | 200 | 8000
4 | 2025-05-12 | SHUBHAM | M10 | CUM | 17.5 | 4200 | 4400 | 200 | 3500
5 | 2025-05-25 | SHUBHAM | M10 | CUM | 7.2 | 4200 | 4400 | 200 | 1440
6 | 2025-05-26 | SHUBHAM | M10 | CUM | 10 | 4200 | 4400 | 200 | 2000
7 | 2025-05-29 | SHUBHAM | M25 | CUM | 35 | 5200 | 5100 | -100 | -3500
8 | 2025-05-29 | ULTRATECH | M25 | CUM | 35 | 5200 | 5300 | 100 | 3500
9 | 2025-05-29 | SHUBHAM | M25 | CUM | 273 | 5200 | 5100 | -100 | -27300
10 | 2025-05-30 | ULTRATECH | M25 | CUM | 56 | 5200 | 5300 | 100 | 5600
11 | 2025-05-31 | SHUBHAM | M25 | CUM | 182 | 5200 | 5100 | -100 | -18200
12 | 2025-05-31 | ULTRATECH | M25 | CUM | 182 | 5200 | 5300 | 100 | 18200
13 | 2025-06-10 | ULTRATECH | M25 | CUM | 147 | 5200 | 5300 | 100 | 14700
14 | 2025-06-11 | ULTRATECH | M25 | CUM | 2 | 5200 | 5300 | 100 | 200
15 | 2025-06-12 | ULTRATECH | M25 | CUM | 21 | 5200 | 5300 | 100 | 2100
16 | 2025-06-12 | SHUBHAM | M25 | CUM | 133 | 5200 | 5100 | -100 | -13300
17 | 2025-06-13 | SRIJAN | M25 | CUM | 133 | 5200 | 5300 | 100 | 13300
18 | 2025-06-13 | SHUBHAM | M25 | CUM | 214 | 5200 | 5100 | -100 | -21400
19 | 2025-06-13 | ULTRATECH | M25 | CUM | 84 | 5200 | 5300 | 100 | 8400
20 | 2025-06-14 | SHUBHAM | M25 | CUM | 24 | 5200 | 5100 | -100 | -2400
21 | 2025-06-14 | ULTRATECH | M25 | CUM | 49 | 5200 | 5300 | 100 | 4900
22 | 2025-06-22 | ULTRATECH | M35 | CUM | 3 | 5200 | 5700 | 500 | 1500
23 | 2025-06-23 | ULTRATECH | M35 | CUM | 4 | 5200 | 5700 | 500 | 2000
24 | 2025-06-24 | ULTRATECH | M35 | CUM | 5 | 5200 | 5700 | 500 | 2500
25 | 2025-06-25 | ULTRATECH | M35 | CUM | 5 | 5200 | 5700 | 500 | 2500
26 | 2025-06-26 | ULTRATECH | M35 | CUM | 6 | 5200 | 5700 | 500 | 3000
27 | 2025-06-27 | ULTRATECH | M35 | CUM | 4 | 5200 | 5700 | 500 | 2000
28 | 2025-06-29 | ULTRATECH | M35 | CUM | 3 | 5200 | 5700 | 500 | 1500
29 | 2025-07-01 | SRIJAN | M35 | CUM | 8 | 5200 | 5700 | 500 | 4000
30 | 2025-07-02 | SRIJAN | M35 | CUM | 4.5 | 5200 | 5700 | 500 | 2250
31 | 2025-07-04 | SRIJAN | M35 | CUM | 3.5 | 5200 | 5700 | 500 | 1750
32 | 2025-07-05 | SRIJAN | M35 | CUM | 8 | 5200 | 5700 | 500 | 4000
33 | 2025-07-07 | SRIJAN | M35 | CUM | 3 | 5200 | 5700 | 500 | 1500
34 | 2025-07-08 | SRIJAN | M35 | CUM | 4 | 5200 | 5700 | 500 | 2000
35 | 2025-07-08 | SRIJAN | M25 | CUM | 14 | 5200 | 5300 | 100 | 1400
36 | 2025-07-09 | SRIJAN | M35 | CUM | 3.5 | 5200 | 5700 | 500 | 1750
37 | 2025-07-10 | SRIJAN | M35 | CUM | 3.5 | 5200 | 5700 | 500 | 1750
38 | 2025-09-25 | SHUBHAM | M35 | CUM | 3 | 5200 | 5500 | 300 | 900
39 | 2025-09-25 | SHUBHAM | M25 | CUM | 4 | 5200 | 5100 | -100 | -400
40 | 2025-09-25 | SHUBHAM | M25 | CUM | 4.5 | 5200 | 5100 | -100 | -450
41 | 2025-10-01 | SHUBHAM | M35 | CUM | 3 | 5200 | 5500 | 300 | 900
42 | 2025-10-01 | SHUBHAM | M25 | CUM | 4 | 5200 | 5100 | -100 | -400
43 | 2025-10-01 | SHUBHAM | M25 | CUM | 3.5 | 5200 | 5100 | -100 | -350
44 | 2025-10-07 | SHUBHAM | M35 | CUM | 3 | 5200 | 5500 | 300 | 900
45 | 2025-10-09 | SHUBHAM | M25 | CUM | 4 | 5200 | 5100 | -100 | -400
46 | 2025-10-09 | SHUBHAM | M35 | CUM | 2 | 5200 | 5500 | 300 | 600
47 | 2025-10-09 | SHUBHAM | M25 | CUM | 3 | 5200 | 5100 | -100 | -300
48 | 2025-10-10 | SHUBHAM | M25 | CUM | 2 | 5200 | 5100 | -100 | -200
49 | 2025-10-29 | SHUBHAM | M35 | CUM | 3 | 5200 | 5500 | 300 | 900
50 | 2025-10-30 | SHUBHAM | M25 | CUM | 4 | 5200 | 5100 | -100 | -400
51 | 2025-10-30 | SHUBHAM | M25 | CUM | 3.5 | 5200 | 5100 | -100 | -350
52 | 2025-11-11 | SHUBHAM | M40 | CUM | 2.5 | 5200 | 5300 | 100 | 250
53 | 2025-11-17 | SHUBHAM | M25 | CUM | 4 | 5200 | 4950 | -250 | -1000
54 | 2025-11-17 | SHUBHAM | M40 | CUM | 3.5 | 5200 | 5300 | 100 | 350
55 | 2025-11-18 | SHUBHAM | M40 | CUM | 4.5 | 5200 | 5300 | 100 | 450
56 | 2025-11-19 | SHUBHAM | M25 | CUM | 3 | 5200 | 4950 | -250 | -750
57 | 2025-11-19 | SHUBHAM | M40 | CUM | 3.5 | 5200 | 5300 | 100 | 350
58 | 2025-11-20 | SHUBHAM | M40 | CUM | 3.5 | 5200 | 5300 | 100 | 350
59 | 2025-11-24 | ELSA | M25 | CUM | 0.58 | 5200 | 4950 | -250 | -145
60 | 2025-11-28 | SHUBHAM | M40 | CUM | 3 | 5200 | 5300 | 100 | 300
61 | 2025-11-29 | SHUBHAM | M40 | CUM | 7 | 5200 | 5300 | 100 | 700
62 | 2025-11-30 | SHUBHAM | M40 | CUM | 3 | 5200 | 5300 | 100 | 300
63 | 2025-12-01 | ELSA | M25 | CUM | 6.82 | 5200 | 4950 | -250 | -1705
64 | 2025-12-02 | ELSA | M25 | CUM | 0.66 | 5200 | 4950 | -250 | -165
65 | 2025-12-02 | SHUBHAM | M40 | CUM | 11.5 | 5200 | 5300 | 100 | 1150
66 | 2025-12-03 | SHUBHAM | M40 | CUM | 6.5 | 5200 | 5300 | 100 | 650
67 | 2025-12-05 | SHUBHAM | M40 | CUM | 3 | 5200 | 5300 | 100 | 300
68 | 2025-12-06 | SHUBHAM | M40 | CUM | 6 | 5200 | 5300 | 100 | 600
69 | 2025-12-08 | SHUBHAM | M40 | CUM | 2.5 | 5200 | 5300 | 100 | 250
70 | 2025-12-09 | SHUBHAM | M25 | CUM | 8.5 | 5200 | 4950 | -250 | -2125
71 | 2025-12-18 | ELSA | M25 | CUM | 1 | 5200 | 4950 | -250 | -250
72 | 18.12.2025 | SHUBHAM | M40 | CUM | 2 | 5200 | 5300 | 100 | 200
73 | 19.12.2025 | SHUBHAM | M40 | CUM | 3 | 5200 | 5300 | 100 | 300
74 | 20.12.2025 | SHUBHAM | M40 | CUM | 3 | 5200 | 5300 | 100 | 300
75 | 20.12.2025 | SHUBHAM | M40 | CUM | 3.5 | 5200 | 5300 | 100 | 350
76 | 21.12.2025 | SHUBHAM | M40 | CUM | 3 | 5200 | 5300 | 100 | 300
77 | 21.12.2025 | SHUBHAM | M40 | CUM | 3 | 5200 | 5300 | 100 | 300
78 | 23.12.2025 | SHUBHAM | M40 | CUM | 3 | 5200 | 5300 | 100 | 300
79 | 25.12.2025 | SHUBHAM | M40 | CUM | 3 | 5200 | 5300 | 100 | 300
80 | 25.12.2025 | SHUBHAM | M40 | CUM | 2.5 | 5200 | 5300 | 100 | 250
81 | 26.12.2025 | SHUBHAM | M40 | CUM | 3 | 5200 | 5300 | 100 | 300
82 | 29.12.2025 | SHUBHAM | M40 | CUM | 3 | 5200 | 5300 | 100 | 300
83 | 31.12.2025 | SHUBHAM | M40 | CUM | 3.5 | 5200 | 5300 | 100 | 350
84 | 31.12.2025 | SHUBHAM | M40 | CUM | 4 | 5200 | 5300 | 100 | 400
85 | 01.01.2026 | SHUBHAM | M40 | CUM | 3.5 | 5200 | 5300 | 100 | 350
86 | 03.01.2026 | SHUBHAM | M40 | CUM | 3.5 | 5200 | 5300 | 100 | 350
87 | 04.01.2026 | SHUBHAM | M40 | CUM | 6 | 5200 | 5300 | 100 | 600
88 | 05.01.2026 | SHUBHAM | M40 | CUM | 4 | 5200 | 5300 | 100 | 400
89 | 06.01.2026 | SHUBHAM | M40 | CUM | 5.5 | 5200 | 5300 | 100 | 550
90 | 21.01.2026 | ULTRATECH | M40 | CUM | 12 | 5200 | 5500 | 300 | 3600
91 | 21.01.2026 | ULTRATECH | M25 | CUM | 35 | 5200 | 5100 | -100 | -3500
92 | 22.01.2026 | ULTRATECH | M25 | CUM | 63 | 5200 | 5100 | -100 | -6300
93 | 22.01.2026 | SHUBHAM | M25 | CUM | 6 | 5200 | 4950 | -250 | -1500
94 | 30.01.2026 | SHUBHAM | M40 | CUM | 12 | 5200 | 5300 | 100 | 1200
95 | 30.01.2026 | SHUBHAM | M25 | CUM | 35 | 5200 | 4950 | -250 | -8750
96 | 31.01.2026 | SHUBHAM | M25 | CUM | 28 | 5200 | 4950 | -250 | -7000
97 | 31.01.2026 | SHUBHAM | M40 | CUM | 6 | 5200 | 5300 | 100 | 600
98 | 01.02.2026 | SHUBHAM | M40 | CUM | 7 | 5200 | 5300 | 100 | 700
99 | 02.02.2026 | SHUBHAM | M40 | CUM | 5.5 | 5200 | 5300 | 100 | 550
100 | 05.02.2026 | ULTRATECH | M40 | CUM | 4 | 5200 | 5500 | 300 | 1200
101 | 06.02.2026 | ULTRATECH | M40 | CUM | 4 | 5200 | 5500 | 300 | 1200
102 | 07.02.2026 | ULTRATECH | M40 | CUM | 4.5 | 5200 | 5500 | 300 | 1350
103 | 09.02.2026 | ULTRATECH | M40 | CUM | 4 | 5200 | 5500 | 300 | 1200
104 | 10.02.2026 | ULTRATECH | M40 | CUM | 6.5 | 5200 | 5500 | 300 | 1950
105 | 11.02.2026 | ULTRATECH | M40 | CUM | 3.5 | 5200 | 5500 | 300 | 1050
106 | 12.02.2026 | ULTRATECH | M40 | CUM | 13 | 5200 | 5500 | 300 | 3900
107 | 12.02.2026 | ULTRATECH | M25 | CUM | 7 | 5200 | 5100 | -100 | -700
108 | 13.02.2026 | ULTRATECH | M40 | CUM | 9 | 5200 | 5500 | 300 | 2700
109 | 13.02.2026 | ULTRATECH | M25 | CUM | 98 | 5200 | 5100 | -100 | -9800
110 | 14.02.2026 | ULTRATECH | M40 | CUM | 4 | 5200 | 5500 | 300 | 1200
111 | 16.02.2026 | ULTRATECH | M40 | CUM | 3 | 5200 | 5500 | 300 | 900
112 | 17.02.2026 | ULTRATECH | M40 | CUM | 3 | 5200 | 5500 | 300 | 900
113 | 18.02.2026 | ULTRATECH | M40 | CUM | 4 | 5200 | 5500 | 300 | 1200
114 | 20.02.2026 | ULTRATECH | M40 | CUM | 8 | 5200 | 5500 | 300 | 2400
115 | 23.02.2026 | ULTRATECH | M40 | CUM | 4 | 5200 | 5500 | 300 | 1200
116 | 24.02.2026 | ULTRATECH | M40 | CUM | 3.5 | 5200 | 5500 | 300 | 1050
117 | 24.02.2026 | ULTRATECH | M25 | CUM | 7 | 5200 | 5100 | -100 | -700
118 | 25.02.2026 | ULTRATECH | M25 | CUM | 98 | 5200 | 5100 | -100 | -9800
119 | 25.02.2026 | ULTRATECH | M40 | CUM | 19.5 | 5200 | 5500 | 300 | 5850
120 | 26.02.2026 | ULTRATECH | M40 | CUM | 3.5 | 5200 | 5500 | 300 | 1050
121 | 27.02.2026 | ULTRATECH | M40 | CUM | 9.5 | 5200 | 5500 | 300 | 2850
122 | 02.03.2026 | ULTRATECH | M40 | CUM | 11 | 5200 | 5500 | 300 | 3300
123 | 02.03.2026 | ULTRATECH | M25 | CUM | 77 | 5200 | 5500 | 300 | 23100
124 | 11.03.2026 | SHUBHAM | M25 | CUM | 21 | 5200 | 4950 | -250 | -5250
125 | 11.03.2026 | SHUBHAM | M40 | CUM | 5 | 5200 | 5300 | 100 | 500
126 | 12.03.2026 | SHUBHAM | M25 | CUM | 77 | 5200 | 4950 | -250 | -19250
127 | 12.03.2026 | SHUBHAM | M40 | CUM | 9 | 5200 | 5300 | 100 | 900
128 | 13.03.2026 | SHUBHAM | M25 | CUM | 7 | 5200 | 4950 | -250 | -1750
| Total Qty upto date |  |  |  | 2665.46 |  |  |  | 37190

## EARTH WORK MB
COMPANY- OMAXE PANCHAM REALCON PVT LTD
PROJECT- TOWER-E
LOCATION- NAINI, PRAYAGRAJ
MB SHEET- SOIL SURFACE DRESSING BELOW PLINTH BEAM
& SOIL BACK FILLING WORK
S.NO. | DESCRIPTION | UNIT | NOS | NOS | MEASUREMENT |  |  | QTY. | REMARKS
[5 empty] | L | B | H/T
SOIL DRESSING FOR RAFT PCC
1 | GRID (22'-43'/A-Q') | SQM | 1 | 1 | 32.365 | 37.325 |  | 1208.0236 | 3RD RA
2 |  | SQM | 1 | 1 | 9.21 | 0.515 |  | 4.7431
3 | GRID (22'-26'/M'-Q') | SQM | -1 | 1 | 11.005 | 12.415 |  | -136.6271
4 | GRID (38'-43'/A-E') | SQM | -1 | 1 | 11.09 | 10.285 |  | -114.0606
5 | GRID (22'-30'/A-B') | SQM | -1 | 1 | 11.285 | 3.72 |  | -41.9802
6 |  | SQM | -1 | 1 | 1.695 | 2.315 |  | -3.9239
7 |  | SQM | -1 | 1 | 3.95 | 1.5 |  | -5.925
8 |  | SQM | -1 | 1 | 15.8 | 0.215 |  | -3.397
1 | GRID (1-22'/A-Q') | SQM | 1 | 1 | 32.365 | 41.495 |  | 1342.9857 | 4TH RA
2 |  | SQM | 1 | 1 | 9.21 | 0.515 |  | 4.7431
3 | GRID (17'-22'/M'-Q') | SQM | -1 | 1 | 15.175 | 12.415 |  | -188.3976
4 | GRID (1-5'/A-E') | SQM | -1 | 1 | 11.09 | 10.285 |  | -114.0606
5 | GRID (14'-22'/A-B') | SQM | -1 | 1 | 15.455 | 3.72 |  | -57.4926
6 |  | SQM | -1 | 1 | 1.695 | 2.315 |  | -3.9239
7 |  | SQM | -1 | 1 | 3.95 | 1.5 |  | -5.925
8 |  | SQM | -1 | 1 | 15.8 | 0.215 |  | -3.397
FLAT AREA SOIL DRESSING WORK GRID (22-43/A-Q)
7TH RA
| 1 | SQM | 1 | 1 | 5.15 | 3.15
| 2,3 | SQM | 1 | 2 | 3.17 | 2.41
| 2' | SQM | 1 | 1 | 3.55 | 3.17
| 4,10 | SQM | 1 | 1 | 5.49 | 3.25
| 5,9 | SQM | 1 | 1 | 2.925 | 1.7
| 6 | SQM | 1 | 1 | 3.385 | 1.425
| 7 | SQM | 1 | 1 | 1.455 | 1.425
| 8 | SQM | 1 | 1 | 1.7 | 1.425
| 11 | SQM | 1 | 1 | 3.33 | 1.83
|  | SQM | 1 | 1 | 4.27 | 1.93
|  | SQM | 1 | 1 | 7.665 | 3.14
| 12 | SQM | 1 | 1 | 4.27 | 1.7
| 13 | SQM | 1 | 1 | 1.6 | 1.44
| 14 | SQM | 1 | 1 | 1.69 | 1.6
| 15,16 | SQM | 1 | 2 | 3.56 | 3.275
| 17 | SQM | 1 | 1 | 2.25 | 1.525
| 18 | SQM | 1 | 1 | 6.165 | 3.72
|  | SQM | 1 | 1 | 3.915 | 0.385
| 19 | SQM | 1 | 1 | 3.55 | 3.2
| 20 | SQM | 1 | 1 | 5.35 | 3.575
| 21 | SQM | 1 | 1 | 2.815 | 1.8
|  | SQM | 1 | 1 | 4.945 | 2.1
|  | SQM | 1 | 1 | 3.115 | 0.95
| 22 | SQM | 1 | 1 | 5.935 | 2.345
|  | SQM | -1 | 1 | 1.3 | 0.5
|  | SQM | 1 | 1 | 2.03 | 1.5
| 23 | SQM | 1 | 1 | 5.7 | 3.2
| 24 | SQM | 1 | 1 | 3.95 | 1.61
|  | SQM | 1 | 1 | 1.92 | 1.5
| 25 | SQM | 1 | 1 | 2.225 | 1.495
| 26 | SQM | 1 | 1 | 3.95 | 3.845
| 27 | SQM | 1 | 1 | 5.72 | 2.44
|  | SQM | 1 | 1 | 1.2 | 0.35
| 28 | SQM | 1 | 1 | 3.23 | 3.075
|  | SQM | 1 | 1 | 5.14 | 3.17
| 29 | SQM | 1 | 1 | 3.86 | 3.335
| 30 | SQM | 1 | 1 | 4.92 | 3.86
| 31 | SQM | 1 | 1 | 3.55 | 3.265
| 32 | SQM | 1 | 1 | 3.52 | 3.08
| 33 | SQM | 1 | 1 | 3.435 | 2.345
| 34 | SQM | 1 | 1 | 3.435 | 2.245
| 35 | SQM | 1 | 1 | 4.79 | 3.19
|  | SQM | 1 | 1 | 1.4 | 0.655
| 36 | SQM | 1 | 1 | 3.475 | 2.23
| 37,42 | SQM | 1 | 2 | 3.55 | 3.265
| 38,41 | SQM | 1 | 2 | 3.55 | 3.08
| 39,40 | SQM | 1 | 2 | 5.15 | 3.27
|  | SQM | 1 | 2 | 3.24 | 3.075
| 43.46 | SQM | 1 | 2 | 4.92 | 3.86
| 44,45 | SQM | 1 | 2 | 3.86 | 3.335
[7 empty] | TOTAL | 1881.385
SOIL BACK FILLING GRID (1-43/A-Q)
| BACK FILLING | SQM | 1 | 1 | 2463.03 |  | 2.65 | 6527.0295 |  | Upto Road LVL. (HT From JK Bill)
| DED. PCC | SQM | -1 | 1 | 1851.82 |  | 0.1 | -185.182
| DED. RAFT RCC | SQM | -1 | 1 |  |  | 1552.4224 | -1552.4224
| DED. PADESTIAL RCC | SQM | -1 | 1 |  |  | 64.0259 | -64.0259
[7 empty] | TOTAL | 4725.3991

## CONCRETE RECO.
RCC SUMMARY : OMAXE TOWER-E
M/s. MARCO ENTERPRISES
S.No. | Item Discription | Grade | Floor Name | NO | Unit Qty. | Quantity | Unit | M10 | M25 | M30 | M35 | M40
TOWER-E
1 | RAFT PCC GRID (A-Q/23-43) | M10 | AS SUB-STRUCTURE | 1 | 56.7982 | 56.7982 | Cum | 56.7982 | - | - | - | -
2 | RAFT RCC GRID (A-Q/23-43) | M25 | AS SUB-STRUCTURE | 1 | 748.2097 | 748.2097 | Cum | - | 748.2097 | - | - | -
3 | RAFT PCC GRID (A-Q/1-23) | M10 | AS SUB-STRUCTURE | 1 | 22.6685 | 22.6685 | Cum | 22.6685 | - | - | - | -
4 | RAFT RCC GRID (A-Q/1-43) | M25 | AS SUB-STRUCTURE | 1 | 792.1258 | 792.1258 | Cum | - | 792.1258 | - | - | -
5 | COMPENSATORY STRIP (22-23/B'-L') | M25 | AS SUB-STRUCTURE | 1 | 12.087 | 12.087 | Cum | - | 12.087 | - | - | -
6 | PADESTIAL & LIFT (1-43/A-Q) | M35 | AS SUB-STRUCTURE | 1 | 64.0259 | 64.0259 | Cum | - | - | - | 64.0259 | -
7 | PLINTH BEAM (1-43/A-Q) | M25 | AS SUB-STRUCTURE | 1 | 51.6018 | 51.6018 | Cum | - | 51.6018 | - | - | -
8 | COLUMN JUNCTION AT PLINTH BEAM LVL (1-43/A-Q) | M35 | AS SUB-STRUCTURE | 1 | 14 | 14 | Cum | - | - | - | 14 | -
9 | COLUMN JUNCTION AT PLINTH BEAM LVL (1-43/A-Q) | M40 | AS SUB-STRUCTURE | 1 | 4.497 | 4.497 | Cum | - | - | - | - | 4.497
10 | COLUMN FROM PLINTH BEAM LVL TO 1ST FLOOR LVL (22-43/A-Q) | M40 | AS SUPER-STRUCTURE | 1 | 48.0455 | 48.0455 | Cum | - | - | - | - | 48.0455
11 | COLUMN FROM PLINTH BEAM LVL TO 1ST FLOOR LVL (1-22/A-Q) | M40 | AS SUPER-STRUCTURE | 1 | 45.9755 | 45.9755 | Cum | - | - | - | - | 45.9755
12 | EXTRA HEIGHT COLUMN FROM PLINTH BEAM LVL TO 1ST FLOOR LVL (1-43/A-Q) | M40 | AS SUPER-STRUCTURE | 1 | 4.9455 | 4.9455 | Cum | - | - | - | - | 4.9455
13 | SLAB AT 1ST FLOOR LVL (22-43/A-Q) | M40 | AS SUPER-STRUCTURE | 1 | 24 | 24 | Cum | - | - | - | - | 24
14 | SLAB AT 1ST FLOOR LVL (22-43/A-Q) | M25 | AS SUPER-STRUCTURE | 1 | 129.7933 | 129.7933 | Cum | - | 129.7933 | - | - | -
15 | SLAB AT 1ST FLOOR LVL (1-22/A-Q) | M40 | AS SUPER-STRUCTURE | 1 | 15 | 15 | Cum | - | - | - | - | 15
16 | SLAB AT 1ST FLOOR LVL (1-22/A-Q) | M25 | AS SUPER-STRUCTURE | 1 | 138.7933 | 138.7933 | Cum | - | 138.7933 | - | - | -
18 | COLUMN FROM 1ST TO 2ND FLOOR LVL (1-43/A-Q) | M40 | AS SUPER-STRUCTURE | 1 | 94.021 | 94.021 | Cum | - | - | - | - | 94.021
21 | SLAB AT 2ND FLOOR LVL (1-22/A-Q) | M40 | AS SUPER-STRUCTURE | 1 | 29.1595 | 29.1595 | Cum | - | - | - | - | 29.1595
22 | SLAB AT 2ND FLOOR LVL (1-22/A-Q) | M25 | AS SUPER-STRUCTURE | 1 | 300.8041 | 300.8041 | Cum | - | 300.8041 | - | - | -
22 | COLUMN FROM 2ND TO 3RD FLOOR LVL (1-43/A-Q) | M40 | AS SUPER-STRUCTURE | 0.5 | 47.0105 | 23.5052 | Cum | - | - | - | - | 23.5052
| TOTAL RCC QTY (THEORITICAL) |  |  |  |  | 2620.0568 | Cum | 79.4667 | 2173.4149 | 0 | 78.0259 | 289.1492
| TOTAL RCC QTY (CASTING) |  |  |  |  | 2666.46 | Cum | 83.4 | 2200.06 | 0 | 82 | 301
| DIFFERENCE (WASTAGE) |  |  |  |  | -46.4032 | Cum | -3.9333 | -26.6451 | 0 | -3.9741 | -11.8508
| WASTAGE % |  |  |  |  | -1.771% |  | -4.95% | -1.226% | #DIV/0! | -5.093% | -4.098%
| PREV. BILL RCC QTY (THEORITICAL) |  |  |  |  | 2172.57 | Cum | 79.4667 | 1871.61 | 0 | 78.03 | 266.98
| PREV. BILL RCC QTY (CASTING-ACTUAL) |  |  |  |  | 2233.46 | Cum | 83.4 | 1911.06 | 0 | 82 | 286
| DIFFERENCE (WASTAGE) |  |  |  |  | -60.89 | Cum | -3.9333 | -39.45 | 0 | -3.97 | -19.02
| WASTAGE % |  |  |  |  | -2.803% |  | -4.95% | -2.108% | #DIV/0! | -5.088% | -7.124%
| THIS BILL RCC QTY (THEORITICAL) |  |  |  |  | 447.4868 | Cum | 0 | 301.8049 | 0 | -0.004088 | 22.1692
| THIS BILL RCC QTY (CASTING-ACTUAL) |  |  |  |  | 433 | Cum | 0 | 289 | 0 | 0 | 15
| DIFFERENCE (WASTAGE) |  |  |  |  | 14.4868 | Cum | 0 | 12.8049 | 0 | -0.004088 | 7.1692
| WASTAGE % |  |  |  |  | 3.237% |  | #DIV/0! | 4.243% | #DIV/0! | 100% | 32.34%

## CONCRETE SUMMARY
TOWER-E CONCRETE WORK SUMMARY
|  |  | QTY | [9 empty] | TOTAL
2 | CONCRETE WORK |  | 3rd RA | 4th RA | 5th RA | 6th RA | 7th RA | 8th RA | 9th RA | 10th RA | 11th RA
Rates for all cement concrete items plain and reinforced described below shall include work from Basement Level to top of last roof including roof of machine room, mumty, over head water tanks and parapets above at all floors and for all heights. The contractor should provide full time sufficient pipes with accessories and pumps based on the site requirement for pumping and laying of concrete as directed by the EIC. The rate inclusive of standard rigid pipe line and its supports, lifting, laying charges, etc., at all heights and levels. No additional payment shall be payable to the contractor on account of using or change in any size of coarse aggregate in PCC/ RCC work at any stage during currency of works. (This section covers cast in situ structural and architectural as well.)
2.1 | Plain Cement Concrete: Providing and laying plain cement concrete of specified grade as bed concrete under foundation, bases for rafts, underground water tank, building machine equipments, column footing, under floor landings, below road and pathways, cill, coping, screeding at roof to required slope and other locations as called for laid, consolidated and cured etc. complete including finishing the top surface to receive the next course / layer as per specification and drawing. (Shuttering shall be paid in Item No.3.1.1) M10 Grade (Basic Rate of PCC - Rs. 4200/cum) without pump | CUM | QTY 3rd RA: 56.7982; QTY 4th RA: 22.6685 |  | 79.4667
2.2. | Providing and laying cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) for ledge wall below balcony railings, band, mullion, lintel etc. (Shuttering shall be paid separately in respective item) as per drawing and as directed by the Project Manager. | CUM | [10 empty] | 0
2.3. | Providing and laying damp proof course 40mm thick including shttering with cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) including mixing of water proofing compound @ 2% of cement content and applying two layers of bitumen @ 1.70 Kg/Sqm of grade 85/25 and as directed by the Project Manager. | SQM | [10 empty] | 0
2.4. | RCC WORK
Providing & Laying RMC M-25 Grade as per approved design mix concrete (strictly controlled conditions) with flyash (as per approved design mix) with automatic batching plant machine mixed and machine vibrated RCC with melamine based plasticisers etc., upto any level, including finishing the exposed surface, fixing/ removal of pockets, fixing of sleeves and inserts (sleeves provided by client), curing etc complete, as per drawing (including all size and shape like circular, semi-circular, oval etc.) and as directed for all lead and lift, excluding cost of centering, shuttering and steel reinforcement but including cost of making shear keys and provision of construction / contraction / control joints in various locations. Checking from Client should not be considered as final and any defects arising during or after casting should be borne & bear by contractor at his own cost. This is inclusive of leaving shuttering & centring for pour strip, slab in slope, RCC members in curved, etc., nothing is payable extra on this account. RMC (M-25) Basic Rate - Rs. 5200/cum without pump excluding GST
2.4.1. | Foundation, column footings, raft slab, raft beams, plinth beam, lift pits, sump pits, pedestals / bases of column, column upto plinth, swimming pool, Retaining wall foundations, grade slab etc. | CUM | QTY 3rd RA: 748.2097; QTY 4th RA: 792.1258; QTY 5th RA: 76.1129; QTY 7th RA: 70.0988 |  | 1686.5471
2.4.2. | Suspended floors, roofs, balconies, shelves/ counters, stair waist slabs, folded plate stairs and landings, swimming pool slab, lintel and floor beams, landing beams, girders (deep beams), RCC bands, swimming pool beam, cantilever projections, coping, cills, slab of tank etc at all levels.
2.4.2.1. | Stilt Floor level to 7th Floor level | CUM | QTY 8th RA: 153.7933; QTY 9th RA: 153.7933; QTY 10th RA: 153.607; QTY 11th RA: 153.607 |  | 614.8006
2.4.2.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | CUM | [10 empty] | 0
2.4.2.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | CUM | [10 empty] | 0
2.5. | Columns, Wall, pillars, piers, abutments, posts and struts, offset and projection of columns, water tank walls, lift walls, Retaining Wall, swimming pool, Parapets, planters, vertical projection of pergolas, wall and ramp walls etc. at all levels. | [12 empty] | 170
2.5.1. | Stilt Floor level to 7th Floor level | CUM | QTY 7th RA: 48.0455; QTY 8th RA: 50.921; QTY 10th RA: 94.021; QTY 11th RA: 76.17 |  | 269.1575
2.5.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | CUM | [10 empty] | 0
2.5.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | CUM | [10 empty] | 0
2.5.4. | Finishing vaccum dewatering continuous concrete flooring 100-150 mm thick with specified grade concrete including necessary formwork in required level, vibrating concrete both by poker vibrators / leveling vaccum processing of the concrete and planning the surface by skin powered floater trowels with broom/plain finish including groove cutting & filling etc. complete. (Concrete shall be paid in the respective items above). | SQM | [10 empty] | 0
|  |  | 805.0079 | 814.7942 | 76.1129 | 0 | 118.1443 | 204.7143 | 153.7933 | 247.628 | 229.777 | TOTAL | 2649.9719

## PCC & RCC REC.
S.NO. | MONTH | DATE | RMC |  |  |  |  | ELSA |  |  |  |  | MANUAL |  |  |  |  | WORK IN PROGRSS | TOTAL | REMARK
|  |  | GRADE |  |  |  |  | GRADE |  |  |  |  | GRADE
|  |  | M10 | M25 | M30 | M35 | M40 | M10 | M25 | M30 | M35 | M40 | M10 | M25 | M30 | M35 | M40
1 | 2025-05-01 | 2025-05-14 | [5 empty] | 3.3 | [11 empty] | TOWER-E RAFT PCC
2 |  | 2025-05-20 | [5 empty] | 5.4 | [11 empty] | TOWER-E RAFT PCC
3 |  | 2025-05-09 | 40 | [16 empty] | TOWER-E RAFT PCC
4 |  | 2025-05-12 | 17.5 | [16 empty] | TOWER-E RAFT PCC
5 |  | 2025-05-25 | [5 empty] | 7.2 | [11 empty] | TOWER-E RAFT PCC
6 |  | 2025-05-26 | [5 empty] | 10 | [11 empty] | TOWER-E RAFT PCC
7 |  | 2025-05-29 |  | 70 | [15 empty] | TOWER-E RAFT RCC (23-43)
8 |  | 2025-05-30 |  | 329 | [15 empty] | TOWER-E RAFT RCC (23-43)
9 |  | 2025-05-31 |  | 364 | [15 empty] | TOWER-E RAFT RCC (23-43)
10 | 2025-06-01 | 2025-06-10 |  | 147 | [15 empty] | TOWER-E RAFT RCC (1-23)
11 |  | 2025-06-11 |  | 2 | [15 empty] | TOWER-E RAFT RCC (1-23)
12 |  | 2025-06-12 |  | 154 | [15 empty] | TOWER-E RAFT RCC (1-23)
13 |  | 2025-06-13 |  | 431 | [15 empty] | TOWER-E RAFT RCC (1-23)
14 |  | 2025-06-14 |  | 73 | [15 empty] | TOWER-E RAFT RCC (1-23)
15 |  | 2025-06-22 |  |  |  | 3 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
16 |  | 2025-06-23 |  |  |  | 4 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
17 |  | 2025-06-24 |  |  |  | 5 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
18 |  | 2025-06-25 |  |  |  | 5 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
19 |  | 2025-06-26 |  |  |  | 6 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
20 |  | 2025-06-27 |  |  |  | 4 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
21 |  | 2025-06-29 |  |  |  | 3 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
22 | 2025-07-01 | 2025-07-01 |  |  |  | 8 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
23 |  | 2025-07-02 |  |  |  | 4.5 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
24 |  | 2025-07-04 |  |  |  | 3.5 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
25 |  | 2025-07-05 |  |  |  | 8 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
26 |  | 2025-07-07 |  |  |  | 3 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
27 |  | 2025-07-08 |  |  |  | 4 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
28 |  | 2025-07-08 |  | 14 | [15 empty] | TOWER-E RAFT COMPENSATORY STRIP (22-23/B'-L')
29 |  | 2025-07-09 |  |  |  | 3.5 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
30 |  | 2025-07-10 |  |  |  | 3.5 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
31 | 2025-09-01 | 2025-09-25 |  |  |  | 3 | [13 empty] | COLUMN JUNCTION AT PLINTH BEAM
32 |  | 2025-09-25 |  | 4 | [15 empty] | PLINTH BEAM
33 |  | 2025-09-25 |  | 4.5 | [15 empty] | PLINTH BEAM
34 | 2025-10-01 | 2025-10-01 |  |  |  | 3 | [13 empty] | COLUMN JUNCTION AT PLINTH BEAM
35 |  | 2025-10-01 |  | 4 | [15 empty] | PLINTH BEAM
36 |  | 2025-10-01 |  | 3.5 | [15 empty] | PLINTH BEAM
37 |  | 2025-10-07 |  |  |  | 3 | [13 empty] | COLUMN JUNCTION AT PLINTH BEAM
38 |  | 2025-10-09 |  | 4 | [15 empty] | PLINTH BEAM
39 |  | 2025-10-09 |  |  |  | 2 | [13 empty] | COLUMN JUNCTION AT PLINTH BEAM
40 |  | 2025-10-09 |  | 3 | [15 empty] | PLINTH BEAM
41 |  | 2025-10-10 |  | 2 | [15 empty] | PLINTH BEAM
42 |  | 2025-10-29 |  |  |  | 3 | [13 empty] | COLUMN JUNCTION AT PLINTH BEAM
43 |  | 2025-10-30 |  | 4 | [15 empty] | PLINTH BEAM
44 |  | 2025-10-30 |  | 3.5
45 | 2025-11-01 | 2025-11-11 |  |  |  |  | 2.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
46 |  | 2025-11-17 |  | 4 | [15 empty] | PLINTH BEAM
47 |  | 2025-11-17 |  |  |  |  | 3.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
48 |  | 2025-11-18 |  |  |  |  | 4.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
49 |  | 2025-11-19 |  | 3 | [15 empty] | PLINTH BEAM
50 |  | 2025-11-19 |  |  |  |  | 3.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
51 |  | 2025-11-20 |  |  |  |  | 3.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
52 |  | 2025-11-24 | [6 empty] | 0.58 | [10 empty] | PLINTH BEAM
53 |  | 2025-11-28 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
54 |  | 2025-11-29 |  |  |  |  | 7 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
55 |  | 2025-11-30 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
56 | 2025-12-01 | 2025-12-01 | [6 empty] | 6.82 | [10 empty] | PLINTH BEAM
57 |  | 2025-12-02 |  |  |  |  | 4 |  | 0.66 | [10 empty] | PLINTH BEAM
58 |  | 2025-12-02 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
59 |  | 2025-12-02 |  |  |  |  | 4.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
60 |  | 2025-12-03 |  |  |  |  | 6.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
61 |  | 2025-12-05 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
62 |  | 2025-12-06 |  |  |  |  | 6 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
63 |  | 2025-12-08 |  |  |  |  | 2.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
64 |  | 2025-12-09 |  | 8.5 | [15 empty] | PLINTH BEAM
65 |  | 2025-12-18 | [6 empty] | 1 | [10 empty] | PLINTH BEAM
66 |  | 18.12.2025 |  |  |  |  | 2 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
67 |  | 19.12.2025 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
68 |  | 20.12.2025 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
69 |  | 20.12.2025 |  |  |  |  | 3.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
70 |  | 21.12.2025 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
71 |  | 21.12.2025 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
72 |  | 23.12.2025 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
73 |  | 25.12.2025 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
74 |  | 25.12.2025 |  |  |  |  | 2.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
75 |  | 26.12.2025 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
76 |  | 29.12.2025 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
77 |  | 31.12.2025 |  |  |  |  | 3.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
78 |  | 31.12.2025 |  |  |  |  | 4 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
79 | 2026-01-01 | 01.01.2026 |  |  |  |  | 3.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
80 |  | 03.01.2026 |  |  |  |  | 3.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
81 |  | 04.01.2026 |  |  |  |  | 6 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
82 |  | 05.01.2026 |  |  |  |  | 4 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
83 |  | 06.01.2026 |  |  |  |  | 5.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
84 |  | 21.01.2026 |  |  |  |  | 12 | [12 empty] | 1ST FLOOR LVL SLAB
85 |  | 21.01.2026 |  | 35 | [15 empty] | 1ST FLOOR LVL SLAB
86 |  | 22.01.2026 |  | 69 | [15 empty] | 1ST FLOOR LVL SLAB
87 |  | 30.01.2026 |  | 35 |  |  | 12 | [12 empty] | 1ST FLOOR LVL SLAB
88 |  | 31.01.2026 |  | 28 | [15 empty] | 1ST FLOOR LVL SLAB
89 |  | 31.01.2026 |  |  |  |  | 6 | [12 empty] | 1ST FLOOR LVL COLUMN
90 | 2026-02-01 | 01.02.2026 |  |  |  |  | 7 | [12 empty] | 1ST FLOOR LVL COLUMN
91 |  | 02.02.2026 |  |  |  |  | 5.5 | [12 empty] | 1ST FLOOR LVL COLUMN
92 |  | 05.02.2026 |  |  |  |  | 4 | [12 empty] | 1ST FLOOR LVL COLUMN
93 |  | 06.02.2026 |  |  |  |  | 4 | [12 empty] | 1ST FLOOR LVL COLUMN
94 |  | 07.02.2026 |  |  |  |  | 4.5 | [12 empty] | 1ST FLOOR LVL COLUMN
95 |  | 09.02.2026 |  |  |  |  | 4 | [12 empty] | 1ST FLOOR LVL COLUMN
96 |  | 10.02.2026 |  |  |  |  | 6.5 | [12 empty] | 1ST FLOOR LVL COLUMN
97 |  | 11.02.2026 |  |  |  |  | 3.5 | [12 empty] | 1ST FLOOR LVL COLUMN
98 |  | 12.02.2026 |  |  |  |  | 3 | [12 empty] | 1ST FLOOR LVL COLUMN
99 |  | 12.02.2026 |  | 7 |  |  | 10 | [12 empty] | 1ST FLOOR LVL SLAB
100 |  | 13.02.2026 |  | 98 |  |  | 5 | [12 empty] | 1ST FLOOR LVL SLAB
101 |  | 13.02.2026 |  |  |  |  | 4 | [12 empty] | 1ST FLOOR LVL COLUMN
102 |  | 14.02.2026 |  |  |  |  | 4 | [12 empty] | 1ST FLOOR LVL COLUMN
103 |  | 16.02.2026 |  |  |  |  | 3 | [12 empty] | 1ST FLOOR LVL COLUMN
104 |  | 17.02.2026 |  |  |  |  | 3 | [12 empty] | 1ST FLOOR LVL COLUMN
105 |  | 18.02.2026 |  |  |  |  | 4 | [12 empty] | 1ST FLOOR LVL COLUMN
106 |  | 20.02.2026 |  |  |  |  | 8 | [12 empty] | 1ST FLOOR LVL COLUMN
107 |  | 23.02.2026 |  |  |  |  | 4 | [12 empty] | 1ST FLOOR LVL COLUMN
108 |  | 24.02.2026 |  |  |  |  | 3.5 | [12 empty] | 1ST FLOOR LVL COLUMN
109 |  | 24.02.2026 |  | 7 | [15 empty] | 2ND FLOOR LVL SLAB
110 |  | 25.02.2026 |  | 98 |  |  | 19.5 | [12 empty] | 2ND FLOOR LVL SLAB
111 |  | 26.02.2026 |  |  |  |  | 3.5 | [12 empty] | 1ST FLOOR LVL COLUMN
112 |  | 27.02.2026 |  |  |  |  | 9.5 | [12 empty] | 1ST FLOOR LVL COLUMN
113 | 2026-03-01 | 2.03.2026 |  | 77 |  |  | 11 | [12 empty] | 2ND FLOOR LVL SLAB
114 |  | 11.03.2026 |  | 21 | [15 empty] | 2ND FLOOR LVL SLAB
115 |  | 11.03.2026 |  |  |  |  | 4 | [12 empty] | 2ND FLOOR LVL SLAB
116 |  | 12.03.2026 |  |  |  |  | 11 | [12 empty] | 2ND FLOOR LVL SLAB
117 |  | 12.03.2026 |  | 77 | [15 empty] | 2ND FLOOR LVL SLAB
118 |  | 13.03.2026 |  | 7 | [15 empty] | 2ND FLOOR LVL SLAB
| TOTAL |  | 57.5 | 2191 | 0 | 82 | 301 | 25.9 | 9.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2666.46
| GRAND TOTAL |  | 57.5 | 2191 | 0 | 82 | 301 | 25.9 | 9.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2666.46
| TOTAL RCC BY RMC/ELSA /MANUAL |  | 2631.5 |  |  |  |  | 34.96 |  |  |  |  | 0 |  |  |  |  | 0 | 2666.46
| RCC BY RMC + ELSA |  | 2666.46

## RMC RECEIVING
M/s. MARCO ENTERPRISES : RMC RECEIVING AT OMAXE ANANDA TOWER-E -PRAYAGRAJ
SN | DATE | VEHICLE NO | CHALLAN NO/INVOICE NO. | MATERIAL GRADE | UNIT | RMC PLANT QTY (M 10) | RMC PLANT QTY (M 25) | RMC PLANT QTY (M 30) | RMC PLANT QTY (M 35) | RMC PLANT QTY (M 40) | ACTUAL CEMENT WEIGHT BY DESIGN MIX | CEMENT WEIGHT BY RMC PLANT | CEMENT DIFF (IN KG) | IN TIME | OUT TIME | TOWER NO | TYPE OF WORK | RMC SUPPLIER | REMARKS
1 | 2025-05-09 | UP32VN6145 | 449 | RMC10 | CUM | 7 |  |  |  |  | 1540 | 1540 | 0 | 10:50 | 12:15 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
2 | 2025-05-09 | UP32WN8332 | 450 | RMC10 | CUM | 7 |  |  |  |  | 1540 | 1540 | 0 | 12:30 | 13:40 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
3 | 2025-05-09 | UP53HT5034 | 451 | RMC10 | CUM | 7 |  |  |  |  | 1540 | 1540 | 0 | 13:52 | 14:40 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
4 | 2025-05-09 | UP32VN6145 | 453 | RMC10 | CUM | 7 |  |  |  |  | 1540 | 1540 | 0 | 14:50 | 16:00 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
5 | 2025-05-09 | UP32WN8334 | 454 | RMC10 | CUM | 6 |  |  |  |  | 1320 | 1320 | 0 | 16:30 | 17:45 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
6 | 2025-05-09 | UP53HT5034 | 457 | RMC10 | CUM | 6 |  |  |  |  | 1320 | 1320 | 0 | 18:35 | 19:30 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
7 | 2025-05-12 | UP32WN8334 | 487 | RMC10 | CUM | 5 |  |  |  |  | 1100 | 1096 | -4 | 18:35 | 19:30 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
8 | 2025-05-12 | UP32WN8334 | 488 | RMC10 | CUM | 5 |  |  |  |  | 1100 | 1096 | -4 | 18:35 | 19:30 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
9 | 2025-05-12 | UP32VN6144 | 490 | RMC10 | CUM | 5.5 |  |  |  |  | 1210 | 1210 | 0 | 18:35 | 19:30 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
10 | 2025-05-12 | UP32VN6144 | 494 | RMC10 | CUM | 2 |  |  |  |  | 440 | 440 | 0 | 18:35 | 19:30 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
11 | 29.05.2025 | UP32VN6145 | 721 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 22:30 | 23:08 | TOWER-E (23-43) | RAFT | SHUBHAM
12 | 29.05.2025 | UP32WN8334 | 722 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 23:12 | 23:33 | TOWER-E (23-43) | RAFT | SHUBHAM
13 | 29.05.2025 | UP32WN8333 | 723 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 23:39 | 12:02PM | TOWER-E (23-43) | RAFT | SHUBHAM
14 | 29.05.2025 | UP32HT5032 | 724 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2574 | 19 | 12:05 | 0:19 | TOWER-E (23-43) | RAFT | SHUBHAM
15 | 29.05.2025 | UP32HT5034 | 725 | RMC 25 | CUM |  | 5.5 |  |  |  | 2007.5 | 2018 | 10.5 | 0:23 | 0:42 | TOWER-E (23-43) | RAFT | SHUBHAM
| 29.05.2025 | UP32HT5034 | 726 | RMC 25 | CUM |  | 1.5 |  |  |  | 547.5 | 548 | 0.5 | 0:23 | 0:42 | TOWER-E (23-43) | RAFT | SHUBHAM
16 | 29.05.2025 | UP70QT2013 | 905350012 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 22:30 | 23:07 | TOWER-E (23-43) | RAFT | ULTRATECH
17 | 29.05.2025 | UP70QT2341 | 905350013 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 23:13 | 23:41 | TOWER-E (23-43) | RAFT | ULTRATECH
18 | 29.05.2025 | UP70QT2015 | 905350014 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 23:41 | 24:12 | TOWER-E (23-43) | RAFT | ULTRATECH
19 | 29.05.2025 | UP70QT2342 | 905350015 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 1:16 | 1:43 | TOWER-E (23-43) | RAFT | ULTRATECH
20 | 29.05.2025 | UP70QT2014 | 905350016 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 1:49 | 2:05 | TOWER-E (23-43) | RAFT | ULTRATECH
21 | 30.05.2025 | UP32VN6145 | 727 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 1:02 | 1:50 | TOWER-E (23-43) | RAFT | SHUBHAM
22 | 30.05.2025 | UP32WN8334 | 728 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2551 | -4 | 1:52 | 2:15 | TOWER-E (23-43) | RAFT | SHUBHAM
23 | 30.05.2025 | UP32WN8332 | 729 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 2:19 | 2:33 | TOWER-E (23-43) | RAFT | SHUBHAM
24 | 30.05.2025 | UP32WN8333 | 730 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 2:35 | 3:03 | TOWER-E (23-43) | RAFT | SHUBHAM
25 | 30.05.2025 | UP32VN6144 | 731 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 3:03 | 3:23 | TOWER-E (23-43) | RAFT | SHUBHAM
26 | 30.05.2025 | UP53HT5032 | 732 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 3:26 | 3:48 | TOWER-E (23-43) | RAFT | SHUBHAM
27 | 30.05.2025 | UP32VN6145 | 733 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2570 | 15 | 3:53 | 4:06 | TOWER-E (23-43) | RAFT | SHUBHAM
28 | 30.05.2025 | UP32HT5034 | 734 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 4:14 | 4:25 | TOWER-E (23-43) | RAFT | SHUBHAM
29 | 30.05.2025 | UP32WN8334 | 735 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 4:39 | 4:59 | TOWER-E (23-43) | RAFT | SHUBHAM
30 | 30.05.2025 | UP53HT5034 | 736 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 5:05 | 6:32 | TOWER-E (23-43) | RAFT | SHUBHAM
31 | 30.05.2025 | UP32WN8332 | 737 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2559 | 4 | 6:37 | 7:24 | TOWER-E (23-43) | RAFT | SHUBHAM
32 | 30.05.2025 | UP32VN6144 | 738 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 7:27 | 7:49 | TOWER-E (23-43) | RAFT | SHUBHAM
33 | 30.05.2025 | UP53HT5032 | 739 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2559 | 4 | 7:19 | 8:17 | TOWER-E (23-43) | RAFT | SHUBHAM
34 | 30.05.2025 | UP53HT5034 | 740 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2573 | 18 | 8:25 | 9:10 | TOWER-E (23-43) | RAFT | SHUBHAM
35 | 30.05.2025 | UP32WN8334 | 741 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 9:15 | 9:45 | TOWER-E (23-43) | RAFT | SHUBHAM
36 | 30.05.2025 | UP32WN8333 | 742 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2574 | 19 | 9:50 | 10:46 | TOWER-E (23-43) | RAFT | SHUBHAM
37 | 30.05.2025 | UP32VN6145 | 743 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2552 | -3 | 10:45 | 12:05 | TOWER-E (23-43) | RAFT | SHUBHAM
38 | 30.05.2025 | UP32WN8332 | 744 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2569 | 14 | 12:11 | 13:00 | TOWER-E (23-43) | RAFT | SHUBHAM
39 | 30.05.2025 | UP32VN6144 | 745 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 13:00 | 13:38 | TOWER-E (23-43) | RAFT | SHUBHAM
40 | 30.05.2025 | UP53HT5032 | 746 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 13:41 | 14:00 | TOWER-E (23-43) | RAFT | SHUBHAM
41 | 30.05.2025 | UP53HT5034 | 747 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 14:00 | 14:26 | TOWER-E (23-43) | RAFT | SHUBHAM
42 | 30.05.2025 | UP32WN8334 | 748 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 14:30 | 14:57 | TOWER-E (23-43) | RAFT | SHUBHAM
43 | 30.05.2025 | UP32WN8333 | 749 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2559 | 4 | 15:03 | 15:35 | TOWER-E (23-43) | RAFT | SHUBHAM
44 | 30.05.2025 | UP32WN8332 | 751 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 15:38 | 16:00 | TOWER-E (23-43) | RAFT | SHUBHAM
45 | 30.05.2025 | UP32VN6144 | 752 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2568 | 13 | 16:52 | 17:28 | TOWER-E (23-43) | RAFT | SHUBHAM
46 | 30.05.2025 | UP53HT5032 | 753 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 16:30 | 16:45 | TOWER-E (23-43) | RAFT | SHUBHAM
47 | 30.05.2025 | UP53HT5034 | 754 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 17:32 | 17:45 | TOWER-E (23-43) | RAFT | SHUBHAM
48 | 30.05.2025 | UP32WN8334 | 755 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 17:46 | 18:06 | TOWER-E (23-43) | RAFT | SHUBHAM
49 | 30.05.2025 | UP32WN8333 | 756 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2570 | 15 | 18:15 | 18:30 | TOWER-E (23-43) | RAFT | SHUBHAM
50 | 30.05.2025 | UP32WN8332 | 757 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 18:48 | 19:40 | TOWER-E (23-43) | RAFT | SHUBHAM
51 | 30.05.2025 | UP32VN6144 | 758 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 19:50 | 20:07 | TOWER-E (23-43) | RAFT | SHUBHAM
52 | 30.05.2025 | UP53HT5032 | 759 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 20:31 | 21:05 | TOWER-E (23-43) | RAFT | SHUBHAM
53 | 30.05.2025 | UP53HT5034 | 760 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 21:11 | 23:30 | TOWER-E (23-43) | RAFT | SHUBHAM
54 | 30.05.2025 | UP32VN6145 | 761 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 24:07 | 24:24 | TOWER-E (23-43) | RAFT | SHUBHAM
55 | 30.05.2025 | UP32WN8334 | 762 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 24:06 | 24:46 | TOWER-E (23-43) | RAFT | SHUBHAM
56 | 30.05.2025 | UP32WN8333 | 763 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 24:51 | 1:08 | TOWER-E (23-43) | RAFT | SHUBHAM
57 | 30.05.2025 | UP32WN8332 | 764 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 1:10 | 1:40 | TOWER-E (23-43) | RAFT | SHUBHAM
58 | 30.05.2025 | UP32VN6144 | 765 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2552 | -3 | 1:43 | 2:07 | TOWER-E (23-43) | RAFT | SHUBHAM
59 | 30.05.2025 | UP53HT5032 | 766 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 2:10 | 2:48 | TOWER-E (23-43) | RAFT | SHUBHAM
60 | 30.05.2025 | UP70QT2013 | 905350017 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 2:11 | 2:29 | TOWER-E (23-43) | RAFT | ULTRATECH
61 | 30.05.2025 | UP70QT2341 | 905350018 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 2:37 | 2:53 | TOWER-E (23-43) | RAFT | ULTRATECH
62 | 30.05.2025 | UP70QT2015 | 905350019 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 2:58 | 3:14 | TOWER-E (23-43) | RAFT | ULTRATECH
63 | 30.05.2025 | UP70QT2342 | 905350020 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 3:27 | 3:40 | TOWER-E (23-43) | RAFT | ULTRATECH
64 | 30.05.2025 | UP70QT2014 | 905350021 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 3:54 | 4:36 | TOWER-E (23-43) | RAFT | ULTRATECH
65 | 30.05.2025 | UP70QT2013 | 905350022 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2552 | -3 | 4:45 | 5:03 | TOWER-E (23-43) | RAFT | ULTRATECH
66 | 30.05.2025 | UP70QT2341 | 905350023 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 5:10 | 5:31 | TOWER-E (23-43) | RAFT | ULTRATECH
67 | 30.05.2025 | UP70QT2015 | 905350024 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 5:36 | 5:51 | TOWER-E (23-43) | RAFT | ULTRATECH
68 | 31.05.2025 | UP32VN6140 | 767 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 3:09 | 3:33 | TOWER-E (23-43) | RAFT | SHUBHAM
69 | 31.05.2025 | UP53HT5034 | 768 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 3:43 | 4:11 | TOWER-E (23-43) | RAFT | SHUBHAM
70 | 31.05.2025 | UP32VN6144 | 771 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 10:50 | 11:06 | TOWER-E (23-43) | RAFT | SHUBHAM
71 | 31.05.2025 | UP32VN6140 | 772 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 11:17 | 11:39 | TOWER-E (23-43) | RAFT | SHUBHAM
72 | 31.05.2025 | UP32WN8332 | 773 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 11:40 | 12:01 | TOWER-E (23-43) | RAFT | SHUBHAM
73 | 31.05.2025 | UP53HT5034 | 774 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 12:03 | 12:16 | TOWER-E (23-43) | RAFT | SHUBHAM
74 | 31.05.2025 | UP32WN8334 | 775 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 12:28 | 12:39 | TOWER-E (23-43) | RAFT | SHUBHAM
75 | 31.05.2025 | UP32VN6145 | 776 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 13:18 | 13:32 | TOWER-E (23-43) | RAFT | SHUBHAM
76 | 31.05.2025 | UP53HT5034 | 777 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 13:35 | 14:04 | TOWER-E (23-43) | RAFT | SHUBHAM
77 | 31.05.2025 | UP32VN6140 | 778 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 14:09 | 14:39 | TOWER-E (23-43) | RAFT | SHUBHAM
78 | 31.05.2025 | UP32WN8332 | 779 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 14:41 | 15:02 | TOWER-E (23-43) | RAFT | SHUBHAM
79 | 31.05.2025 | UP32VN6144 | 780 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2571 | 16 | 15:11 | 15:36 | TOWER-E (23-43) | RAFT | SHUBHAM
80 | 31.05.2025 | UP53HT5032 | 781 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 15:38 | 16:28 | TOWER-E (23-43) | RAFT | SHUBHAM
81 | 31.05.2025 | UP32WN8334 | 782 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 16:30 | 17:00 | TOWER-E (23-43) | RAFT | SHUBHAM
82 | 31.05.2025 | UP32VN6145 | 783 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 17:18 | 17:32 | TOWER-E (23-43) | RAFT | SHUBHAM
83 | 31.05.2025 | UP53HT5034 | 784 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 17:43 | 17:53 | TOWER-E (23-43) | RAFT | SHUBHAM
84 | 31.05.2025 | UP32WN8333 | 785 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 18:00 | 18:55 | TOWER-E (23-43) | RAFT | SHUBHAM
85 | 31.05.2025 | UP32VN6144 | 786 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 19:05 | 19:15 | TOWER-E (23-43) | RAFT | SHUBHAM
86 | 31.05.2025 | UP32WN8332 | 787 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 19:20 | 19:32 | TOWER-E (23-43) | RAFT | SHUBHAM
87 | 31.05.2025 | UP32VN6144 | 788 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 19:39 | 19:55 | TOWER-E (23-43) | RAFT | SHUBHAM
88 | 31.05.2025 | UP53HT5032 | 789 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 19:56 | 20:16 | TOWER-E (23-43) | RAFT | SHUBHAM
89 | 31.05.2025 | UP32WN8334 | 790 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 20:34 | 20:54 | TOWER-E (23-43) | RAFT | SHUBHAM
90 | 31.05.2025 | UP32VN6145 | 791 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 21:05 | 21:40 | TOWER-E (23-43) | RAFT | SHUBHAM
91 | 31.05.2025 | UP32WN8333 | 792 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 22:00 | 22:30 | TOWER-E (23-43) | RAFT | SHUBHAM
92 | 31.05.2025 | UP32VN6140 | 793 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 22:35 | 23:23 | TOWER-E (23-43) | RAFT | SHUBHAM
93 | 31.05.2025 | UP53HT5034 | 794 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 23:28 | 23:47 | TOWER-E (23-43) | RAFT | SHUBHAM
94 | 31.05.2025 | UP70QT2014 | 905350025 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 1:27 | 2:05 | TOWER-E (23-43) | RAFT | ULTRATECH
95 | 31.05.2025 | UP70QT2341 | 905350026 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 2:10 | 2:36 | TOWER-E (23-43) | RAFT | ULTRATECH
96 | 31.05.2025 | UP70QT2015 | 905350028 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 10:58 | 11:30 | TOWER-E (23-43) | RAFT | ULTRATECH
97 | 31.05.2025 | UP70QT2013 | 905350029 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 12:19 | 13:18 | TOWER-E (23-43) | RAFT | ULTRATECH
98 | 31.05.2025 | UP70QT2342 | 905350030 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 11:50 | 12:08 | TOWER-E (23-43) | RAFT | ULTRATECH
99 | 31.05.2025 | UP70QT2014 | 905350031 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2552 | -3 | 13:28 | 13:58 | TOWER-E (23-43) | RAFT | ULTRATECH
100 | 31.05.2025 | UP70QT2341 | 905350032 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 14:07 | 14:38 | TOWER-E (23-43) | RAFT | ULTRATECH
101 | 31.05.2025 | UP70QT2015 | 905350033 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 14:43 | 15:24 | TOWER-E (23-43) | RAFT | ULTRATECH
102 | 31.05.2025 | UP70QT2342 | 905350034 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 15:31 | 15:48 | TOWER-E (23-43) | RAFT | ULTRATECH
103 | 31.05.2025 | UP70QT2013 | 905350035 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 15:54 | 16:16 | TOWER-E (23-43) | RAFT | ULTRATECH
104 | 31.05.2025 | UP70QT2014 | 905350036 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 16:27 | 16:48 | TOWER-E (23-43) | RAFT | ULTRATECH
105 | 31.05.2025 | UP70QT2341 | 905350037 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 16:54 | 17:33 | TOWER-E (23-43) | RAFT | ULTRATECH
106 | 31.05.2025 | UP70QT2015 | 905350038 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 17:39 | 18:33 | TOWER-E (23-43) | RAFT | ULTRATECH
107 | 31.05.2025 | UP70QT2342 | 905350039 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 18:39 | 19:05 | TOWER-E (23-43) | RAFT | ULTRATECH
108 | 31.05.2025 | UP70QT2013 | 905350041 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 19:10 | 19:31 | TOWER-E (23-43) | RAFT | ULTRATECH
109 | 31.05.2025 | UP70QT2014 | 905350042 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 19:36 | 20:16 | TOWER-E (23-43) | RAFT | ULTRATECH
110 | 31.05.2025 | UP70QT2341 | 905350043 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 20:25 | 21:00 | TOWER-E (23-43) | RAFT | ULTRATECH
111 | 31.05.2025 | UP70QT2015 | 905350044 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 21:08 | 21:40 | TOWER-E (23-43) | RAFT | ULTRATECH
112 | 31.05.2025 | UP70QT2342 | 905350045 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 22:00 | 22:25 | TOWER-E (23-43) | RAFT | ULTRATECH
113 | 31.05.2025 | UP70QT2013 | 905350046 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 22:28 | 23:05 | TOWER-E (23-43) | RAFT | ULTRATECH
114 | 31.05.2025 | UP70QT2014 | 905350047 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 23:50 | 1:12 | TOWER-E (23-43) | RAFT | ULTRATECH
115 | 31.05.2025 | UP70QT2341 | 905350048 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 23:55 | 1:12 | TOWER-E (23-43) | RAFT | ULTRATECH
116 | 31.05.2025 | UP70QT2015 | 905350049 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 1:20 | 1:30 | TOWER-E (23-43) | RAFT | ULTRATECH
117 | 31.05.2025 | UP70QT2342 | 905350050 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 1:35 | 1:45 | TOWER-E (23-43) | RAFT | ULTRATECH
118 | 31.05.2025 | UP70QT2013 | 905350051 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 1:55 | 2:15 | TOWER-E (23-43) | RAFT | ULTRATECH
119 | 31.05.2025 | UP70QT2014 | 905350052 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 2:00 | 2:20 | TOWER-E (23-43) | RAFT | ULTRATECH
120 | 10.06.2025 | UP70QT2015 | 905350080 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 14:10 | 14:30 | TOWER-E (1-23) | RAFT | ULTRATECH
121 | 10.06.2025 | UP70QT2342 | 905350081 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 14:38 | 14:48 | TOWER-E (1-23) | RAFT | ULTRATECH
122 | 10.06.2025 | UP70QT2013 | 905350082 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2552 | -3 | 14:52 | 15:04 | TOWER-E (1-23) | RAFT | ULTRATECH
123 | 10.06.2025 | UP70QT2341 | 905350083 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 15:37 | 15:47 | TOWER-E (1-23) | RAFT | ULTRATECH
124 | 10.06.2025 | UP70QT2014 | 905350084 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 15:50 | 16:19 | TOWER-E (1-23) | RAFT | ULTRATECH
125 | 10.06.2025 | UP70QT2015 | 905350085 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 16:35 | 16:47 | TOWER-E (1-23) | RAFT | ULTRATECH
126 | 10.06.2025 | UP70QT2342 | 905350086 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 16:54 | 17:01 | TOWER-E (1-23) | RAFT | ULTRATECH
127 | 10.06.2025 | UP70QT2013 | 905350087 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 17:10 | 17:20 | TOWER-E (1-23) | RAFT | ULTRATECH
128 | 10.06.2025 | UP70QT2341 | 905350094 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 21:44 | 21:56 | TOWER-E (1-23) | RAFT | ULTRATECH
129 | 10.06.2025 | UP70QT2014 | 905350089 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 18:19 | 18:30 | TOWER-E (1-23) | RAFT | ULTRATECH
130 | 10.06.2025 | UP70QT2015 | 905350090 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 18:34 | 18:51 | TOWER-E (1-23) | RAFT | ULTRATECH
131 | 10.06.2025 | UP70QT2013 | 905350091 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 19:14 | 19:25 | TOWER-E (1-23) | RAFT | ULTRATECH
132 | 10.06.2025 | UP70QT2014 | 905350092 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 19:30 | 19:40 | TOWER-E (1-23) | RAFT | ULTRATECH
133 | 10.06.2025 | UP70QT2342 | 905350093 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 21:44 | 21:54 | TOWER-E (1-23) | RAFT | ULTRATECH
134 | 10.06.2025 | UP70QT2015 | 905350095 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 22:30 | 23:10 | TOWER-E (1-23) | RAFT | ULTRATECH
135 | 10.06.2025 | UP70QT2013 | 905350096 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 22:00 | 22:23 | TOWER-E (1-23) | RAFT | ULTRATECH
136 | 10.06.2025 | UP70QT2341 | 905350097 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 23:18 | 23:53 | TOWER-E (1-23) | RAFT | ULTRATECH
137 | 10.06.2025 | UP70QT2014 | 905350098 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 24:12 | 24:32 | TOWER-E (1-23) | RAFT | ULTRATECH
138 | 10.06.2025 | UP70QT2015 | 905350099 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 24:36 | 1:05 | TOWER-E (1-23) | RAFT | ULTRATECH
139 | 10.06.2025 | UP70QT2013 | 905350100 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 1:10 | 1:25 | TOWER-E (1-23) | RAFT | ULTRATECH
140 | 10.06.2025 | UP70QT2342 | 905350101 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 1:33 | 1:48 | TOWER-E (1-23) | RAFT | ULTRATECH
141 | 11.06.2025 | UP70QT2341 | 905350102 | RMC 25 | CUM |  | 2 |  |  |  | 730 | 730 | 0 | 2:10 | 2:14 | TOWER-E (1-23) | RAFT | ULTRATECH
142 | 12.06.2025 | UP70QT2014 | 905350111 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 2:10 | 2:50 | TOWER-E (1-23) | RAFT | ULTRATECH
143 | 12.06.2025 | UP70QT2013 | 905350113 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 2:55 | 4:30 | TOWER-E (1-23) | RAFT | ULTRATECH
144 | 12.06.2025 | UP70QT2014 | 905350115 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 4:35 | 5:27 | TOWER-E (1-23) | RAFT | ULTRATECH
145 | 12.06.2025 | UP32VN6140 | 1033 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2568 | 13 | 12:00 | 12:47 | TOWER-E (1-23) | RAFT | SHUBHAM
146 | 12.06.2025 | UP32WN8332 | 1034 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 12:51 | 13:35 | TOWER-E (1-23) | RAFT | SHUBHAM
147 | 12.06.2025 | UP53HT5034 | 1036 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 13:44 | 14:02 | TOWER-E (1-23) | RAFT | SHUBHAM
148 | 12.06.2025 | UP32WN8333 | 1038 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 14:20 | 14:45 | TOWER-E (1-23) | RAFT | SHUBHAM
149 | 12.06.2025 | UP53HT5032 | 1040 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2570 | 15 | 15:08 | 15:40 | TOWER-E (1-23) | RAFT | SHUBHAM
150 | 12.06.2025 | UP53HT5034 | 1041 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 15:43 | 16:29 | TOWER-E (1-23) | RAFT | SHUBHAM
151 | 12.06.2025 | UP32WN8333 | 1042 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 16:32 | 17:44 | TOWER-E (1-23) | RAFT | SHUBHAM
152 | 12.06.2025 | UP32VN6145 | 1043 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 17:55 | 18:40 | TOWER-E (1-23) | RAFT | SHUBHAM
153 | 12.06.2025 | UP53HT5034 | 1044 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2567 | 12 | 18:43 | 19:04 | TOWER-E (1-23) | RAFT | SHUBHAM
154 | 12.06.2025 | UP32WN8332 | 1045 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 19:16 | 20:12 | TOWER-E (1-23) | RAFT | SHUBHAM
155 | 12.06.2025 | UP53HT5032 | 1046 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 20:38 | 21:24 | TOWER-E (1-23) | RAFT | SHUBHAM
156 | 12.06.2025 | UP32VN6144 | 1047 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 21:35 | 21:53 | TOWER-E (1-23) | RAFT | SHUBHAM
157 | 12.06.2025 | UP32VN6145 | 1048 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2559 | 4 | 22:00 | 22:31 | TOWER-E (1-23) | RAFT | SHUBHAM
158 | 12.06.2025 | UP32VN6140 | 1049 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2567 | 12 | 22:32 | 22:48 | TOWER-E (1-23) | RAFT | SHUBHAM
159 | 12.06.2025 | UP53HT5034 | 1050 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 22:53 | 23:41 | TOWER-E (1-23) | RAFT | SHUBHAM
160 | 12.06.2025 | UP32WN8333 | 1051 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 22:14 | 23:41 | TOWER-E (1-23) | RAFT | SHUBHAM
161 | 12.06.2025 | UP32WN8332 | 1052 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2568 | 13 | 23:45 | 24:04 | TOWER-E (1-23) | RAFT | SHUBHAM
162 | 12.06.2025 | UP53HT5032 | 1053 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 24:06 | 24:24 | TOWER-E (1-23) | RAFT | SHUBHAM
163 | 12.06.2025 | UP32VN6144 | 1054 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 24:27 | 24:54 | TOWER-E (1-23) | RAFT | SHUBHAM
164 | 13.06.2025 | UP70NT8335 | 471 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2552 | -3 | 12:43 | 13:00 | TOWER-E (1-23) | RAFT | SRIJAN
165 | 13.06.2025 | NEW 9655 | 472 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 13:04 | 13:15 | TOWER-E (1-23) | RAFT | SRIJAN
166 | 13.06.2025 | NEW 8917 | 473 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 13:19 | 13:32 | TOWER-E (1-23) | RAFT | SRIJAN
167 | 13.06.2025 | NEW 9048 | 474 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 13:35 | 13:45 | TOWER-E (1-23) | RAFT | SRIJAN
168 | 13.06.2025 | UP70NT8336 | 475 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 13:52 | 14:05 | TOWER-E (1-23) | RAFT | SRIJAN
169 | 13.06.2025 | UP70NT8335 | 476 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556.59 | 1.59 | 14:30 | 14:40 | TOWER-E (1-23) | RAFT | SRIJAN
170 | 13.06.2025 | NEW 9655 | 477 | RMC 25 | CUM |  | 8 |  |  |  | 2920 | 2921.3 | 1.3 | 14:30 | 14:40 | TOWER-E (1-23) | RAFT | SRIJAN
171 | 13.06.2025 | NEW 8917 | 478 | RMC 25 | CUM |  | 8 |  |  |  | 2920 | 2920.69 | 0.69 | 15:09 | 15:29 | TOWER-E (1-23) | RAFT | SRIJAN
172 | 13.06.2025 | NEW 9048 | 479 | RMC 25 | CUM |  | 8 |  |  |  | 2920 | 2916.79 | -3.21 | 15:33 | 15:45 | TOWER-E (1-23) | RAFT | SRIJAN
173 | 13.06.2025 | UP70NT8336 | 480 | RMC 25 | CUM |  | 8 |  |  |  | 2920 | 2918.69 | -1.31 | 16:03 | 16:35 | TOWER-E (1-23) | RAFT | SRIJAN
174 | 13.06.2025 | UP70NT8335 | 481 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554.5 | -0.5 | 17:13 | 17:13 | TOWER-E (1-23) | RAFT | SRIJAN
175 | 13.06.2025 | NEW 9655 | 482 | RMC 25 | CUM |  | 8 |  |  |  | 2920 | 2919 | -1 | 17:14 | 17:38 | TOWER-E (1-23) | RAFT | SRIJAN
176 | 13.06.2025 | NEW 8917 | 483 | RMC 25 | CUM |  | 8 |  |  |  | 2920 | 2919 | -1 | 17:40 | 18:10 | TOWER-E (1-23) | RAFT | SRIJAN
177 | 13.06.2025 | NEW 9048 | 484 | RMC 25 | CUM |  | 8 |  |  |  | 2920 | 2917 | -3 | 18:30 | 19:20 | TOWER-E (1-23) | RAFT | SRIJAN
178 | 13.06.2025 | NEW 9655 | 487 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555.6 | 0.6 | 20:02 | 19:20 | TOWER-E (1-23) | RAFT | SRIJAN
179 | 13.06.2025 | UP70NT8335 | 486 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555.6 | 0.6 | 20:06 | 20:58 | TOWER-E (1-23) | RAFT | SRIJAN
180 | 13.06.2025 | UP70NT8336 | 489 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 20:06 | 20:58 | TOWER-E (1-23) | RAFT | SRIJAN
181 | 13.06.2025 | NEW 8917 | 488 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554.59 | -0.41 | 21:30 | 22:02 | TOWER-E (1-23) | RAFT | SRIJAN
182 | 13.06.2025 | UP32VN6140 | 1055 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 24:57 | 1:11 | TOWER-E (1-23) | RAFT | SHUBHAM
183 | 13.06.2025 | UP32VN6145 | 1056 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 1:13 | 1:46 | TOWER-E (1-23) | RAFT | SHUBHAM
184 | 13.06.2025 | UP53HT5034 | 1057 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 1:48 | 2:02 | TOWER-E (1-23) | RAFT | SHUBHAM
185 | 13.06.2025 | UP32WN8332 | 1058 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 2:05 | 2:20 | TOWER-E (1-23) | RAFT | SHUBHAM
186 | 13.06.2025 | UP32VN6144 | 1059 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 2:23 | 2:39 | TOWER-E (1-23) | RAFT | SHUBHAM
187 | 13.06.2025 | UP32VN6145 | 1060 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 3:16 | 3:42 | TOWER-E (1-23) | RAFT | SHUBHAM
188 | 13.06.2025 | UP32WN8332 | 1062 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 3:45 | 3:57 | TOWER-E (1-23) | RAFT | SHUBHAM
189 | 13.06.2025 | UP32VN6144 | 1063 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 4:04 | 4:22 | TOWER-E (1-23) | RAFT | SHUBHAM
190 | 13.06.2025 | UP32VN6145 | 1064 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 5:05 | 5:21 | TOWER-E (1-23) | RAFT | SHUBHAM
191 | 13.06.2025 | UP32VN6145 | 1065 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 9:48 | 10:30 | TOWER-E (1-23) | RAFT | SHUBHAM
192 | 13.06.2025 | UP32WN8333 | 1066 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 10:35 | 10:50 | TOWER-E (1-23) | RAFT | SHUBHAM
193 | 13.06.2025 | UP53HT5034 | 1068 | RMC 25 | CUM |  | 4 |  |  |  | 1460 | 1463 | 3 | 11:30 | 11:36 | TOWER-E (1-23) | RAFT | SHUBHAM
194 | 13.06.2025 | UP53HT5034 | 1069 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 14:55 | 15:23 | TOWER-E (1-23) | RAFT | SHUBHAM
195 | 13.06.2025 | UP32VN6140 | 1070 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2559 | 4 | 15:28 | 15:40 | TOWER-E (1-23) | RAFT | SHUBHAM
196 | 13.06.2025 | UP32VN6145 | 1071 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 15:51 | 15:59 | TOWER-E (1-23) | RAFT | SHUBHAM
197 | 13.06.2025 | UP53HT5034 | 1073 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 16:37 | 16:48 | TOWER-E (1-23) | RAFT | SHUBHAM
198 | 13.06.2025 | UP32VN6145 | 1075 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 17:07 | 17:22 | TOWER-E (1-23) | RAFT | SHUBHAM
199 | 13.06.2025 | UP32VN6144 | 1076 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 17:47 | 18:15 | TOWER-E (1-23) | RAFT | SHUBHAM
200 | 13.06.2025 | UP53HT5034 | 1077 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2568 | 13 | 18:31 | 18:50 | TOWER-E (1-23) | RAFT | SHUBHAM
201 | 13.06.2025 | UP32WN8333 | 1079 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2571 | 16 | 18:57 | 19:12 | TOWER-E (1-23) | RAFT | SHUBHAM
202 | 13.06.2025 | UP32VN6144 | 1080 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 19:18 | 19:34 | TOWER-E (1-23) | RAFT | SHUBHAM
203 | 13.06.2025 | UP53HT5034 | 1081 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 19:42 | 20:02 | TOWER-E (1-23) | RAFT | SHUBHAM
204 | 13.06.2025 | UP32WN8333 | 1082 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 20:14 | 20:34 | TOWER-E (1-23) | RAFT | SHUBHAM
205 | 13.06.2025 | UP32VN6144 | 1083 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 20:41 | 21:11 | TOWER-E (1-23) | RAFT | SHUBHAM
206 | 13.06.2025 | UP53HT5034 | 1084 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 21:25 | 21:40 | TOWER-E (1-23) | RAFT | SHUBHAM
207 | 13.06.2025 | UP32WN8333 | 1085 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2568 | 13 | 21:46 | 22:40 | TOWER-E (1-23) | RAFT | SHUBHAM
208 | 13.06.2025 | UP32VN6145 | 1086 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 22:00 | 22:26 | TOWER-E (1-23) | RAFT | SHUBHAM
209 | 13.06.2025 | UP53HT5034 | 1087 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 22:48 | 23:23 | TOWER-E (1-23) | RAFT | SHUBHAM
210 | 13.06.2025 | UP32VN6144 | 1088 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 23:26 | 23:45 | TOWER-E (1-23) | RAFT | SHUBHAM
211 | 13.06.2025 | UP32VN6145 | 1089 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2569 | 14 | 24:04 | 24:20 | TOWER-E (1-23) | RAFT | SHUBHAM
212 | 13.06.2025 | UP32WN8333 | 1090 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 24:24 | 24:51 | TOWER-E (1-23) | RAFT | SHUBHAM
213 | 13.06.2025 | UP70QT2341 | 905350120 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 3:37 | 5:02 | TOWER-E (1-23) | RAFT | ULTRATECH
214 | 13.06.2025 | UP70QT2014 | 905350119 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 5:06 | 5:09 | TOWER-E (1-23) | RAFT | ULTRATECH
215 | 13.06.2025 | UP70QT2015 | 905350121 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 5:20 | 5:36 | TOWER-E (1-23) | RAFT | ULTRATECH
216 | 13.06.2025 | UP70QT2013 | 905350122 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 5:41 | 6:03 | TOWER-E (1-23) | RAFT | ULTRATECH
217 | 13.06.2025 | UP70QT2342 | 905350123 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 6:33 | 6:45 | TOWER-E (1-23) | RAFT | ULTRATECH
218 | 13.06.2025 | UP70QT2341 | 905350124 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 7:42 | 8:07 | TOWER-E (1-23) | RAFT | ULTRATECH
219 | 13.06.2025 | UP70QT2014 | 905350125 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 8:12 | 8:30 | TOWER-E (1-23) | RAFT | ULTRATECH
220 | 13.06.2025 | UP70QT2013 | 905350126 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 8:39 | 9:15 | TOWER-E (1-23) | RAFT | ULTRATECH
221 | 13.06.2025 | UP70QT2342 | 905350128 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 9:24 | 10:45 | TOWER-E (1-23) | RAFT | ULTRATECH
222 | 13.06.2025 | UP70QT2014 | 905350130 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 11:04 | 11:35 | TOWER-E (1-23) | RAFT | ULTRATECH
223 | 13.06.2025 | UP70QT2013 | 905350131 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 11:46 | 12:18 | TOWER-E (1-23) | RAFT | ULTRATECH
224 | 13.06.2025 | UP70QT2015 | 905350132 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 13:11 | 13:24 | TOWER-E (1-23) | RAFT | ULTRATECH
225 | 14.06.2025 | UP53HT5034 | 1091 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 24:56 | 1:07 | TOWER-E (1-23) | RAFT | SHUBHAM
226 | 14.06.2025 | UP32VN6144 | 1092 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2559 | 4 | 1:49 | 2:16 | TOWER-E (1-23) | RAFT | SHUBHAM
227 | 14.06.2025 | UP32VN6145 | 1093 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 2:24 | 3:08 | TOWER-E (1-23) | RAFT | SHUBHAM
228 | 14.06.2025 | UP32VN6144 | 1094 | RMC 25 | CUM |  | 3 |  |  |  | 1095 | 1097 | 2 | 5:12 | 5:12 | TOWER-E (1-23) | RAFT | SHUBHAM
229 | 14.06.2025 | UP70QT2342 | 905350133 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 13:37 | 13:45 | TOWER-E (1-23) | RAFT | ULTRATECH
230 | 14.06.2025 | UP70QT2341 | 905350134 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 14:21 | 15:09 | TOWER-E (1-23) | RAFT | ULTRATECH
231 | 14.06.2025 | UP70QT2013 | 905350135 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 15:19 | 16:09 | TOWER-E (1-23) | RAFT | ULTRATECH
232 | 14.06.2025 | UP70QT2015 | 905350136 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 15:25 | 16:20 | TOWER-E (1-23) | RAFT | ULTRATECH
233 | 14.06.2025 | UP70QT2342 | 905350137 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 16:25 | 16:50 | TOWER-E (1-23) | RAFT | ULTRATECH
234 | 14.06.2025 | UP70QT2341 | 905350138 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 16:55 | 17:15 | TOWER-E (1-23) | RAFT | ULTRATECH
235 | 14.06.2025 | UP70QT2013 | 905350139 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 17:20 | 18:10 | TOWER-E (1-23) | RAFT | ULTRATECH
236 | 2025-06-22 | UP70QT2341 | 905350161 | RMC 35 | CUM |  |  |  | 3 |  | 1245 | 1245 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | ULTRATECH
237 | 2025-06-23 | UP70QT2013 | 905350165 | RMC 35 | CUM |  |  |  | 4 |  | 1660 | 1660 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | ULTRATECH
238 | 2025-06-24 | UP70QT2342 | 905350166 | RMC 35 | CUM |  |  |  | 5 |  | 2075 | 2075 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | ULTRATECH
239 | 2025-06-25 | UP70QT2342 | 905350167 | RMC 35 | CUM |  |  |  | 5 |  | 2075 | 2075 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | ULTRATECH
240 | 2025-06-26 | UP70QT2014 | 905350168 | RMC 35 | CUM |  |  |  | 6 |  | 2490 | 2490 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | ULTRATECH
241 | 2025-06-27 | UP70QT2342 | 905350171 | RMC 35 | CUM |  |  |  | 4 |  | 1660 | 1660 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | ULTRATECH
242 | 2025-06-29 | UP70QT2014 | 905350190 | RMC 35 | CUM |  |  |  | 3 |  | 1245 | 1245 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | ULTRATECH
243 | 2025-07-01 | 9655 | 563 | RMC 35 | CUM |  |  |  | 4 |  | 1660 | 1660 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
244 | 2025-07-01 | UP70NT8336 | 564 | RMC 35 | CUM |  |  |  | 4 |  | 1660 | 1660 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
245 | 2025-07-02 | 9048 | 565 | RMC 35 | CUM |  |  |  | 4.5 |  | 1867.5 | 1867.5 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
246 | 2025-07-04 | 9048 | 571 | RMC 35 | CUM |  |  |  | 3.5 |  | 1452.5 | 1452.5 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
247 | 2025-07-05 | 9048 | 582 | RMC 35 | CUM |  |  |  | 4 |  | 1660 | 1660 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
248 | 2025-07-05 | 8917 | 583 | RMC 35 | CUM |  |  |  | 4 |  | 1660 | 1660 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
249 | 2025-07-07 | UP70NT8335 | 591 | RMC 35 | CUM |  |  |  | 3 |  | 1245 | 1245 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
250 | 2025-07-08 | UP70NT8335 | 600 | RMC 35 | CUM |  |  |  | 4 |  | 1660 | 1660 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
251 | 2025-07-08 | UP70NT8335 | 604 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 |  |  | TOWER-E (1-43) | COMP. STRIP | SRIJAN
252 | 2025-07-08 | UP70NT8336 | 603 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 |  |  | TOWER-E (1-43) | COMP. STRIP | SRIJAN
253 | 2025-07-09 | 9048 | 605 | RMC 35 | CUM |  |  |  | 3.5 |  | 1452.5 | 1452.5 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
254 | 2025-07-10 | 8917 | 6009 | RMC 35 | CUM |  |  |  | 3.5 |  | 1452.5 | 1452.5 | 0 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
255 | 25.09.2025 | UP32WN8333 | 1950 | M35 | CUM |  |  |  | 3 |  | 1245 | 1245 | 0 |  |  | TOWER-E PLINTH BEAM | COL. JUN. | SHUBHAM
256 | 25.09.2025 | UP32WN8333 | 1957 | M25 | CUM |  | 4 |  |  |  | 1660 | 1660 | 0 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
257 | 25.09.2025 | UP32WN8333 | 1959 | M25 | CUM |  | 4.5 |  |  |  | 1867.5 | 1867.5 | 0 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
258 | 01.10.2025 | UP32VN6140 | 1990 | M35 | CUM |  |  |  | 3 |  | 1245 | 1245 | 0 |  |  | TOWER-E PLINTH BEAM | COL. JUN. | SHUBHAM
259 | 01.10.2025 | UP32WN8334 | 1993 | M25 | CUM |  | 4 |  |  |  | 1660 | 1660 | 0 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
260 | 01.10.2025 | UP32VN6140 | 1994 | M25 | CUM |  | 3.5 |  |  |  | 1452.5 | 1452.5 | 0 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
261 | 07.10.2025 | UP32VN6140 | 2037 | M35 | CUM |  |  |  | 3 |  | 1245 | 1245 | 0 |  |  | TOWER-E PLINTH BEAM | COL. JUN. | SHUBHAM
262 | 09.10.2025 | UP32WN8332 | 2071 | M25 | CUM |  | 4 |  |  |  | 1660 | 1660 | 0 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
263 | 09.10.2025 | UP32VN6140 | 2072 | M35 | CUM |  |  |  | 2 |  | 830 | 830 | 0 |  |  | TOWER-E PLINTH BEAM | COL. JUN. | SHUBHAM
264 | 09.10.2025 | UP53HT5032 | 2073 | M25 | CUM |  | 3 |  |  |  | 1245 | 1245 | 0 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
265 | 10.10.2025 | UP32WN8334 | 2087 | M25 | CUM |  | 2 |  |  |  | 830 | 830 | 0 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
266 | 29.10.2025 | UP53HT5034 | 2316 | M35 | CUM |  |  |  | 3 |  | 1245 | 1245 | 0 |  |  | TOWER-E PLINTH BEAM | COL. JUN. | SHUBHAM
267 | 30.10.2025 | UP32VN6144 | 2332 | M25 | CUM |  | 4 |  |  |  | 1660 | 1660 | 0 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
268 | 30.10.2025 | UP53HT5032 | 2338 | M25 | CUM |  | 3.5 |  |  |  | 1452.5 | 1452.5 | 0 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
269 | 11.11.2025 | UP53HT5034 | 2535 | M40 | CUM |  |  |  |  | 2.5 | 1037.5 | 1037.5 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
270 | 17.11.2025 | UP32WN8334 | 2615 | M25 | CUM |  | 4 |  |  |  | 1660 | 1660 | 0 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
271 | 17.11.2025 | UP32VN6144 | 2604 | M40 | CUM |  |  |  |  | 3.5 | 1452.5 | 1452.5 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
272 | 18.11.2025 | UP53HT5032 | 2633 | M40 | CUM |  |  |  |  | 4.5 | 1867.5 | 1867.5 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
273 | 19.11.2025 | UP32WN8333 | 2643 | M25 | CUM |  | 3 |  |  |  | 1245 | 1245 | 0 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
274 | 19.11.2025 | UP32WN8334 | 2661 | M40 | CUM |  |  |  |  | 3.5 | 1452.5 | 1452.5 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
275 | 20.11.2025 | UP32WN8334 | 2694 | M40 | CUM |  |  |  |  | 3.5 | 1452.5 | 1452.5 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
276 | 28.11.2025 | UP32WN8333 | 2831 | M40 | CUM |  |  |  |  | 3 | 1245 | 1245 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
277 | 29.11.2025 | UP32VN6144 | 2844 | M40 | CUM |  |  |  |  | 3 | 1245 | 1245 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
278 | 29.11.2025 | UP53HT5032 | 2855 | M40 | CUM |  |  |  |  | 4 | 1660 | 1660 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
279 | 30.11.2025 | UP32WN8334 | 2874 | M40 | CUM |  |  |  |  | 3 | 1245 | 1245 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
280 | 02.12.2025 | UP53HT5034 | 2912 | M40 | CUM |  |  |  |  | 3 | 1245 | 1245 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
281 | 02.12.2025 | UP32WN8332 | 2920 | M40 | CUM |  |  |  |  | 4.5 | 1867.5 | 1867.5 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
282 | 03.12.2025 | UP32WN8333 | 2931 | M40 | CUM |  |  |  |  | 3.5 | 1452.5 | 1452.5 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
283 | 03.12.2025 | UP32WN8333 | 2935 | M40 | CUM |  |  |  |  | 3 | 1245 | 1245 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
284 | 05.12.2025 | UP32VN6140 | 2954 | M40 | CUM |  |  |  |  | 3 | 1245 | 1245 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
285 | 06.12.2025 | UP32WN8332 | 2957 | M40 | CUM |  |  |  |  | 3.5 | 1452.5 | 1452.5 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
286 | 06.12.2025 | UP32WN8334 | 2966 | M40 | CUM |  |  |  |  | 2.5 | 1037.5 | 1037.5 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
287 | 08.12.2025 | UP53HT5032 | 2995 | M40 | CUM |  |  |  |  | 2.5 | 1037.5 | 1037.5 | 0 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
288 | 09.12.2025 | UP32VN6140 | 3009 | M25 | CUM |  | 3.5 |  |  |  | 1452.5 | 1452.5 | 0 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
289 | 09.12.2025 | UP32WN8333 | 3012 | M25 | CUM |  | 3 |  |  |  | 1245 | 1245 | 0 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
290 | 18.12.2025 | UP32VN6144 | 3183 | M40 | CUM |  |  |  |  | 2 | 830 |  | -830 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
291 | 19.12.2025 | UP32WN8334 | 3197 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
292 | 20.12.2025 | UP32WN8332 | 3217 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
293 | 20.12.2025 | UP32WN8332 | 3220 | M40 | CUM |  |  |  |  | 3.5 | 1452.5 |  | -1452.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
294 | 21.12.2025 | UP53HT5034 | 3227 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
295 | 21.12.2025 | UP53HT5032 | 3231 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
296 | 23.12.2025 | UP32WN8332 | 3262 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
300 | 25.12.2025 | UP53HT5032 | 3292 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
301 | 25.12.2025 | UP32WN8334 | 3295 | M40 | CUM |  |  |  |  | 2.5 | 1037.5 |  | -1037.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
302 | 26.12.2025 | UP53HT5034 | 3312 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
303 | 29.12.2025 | UP32VN6144 | 3375 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
304 | 31.12.2025 | UP32WN8333 | 3405 | M40 | CUM |  |  |  |  | 3.5 | 1452.5 |  | -1452.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
305 | 31.12.2025 | UP53HT5034 | 3409 | M40 | CUM |  |  |  |  | 4 | 1660 |  | -1660 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
306 | 01.01.2026 | UP32VN6140 | 3420 | M40 | CUM |  |  |  |  | 3.5 | 1452.5 |  | -1452.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
309 | 03.01.2026 | UP32WN8333 | 3444 | M40 | CUM |  |  |  |  | 3.5 | 1452.5 |  | -1452.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
323 | 04.01.2026 | UP53HT5034 | 3453 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
324 | 04.01.2026 | UP32WN8333 | 3462 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
325 | 05.01.2026 | UP32WN8333 | 3478 | M40 | CUM |  |  |  |  | 4 | 1660 |  | -1660 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
326 | 06.01.2026 | UP32WN8334 | 3483 | M40 | CUM |  |  |  |  | 3.5 | 1452.5 |  | -1452.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
327 | 06.01.2026 | UP32WN8333 | 3488 | M40 | CUM |  |  |  |  | 2 | 830 |  | -830 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
328 | 21.01.2026 | UP70QT2014 | 905351163 | M40 | CUM |  |  |  |  | 4 | 1660 |  | -1660 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
329 | 21.01.2026 | UP70QT2342 | 905351165 | M40 | CUM |  |  |  |  | 4 | 1660 |  | -1660 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
330 | 21.01.2026 | UP70QT2015 | 905351167 | M40 | CUM |  |  |  |  | 4 | 1660 |  | -1660 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
331 | 21.01.2026 | UP70QT2014 | 905351170 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
332 | 21.01.2026 | UP70QT2013 | 905351171 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
333 | 21.01.2026 | UP70QT2341 | 905351172 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
334 | 21.01.2026 | UP70QT2342 | 905351173 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
335 | 21.01.2026 | UP70QT2014 | 905351174 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
336 | 22.01.2026 | UP70QT2015 | 905351175 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
337 | 22.01.2026 | UP70QT2013 | 905351176 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
338 | 22.01.2026 | UP70QT2341 | 905351177 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
339 | 22.01.2026 | UP70QT2342 | 905351178 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
340 | 22.01.2026 | UP70QT2014 | 905351179 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
341 | 22.01.2026 | UP70QT2015 | 905351180 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
342 | 22.01.2026 | UP70QT2013 | 905351181 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
343 | 22.01.2026 | UP70QT2342 | 905351182 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
344 | 22.01.2026 | UP70QT2341 | 905351183 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
345 | 22.01.2026 | UP32VN6144 | 3714 | M25 | CUM |  | 6 |  |  |  | 2190 |  | -2190 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | SHUBHAM
346 | 30.01.2026 | UP32WN8334 | 3858 | M40 | CUM |  |  |  |  | 4 | 1660 |  | -1660 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | SHUBHAM
347 | 30.01.2026 | UP32VN6144 | 3861 | M40 | CUM |  |  |  |  | 4 | 1660 |  | -1660 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | SHUBHAM
348 | 30.01.2026 | UP32WN8333 | 3863 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | SHUBHAM
349 | 30.01.2026 | UP32WN8334 | 3865 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | SHUBHAM
350 | 30.01.2026 | UP53HT5032 | 3866 | M40 | CUM |  |  |  |  | 4 | 1660 |  | -1660 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | SHUBHAM
351 | 30.01.2026 | UP32VN6144 | 3868 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | SHUBHAM
352 | 30.01.2026 | UP32WN8332 | 3869 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | SHUBHAM
353 | 30.01.2026 | UP32WN8333 | 3870 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | SHUBHAM
354 | 31.01.2026 | UP32WN8334 | 3871 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | SHUBHAM
355 | 31.01.2026 | UP53HT5034 | 3872 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | SHUBHAM
356 | 31.01.2026 | UP53HT5032 | 3873 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | SHUBHAM
357 | 31.01.2026 | UP32VN6144 | 3874 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | SHUBHAM
358 | 31.01.2026 | UP53HT5034 | 3877 | M40 | CUM |  |  |  |  | 3.5 | 1277.5 |  | -1277.5 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | SHUBHAM
359 | 31.01.2026 | UP32VN6144 | 3879 | M40 | CUM |  |  |  |  | 2.5 | 912.5 |  | -912.5 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | SHUBHAM
360 | 01.02.2026 | UP53HT5032 | 3890 | M40 | CUM |  |  |  |  | 3 | 1095 |  | -1095 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | SHUBHAM
361 | 01.02.2026 | UP32VN6144 | 3895 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | SHUBHAM
362 | 02.02.2026 | UP53HT5034 | 3898 | M40 | CUM |  |  |  |  | 2 | 730 |  | -730 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | SHUBHAM
363 | 02.02.2026 | UP32WN8334 | 3902 | M40 | CUM |  |  |  |  | 3.5 | 1277.5 |  | -1277.5 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | SHUBHAM
364 | 05.02.2026 | UP70QT2015 | 905351269 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
365 | 06.02.2026 | UP70QT2014 | 905351276 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
366 | 07.02.2026 | UP70QT2342 | 905351299 | M40 | CUM |  |  |  |  | 4.5 | 1642.5 |  | -1642.5 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
367 | 09.02.2026 | UP70QT2013 | 905351342 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
368 | 10.02.2026 | UP70QT2013 | 905351359 | M40 | CUM |  |  |  |  | 3 | 1095 |  | -1095 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
369 | 10.02.2026 | UP70QT2342 | 905351361 | M40 | CUM |  |  |  |  | 3.5 | 1277.5 |  | -1277.5 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
370 | 11.02.2026 | UP70QT2015 | 905351379 | M40 | CUM |  |  |  |  | 3.5 | 1277.5 |  | -1277.5 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
371 | 12.02.2026 | UP70QT2015 | 905351384 | M40 | CUM |  |  |  |  | 3 | 1095 |  | -1095 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
372 | 12.02.2026 | UP70QT2341 | 905351392 | M40 | CUM |  |  |  |  | 5 | 1825 |  | -1825 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
373 | 12.02.2026 | UP70QT2014 | 905351396 | M40 | CUM |  |  |  |  | 5 | 1825 |  | -1825 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
374 | 12.02.2026 | UP70QT2342 | 905351400 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
375 | 13.02.2026 | UP70QT2014 | 905351402 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
376 | 13.02.2026 | UP70QT2341 | 905351403 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
377 | 13.02.2026 | UP70QT2342 | 905351404 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
378 | 13.02.2026 | UP70QT2014 | 905351405 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
379 | 13.02.2026 | UP70QT2015 | 905351407 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
380 | 13.02.2026 | UP70QT2342 | 905351408 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
381 | 13.02.2026 | UP70QT2341 | 905351409 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
382 | 13.02.2026 | UP70QT2015 | 905351410 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
383 | 13.02.2026 | UP70QT2014 | 905351411 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
384 | 13.02.2026 | UP70QT2342 | 905351412 | M40 | CUM |  |  |  |  | 5 | 1825 |  | -1825 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
385 | 13.02.2026 | UP70QT2342 | 905351413 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
386 | 13.02.2026 | UP70QT2015 | 905351414 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
387 | 13.02.2026 | UP70QT2013 | 905351415 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
388 | 13.02.2026 | UP70QT2014 | 905351416 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
389 | 13.02.2026 | UP70QT2013 | 905351419 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
390 | 13.02.2026 | UP70QT2341 | 905351420 | M25 | CUM |  | 6 |  |  |  | 2190 |  | -2190 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
391 | 13.02.2026 | UP70QT2015 | 905351422 | M25 | CUM |  | 3 |  |  |  | 1095 |  | -1095 |  |  | TOWER-E 1ST FLOOR LVL | SLAB | ULTRATECH
392 | 13.02.2026 | UP70QT2013 | 905351423 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
393 | 14.02.2026 | UP70QT2342 | 905351438 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
394 | 16.02.2026 | UP70QT2342 | 905351451 | M40 | CUM |  |  |  |  | 3 | 1095 |  | -1095 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
395 | 17.02.2026 | UP70QT2014 | 905351463 | M40 | CUM |  |  |  |  | 3 | 1095 |  | -1095 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
396 | 18.02.2026 | UP70QT2013 | 905351474 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
397 | 20.02.2026 | UP70QT2341 | 905351505 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
398 | 20.02.2026 | UP70QT2341 | 905351509 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
399 | 23.02.2026 | UP70QT2013 | 905351563 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
400 | 24.02.2026 | UP70QT2013 | 905351577 | M40 | CUM |  |  |  |  | 3.5 | 1277.5 |  | -1277.5 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
401 | 24.02.2026 | UP70QT2014 | 905351579 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
402 | 25.02.2026 | UP70QT2015 | 905351586 | M40 | CUM |  |  |  |  | 7 | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
403 | 25.02.2026 | UP70QT2341 | 905351587 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
404 | 25.02.2026 | UP70QT2015 | 905351588 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
405 | 25.02.2026 | UP70QT2014 | 905351589 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
406 | 25.02.2026 | UP70QT2342 | 905351590 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
407 | 25.02.2026 | UP70QT2341 | 905351591 | M40 | CUM |  |  |  |  | 5 | 1825 |  | -1825 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
408 | 25.02.2026 | UP70QT2015 | 905351592 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
409 | 25.02.2026 | UP70QT2014 | 905351593 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
410 | 25.02.2026 | UP70QT2013 | 905351594 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
411 | 25.02.2026 | UP70QT2342 | 905351595 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
412 | 25.02.2026 | UP70QT2341 | 905351596 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
413 | 25.02.2026 | UP70QT2015 | 905351597 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
414 | 25.02.2026 | UP70QT2014 | 905351598 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
415 | 25.02.2026 | UP70QT2013 | 905351599 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
416 | 25.02.2026 | UP70QT2342 | 905351600 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
417 | 25.02.2026 | UP70QT2341 | 905351601 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
418 | 25.02.2026 | UP70QT2013 | 905351604 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
419 | 25.02.2026 | UP70QT2341 | 905351606 | M40 | CUM |  |  |  |  | 3.5 | 1277.5 |  | -1277.5 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
420 | 26.02.2026 | UP70QT2013 | 905351620 | M40 | CUM |  |  |  |  | 3.5 | 1277.5 |  | -1277.5 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
421 | 27.02.2026 | UP70QT2341 | 905351643 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
422 | 27.02.2026 | UP70QT2015 | 905351645 | M40 | CUM |  |  |  |  | 5.5 | 2007.5 |  | -2007.5 |  |  | TOWER-E 1ST FLOOR LVL | COLUMN | ULTRATECH
423 | 2.03.2026 | UP70QT2013 | 905351712 | M40 | CUM |  |  |  |  | 7 | 2555 |  | -2555 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
424 | 2.03.2026 | UP70QT2015 | 905351713 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | ULTRATECH
425 | 2.03.2026 | UP70QT2014 | 905351714 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | ULTRATECH
426 | 2.03.2026 | UP70QT2342 | 905351715 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | ULTRATECH
427 | 2.03.2026 | UP70QT2341 | 905351716 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | ULTRATECH
428 | 2.03.2026 | UP70QT2015 | 905351717 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | ULTRATECH
429 | 2.03.2026 | UP70QT2014 | 905351718 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | ULTRATECH
430 | 2.03.2026 | UP70QT2013 | 905351719 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | ULTRATECH
431 | 2.03.2026 | UP70QT2342 | 905351720 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | ULTRATECH
432 | 2.03.2026 | UP70QT2341 | 905351721 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 2ND FLOOR LVL | SLAB | ULTRATECH
433 | 2.03.2026 | UP70QT2015 | 905351722 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | ULTRATECH
434 | 2.03.2026 | UP70QT2014 | 905351723 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | ULTRATECH
435 | 2.03.2026 | UP70QT2013 | 905351724 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | ULTRATECH
436 | 11.03.2026 | UP32WN8333 | 4450 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
437 | 11.03.2026 | UP53HT5034 | 4451 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
438 | 11.03.2026 | UP32VN6144 | 4452 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
439 | 11.03.2026 | UP32WN8332 | 4453 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
440 | 12.03.2026 | UP53HT5034 | 4454 | M41 | CUM |  |  |  |  | 3 | 1095 |  | -1095 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
441 | 12.03.2026 | UP32VN6140 | 4455 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
442 | 12.03.2026 | UP32WN8333 | 4456 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
443 | 12.03.2026 | UP32VN6144 | 4458 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
444 | 12.03.2026 | UP53HT5034 | 4461 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
445 | 12.03.2026 | UP32VN6144 | 4462 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
446 | 12.03.2026 | UP32VN6140 | 4463 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
447 | 12.03.2026 | UP32WN8332 | 4464 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
448 | 12.03.2026 | UP32WN8333 | 4465 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
449 | 12.03.2026 | UP32VN6140 | 4466 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
450 | 12.03.2026 | UP53HT5034 | 4467 | M40 | CUM |  |  |  |  | 4 | 1460 |  | -1460 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
451 | 12.03.2026 | UP32VN6140 | 4470 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
452 | 12.03.2026 | UP32VN6140 | 4472 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
453 | 12.03.2026 | UP53HT5032 | 4473 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
454 | 13.03.2026 | UP32VN6144 | 4475 | M25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E 2nd FLOOR LVL | SLAB | SHUBHAM
| Total Qty upto date |  |  |  |  | 57.5 | 2191 | 0 | 82 | 301 | 883717.5 | 668013.35 | -215704.15
[6 empty] | 2631.5 |  |  |  |  | 17674.35 | 13360.267 | BAGS
[6 empty] | 57.5 | 2191 | 0 | 82 | 301

## TYP. RCC
S.NO. | DESCRIPTION | UNIT | NOS | NOS | MEASUREMENT |  |  | QTY. | REMARKS
[5 empty] | L | B | H/T
COLUMN (1-43/A-Q) FROM 1ST FLOOR LVL to 2nd floor LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 62 | 1 | 0.3 | 0.6 | 2.5 | 27.9
2 | C4, C5 (300X750) | CUM | 30 | 1 | 0.3 | 0.7 | 2.5 | 15.75
3 | C6, C11 (300X715) | CUM | 14 | 1 | 0.3 | 0.715 | 2.5 | 7.5075
4 | C7 (300X800) | CUM | 4 | 1 | 0.3 | 0.8 | 2.5 | 2.4
5 | SW 1 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 2.5 | 0.7475
6 |  | CUM | 2 | 1 | 0.23 | 1.42 | 2.5 | 1.633
7 | SW 2 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 2.5 | 0.7475
8 |  | CUM | 2 | 1 | 0.23 | 1.62 | 2.5 | 1.863
9 | SW 3 (230x1000) | CUM | 2 | 1 | 0.23 | 1 | 2.5 | 1.15
10 | SW 4 (230x1150) | CUM | 2 | 1 | 0.23 | 1.15 | 2.5 | 1.3225
11 | SW 5 (230x1700) | CUM | 4 | 1 | 0.23 | 1.7 | 2.5 | 3.91
12 | SW 6 (230x1185) | CUM | 4 | 1 | 0.23 | 1.185 | 2.5 | 2.7255
13 | SW 7 (230x1855) | CUM | 2 | 1 | 0.23 | 1.855 | 2.5 | 2.1333
14 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 2.5 | 2.07
15 | SW 9 (L-SHAPE) | CUM | 6 | 1 | 0.23 | 0.65 | 2.5 | 2.2425
16 |  | CUM | 6 | 1 | 0.23 | 1.62 | 2.5 | 5.589
17 | SW 10 (230x3445) | CUM | 2 | 1 | 0.23 | 3.445 | 2.5 | 3.9617
18 | SW 11 (230x4065) | CUM | 2 | 1 | 0.23 | 4.065 | 2.5 | 4.6748
19 | SW 12 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 2.5 | 0.7475
20 |  | CUM | 2 | 1 | 0.23 | 1.305 | 2.5 | 1.5007
21 | SW 13 (200x3445) | CUM | 2 | 1 | 0.2 | 3.445 | 2.5 | 3.445
[7 empty] | TOTAL | 94.021
COLUMN Junction (1-43/A-Q) 1ST FLOOR LVL to 2nd floor LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 62 | 1 | 0.3 | 0.6 | 0.45 | 5.022
2 | C4, C5 (300X750) | CUM | 30 | 1 | 0.3 | 0.7 | 0.45 | 2.835
3 | C6, C11 (300X715) | CUM | 14 | 1 | 0.3 | 0.715 | 0.45 | 1.3514
4 | C7 (300X800) | CUM | 4 | 1 | 0.3 | 0.8 | 0.45 | 0.432
5 | SW 1 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.45 | 0.13455
6 |  | CUM | 2 | 1 | 0.23 | 1.42 | 0.45 | 0.29394
7 | SW 2 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.45 | 0.13455
8 |  | CUM | 2 | 1 | 0.23 | 1.62 | 0.45 | 0.33534
9 | SW 3 (230x1000) | CUM | 2 | 1 | 0.23 | 1 | 0.45 | 0.207
10 | SW 4 (230x1150) | CUM | 2 | 1 | 0.23 | 1.15 | 0.45 | 0.23805
11 | SW 5 (230x1700) | CUM | 4 | 1 | 0.23 | 1.7 | 0.45 | 0.7038
12 | SW 6 (230x1185) | CUM | 4 | 1 | 0.23 | 1.185 | 0.45 | 0.49059
13 | SW 7 (230x1855) | CUM | 2 | 1 | 0.23 | 1.855 | 0.45 | 0.38399
14 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 0.45 | 0.3726
15 | SW 9 (L-SHAPE) | CUM | 6 | 1 | 0.23 | 0.65 | 0.45 | 0.40365
16 |  | CUM | 6 | 1 | 0.23 | 1.62 | 0.45 | 1.006
17 | SW 10 (230x3445) | CUM | 2 | 1 | 0.23 | 3.445 | 0.45 | 0.71312
18 | SW 11 (230x4065) | CUM | 2 | 1 | 0.23 | 4.065 | 0.45 | 0.84146
19 | SW 12 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.45 | 0.13455
20 |  | CUM | 2 | 1 | 0.23 | 1.305 | 0.45 | 0.27013
21 | SW 13 (200x3445) | CUM | 2 | 1 | 0.2 | 3.445 | 0.45 | 0.6201
[7 empty] | TOTAL | 16.9238
COLUMN & Beam Junction (1-43/A-Q) 1ST FLOOR LVL to 2nd floor LVL
1 | B1 200X500 GridA ,32to38 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
2 | B1 200X500 GridA ,7to13 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
3 | B2 200X500 GridB, 28to32 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
4 | B2 200X500 GridB, 13to16 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
5 | B3 AT GRID B-C/27-28 | CUM | 1 | 1 | 0.5 | 0.35 | 0.1 | 0.0175
6 | B3 AT GRID B-C/16to17 | CUM | 1 | 1 | 0.5 | 0.35 | 0.1 | 0.0175
7 | B3 AT GRID L-M/27-28 | CUM | 1 | 1 | 1 | 0.35 | 0.115 | 0.04025
8 | B3 AT GRID L-M/16to17 | CUM | 1 | 1 | 1 | 0.35 | 0.115 | 0.04025
9 | B3 AT GRID Q/27-28 | CUM | 1 | 1 | 0.5 | 0.35 | 0.115 | 0.020125
10 | B3 AT GRID Q/16to17 | CUM | 1 | 1 | 0.5 | 0.35 | 0.115 | 0.020125
11 | B3 AT GRID E/32-33 | CUM | 1 | 1 | 1 | 0.35 | 0.1 | 0.035
12 | B3 AT GRID E/11to12 | CUM | 1 | 1 | 1 | 0.35 | 0.1 | 0.035
13 | B3 AT GRID Q/32-33 | CUM | 1 | 1 | 0.5 | 0.35 | 0.1 | 0.0175
14 | B3 AT GRID Q/11to12 | CUM | 1 | 1 | 0.5 | 0.35 | 0.1 | 0.0175
15 | B3 AT GRID F/43 | CUM | 1 | 1 | 0.5 | 0.35 | 0.1 | 0.0175
16 | B3 AT GRID F/1 | CUM | 1 | 1 | 0.5 | 0.35 | 0.1 | 0.0175
17 | B3 AT GRID F/39-40 | CUM | 1 | 1 | 0.5 | 0.35 | 0.1 | 0.0175
18 | B3 AT GRID F/4to5 | CUM | 1 | 1 | 0.5 | 0.35 | 0.1 | 0.0175
19 | B3 AT GRID Q/39-40 | CUM | 1 | 1 | 0.5 | 0.35 | 0.1 | 0.0175
20 | B3 AT GRID Q/4to5 | CUM | 1 | 1 | 0.5 | 0.35 | 0.1 | 0.0175
21 | B4 200X350 GridBtoC,27to28 | CUM | 1 | 1 | 1 | 0.35 | 0.2 | 0.07
22 | B4 200X350 GridBtoC,16to17 | CUM | 1 | 1 | 1 | 0.35 | 0.2 | 0.07
23 | B4 200X350 GridLtoN,27to28 | CUM | 1 | 1 | 0.5 | 0.35 | 0.2 | 0.035
24 | B4 200X350 GridLtoN,16to17 | CUM | 1 | 1 | 0.5 | 0.35 | 0.2 | 0.035
25 | B5 200X450 GridC , 32to38 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
26 | B5 200X450 GridC , 6to12 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
27 | B6 230X350 Grid D,35to38 | CUM | 1 | 1 | 1 | 0.35 | 0.23 | 0.0805
28 | B6 230X350 Grid D,6to9 | CUM | 1 | 1 | 1 | 0.35 | 0.23 | 0.0805
29 | B7 200X450GridD,32to35 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
30 | B7 200X450GridD,9to12 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
31 | B8 200X500 GridD,26to28 | CUM | 1 | 1 | 1 | 0.5 | 0.2 | 0.1
32 | B8 200X500 GridD,16to18 | CUM | 1 | 1 | 1 | 0.5 | 0.2 | 0.1
33 | B8 200X350GridD,25to26 | CUM | 1 | 1 | 0.5 | 0.35 | 0.2 | 0.035
34 | B8 200X350GridD,18to19 | CUM | 1 | 1 | 0.5 | 0.35 | 0.2 | 0.035
35 | B9 200X500 GridC,23to25 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
36 | B9 200X500 GridL,23to25 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
37 | B9 200X500 GridC,19to21 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
38 | B9 200X500 GridL,19to21 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
39 | B11 200X450 Grid DtoE, 23to25 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
40 | B11 200X450 Grid DtoE, 19to21 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
41 | B11 200X450 Grid J, 23to25 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
42 | B11 200X450 Grid J, 19to21 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
43 | B12 200X450 GridE 20to22 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
44 | B12 200X450 GridE 22to24 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
45 | B13 200X450 GridDto E,28to32 | CUM | 1 | 1 | 0.5 | 0.35 | 0.2 | 0.035
46 | B13 200X450 GridDto E,13to16 | CUM | 1 | 1 | 0.5 | 0.35 | 0.2 | 0.035
47 | B13 200X350GridDto E,32to35 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
48 | B13 200X350GridDto E,10to13 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
49 | B14 200X450GridE,26to28 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
50 | B14 200X450GridE,16to18 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
51 | B14 200X450GridE,28to29 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
52 | B14 200X450GridE,15to16 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
53 | B15 200X500 Grid E,34to38 | CUM | 1 | 1 | 1 | 0.5 | 0.2 | 0.1
54 | B15 200X500 Grid E,7to11 | CUM | 1 | 1 | 1 | 0.5 | 0.2 | 0.1
55 | B16 200X350 GridF&Q27to43 | CUM | 1 | 3 | 1 | 0.35 | 0.2 | 0.21
56 | B16 200X350 GridF&Q1t17 | CUM | 1 | 3 | 1 | 0.35 | 0.2 | 0.21
57 | B17 200X500 GridH,37to39 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
58 | B17 200X500 GridH,5to7 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
59 | B18 230X500 Grid F,30to33 | CUM | 1 | 1 | 1 | 0.5 | 0.23 | 0.115
60 | B18 230X500 Grid F,11to14 | CUM | 1 | 1 | 1 | 0.5 | 0.23 | 0.115
61 | B19 200X450 Grid G,25to28 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
62 | B19 200X450 Grid G,16to19 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
63 | B20 200X350 Grid G,21to22 | CUM | 1 | 1 | 0.5 | 0.35 | 0.2 | 0.035
64 | B20 200X350 Grid G,22to23 | CUM | 1 | 1 | 0.5 | 0.35 | 0.2 | 0.035
65 | B21 230X450 Grid I ,22to24 | CUM | 1 | 1 | 0.5 | 0.45 | 0.23 | 0.05175
66 | B21 230X450 Grid I ,20to22 | CUM | 1 | 1 | 0.5 | 0.45 | 0.23 | 0.05175
67 | B22 200x450 Grid I,26 to28 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
68 | B22 200x450 Grid I,16 to18 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
69 | B23 200X450 Grid J,30to35 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
70 | B23 200X450 Grid J,9to15 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
71 | B24 200X450 Grid J, 28to37 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
72 | B24 200X450 Grid J, 7to16 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
73 | B25 200X500 grid J,39to43 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
74 | B25 200X500 grid J,1to5 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
75 | B25 200X500 grid P,39to43 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
76 | B25 200X500 grid P,1to5 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
77 | B25 200X500 grid P,10to17 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
78 | B25 200X500 grid P,27to34 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
79 | B26 200X500 Grid L&D,27to43 | CUM | 1 | 3 | 0.5 | 0.5 | 0.2 | 0.15
80 | B26 200X350 Grid L&D,27to43 | CUM | 1 | 3 | 0.5 | 0.35 | 0.2 | 0.105
81 | B26 200X500 Grid L&D,1to17 | CUM | 1 | 3 | 0.5 | 0.5 | 0.2 | 0.15
82 | B26 200X350 Grid L&D,1to17 | CUM | 1 | 3 | 0.5 | 0.35 | 0.2 | 0.105
83 | B27 200X450 Grid L,37to40 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
84 | B27 200X450 Grid L,4to7 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
85 | B28 230X450 Grid K,32to37 | CUM | 1 | 1 | 1 | 0.45 | 0.23 | 0.1035
86 | B28 230X450 Grid K,6to12 | CUM | 1 | 1 | 1 | 0.45 | 0.23 | 0.1035
87 | B29 200X450 Grid K, 25to31 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
88 | B29 200X450 Grid K, 13to19 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
89 | B30 200X450 Grid N,28to36 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
90 | B30 200X350 Grid N,9to16 | CUM | 1 | 1 | 1 | 0.35 | 0.2 | 0.07
91 | B31 200X350 Grid N,38to41 | CUM | 1 | 1 | 0.5 | 0..35 | 0.2 | 0.1
92 | B31 200X350 Grid N,3to6 | CUM | 1 | 1 | 0.5 | 0..35 | 0.2 | 0.1
93 | B32 230X450 Grid O,32to40 | CUM | 1 | 2 | 1 | 0.45 | 0.23 | 0.207
94 | B32 230X450 Grid O,4to12 | CUM | 1 | 2 | 1 | 0.45 | 0.23 | 0.207
95 | B33 200X500 Grid PtoQ,34to39 | CUM | 1 | 1 | 1 | 0.5 | 0.2 | 0.1
96 | B33 200X500 Grid PtoQ,5to10 | CUM | 1 | 1 | 1 | 0.5 | 0.2 | 0.1
97 | B34 230X500 grid HtoL,43 | CUM | 1 | 1 | 1 | 0.5 | 0.23 | 0.115
98 | B34 230X500 grid DtoQ,43 | CUM | 1 | 1 | 0.5 | 0.5 | 0.23 | 0.0575
99 | B34 230X500 grid DtoQ,27 | CUM | 1 | 1 | 0.5 | 0.5 | 0.23 | 0.0575
100 | B34 230X500 grid DtoQ,17 | CUM | 1 | 1 | 0.5 | 0.5 | 0.23 | 0.0575
101 | B34 230X500 grid HtoL,1 | CUM | 1 | 1 | 0.5 | 0.5 | 0.23 | 0.0575
102 | B34 230X500 grid DtoQ,1 | CUM | 1 | 1 | 1 | 0.5 | 0.23 | 0.115
103 | B36 200X450 Grid JtoQ,27to43 | CUM | 1 | 3 | 0.5 | 0.45 | 0.2 | 0.135
104 | B36 200X450 Grid JtoQ,1to17 | CUM | 1 | 3 | 0.5 | 0.45 | 0.2 | 0.135
105 | B37 200X450 JtoQ,27to43 | CUM | 1 | 3 | 0.5 | 0.45 | 0.2 | 0.135
106 | B37 200X450 JtoQ,1to17 | CUM | 1 | 3 | 0.5 | 0.45 | 0.2 | 0.135
107 | B38 200X450 JtoQ,27to43 | CUM | 1 | 2 | 0.5 | 0.45 | 0.2 | 0.09
108 | B38 200X450 JtoQ,1to17 | CUM | 1 | 2 | 0.5 | 0.45 | 0.2 | 0.09
109 | B39 200X500 Grid FtoQ,34&39 | CUM | 1 | 3 | 1 | 0.5 | 0.2 | 0.3
110 | B39 200X500 Grid FtoQ,5&11 | CUM | 1 | 3 | 1 | 0.5 | 0.2 | 0.3
111 | B40 200X450 Grid MtoO,38 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
112 | B40 200X450 Grid MtoO,6 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
113 | B41 200X450 GridOtoQ,37 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
114 | B41 200X450 GridOtoQ,7 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
115 | B42 200X350 Grid Nto O,32to33 | CUM | 1 | 2 | 0.5 | 0.35 | 0.2 | 0.07
116 | B42 200X350 Grid Nto O,12to14 | CUM | 1 | 2 | 0.5 | 0.35 | 0.2 | 0.07
117 | B43 200X450 Grid NtoO,36 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
118 | B43 200X450 Grid NtoO,8 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
119 | B44 200X500 Grid HtoL,37 | CUM | 1 | 1 | 1 | 0.5 | 0.2 | 0.1
120 | B44 200X500 Grid HtoL,7 | CUM | 1 | 1 | 1 | 0.5 | 0.2 | 0.1
121 | B45 200X500 Grid BtoD,38 | CUM | 1 | 1 | 1 | 0.5 | 0.2 | 0.1
122 | B45 200X500 Grid BtoD,6 | CUM | 1 | 1 | 1 | 0.5 | 0.2 | 0.1
123 | B46 200X350 Grid DtoE,37 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
124 | B46 200X350 Grid DtoE,7 | CUM | 1 | 1 | 0.5 | 0.35 | 0.2 | 0.035
125 | B47 200X450 Grid AtoC ,35 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
126 | B47 200X450 Grid AtoC ,9 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
127 | B48 200X450 Grid DtoE,34 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
128 | B48 200X450 Grid DtoE,11 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
129 | B49 200X500 Grid AtoC,32 | CUM | 1 | 1 | 1 | 0.5 | 0.2 | 0.1
130 | B49 200X500 Grid AtoC,12 | CUM | 1 | 1 | 1 | 0.5 | 0.2 | 0.1
131 | B50 200X450 Grid CtoE,31 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
132 | B50 200X450 Grid CtoE,12 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
133 | B52 230X500 Grid EtoJ,35 | CUM | 1 | 1 | 1 | 0.5 | 0.23 | 0.115
134 | B52 230X500 Grid EtoJ,9 | CUM | 1 | 1 | 1 | 0.5 | 0.23 | 0.115
135 | B54 230X450 Grid JtoK,32 | CUM | 1 | 1 | 0.5 | 0.45 | 0.23 | 0.05175
136 | B54 230X450 Grid JtoK,13 | CUM | 1 | 1 | 0.5 | 0.45 | 0.23 | 0.05175
137 | B55 230X450 Grid EtoJ,29 | CUM | 1 | 1 | 1 | 0.45 | 0.23 | 0.1035
138 | B55 230X450 Grid EtoJ,15 | CUM | 1 | 1 | 1 | 0.45 | 0.23 | 0.1035
139 | B56 230X450 Grid ItoK,28 | CUM | 1 | 1 | 1 | 0.45 | 0.23 | 0.1035
140 | B56 230X450 Grid ItoK,16 | CUM | 1 | 1 | 1 | 0.45 | 0.23 | 0.1035
141 | B57 200X450 GridDtoE,28 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
142 | B57 230X450 GridCtoD,28 | CUM | 1 | 1 | 1 | 0.45 | 0.23 | 0.1035
143 | B57 200X450 GridDtoE,16 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
144 | B57 230X450 GridCtoD,16 | CUM | 1 | 1 | 1 | 0.45 | 0.23 | 0.1035
145 | B58 200X500 Grid CtoD,27 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
146 | B58 200X500 Grid KtoM,27 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
147 | B58 200X500 Grid CtoD,17 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
148 | B58 200X500 Grid KtoM,17 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
149 | B59 200X450 Grid EtoI,27to28 | CUM | 1 | 1 | 1 | 0.5 | 0.2 | 0.1
150 | B59 200X450 Grid EtoI,16to17 | CUM | 1 | 1 | 1 | 0.5 | 0.2 | 0.1
151 | B60 200X450 Grid DtoE,26 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
152 | B60 200X450 Grid ItoK,26 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
153 | B60 200X450 Grid DtoE,18 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
154 | B60 200X450 Grid ItoK,18 | CUM | 1 | 1 | 0.5 | 0.45 | 0.2 | 0.045
155 | B61 200X350 Grid CtoD,25 | CUM | 1 | 1 | 0.5 | 0.35 | 0.2 | 0.035
156 | B61 200X350 Grid JtoK,25 | CUM | 1 | 1 | 1 | 0.35 | 0.2 | 0.07
157 | B61 200X350 Grid CtoD,19 | CUM | 1 | 1 | 1 | 0.35 | 0.2 | 0.07
158 | B61 200X350 Grid JtoK,19 | CUM | 1 | 1 | 1 | 0.35 | 0.2 | 0.07
159 | B62 200X450 GridEtoJ,24to25 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
160 | B62 200X450 GridEtoJ,19to20 | CUM | 1 | 1 | 1 | 0.45 | 0.2 | 0.09
161 | B64 200X500 Grid CtoE,23 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
162 | B64 200X500 Grid ItoL,23 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
163 | B64 200X500 Grid CtoE,21 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
164 | B64 200X500 Grid ItoL,21 | CUM | 1 | 1 | 0.5 | 0.5 | 0.2 | 0.05
[6 empty] | Total |  | 12.2358
Total M-40 of Column , Column junction & Column beam Junction
123.1805
Beam RCC(1to 43 &AtoQ
1 | B1 200X500 GridA ,32to38 | CUM | 1 | 1 | 5.825 | 0.5 | 0.2 | 0.5825
2 | B1 200X500 GridA ,7to13 | CUM | 1 | 1 | 5.825 | 0.5 | 0.2 | 0.5825
3 | B2 200X500 GridB, 28to32 | CUM | 1 | 1 | 3.3 | 0.5 | 0.2 | 0.33
4 | B2 200X500 GridB, 13to16 | CUM | 1 | 1 | 3.3 | 0.5 | 0.2 | 0.33
5 | B3 100X350 AT GRID B-C/27-28 | CUM | 1 | 1 | 1.395 | 0.35 | 0.1 | 0.048825
6 | B3 100X350 AT GRID B-C/16to17 | CUM | 1 | 1 | 1.395 | 0.35 | 0.1 | 0.048825
7 | B3 100X350 AT GRID L-M/27-28 | CUM | 1 | 1 | 1.395 | 0.35 | 0.115 | 0.056149
8 | B3 100X350 AT GRID L-M/16to17 | CUM | 1 | 1 | 1.395 | 0.35 | 0.115 | 0.056149
9 | B3 100X350 AT GRID Q/27-28 | CUM | 1 | 1 | 2.055 | 0.35 | 0.115 | 0.082714
10 | B3 100X350 AT GRID Q/16to17 | CUM | 1 | 1 | 2.055 | 0.35 | 0.115 | 0.082714
11 | B3 100X350 AT GRID E/32-33 | CUM | 1 | 1 | 1.185 | 0.35 | 0.1 | 0.041475
12 | B3100X350 AT GRID E/11to12 | CUM | 1 | 1 | 1.185 | 0.35 | 0.1 | 0.041475
13 | B3 100X350 AT GRID Q/32-33 | CUM | 1 | 1 | 1.185 | 0.35 | 0.1 | 0.041475
14 | B3 100X350 AT GRID Q/11to12 | CUM | 1 | 1 | 1.185 | 0.35 | 0.1 | 0.041475
15 | B3 100X350 AT GRID F/43 | CUM | 1 | 1 | 2.055 | 0.35 | 0.1 | 0.071925
16 | B3 100X350 AT GRID F/1 | CUM | 1 | 1 | 2.055 | 0.35 | 0.1 | 0.071925
17 | B3 100X350 AT GRID Q/43 | CUM | 1 | 1 | 2.055 | 0.35 | 0.1 | 0.071925
18 | B3 100X350 AT GRID Q/1 | CUM | 1 | 1 | 2.055 | 0.35 | 0.1 | 0.071925
19 | B3 100X350 AT GRID F/39-40 | CUM | 1 | 1 | 1.485 | 0.35 | 0.1 | 0.051975
20 | B3 100X350 AT GRID F/4to5 | CUM | 1 | 1 | 1.485 | 0.35 | 0.1 | 0.051975
21 | B3 100X350 AT GRID Q/39-40 | CUM | 1 | 1 | 1.485 | 0.35 | 0.1 | 0.051975
22 | B3 100X350 AT GRID Q/4to5 | CUM | 1 | 1 | 1.485 | 0.35 | 0.1 | 0.051975
23 | B3 100X350 AT GRID M & O/39-40 | CUM | 1 | 3 | 2.315 | 0.35 | 0.1 | 0.24307
24 | B3 100X350 AT GRID M & O/3to4 | CUM | 1 | 3 | 2.315 | 0.35 | 0.1 | 0.24307
25 | B3 100X350 AT GRID C,K/25 | CUM | 1 | 2 | 2.315 | 0.35 | 0.1 | 0.16205
26 | B3 100X350 AT GRID C,K/19 | CUM | 1 | 2 | 2.315 | 0.35 | 0.1 | 0.16205
27 | B4 200X350 GridBtoC,27to28 | CUM | 1 | 1 | 1.395 | 0.35 | 0.2 | 0.09765
28 | B4 200X350 GridBtoC,16to17 | CUM | 1 | 1 | 1.395 | 0.35 | 0.2 | 0.09765
29 | B4 200X350 GridLtoN,27to28 | CUM | 1 | 1 | 1.395 | 0.35 | 0.2 | 0.09765
30 | B4 200X350 GridLtoN,16to17 | CUM | 1 | 1 | 1.395 | 0.35 | 0.2 | 0.09765
31 | B5 200X450 GridC , 32to38 | CUM | 1 | 1 | 6.875 | 0.45 | 0.2 | 0.61875
32 | B5 200X450 GridC , 6to12 | CUM | 1 | 1 | 6.875 | 0.45 | 0.2 | 0.61875
33 | B6 230X350 Grid D,35to38 | CUM | 1 | 1 | 3.16 | 0.35 | 0.23 | 0.25438
34 | B6 230X350 Grid D,6to9 | CUM | 1 | 1 | 3.16 | 0.35 | 0.23 | 0.25438
35 | B7 200X450GridD,32to35 | CUM | 1 | 1 | 3 | 0.45 | 0.2 | 0.27
36 | B7 200X450GridD,9to12 | CUM | 1 | 1 | 3 | 0.45 | 0.2 | 0.27
37 | B8 200X500 GridD,26to28 | CUM | 1 | 1 | 2.875 | 0.5 | 0.2 | 0.2875
38 | B8 200X500 GridD,16to18 | CUM | 1 | 1 | 2.875 | 0.5 | 0.2 | 0.2875
39 | B8 200X350GridD,25to26 | CUM | 1 | 1 | 2.93 | 0.35 | 0.2 | 0.2051
40 | B8 200X350GridD,18to19 | CUM | 1 | 1 | 2.93 | 0.35 | 0.2 | 0.2051
41 | B9 200X500 GridC,23to25 | CUM | 1 | 1 | 4.69 | 0.5 | 0.2 | 0.469
42 | B9 200X500 GridL,23to25 | CUM | 1 | 1 | 4.69 | 0.5 | 0.2 | 0.469
43 | B9 200X500 GridC,19to21 | CUM | 1 | 1 | 4.69 | 0.5 | 0.2 | 0.469
44 | B9 200X500 GridL,19to21 | CUM | 1 | 1 | 4.69 | 0.5 | 0.2 | 0.469
45 | B10 200X500 Grid D ,21to23 | CUM | 1 | 1 | 6.3 | 0.5 | 0.2 | 0.63
46 | B10 200X500 Grid K ,21to23 | CUM | 1 | 1 | 6.3 | 0.5 | 0.2 | 0.63
47 | B11 200X450 Grid DtoE, 23to25 | CUM | 1 | 1 | 4.69 | 0.45 | 0.2 | 0.4221
48 | B11 200X450 Grid DtoE, 19to21 | CUM | 1 | 1 | 4.69 | 0.45 | 0.2 | 0.4221
49 | B11 200X450 Grid J, 23to25 | CUM | 1 | 1 | 4.69 | 0.45 | 0.2 | 0.4221
50 | B11 200X450 Grid J, 19to21 | CUM | 1 | 1 | 4.69 | 0.45 | 0.2 | 0.4221
51 | B12 200X450 GridE 20to22 | CUM | 1 | 1 | 5.76 | 0.45 | 0.2 | 0.5184
52 | B12 200X450 GridE 22to24 | CUM | 1 | 1 | 5.76 | 0.45 | 0.2 | 0.5184
53 | B13 200X450 GridDto E,28to32 | CUM | 1 | 1 | 4.15 | 0.35 | 0.2 | 0.2905
54 | B13 200X450 GridDto E,13to16 | CUM | 1 | 1 | 4.15 | 0.35 | 0.2 | 0.2905
55 | B13 200X350GridDto E,32to35 | CUM | 1 | 1 | 1.65 | 0.45 | 0.2 | 0.1485
56 | B13 200X350GridDto E,10to13 | CUM | 1 | 1 | 1.65 | 0.45 | 0.2 | 0.1485
57 | B14 200X450GridE,26to28 | CUM | 1 | 1 | 2.2 | 0.45 | 0.2 | 0.198
58 | B14 200X450GridE,16to18 | CUM | 1 | 1 | 2.2 | 0.45 | 0.2 | 0.198
59 | B14 200X450GridE,28to29 | CUM | 1 | 1 | 1.5 | 0.45 | 0.2 | 0.135
60 | B14 200X450GridE,15to16 | CUM | 1 | 1 | 1.5 | 0.45 | 0.2 | 0.135
61 | B15 200X500 Grid E,34to38 | CUM | 1 | 1 | 3.115 | 0.5 | 0.2 | 0.3115
62 | B15 200X500 Grid E,7to11 | CUM | 1 | 1 | 3.115 | 0.5 | 0.2 | 0.3115
63 | B16 200X350 GridF&Q27to43 | CUM | 1 | 3 | 7.61 | 0.35 | 0.2 | 1.5981
64 | B16 200X350 GridF&Q1t17 | CUM | 1 | 3 | 7.61 | 0.35 | 0.2 | 1.5981
65 | B17 200X500 GridH,37to39 | CUM | 1 | 1 | 3.215 | 0.5 | 0.2 | 0.3215
66 | B17 200X500 GridH,5to7 | CUM | 1 | 1 | 3.215 | 0.5 | 0.2 | 0.3215
67 | B18 230X500 Grid F,30to33 | CUM | 1 | 1 | 2.76 | 0.5 | 0.23 | 0.3174
68 | B18 230X500 Grid F,11to14 | CUM | 1 | 1 | 2.76 | 0.5 | 0.23 | 0.3174
69 | B19 200X450 Grid G,25to28 | CUM | 1 | 1 | 6.79 | 0.45 | 0.2 | 0.6111
70 | B19 200X450 Grid G,16to19 | CUM | 1 | 1 | 6.79 | 0.45 | 0.2 | 0.6111
71 | B20 200X350 Grid G,21to22 | CUM | 1 | 1 | 2.41 | 0.35 | 0.2 | 0.1687
72 | B20 200X350 Grid G,22to23 | CUM | 1 | 1 | 2.41 | 0.35 | 0.2 | 0.1687
73 | B21 230X450 Grid I ,22to24 | CUM | 1 | 1 | 5.76 | 0.45 | 0.23 | 0.59616
74 | B21 230X450 Grid I ,20to22 | CUM | 1 | 1 | 5.76 | 0.45 | 0.23 | 0.59616
75 | B22 200x450 Grid I,26 to28 | CUM | 1 | 1 | 4.69 | 0.45 | 0.2 | 0.4221
76 | B22 200x450 Grid I,16 to18 | CUM | 1 | 1 | 4.69 | 0.45 | 0.2 | 0.4221
77 | B23 200X450 Grid J,30to35 | CUM | 1 | 1 | 5.63 | 0.45 | 0.2 | 0.5067
78 | B23 200X450 Grid J,9to15 | CUM | 1 | 1 | 5.63 | 0.45 | 0.2 | 0.5067
79 | B24 200X450 Grid J, 28to37 | CUM | 1 | 1 | 9.22 | 0.45 | 0.2 | 0.8298
80 | B24 200X450 Grid J, 7to16 | CUM | 1 | 1 | 9.22 | 0.45 | 0.2 | 0.8298
81 | B25 200X500 grid J,39to43 | CUM | 1 | 1 | 7.95 | 0.5 | 0.2 | 0.795
82 | B25 200X500 grid J,1to5 | CUM | 1 | 1 | 7.95 | 0.5 | 0.2 | 0.795
83 | B25 200X500 grid P,39to43 | CUM | 1 | 1 | 7.95 | 0.5 | 0.2 | 0.795
84 | B25 200X500 grid P,1to5 | CUM | 1 | 1 | 7.95 | 0.5 | 0.2 | 0.795
85 | B25 200X500 grid P,10to17 | CUM | 1 | 1 | 7.95 | 0.5 | 0.2 | 0.795
86 | B25 200X500 grid P,27to34 | CUM | 1 | 1 | 7.95 | 0.5 | 0.2 | 0.795
87 | B25 200X450 BESIDE STAIRS | CUM | 2 | 1 | 5.63 | 0.45 | 0.2 | 1.0134
88 | B26 200X500 Grid L&D,27to43 | CUM | 1 | 3 | 3.17 | 0.5 | 0.2 | 0.951
89 | B26 200X350 Grid L&D,27to43 | CUM | 1 | 3 | 4.72 | 0.35 | 0.2 | 0.9912
90 | B26 200X500 Grid L&D,1to17 | CUM | 1 | 3 | 3.17 | 0.5 | 0.2 | 0.951
91 | B26 200X350 Grid L&D,1to17 | CUM | 1 | 3 | 4.72 | 0.35 | 0.2 | 0.9912
92 | B27 200X450 Grid L,37to40 | CUM | 1 | 1 | 5.125 | 0.45 | 0.2 | 0.46125
93 | B27 200X450 Grid L,4to7 | CUM | 1 | 1 | 5.125 | 0.45 | 0.2 | 0.46125
94 | B28 230X450 Grid K,32to37 | CUM | 1 | 1 | 5.24 | 0.45 | 0.23 | 0.54234
95 | B28 230X450 Grid K,6to12 | CUM | 1 | 1 | 5.24 | 0.45 | 0.23 | 0.54234
96 | B29 200X450 Grid K, 25to31 | CUM | 1 | 1 | 9.75 | 0.45 | 0.2 | 0.8775
97 | B29 200X450 Grid K, 13to19 | CUM | 1 | 1 | 9.75 | 0.45 | 0.2 | 0.8775
98 | B30 200X450 Grid N,28to36 | CUM | 1 | 1 | 7.305 | 0.45 | 0.2 | 0.65745
99 | B30 200X350 Grid N,9to16 | CUM | 1 | 1 | 7.305 | 0.35 | 0.2 | 0.51135
100 | B31 200X350 Grid N,38to41 | CUM | 1 | 1 | 5.235 | 0..35 | 0.2 | 1.047
101 | B31 200X350 Grid N,3to6 | CUM | 1 | 1 | 5.235 | 0..35 | 0.2 | 1.047
102 | B32 230X450 Grid O,32to40 | CUM | 1 | 2 | 10.2 | 0.45 | 0.23 | 2.1114
103 | B32 230X450 Grid O,4to12 | CUM | 1 | 2 | 10.2 | 0.45 | 0.23 | 2.1114
104 | B33 200X500 Grid PtoQ,34to39 | CUM | 1 | 1 | 6.38 | 0.5 | 0.2 | 0.638
105 | B33 200X500 Grid PtoQ,5to10 | CUM | 1 | 1 | 6.38 | 0.5 | 0.2 | 0.638
106 | B34 230X500 grid HtoL,43 | CUM | 1 | 1 | 5.36 | 0.5 | 0.23 | 0.6164
107 | B34 230X500 grid DtoQ,43 | CUM | 1 | 1 | 5.36 | 0.5 | 0.23 | 0.6164
108 | B34 230X500 grid DtoQ,27 | CUM | 1 | 1 | 5.36 | 0.5 | 0.23 | 0.6164
109 | B34 230X500 grid DtoQ,17 | CUM | 1 | 1 | 5.36 | 0.5 | 0.23 | 0.6164
110 | B34 230X500 grid HtoL,1 | CUM | 1 | 1 | 5.36 | 0.5 | 0.23 | 0.6164
111 | B34 230X500 grid DtoQ,1 | CUM | 1 | 1 | 5.36 | 0.5 | 0.23 | 0.6164
112 | B35 200X450 Gid ItoQ,27to43 | CUM | 1 | 3 | 3.86 | 0.45 | 0.2 | 1.0422
113 | B35 200X450 Gid ItoQ,1to17 | CUM | 1 | 3 | 3.86 | 0.45 | 0.2 | 1.0422
114 | B36 200X450 Grid JtoQ,27to43 | CUM | 1 | 3 | 3.45 | 0.45 | 0.2 | 0.9315
115 | B36 200X450 Grid JtoQ,1to17 | CUM | 1 | 3 | 3.45 | 0.45 | 0.2 | 0.9315
116 | B37 200X450 JtoQ,27to43 | CUM | 1 | 3 | 6.36 | 0.45 | 0.2 | 1.7172
117 | B37 200X450 JtoQ,1to17 | CUM | 1 | 3 | 6.36 | 0.45 | 0.2 | 1.7172
118 | B38 200X450 JtoQ,27to43 | CUM | 1 | 2 | 7.13 | 0.45 | 0.2 | 1.2834
119 | B38 200X450 JtoQ,1to17 | CUM | 1 | 2 | 7.13 | 0.45 | 0.2 | 1.2834
120 | B39 200X500 Grid FtoQ,34&39 | CUM | 1 | 3 | 3.32 | 0.5 | 0.2 | 0.996
121 | B39 200X500 Grid FtoQ,5&11 | CUM | 1 | 3 | 3.32 | 0.5 | 0.2 | 0.996
122 | B40 200X450 Grid MtoO,38 | CUM | 1 | 1 | 4.19 | 0.45 | 0.2 | 0.3771
123 | B40 200X450 Grid MtoO,6 | CUM | 1 | 1 | 4.19 | 0.45 | 0.2 | 0.3771
124 | B41 200X450 GridOtoQ,37 | CUM | 1 | 1 | 5.25 | 0.45 | 0.2 | 0.4725
125 | B41 200X450 GridOtoQ,7 | CUM | 1 | 1 | 5.25 | 0.45 | 0.2 | 0.4725
126 | B42 200X350 Grid Nto O,32to33 | CUM | 1 | 2 | 5.83 | 0.35 | 0.2 | 0.8162
127 | B42 200X350 Grid Nto O,12to14 | CUM | 1 | 2 | 5.83 | 0.35 | 0.2 | 0.8162
128 | B43 200X450 Grid NtoO,36 | CUM | 1 | 1 | 2.18 | 0.45 | 0.2 | 0.1962
129 | B43 200X450 Grid NtoO,8 | CUM | 1 | 1 | 2.18 | 0.45 | 0.2 | 0.1962
130 | B44 200X500 Grid HtoL,37 | CUM | 1 | 1 | 5.15 | 0.5 | 0.2 | 0.515
131 | B44 200X500 Grid HtoL,7 | CUM | 1 | 1 | 5.15 | 0.5 | 0.2 | 0.515
132 | B45 200X500 Grid BtoD,38 | CUM | 1 | 1 | 3.8 | 0.5 | 0.2 | 0.38
133 | B45 200X500 Grid BtoD,6 | CUM | 1 | 1 | 3.8 | 0.5 | 0.2 | 0.38
134 | B46 200X350 Grid DtoE,37 | CUM | 1 | 1 | 3.15 | 0.5 | 0.2 | 0.315
135 | B46 200X350 Grid DtoE,7 | CUM | 1 | 1 | 3.15 | 0.35 | 0.2 | 0.2205
136 | B47 200X450 Grid AtoC ,35 | CUM | 1 | 1 | 4.55 | 0.45 | 0.2 | 0.4095
137 | B47 200X450 Grid AtoC ,9 | CUM | 1 | 1 | 4.55 | 0.45 | 0.2 | 0.4095
138 | B48 200X450 Grid DtoE,34 | CUM | 1 | 1 | 2.5 | 0.45 | 0.2 | 0.225
139 | B48 200X450 Grid DtoE,11 | CUM | 1 | 1 | 2.5 | 0.45 | 0.2 | 0.225
140 | B49 200X500 Grid AtoC,32 | CUM | 1 | 1 | 3.15 | 0.5 | 0.2 | 0.315
141 | B49 200X500 Grid AtoC,12 | CUM | 1 | 1 | 3.15 | 0.5 | 0.2 | 0.315
142 | B50 200X450 Grid CtoE,31 | CUM | 1 | 1 | 3.12 | 0.45 | 0.2 | 0.2808
143 | B50 200X450 Grid CtoE,12 | CUM | 1 | 1 | 3.12 | 0.45 | 0.2 | 0.2808
144 | B51 200X350 Grid EtoF,32to33 | CUM | 1 | 1 | 2.35 | 0.35 | 0.2 | 0.1645
145 | B51 200X350 Grid EtoF,11to12 | CUM | 1 | 1 | 2.35 | 0.35 | 0.2 | 0.1645
146 | B52 230X500 Grid EtoJ,35 | CUM | 1 | 1 | 3.18 | 0.5 | 0.23 | 0.3657
147 | B52 230X500 Grid EtoJ,9 | CUM | 1 | 1 | 3.18 | 0.5 | 0.23 | 0.3657
148 | B53 200X350 Grid EtoJ,9 to 15 | CUM | 1 | 1 | 2.335 | 0.35 | 0.2 | 0.16345
149 | B53 200X350 Grid EtoJ,35to40 | CUM | 1 | 1 | 2.335 | 0.35 | 0.2 | 0.16345
150 | B54 230X450 Grid JtoK,32 | CUM | 1 | 1 | 2.37 | 0.45 | 0.23 | 0.2453
151 | B54 230X450 Grid JtoK,13 | CUM | 1 | 1 | 2.37 | 0.45 | 0.23 | 0.2453
152 | B55 230X450 Grid EtoJ,29 | CUM | 1 | 1 | 5.6 | 0.45 | 0.23 | 0.5796
153 | B55 230X450 Grid EtoJ,15 | CUM | 1 | 1 | 5.6 | 0.45 | 0.23 | 0.5796
154 | B56 230X450 Grid ItoK,28 | CUM | 1 | 1 | 5.67 | 0.45 | 0.23 | 0.58684
155 | B56 230X450 Grid ItoK,16 | CUM | 1 | 1 | 5.67 | 0.45 | 0.23 | 0.58684
156 | B57 200X450 GridDtoE,28 | CUM | 1 | 1 | 3.43 | 0.45 | 0.2 | 0.3087
157 | B57 230X450 GridCtoD,28 | CUM | 1 | 1 | 1.98 | 0.45 | 0.23 | 0.20493
158 | B57 200X450 GridDtoE,16 | CUM | 1 | 1 | 3.43 | 0.45 | 0.2 | 0.3087
159 | B57 230X450 GridCtoD,16 | CUM | 1 | 1 | 1.98 | 0.45 | 0.23 | 0.20493
160 | B58 200X500 Grid CtoD,27 | CUM | 1 | 1 | 2.25 | 0.5 | 0.2 | 0.225
161 | B58 200X500 Grid KtoM,27 | CUM | 1 | 1 | 2.25 | 0.5 | 0.2 | 0.225
162 | B58 200X500 Grid CtoD,17 | CUM | 1 | 1 | 2.25 | 0.5 | 0.2 | 0.225
163 | B58 200X500 Grid KtoM,17 | CUM | 1 | 1 | 2.25 | 0.5 | 0.2 | 0.225
164 | B59 200X450 Grid EtoI,27to28 | CUM | 1 | 1 | 3.15 | 0.5 | 0.2 | 0.315
165 | B59 200X450 Grid EtoI,16to17 | CUM | 1 | 1 | 3.15 | 0.5 | 0.2 | 0.315
166 | B60 200X450 Grid DtoE,26 | CUM | 1 | 1 | 3.1 | 0.45 | 0.2 | 0.279
167 | B60 200X450 Grid ItoK,26 | CUM | 1 | 1 | 3.1 | 0.45 | 0.2 | 0.279
168 | B60 200X450 Grid DtoE,18 | CUM | 1 | 1 | 3.1 | 0.45 | 0.2 | 0.279
169 | B60 200X450 Grid ItoK,18 | CUM | 1 | 1 | 3.1 | 0.45 | 0.2 | 0.279
170 | B61 200X350 Grid CtoD,25 | CUM | 1 | 1 | 3.05 | 0.35 | 0.2 | 0.2135
171 | B61 200X350 Grid JtoK,25 | CUM | 1 | 1 | 3.05 | 0.35 | 0.2 | 0.2135
172 | B61 200X350 Grid CtoD,19 | CUM | 1 | 1 | 3.05 | 0.35 | 0.2 | 0.2135
173 | B61 200X350 Grid JtoK,19 | CUM | 1 | 1 | 3.05 | 0.35 | 0.2 | 0.2135
174 | B62 200X450 GridEtoJ,24to25 | CUM | 1 | 1 | 6.77 | 0.45 | 0.2 | 0.6093
175 | B62 200X450 GridEtoJ,19to20 | CUM | 1 | 1 | 6.77 | 0.45 | 0.2 | 0.6093
176 | B63 200X450 GridCtoM,24 | CUM | 1 | 1 | 12.7 | 0.45 | 0.2 | 1.143
177 | B63 230X450 GridCtoM,20 | CUM | 1 | 1 | 12.7 | 0.45 | 0.2 | 1.143
178 | B64 200X500 Grid CtoE,23 | CUM | 1 | 1 | 4.45 | 0.5 | 0.2 | 0.445
179 | B64 200X500 Grid ItoL,23 | CUM | 1 | 1 | 4.45 | 0.5 | 0.2 | 0.445
180 | B64 200X500 Grid CtoE,21 | CUM | 1 | 1 | 4.45 | 0.5 | 0.2 | 0.445
181 | B64 200X500 Grid ItoL,21 | CUM | 1 | 1 | 4.45 | 0.5 | 0.2 | 0.445
182 | B65 200X350 Grid EtoI,23 | CUM | 1 | 1 | 3.17 | 0.35 | 0.2 | 0.2219
183 | B65 200X350 Grid EtoI,21 | CUM | 1 | 1 | 3.17 | 0.35 | 0.2 | 0.2219
184 | B66 200X450 Grid DtoE,22 | CUM | 1 | 1 | 3.58 | 0.45 | 0.2 | 0.3222
185 | B66 200X450 Grid ItoK,22 | CUM | 1 | 1 | 3.58 | 0.45 | 0.2 | 0.3222
[5 empty] | Total of Beam RMC |  |  | 87.557
Slab RCC(1to 43 &AtoQ
1 | FLAT NO 9,4
2 | Bed room 1 | CUM | 2 | 1 | 3.726 | 3.55 | 0.135 | 3.5714
3 | Bed Room 2 | CUM | 2 | 1 | 3.55 | 3.2 | 0.135 | 3.0672
4 | Bed Room 3 | CUM | 2 | 1 | 3.26 | 3.15 | 0.125 | 2.5672
5 |  | CUM | 2 | 1 | 0.9 | 0.4 | 0.125 | 0.09
6 | Service slab | CUM | 2 | 1 | 1.165 | 0.515 | 0.125 | 0.14999
7 | TOILET 1 | CUM | 2 | 1 | 3.575 | 1.57 | 0.125 | 1.4032
8 | TOILET 2 | CUM | 2 | 1 | 2.5 | 1.6 | 0.125 | 1
9 | PASSAGE | CUM | 2 | 1 | 2.785 | 1.2 | 0.125 | 0.8355
10 | Living | CUM | 2 | 1 | 6.365 | 3.72 | 0.15 | 7.1033
11 |  | CUM | 2 | 1 | 4.115 | 0.385 | 0.15 | 0.47528
12 | Entry/ Porch | CUM | 2 | 1 | 1.5 | 1.035 | 0.125 | 0.38812
13 | Kitchen | CUM | 2 | 1 | 2.85 | 2.39 | 0.135 | 1.8391
14 | Balcony 1 | CUM | 2 | 1 | 6.4 | 2 | 0.1825 | 4.672
15 | Balcony 2 | CUM | 2 | 1 | 4.065 | 2 | 0.1825 | 2.9675
16 | Kitchen Balcony | CUM | 2 | 1 | 1.4 | 2 | 0.1825 | 1.022
17 |  | CUM | 2 | 1 | 1.185 | 0.435 | 0.2 | 0.20619
18 | FLAT 9 ,4 LOBBY |  | 2 | 1 | 5.09 | 1.58 | 0.125 | 2.0105
19 |  |  | 2 | 1 | 3.25 | 0.97 | 0.125 | 0.78812
20 | LIFT LOBBY,9,4 |  | 2 | 1 | 3.95 | 1.61 | 0.125 | 1.5899
21 |  |  | 2 | 1 | 5.68 | 2.44 | 0.125 | 3.4648
22 | Staircase lobby ,9,4 |  | 2 | 1 | 5.28 | 2.55 | 0.125 | 3.366
23 |  |  | 2 | 1 | 1.43 | 0.75 | 0.125 | 0.26813
24 | FLAT NO 7,8,5,6 | [6 empty] | 0
25 | B. ROOM 1 | CUM | 4 | 1 | 3.6 | 3.49 | 0.135 | 6.7846
26 | B. ROOM 2 | CUM | 4 | 1 | 3.25 | 2.925 | 0.135 | 5.1334
27 | B. ROOM 3 | CUM | 4 | 1 | 3.58 | 3.25 | 0.135 | 6.2829
28 | PASSAGE | CUM | 4 | 1 | 2.925 | 1.74 | 0.125 | 2.5447
29 | KITCHEN | CUM | 4 | 1 | 3.25 | 2.365 | 0.135 | 4.1506
30 | LIVING | CUM | 4 | 1 | 5.23 | 3.33 | 0.15 | 10.4495
31 |  | CUM | 4 | 1 | 3.4 | 0.94 | 0.15 | 1.9176
32 |  | CUM | 4 | 1 | 2.55 | 1.47 | 0.15 | 2.2491
33 | DRESSING AREA | CUM | 4 | 1 | 2.41 | 1.43 | 0.125 | 1.7231
34 | TOILET 1 | CUM | 4 | 1 | 2.225 | 1.495 | 0.125 | 1.6632
35 | TOILET 2 | CUM | 4 | 1 | 3.385 | 1.425 | 0.125 | 2.4118
36 | TOILET 3 | CUM | 4 | 1 | 2.41 | 1.54 | 0.125 | 1.8557
37 | BALCONY 1 | CUM | 4 | 1 | 4.665 | 2 | 0.1825 | 6.8109
38 | BALCONY 2 | CUM | 4 | 1 | 5.105 | 2 | 0.1825 | 7.4533
39 | BALCONY 3 | CUM | 4 | 1 | 3.265 | 2 | 0.1825 | 4.7669
40
41
42
43 | FLAT NO-1,2,3, 10,11,12
44 | B. ROOM 1 |  | 6 | 1 | 3.86 | 3.25 | 0.135 | 10.1615
45 | B. ROOM 2 |  | 6 | 1 | 3.86 | 3.35 | 0.135 | 10.4741
46 | B. ROOM 3 |  | 6 | 1 | 3.55 | 3.265 | 0.125 | 8.6931
47 | Living |  | 6 | 1 | 6.345 | 3.315 | 0.15 | 18.9303
48 |  |  | 6 | 1 | 3.25 | 1.91 | 0.15 | 5.5867
49 | KITCHEN |  | 6 | 1 | 3.435 | 2.345 | 0.135 | 6.5246
50 | TOILET 1 |  | 6 | 1 | 3.86 | 1.44 | 0.125 | 4.1688
51 | TOILET 2 |  | 6 | 1 | 3.55 | 1.425 | 0.125 | 3.7941
52 | TOILET 3 |  | 6 | 1 | 3.55 | 1.425 | 0.125 | 3.7941
53 | Service slab |  | 6 | 1 | 1.245 | 0.515 | 0.125 | 0.48088
54 | Service slab |  | 6 | 1 | 0.97 | 0.415 | 0.125 | 0.30191
55 | BALCONY 1 |  | 6 | 1 | 5.93 | 2 | 0.1825 | 12.9867
56 | BALCONY 2 |  | 6 | 1 | 3.565 | 2 | 0.1825 | 7.8074
57 | BALCONY 3 |  | 6 | 1 | 1.55 | 2 | 0.1825 | 3.3945
58 | [7 empty] | 0
59 | FLAT 1,2,3,10,11,12 LOBBY |  | 2 | 1 | 4.79 | 3.19 | 0.125 | 3.82
60 |  |  | 2 | 1 | 1.4 | 0.655 | 0.125 | 0.22925
61 | Main s/case (3 No) | [6 empty] | 0
62 | Half landing |  | 2 | 2 | 3.2 | 1.5 | 0.175 | 3.36
63 | freight |  | 2 | 2 | 2.409 | 1.5 | 0.175 | 2.5294
64 | mid freight |  | 2 | 1 | 1.484 | 1.5 | 0.175 | 0.7791
65 | top landing |  | 2 | 1 | 3.96 | 0.26 | 0.175 | 0.36036
66 | landing beam 230x450 |  | 2 | 1 | 3.53 | 0.45 | 0.23 | 0.73071
67 | Fire s/case (4 No) | [6 empty] | 0
68 | mid & full landing |  | 2 | 2 | 3.2 | 1.5 | 0.175 | 3.36
69 | freight |  | 2 | 2 | 3.343 | 1.5 | 0.175 | 3.5101
70 | landing beam 230x450 |  | 2 | 1 | 3.2 | 0.23 | 0.45 | 0.6624
[6 empty] | total slab concrete |  | 225.4828
Total M-25 of beam & slab
300.8041

## CONCRETE WORK MB
COMPANY- OMAXE PANCHAM REALCON PVT LTD
PROJECT- TOWER-E
LOCATION- NAINI, PRAYAGRAJ
MB SHEET- CONCRETE WORK
S.NO. | DESCRIPTION | UNIT | NOS | NOS | MEASUREMENT |  |  | QTY. | REMARKS
[5 empty] | L | B | H/T
RAFT PCC- M10 BELOW PLINTH BEAM
1 | GRID (22'-43'/A-Q') | CUM | 1 | 1 | 32.165 | 37.125 | 0.1 | 119.4126 | 3rd RA
2 |  | CUM | 1 | 1 | 9.01 | 0.515 | 0.1 | 0.46402
3 | GRID (22'-26'/M'-Q') | CUM | -1 | 1 | 11.005 | 12.415 | 0.1 | -13.6627
4 | GRID (38'-43'/A-E') | CUM | -1 | 1 | 11.09 | 10.285 | 0.1 | -11.4061
5 | GRID (22'-30'/A-B') | CUM | -1 | 1 | 11.285 | 3.72 | 0.1 | -4.198
6 |  | CUM | -1 | 1 | 1.695 | 2.315 | 0.1 | -0.39239
7 |  | CUM | -1 | 1 | 3.95 | 1.5 | 0.1 | -0.5925
|  |  | -1 | 1 | 15.8 | 0.115 | 0.1 | -0.1817
8 | EXISTING RAFT (DETAILS IN JMR) | CUM | -1 | 1 | 9 | 5.915 | 0.1 | -5.3235
9 |  | CUM | -1 | 1 | 19.05 | 10 | 0.1 | -19.05
10 |  | CUM | -1 | 1 | 6.2 | 6.2 | 0.1 | -3.844
11 |  | CUM | -1 | 1 | 5.5 | 8.05 | 0.1 | -4.4275
[7 empty] | TOTAL | 56.7982
1 | GRID (5'-20/A-C') (DETAILS IN JMR) | CUM | 1 | 1 | 3 | 1.5 | 0.1 | 0.45 | 4th RA
2 |  | CUM | 1 | 1 | 5.875 | 1.5 | 0.1 | 0.88125
3 |  | CUM | 1 | 1 | 9.825 | 0.815 | 0.1 | 0.80074
4 |  | CUM | 1 | 1 | 11.52 | 1.405 | 0.1 | 1.6186
5 |  | CUM | 1 | 1 | 16.5 | 1 | 0.1 | 1.65
6 | GRID (1-18/M'-Q') (DETAILS IN JMR) | CUM | 1 | 1 | 11.03 | 8.67 | 0.1 | 9.563
7 |  | CUM | 1 | 1 | 11.545 | 2.715 | 0.1 | 3.1345
8 |  | CUM | 1 | 1 | 6.065 | 2.515 | 0.1 | 1.5253
9 |  | CUM | 1 | 1 | 1.05 | 2 | 0.1 | 0.21
10 |  | CUM | 1 | 1 | 8.67 | 3.27 | 0.1 | 2.8351
[7 empty] | TOTAL | 22.6685
S.NO. | DESCRIPTION | UNIT | NOS | NOS | MEASUREMENT |  |  | QTY. | REMARKS
[5 empty] | L | B | H/T
RAFT RCC- M25 BELOW PLINTH BEAM
1 | GRID (22'-43'/A-Q') | CUM | 1 | 1 | 31.935 | 36.895 | 0.85 | 1001.5056 | 3rd RA
2 |  | CUM | 1 | 1 | 8.78 | 0.515 | 0.85 | 3.8434
3 | GRID (22'-26'/M'-Q') | CUM | -1 | 1 | 11.005 | 12.415 | 0.85 | -116.133
4 | GRID (38'-43'/A-E') | CUM | -1 | 1 | 11.09 | 10.285 | 0.85 | -96.9516
5 | GRID (22'-30'/A-B') | CUM | -1 | 1 | 11.285 | 3.72 | 0.85 | -35.6832
6 |  | CUM | -1 | 1 | 1.695 | 2.315 | 0.85 | -3.3353
7 |  | CUM | -1 | 1 | 3.95 | 1.5 | 0.85 | -5.0363
[7 empty] | TOTAL | 748.2097
1 | GRID (22'-43'/A-Q') | CUM | 1 | 1 | 31.935 | 40.165 | 0.85 | 1090.2689 | 4th RA
2 |  | CUM | 1 | 1 | 8.78 | 0.515 | 0.85 | 3.8434
3 | GRID (22'-26'/M'-Q') | CUM | -1 | 1 | 14.275 | 12.415 | 0.85 | -150.6405
4 | GRID (38'-43'/A-E') | CUM | -1 | 1 | 11.09 | 10.285 | 0.85 | -96.9516
5 | GRID (22'-30'/A-B') | CUM | -1 | 1 | 14.555 | 3.72 | 0.85 | -46.0229
6 |  | CUM | -1 | 1 | 1.695 | 2.315 | 0.85 | -3.3353
7 |  | CUM | -1 | 1 | 3.95 | 1.5 | 0.85 | -5.0363
[7 empty] | TOTAL | 792.1258
COMPENSATORY STRIP
1 | GRID (22-23/B'-L') | CUM | 1 | 1 | 15.8 | 0.9 | 0.85 | 12.087 | 5th RA
[7 empty] | TOTAL | 12.087
PADESTIAL GRID (1-43/A-Q)
1 | C1, C2, C3, C8 (300X600) | CUM | 46 | 1 | 0.3 | 0.6 | 1.48 | 12.2544
2 | C1 (300X600) | CUM | 6 | 1 | 0.3 | 0.6 | 1.68 | 1.8144
3 | C2 (300X600) | CUM | 6 | 1 | 0.3 | 0.6 | 1.68 | 1.8144
4 | C3 (300X600) | CUM | 2 | 1 | 0.3 | 0.6 | 1.68 | 0.6048
5 | C8 (300X600) | CUM | 2 | 1 | 0.3 | 0.6 | 1.68 | 0.6048
6 | C4, C5 (300X750) | CUM | 24 | 1 | 0.3 | 0.7 | 1.48 | 7.4592
7 | C4 (300X750) | CUM | 4 | 1 | 0.3 | 0.7 | 1.68 | 1.4112
8 | C5 (300X750) | CUM | 2 | 1 | 0.3 | 0.7 | 1.68 | 0.7056
9 | C6 (300X715) | CUM | 14 | 1 | 0.3 | 0.715 | 1.48 | 4.4444
10 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 1.48 | 0.7104
11 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 1.68 | 0.8064
12 | SW 1 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 1.48 | 0.44252
13 |  | CUM | 2 | 1 | 0.23 | 1.42 | 1.48 | 0.96674
14 | SW 2 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 1.48 | 0.44252
15 |  | CUM | 2 | 1 | 0.23 | 1.62 | 1.48 | 1.1029
16 | SW 3 (230x1000) | CUM | 2 | 1 | 0.23 | 1 | 1.48 | 0.6808
17 | SW 4 (230x1150) | CUM | 2 | 1 | 0.23 | 1.15 | 1.48 | 0.78292
18 | SW 5 (230x1700) | CUM | 4 | 1 | 0.23 | 1.7 | 1.68 | 2.6275
19 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 1.48 | 0.80675
20 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 1.68 | 0.91577
21 | SW 7 (230x1855) | CUM | 2 | 1 | 0.23 | 1.855 | 1.48 | 1.2629
22 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 1.48 | 1.2254
23 | SW 9 (L-SHAPE) | CUM | 6 | 1 | 0.23 | 0.65 | 1.48 | 1.3276
24 |  | CUM | 6 | 1 | 0.23 | 1.62 | 1.48 | 3.3087
25 | SW 10 (230x3445) | CUM | 2 | 1 | 0.23 | 3.445 | 1.68 | 2.6623
26 | SW 11 (230x4065) | CUM | 2 | 1 | 0.23 | 4.065 | 1.68 | 3.1414
27 | SW 12 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 1.68 | 0.50232
28 |  | CUM | 2 | 1 | 0.23 | 1.305 | 1.68 | 1.0085
29 | SW 13 (200x3445) | CUM | 2 | 1 | 0.2 | 3.445 | 1.68 | 2.315
30 | LIFT WALL | CUM | 8 | 1 | 0.23 | 1.9 | 1.68 | 5.8733
[7 empty] | TOTAL | 64.0259
[7 empty] | TOTAL | 76.1129
| PLINTH BEAM (1-43/A-Q) | [7 empty] | 7TH RA
1 | PB1 | CUM | 1 | 2 | 3.025 | 0.2 | 0.335 | 0.40535
2 | PB1 | CUM | 1 | 2 | 2.8 | 0.2 | 0.335 | 0.3752
3 | PB2 | CUM | 1 | 2 | 3.3 | 0.2 | 0.335 | 0.4422
4 | PB3 | CUM | 1 | 4 | 1.395 | 0.1 | 0.335 | 0.18693
5 | PB3 | CUM | 1 | 6 | 1.4 | 0.1 | 0.335 | 0.2814
6 | PB3 | CUM | 1 | 2 | 1.2 | 0.1 | 0.335 | 0.0804
7 | PB3 | CUM | 1 | 6 | 1.55 | 0.1 | 0.335 | 0.31155
8 | PB3 | CUM | 1 | 6 | 0.97 | 0.1 | 0.335 | 0.19497
9 | PB4 | CUM | 1 | 6 | 1.395 | 0.2 | 0.335 | 0.56079
10 | PB5 | CUM | 1 | 2 | 3.1 | 0.2 | 0.335 | 0.4154
11 | PB6 | CUM | 1 | 1 | 16.51 | 0.2 | 0.335 | 1.1062
12 | PB7 | CUM | 1 | 2 | 2.875 | 0.2 | 0.335 | 0.38525
13 | PB7 | CUM | 1 | 2 | 2.93 | 0.2 | 0.335 | 0.39262
14 | PB8 | CUM | 1 | 2 | 3.16 | 0.2 | 0.335 | 0.42344
15 | PB9 | CUM | 1 | 2 | 5.635 | 0.2 | 0.335 | 0.75509
16 | PB10 | CUM | 1 | 2 | 4.69 | 0.2 | 0.335 | 0.62846
17 | PB11 | CUM | 1 | 2 | 5.76 | 0.2 | 0.335 | 0.77184
18 | PB12 | CUM | 1 | 2 | 2.22 | 0.2 | 0.335 | 0.29748
19 | PB13 | CUM | 1 | 2 | 3.115 | 0.2 | 0.335 | 0.41741
20 | PB14 | CUM | 1 | 6 | 7.605 | 0.2 | 0.335 | 3.0572
21 | PB15 | CUM | 1 | 2 | 3.215 | 0.2 | 0.335 | 0.43081
22 | PB16 | CUM | 1 | 2 | 2.76 | 0.23 | 0.335 | 0.42532
23 | PB17 | CUM | 1 | 2 | 15.345 | 0.23 | 0.335 | 2.3647
24 | PB18 | CUM | 1 | 2 | 8.02 | 0.2 | 0.335 | 1.0747
25 | PB19 | CUM | 1 | 2 | 5.72 | 0.2 | 0.335 | 0.76648
26 | PB20 | CUM | 1 | 2 | 7.77 | 0.2 | 0.335 | 1.0412
27 | PB21 | CUM | 1 | 6 | 7.955 | 0.2 | 0.335 | 3.1979
28 | PB22 | CUM | 1 | 6 | 5.745 | 0.2 | 0.335 | 2.3095
29 | PB23 | CUM | 1 | 2 | 5.125 | 0.2 | 0.335 | 0.68675
30 | PB24 | CUM | 1 | 2 | 1.4 | 0.23 | 0.335 | 0.21574
31 | PB25 | CUM | 1 | 2 | 6.825 | 0.2 | 0.335 | 0.91455
32 | PB25 | CUM | 1 | 2 | 2.93 | 0.23 | 0.335 | 0.45151
33 | PB26 | CUM | 1 | 1 | 16.51 | 0.23 | 0.335 | 1.2721
34 | PB27 | CUM | 1 | 2 | 3.53 | 0.23 | 0.335 | 0.54397
35 | PB28 | CUM | 1 | 2 | 3.03 | 0.2 | 0.335 | 0.40602
36 | PB29 | CUM | 1 | 2 | 10.2 | 0.2 | 0.335 | 1.3668
37 | PB30 | CUM | 1 | 2 | 6.38 | 0.2 | 0.335 | 0.85492
38 | PB31 | CUM | 1 | 6 | 5.36 | 0.2 | 0.335 | 2.1547
39 | PB32 | CUM | 1 | 20 | 0.515 | 0.1 | 0.335 | 0.34505
40 | PB33 | CUM | 1 | 6 | 3.45 | 0.2 | 0.335 | 1.3869
41 | PB34 | CUM | 1 | 6 | 2.91 | 0.2 | 0.335 | 1.1698
42 | PB35 | CUM | 1 | 2 | 6.38 | 0.2 | 0.335 | 0.85492
43 | PB36 | CUM | 1 | 6 | 3.31 | 0.2 | 0.335 | 1.3306
44 | PB37 | CUM | 1 | 4 | 2.195 | 0.2 | 0.335 | 0.58826
45 | PB38 | CUM | 1 | 2 | 5.245 | 0.2 | 0.335 | 0.70283
46 | PB39 | CUM | 1 | 2 | 2.23 | 0.2 | 0.335 | 0.29882
47 | PB40 | CUM | 1 | 2 | 4.9 | 0.2 | 0.335 | 0.6566
48 | PB41 | CUM | 1 | 2 | 5.145 | 0.2 | 0.335 | 0.68943
49 | PB42 | CUM | 1 | 2 | 3.2 | 0.23 | 0.335 | 0.49312
50 | PB43 | CUM | 1 | 2 | 2.95 | 0.2 | 0.335 | 0.3953
51 | PB44 | CUM | 1 | 2 | 3.8 | 0.2 | 0.335 | 0.5092
52 | PB45 | CUM | 1 | 2 | 4.55 | 0.2 | 0.335 | 0.6097
53 | PB46 | CUM | 1 | 2 | 3.05 | 0.2 | 0.335 | 0.4087
54 | PB47 | CUM | 1 | 2 | 3.115 | 0.2 | 0.335 | 0.41741
55 | PB48 | CUM | 1 | 2 | 1.41 | 0.2 | 0.335 | 0.18894
56 | PB49 | CUM | 1 | 2 | 0.35 | 0.2 | 0.335 | 0.0469
57 | PB50 | CUM | 1 | 2 | 2.37 | 0.2 | 0.335 | 0.31758
58 | PB51 | CUM | 1 | 2 | 3.2 | 0.2 | 0.335 | 0.4288
59 | PB52 | CUM | 1 | 2 | 14.53 | 0.2 | 0.335 | 1.947
60 | PB53 | CUM | 1 | 4 | 2.225 | 0.2 | 0.335 | 0.5963
61 | PB54 | CUM | 1 | 2 | 3.06 | 0.2 | 0.335 | 0.41004
62 | PB55 | CUM | 1 | 2 | 3.06 | 0.2 | 0.335 | 0.41004
63 | PB56 | CUM | 1 | 2 | 1.6 | 0.2 | 0.335 | 0.2144
64 | PB57 | CUM | 1 | 4 | 3.05 | 0.2 | 0.335 | 0.8174
65 | PB58 | CUM | 1 | 2 | 6.54 | 0.2 | 0.335 | 0.87636
66 | PB59 | CUM | 1 | 2 | 6.17 | 0.2 | 0.335 | 0.82678
67 | PB60 | CUM | 1 | 4 | 3.05 | 0.2 | 0.335 | 0.8174
68 | PB60 | CUM | 1 | 4 | 1.7 | 0.2 | 0.335 | 0.4556
69 | PB61 | CUM | 1 | 2 | 3.17 | 0.2 | 0.335 | 0.42478
[7 empty] | TOTAL | 51.6018
COLUMN JUNCTION (1-43/A-Q) AT PLINTH BEAM LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 62 | 1 | 0.3 | 0.6 | 0.45 | 5.022
2 | C4, C5 (300X750) | CUM | 30 | 1 | 0.3 | 0.7 | 0.45 | 2.835
3 | C6, C11 (300X715) | CUM | 14 | 1 | 0.3 | 0.715 | 0.45 | 1.3514
4 | C7 (300X800) | CUM | 4 | 1 | 0.3 | 0.8 | 0.45 | 0.432
5 | SW 1 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.45 | 0.13455
6 |  | CUM | 2 | 1 | 0.23 | 1.42 | 0.45 | 0.29394
7 | SW 2 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.45 | 0.13455
8 |  | CUM | 2 | 1 | 0.23 | 1.62 | 0.45 | 0.33534
9 | SW 3 (230x1000) | CUM | 2 | 1 | 0.23 | 1 | 0.45 | 0.207
10 | SW 4 (230x1150) | CUM | 2 | 1 | 0.23 | 1.15 | 0.45 | 0.23805
11 | SW 5 (230x1700) | CUM | 4 | 1 | 0.23 | 1.7 | 0.45 | 0.7038
12 | SW 6 (230x1185) | CUM | 4 | 1 | 0.23 | 1.185 | 0.45 | 0.49059
13 | SW 7 (230x1855) | CUM | 2 | 1 | 0.23 | 1.855 | 0.45 | 0.38399
14 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 0.45 | 0.3726
15 | SW 9 (L-SHAPE) | CUM | 6 | 1 | 0.23 | 0.65 | 0.45 | 0.40365
16 |  | CUM | 6 | 1 | 0.23 | 1.62 | 0.45 | 1.006
17 | SW 10 (230x3445) | CUM | 2 | 1 | 0.23 | 3.445 | 0.45 | 0.71312
18 | SW 11 (230x4065) | CUM | 2 | 1 | 0.23 | 4.065 | 0.45 | 0.84146
19 | SW 12 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.45 | 0.13455
20 |  | CUM | 2 | 1 | 0.23 | 1.305 | 0.45 | 0.27013
21 | SW 13 (200x3445) | CUM | 2 | 1 | 0.2 | 3.445 | 0.45 | 0.6201
22 | LIFT WALL | CUM | 8 | 1 | 0.23 | 1.9 | 0.45 | 1.5732
[7 empty] | TOTAL | 18.497
COLUMN (22-43/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 31 | 1 | 0.3 | 0.6 | 2.5 | 13.95
2 | C4, C5 (300X750) | CUM | 15 | 1 | 0.3 | 0.7 | 2.5 | 7.875
3 | C6, C11 (300X715) | CUM | 7 | 1 | 0.3 | 0.715 | 2.5 | 3.7538
4 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 2.5 | 1.2
5 | SW 1 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 2.5 | 0.37375
6 |  | CUM | 1 | 1 | 0.23 | 1.42 | 2.5 | 0.8165
7 | SW 2 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 2.5 | 0.37375
8 |  | CUM | 1 | 1 | 0.23 | 1.62 | 2.5 | 0.9315
9 | SW 3 (230x1000) | CUM | 1 | 1 | 0.23 | 1 | 2.5 | 0.575
10 | SW 4 (230x1150) | CUM | 1 | 1 | 0.23 | 1.15 | 2.5 | 0.66125
11 | SW 5 (230x1700) | CUM | 2 | 1 | 0.23 | 1.7 | 2.5 | 1.955
12 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 2.5 | 1.3628
13 | SW 7 (230x1855) | CUM | 1 | 1 | 0.23 | 1.855 | 2.5 | 1.0666 |  | 143
14 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 2.5 | 2.07 |  | 103
15 | SW 9 (L-SHAPE) | CUM | 3 | 1 | 0.23 | 0.65 | 2.5 | 1.1213
16 |  | CUM | 3 | 1 | 0.23 | 1.62 | 2.5 | 2.7945
17 | SW 10 (230x3445) | CUM | 1 | 1 | 0.23 | 3.445 | 2.5 | 1.9809
18 | SW 11 (230x4065) | CUM | 1 | 1 | 0.23 | 4.065 | 2.5 | 2.3374
19 | SW 12 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 2.5 | 0.37375
20 |  | CUM | 1 | 1 | 0.23 | 1.305 | 2.5 | 0.75037
21 | SW 13 (200x3445) | CUM | 1 | 1 | 0.2 | 3.445 | 2.5 | 1.7225
[7 empty] | TOTAL | 48.0455
[7 empty] | TOTAL | 118.1443
COLUMN (1-22/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 31 | 1 | 0.3 | 0.6 | 2.5 | 13.95 | 8TH RA
2 | C4, C5 (300X750) | CUM | 15 | 1 | 0.3 | 0.7 | 2.5 | 7.875
3 | C6, C11 (300X715) | CUM | 7 | 1 | 0.3 | 0.715 | 2.5 | 3.7538
4 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 2.5 | 1.2
5 | SW 1 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 2.5 | 0.37375
6 |  | CUM | 1 | 1 | 0.23 | 1.42 | 2.5 | 0.8165
7 | SW 2 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 2.5 | 0.37375
8 |  | CUM | 1 | 1 | 0.23 | 1.62 | 2.5 | 0.9315
9 | SW 3 (230x1000) | CUM | 1 | 1 | 0.23 | 1 | 2.5 | 0.575
10 | SW 4 (230x1150) | CUM | 1 | 1 | 0.23 | 1.15 | 2.5 | 0.66125
11 | SW 5 (230x1700) | CUM | 2 | 1 | 0.23 | 1.7 | 2.5 | 1.955
12 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 2.5 | 1.3628
13 | SW 7 (230x1855) | CUM | 1 | 1 | 0.23 | 1.855 | 2.5 | 1.0666
14 | SW 8 (230x3600) | CUM | 0 | 0 | 0.23 | 3.6 | 2.5 | 0
15 | SW 9 (L-SHAPE) | CUM | 3 | 1 | 0.23 | 0.65 | 2.5 | 1.1213
16 |  | CUM | 3 | 1 | 0.23 | 1.62 | 2.5 | 2.7945
17 | SW 10 (230x3445) | CUM | 1 | 1 | 0.23 | 3.445 | 2.5 | 1.9809
18 | SW 11 (230x4065) | CUM | 1 | 1 | 0.23 | 4.065 | 2.5 | 2.3374
19 | SW 12 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 2.5 | 0.37375
20 |  | CUM | 1 | 1 | 0.23 | 1.305 | 2.5 | 0.75037
21 | SW 13 (200x3445) | CUM | 1 | 1 | 0.2 | 3.445 | 2.5 | 1.7225
45.9755
COLUMN (1-43/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8 (300X600) | CUM | 46 | 1 | 0.3 | 0.6 | 0.2 | 1.656
2 | C4, C5 (300X750) | CUM | 22 | 1 | 0.3 | 0.7 | 0.2 | 0.924
3 | C6 (300X715) | CUM | 14 | 1 | 0.3 | 0.715 | 0.2 | 0.6006
4 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 0.2 | 0.096
5 | SW 1 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.2 | 0.0598
6 |  | CUM | 2 | 1 | 0.23 | 1.42 | 0.2 | 0.13064
7 | SW 2 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.2 | 0.0598
8 |  | CUM | 2 | 1 | 0.23 | 1.62 | 0.2 | 0.14904
9 | SW 3 (230x1000) | CUM | 2 | 1 | 0.23 | 1 | 0.2 | 0.092
10 | SW 4 (230x1150) | CUM | 2 | 1 | 0.23 | 1.15 | 0.2 | 0.1058
11 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 0.2 | 0.10902
12 | SW 7 (230x1855) | CUM | 2 | 1 | 0.23 | 1.855 | 0.2 | 0.17066
13 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 0.2 | 0.1656
14 | SW 9 (L-SHAPE) | CUM | 6 | 1 | 0.23 | 0.65 | 0.2 | 0.1794
15 |  | CUM | 6 | 1 | 0.23 | 1.62 | 0.2 | 0.44712
4.9455
SLAB RCC
| B1 200X500 | CUM | 1 | 1 | 3.025 | 0.5 | 0.2 | 0.3025
| B1 200X500 | CUM | 1 | 1 | 2.8 | 0.5 | 0.2 | 0.28
| B2 200X500 | CUM | 1 | 1 | 3.3 | 0.5 | 0.2 | 0.33
| B3 AT GRID B-C/27-28 | CUM | 1 | 1 | 1.395 | 0.35 | 0.1 | 0.048825
| B3 AT GRID L-M/27-28 | CUM | 1 | 1 | 1.395 | 0.35 | 0.115 | 0.056149
| B3 AT GRID E/32-33 | CUM | 1 | 1 | 1.185 | 0.35 | 0.1 | 0.041475
| B3 AT GRID F/43 | CUM | 1 | 3 | 2.055 | 0.35 | 0.1 | 0.21578
| B3 AT GRID F/39-40 | CUM | 1 | 3 | 1.485 | 0.35 | 0.1 | 0.15593
| B3 AT GRID M & O/39-40 | CUM | 1 | 3 | 2.315 | 0.35 | 0.1 | 0.24307
| B3 AT GRID C,K/25 | CUM | 1 | 2 | 2.315 | 0.35 | 0.1 | 0.16205
| B4 200X350 | CUM | 1 | 2 | 1.395 | 0.35 | 0.2 | 0.1953
| B5 200X450 | CUM | 1 | 1 | 6.875 | 0.45 | 0.2 | 0.61875
| B6 230X350 | CUM | 1 | 1 | 3.16 | 0.35 | 0.23 | 0.25438
| B7 200X450 | CUM | 1 | 1 | 2.7 | 0.45 | 0.2 | 0.243
| B8 200X500 | CUM | 1 | 1 | 2.875 | 0.5 | 0.2 | 0.2875
| B8 200X350 | CUM | 1 | 1 | 2.93 | 0.35 | 0.2 | 0.2051
| B9 200X500 | CUM | 1 | 1 | 4.69 | 0.5 | 0.2 | 0.469
| B10 200X500 | CUM | 1 | 1 | 3.15 | 0.5 | 0.2 | 0.315
| B11 200X450 | CUM | 1 | 1 | 4.69 | 0.45 | 0.2 | 0.4221
| B12 200X450 | CUM | 1 | 1 | 5.76 | 0.45 | 0.2 | 0.5184
| B13 200X350 | CUM | 1 | 1 | 1.6 | 0.35 | 0.2 | 0.112
| B13 200X450 | CUM | 1 | 1 | 4.105 | 0.45 | 0.2 | 0.36945
| B14 200X450 | CUM | 1 | 1 | 1.5 | 0.45 | 0.2 | 0.135
| B14 200X450 | CUM | 1 | 1 | 2.2 | 0.45 | 0.2 | 0.198
| B15 200X500 | CUM | 1 | 1 | 3.115 | 0.5 | 0.2 | 0.3115
| B16 200X350 | CUM | 1 | 3 | 1.02 | 0.35 | 0.2 | 0.2142
| B16 200X500 | CUM | 1 | 3 | 3.35 | 0.5 | 0.2 | 1.005
| B16 200X500 | CUM | 1 | 3 | 3.25 | 0.5 | 0.2 | 0.975
| B17 200X500 | CUM | 1 | 1 | 3.215 | 0.5 | 0.2 | 0.3215
| B18 230X500 | CUM | 1 | 1 | 2.76 | 0.5 | 0.23 | 0.3174
| B19 200X450 | CUM | 1 | 1 | 6.79 | 0.45 | 0.2 | 0.6111
| B20 200X350 | CUM | 1 | 1 | 2.41 | 0.35 | 0.2 | 0.1687
| B21 230X450 | CUM | 1 | 1 | 5.76 | 0.45 | 0.23 | 0.59616
| B22 200x450 | CUM | 1 | 1 | 4.69 | 0.45 | 0.2 | 0.4221
| B23 200X450 | CUM | 1 | 1 | 2.22 | 0.45 | 0.2 | 0.1998
| B24 200X450 | CUM | 1 | 1 | 5.63 | 0.45 | 0.2 | 0.5067
| B25 200X450 | CUM | 1 | 1 | 1.5 | 0.45 | 0.2 | 0.135
| B25 200X500 | CUM | 1 | 1 | 2.085 | 0.5 | 0.2 | 0.2085
| B25 200X450 BESIDE STAIRS | CUM | 1 | 1 | 5.63 | 0.45 | 0.2 | 0.5067
| B26 200X450 | CUM | 1 | 3 | 3.235 | 0.45 | 0.2 | 0.87345
| B26 200X450 | CUM | 1 | 3 | 4.72 | 0.45 | 0.2 | 1.2744
| B27 200X350 | CUM | 1 | 3 | 2.575 | 0.35 | 0.2 | 0.54075
| B27 200X500 | CUM | 1 | 3 | 3.165 | 0.5 | 0.2 | 0.9495
| B28 200X450 | CUM | 1 | 1 | 5.125 | 0.45 | 0.2 | 0.46125
| B29 200X450 | CUM | 1 | 1 | 1.9 | 0.45 | 0.2 | 0.171
| B29 200X450 | CUM | 1 | 1 | 1.9 | 0.45 | 0.2 | 0.171
| B29 200X450 | CUM | 1 | 1 | 1.4 | 0.45 | 0.2 | 0.126
| B30 200X350 | CUM | 1 | 1 | 2.93 | 0.35 | 0.2 | 0.2051
| B30 200X500 | CUM | 1 | 1 | 2.875 | 0.5 | 0.2 | 0.2875
| B30 200X450 | CUM | 1 | 1 | 3.95 | 0.45 | 0.2 | 0.3555
| B31 200X500 | CUM | 1 | 1 | 4.69 | 0.5 | 0.2 | 0.469
| B31 200X500 | CUM | 1 | 1 | 3.15 | 0.5 | 0.2 | 0.315
| B32 230X450 | CUM | 1 | 2 | 1.9 | 0.45 | 0.23 | 0.3933
| B33 200X350 | CUM | 1 | 1 | 5.235 | 0.35 | 0.2 | 0.36645
| B34 230X450 | CUM | 1 | 1 | 5.1 | 0.45 | 0.23 | 0.52785
| B34 230X450 | CUM | 1 | 1 | 5.1 | 0.45 | 0.23 | 0.52785
| B35 200X500 | CUM | 1 | 2 | 3.19 | 0.5 | 0.2 | 0.638
| B36 200X500 | CUM | 1 | 3 | 1.81 | 0.5 | 0.2 | 0.543
| B36 200X500 | CUM | 1 | 3 | 3.55 | 0.5 | 0.2 | 1.065
| B36 230X500 | CUM | 1 | 3 | 0.515 | 0.5 | 0.23 | 0.17767
| B37 200X450 | CUM | 1 | 3 | 3.86 | 0.45 | 0.2 | 1.0422
| B38 200X450 | CUM | 1 | 3 | 3.45 | 0.45 | 0.2 | 0.9315
| B39 200X450 | CUM | 1 | 3 | 2.91 | 0.45 | 0.2 | 0.7857
| B39 230X350 | CUM | 1 | 3 | 3.55 | 0.35 | 0.23 | 0.85732
| B40 200X450 | CUM | 1 | 2 | 3 | 0.45 | 0.2 | 0.54
| B40 200X350 | CUM | 1 | 2 | 2.065 | 0.35 | 0.2 | 0.2891
| B41 200X500 | CUM | 1 | 3 | 3.31 | 0.5 | 0.2 | 0.993
| B42 200X450 | CUM | 1 | 2 | 3 | 0.45 | 0.2 | 0.54
| B43 200X450 | CUM | 1 | 1 | 5.245 | 0.45 | 0.2 | 0.47205
| B44 200X450 | CUM | 1 | 1 | 3 | 0.45 | 0.2 | 0.27
| B44 200X350 | CUM | 1 | 1 | 1.95 | 0.35 | 0.2 | 0.1365
| B45 200X450 | CUM | 1 | 1 | 2.23 | 0.45 | 0.2 | 0.2007
| B46 200X500 | CUM | 1 | 1 | 5.145 | 0.5 | 0.2 | 0.5145
| B47 200X500 | CUM | 1 | 1 | 3.8 | 0.5 | 0.2 | 0.38
| B48 200X350 | CUM | 1 | 1 | 2.95 | 0.35 | 0.2 | 0.2065
| B49 200X450 | CUM | 1 | 1 | 4.55 | 0.45 | 0.2 | 0.4095
| B50 200X500 | CUM | 1 | 1 | 3.05 | 0.5 | 0.2 | 0.305
| B51 200X450 | CUM | 1 | 1 | 2.5 | 0.45 | 0.2 | 0.225
| B52 230X500 | CUM | 1 | 1 | 3.115 | 0.5 | 0.23 | 0.35823
| B53 200X350 | CUM | 1 | 1 | 2.335 | 0.35 | 0.2 | 0.16345
| B54 230X500 | CUM | 1 | 1 | 3.2 | 0.5 | 0.23 | 0.368
| B55 230X450 | CUM | 1 | 1 | 0.35 | 0.45 | 0.23 | 0.036225
| B56 200X450 | CUM | 1 | 1 | 1.96 | 0.45 | 0.2 | 0.1764
| B57 230X450 | CUM | 1 | 1 | 3.2 | 0.45 | 0.23 | 0.3312
| B57 200X450 | CUM | 1 | 1 | 2.335 | 0.45 | 0.2 | 0.21015
| B58 230X500 | CUM | 1 | 1 | 2.54 | 0.5 | 0.23 | 0.2921
| B58 230X450 | CUM | 1 | 1 | 3.43 | 0.45 | 0.23 | 0.35501
| B59 200X500 | CUM | 1 | 1 | 2.225 | 0.5 | 0.2 | 0.2225
| B60 200X450 | CUM | 1 | 1 | 3.14 | 0.45 | 0.2 | 0.2826
| B61 200X450 | CUM | 1 | 1 | 3.43 | 0.45 | 0.2 | 0.3087
| B61 230X450 | CUM | 1 | 1 | 1.99 | 0.45 | 0.23 | 0.20597
| B62 200X500 | CUM | 1 | 1 | 2.225 | 0.5 | 0.2 | 0.2225
| B63 200X450 | CUM | 1 | 2 | 3.06 | 0.45 | 0.2 | 0.5508
| B64 200X350 | CUM | 1 | 2 | 3.05 | 0.35 | 0.2 | 0.427
| B64 200X350 | CUM | 1 | 2 | 0.38 | 0.35 | 0.2 | 0.0532
| B65 200X450 | CUM | 1 | 2 | 3.385 | 0.45 | 0.2 | 0.6093
| B66 200X450 | CUM | 1 | 2 | 3.25 | 0.45 | 0.2 | 0.585
| B66 200X450 | CUM | 1 | 2 | 1.7 | 0.45 | 0.2 | 0.306
| B66 200X350 | CUM | 1 | 2 | 1.385 | 0.35 | 0.2 | 0.1939
| B67 200X450 | CUM | 1 | 2 | 3.05 | 0.45 | 0.2 | 0.549
| B67 200X450 | CUM | 1 | 2 | 1.7 | 0.45 | 0.2 | 0.306
| B68 200X350 | CUM | 1 | 1 | 3.17 | 0.35 | 0.2 | 0.2219
| B69 200X450 | CUM | 1 | 0.5 | 5.78 | 0.45 | 0.2 | 0.2601
39.8105
FLAT NO 9
| Bed room 1 | CUM | 1 | 1 | 3.575 | 3.55 | 0.135 | 1.7133
| Bed Room 2 | CUM | 1 | 1 | 3.55 | 3.2 | 0.135 | 1.5336
| Bed Room 3 | CUM | 1 | 1 | 3.145 | 3.05 | 0.125 | 1.199
|  | CUM | 1 | 1 | 0.9 | 0.4 | 0.125 | 0.045
| Service slab | CUM | 1 | 1 | 1.165 | 0.515 | 0.125 | 0.074997
| TOILET 1 | CUM | 1 | 1 | 3.575 | 1.57 | 0.125 | 0.70159
| TOILET 2 | CUM | 1 | 1 | 2.5 | 1.6 | 0.125 | 0.5
| PASSAGE | CUM | 1 | 1 | 2.785 | 1.2 | 0.125 | 0.41775
| Living | CUM | 1 | 1 | 6.365 | 3.72 | 0.15 | 3.5517
|  | CUM | 1 | 1 | 4.115 | 0.385 | 0.15 | 0.23764
| Entry/ Porch | CUM | 1 | 1 | 1.5 | 1.035 | 0.125 | 0.19406
| Kitchen | CUM | 1 | 1 | 2.85 | 2.335 | 0.135 | 0.89839
| Balcony 1 | CUM | 1 | 1 | 6.3 | 2 | 0.1825 | 2.2995
| Balcony 2 | CUM | 1 | 1 | 4.065 | 2 | 0.1825 | 1.4837
| Kitchen Balcony | CUM | 1 | 1 | 1.4 | 2 | 0.1825 | 0.511
|  | CUM | 1 | 1 | 1.185 | 0.435 | 0.2 | 0.1031
15.4644
| FLAT NO 8 | [6 empty] | 0
| B. ROOM 1 | CUM | 1 | 1 | 3.56 | 3.275 | 0.135 | 1.574
| B. ROOM 2 | CUM | 1 | 1 | 3.25 | 2.925 | 0.135 | 1.2833
| B. ROOM 3 | CUM | 1 | 1 | 3.58 | 3.05 | 0.135 | 1.4741
| PASSAGE | CUM | 1 | 1 | 2.925 | 1.7 | 0.125 | 0.62156
| KITCHEN | CUM | 1 | 1 | 3.25 | 2.365 | 0.135 | 1.0376
| LIVING | CUM | 1 | 1 | 5.23 | 3.33 | 0.15 | 2.6124
|  | CUM | 1 | 1 | 3.4 | 0.94 | 0.15 | 0.4794
|  | CUM | 1 | 1 | 2.55 | 1.47 | 0.15 | 0.56227
| DRESSING AREA | CUM | 1 | 1 | 2.41 | 1.43 | 0.125 | 0.43079
| TOILET 1 | CUM | 1 | 1 | 2.225 | 1.495 | 0.125 | 0.4158
| TOILET 2 | CUM | 1 | 1 | 3.385 | 1.425 | 0.125 | 0.60295
| TOILET 3 | CUM | 1 | 1 | 2.41 | 1.54 | 0.125 | 0.46393
| BALCONY 1 | CUM | 1 | 1 | 4.665 | 2 | 0.1825 | 1.7027
| BALCONY 2 | CUM | 1 | 1 | 5.105 | 2 | 0.1825 | 1.8633
| BALCONY 3 | CUM | 1 | 1 | 3.265 | 2 | 0.1825 | 1.1917
16.3159
| FLAT NO 7 | [6 empty] | 0
| B. ROOM 1 | CUM | 1 | 1 | 3.56 | 3.245 | 0.125 | 1.444
| B. ROOM 2 | CUM | 1 | 1 | 3.25 | 2.925 | 0.135 | 1.2833
| PASSAGE | CUM | 1 | 1 | 2.925 | 1.7 | 0.125 | 0.62156
| KITCHEN | CUM | 1 | 1 | 3.25 | 2.365 | 0.135 | 1.0376
| LIVING | CUM | 1 | 1 | 5.23 | 3.33 | 0.15 | 2.6124
|  | CUM | 1 | 1 | 3.4 | 0.94 | 0.15 | 0.4794
|  | CUM | 1 | 1 | 2.55 | 1.47 | 0.15 | 0.56227
| TOILET 1 | CUM | 1 | 1 | 2.225 | 1.495 | 0.125 | 0.4158
| TOILET 2 | CUM | 1 | 1 | 3.385 | 1.425 | 0.125 | 0.60295
| BALCONY 1 | CUM | 1 | 1 | 4.665 | 2 | 0.1825 | 1.7027
| BALCONY 2 | CUM | 1 | 1 | 5.105 | 2 | 0.1825 | 1.8633
12.6254
FLAT NO 10,11,12
| B. ROOM 1 |  | 3 | 1 | 3.86 | 3.25 | 0.135 | 5.0807
| B. ROOM 2 |  | 3 | 1 | 3.86 | 3.335 | 0.135 | 5.2136
| B. ROOM 3 |  | 3 | 1 | 3.55 | 3.265 | 0.125 | 4.3465
| Living |  | 3 | 1 | 6.245 | 3.315 | 0.15 | 9.316
|  |  | 3 | 1 | 3.17 | 1.91 | 0.15 | 2.7246
| KITCHEN |  | 3 | 1 | 3.435 | 2.345 | 0.135 | 3.2623
| TOILET 1 |  | 3 | 1 | 3.86 | 1.44 | 0.125 | 2.0844
| TOILET 2 |  | 3 | 1 | 3.55 | 1.425 | 0.125 | 1.897
| TOILET 3 |  | 3 | 1 | 3.55 | 1.425 | 0.125 | 1.897
| Service slab |  | 3 | 1 | 1.245 | 0.515 | 0.125 | 0.24044
| Service slab |  | 3 | 1 | 0.97 | 0.415 | 0.125 | 0.15096
| BALCONY 1 |  | 3 | 1 | 5.93 | 2 | 0.1825 | 6.4933
| BALCONY 2 |  | 3 | 1 | 3.565 | 2 | 0.1825 | 3.9037
| BALCONY 3 |  | 3 | 1 | 1.55 | 2 | 0.1825 | 1.6973
48.3079
| FLAT 7,8 & 9 LOBBY |  | 1 | 1 | 5.09 | 1.5 | 0.125 | 0.95437
|  |  | 1 | 1 | 3.14 | 0.955 | 0.125 | 0.37484
| LIFT LOBBY |  | 1 | 1 | 3.95 | 1.61 | 0.125 | 0.79494
|  |  | 1 | 1 | 5.635 | 2.44 | 0.125 | 1.7187
| FLAT 10,11,12 LOBBY |  | 1 | 1 | 4.79 | 3.19 | 0.125 | 1.91
|  |  | 1 | 1 | 1.4 | 0.655 | 0.125 | 0.11462
Main s/case (3 No)
| Half landing |  | 1 | 2 | 1.5 | 1.5 | 0.175 | 0.7875
| freight |  | 1 | 2 | 2.409 | 1.5 | 0.175 | 1.2647
| mid freight |  | 1 | 1 | 1.484 | 1.5 | 0.175 | 0.38955
| top landing |  | 1 | 1 | 3.96 | 0.26 | 0.175 | 0.18018
| landing beam 230x450 |  | 1 | 1 | 3.53 | 0.45 | 0.23 | 0.36536
Fire s/case (4 No)
| mid & full landing |  | 1 | 2 | 3.2 | 1.5 | 0.175 | 1.68
| freight |  | 1 | 2 | 3.343 | 1.5 | 0.175 | 1.7551
| landing beam 230x450 |  | 1 | 1 | 3.2 | 0.23 | 0.45 | 0.3312
12.621
COLUMN (22-43/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 31 | 1 | 0.3 | 0.6 | 0.45 | 2.511
2 | C4, C5 (300X750) | CUM | 15 | 1 | 0.3 | 0.7 | 0.45 | 1.4175
3 | C6, C11 (300X715) | CUM | 7 | 1 | 0.3 | 0.715 | 0.45 | 0.67568
4 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 0.45 | 0.216
5 | SW 1 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.067275
6 |  | CUM | 1 | 1 | 0.23 | 1.42 | 0.45 | 0.14697
7 | SW 2 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.067275
8 |  | CUM | 1 | 1 | 0.23 | 1.62 | 0.45 | 0.16767
9 | SW 3 (230x1000) | CUM | 1 | 1 | 0.23 | 1 | 0.45 | 0.1035
10 | SW 4 (230x1150) | CUM | 1 | 1 | 0.23 | 1.15 | 0.45 | 0.11903
11 | SW 5 (230x1700) | CUM | 2 | 1 | 0.23 | 1.7 | 0.45 | 0.3519
12 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 0.45 | 0.2453
13 | SW 7 (230x1855) | CUM | 1 | 1 | 0.23 | 1.855 | 0.45 | 0.19199
14 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 0.45 | 0.3726
15 | SW 9 (L-SHAPE) | CUM | 3 | 1 | 0.23 | 0.65 | 0.45 | 0.20183
16 |  | CUM | 3 | 1 | 0.23 | 1.62 | 0.45 | 0.50301
17 | SW 10 (230x3445) | CUM | 1 | 1 | 0.23 | 3.445 | 0.45 | 0.35656
18 | SW 11 (230x4065) | CUM | 1 | 1 | 0.23 | 4.065 | 0.45 | 0.42073
19 | SW 12 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.067275
20 |  | CUM | 1 | 1 | 0.23 | 1.305 | 0.45 | 0.13507
21 | SW 13 (200x3445) | CUM | 1 | 1 | 0.2 | 3.445 | 0.45 | 0.31005
8.6482
153.7933
204.7143
| SLAB RCC | [7 empty] | 9TH RA
| B1 200X500 | CUM | 1 | 1 | 3.025 | 0.5 | 0.2 | 0.3025
| B1 200X500 | CUM | 1 | 1 | 2.8 | 0.5 | 0.2 | 0.28
| B2 200X500 | CUM | 1 | 1 | 3.3 | 0.5 | 0.2 | 0.33
| B3 AT GRID B-C/27-28 | CUM | 1 | 1 | 1.395 | 0.35 | 0.1 | 0.048825
| B3 AT GRID L-M/27-28 | CUM | 1 | 1 | 1.395 | 0.35 | 0.115 | 0.056149
| B3 AT GRID E/32-33 | CUM | 1 | 1 | 1.185 | 0.35 | 0.1 | 0.041475
| B3 AT GRID F/43 | CUM | 1 | 3 | 2.055 | 0.35 | 0.1 | 0.21578
| B3 AT GRID F/39-40 | CUM | 1 | 3 | 1.485 | 0.35 | 0.1 | 0.15593
| B3 AT GRID M & O/39-40 | CUM | 1 | 3 | 2.315 | 0.35 | 0.1 | 0.24307
| B3 AT GRID C,K/25 | CUM | 1 | 2 | 2.315 | 0.35 | 0.1 | 0.16205
| B4 200X350 | CUM | 1 | 2 | 1.395 | 0.35 | 0.2 | 0.1953
| B5 200X450 | CUM | 1 | 1 | 6.875 | 0.45 | 0.2 | 0.61875
| B6 230X350 | CUM | 1 | 1 | 3.16 | 0.35 | 0.23 | 0.25438
| B7 200X450 | CUM | 1 | 1 | 2.7 | 0.45 | 0.2 | 0.243
| B8 200X500 | CUM | 1 | 1 | 2.875 | 0.5 | 0.2 | 0.2875
| B8 200X350 | CUM | 1 | 1 | 2.93 | 0.35 | 0.2 | 0.2051
| B9 200X500 | CUM | 1 | 1 | 4.69 | 0.5 | 0.2 | 0.469
| B10 200X500 | CUM | 1 | 1 | 3.15 | 0.5 | 0.2 | 0.315
| B11 200X450 | CUM | 1 | 1 | 4.69 | 0.45 | 0.2 | 0.4221
| B12 200X450 | CUM | 1 | 1 | 5.76 | 0.45 | 0.2 | 0.5184
| B13 200X350 | CUM | 1 | 1 | 1.6 | 0.35 | 0.2 | 0.112
| B13 200X450 | CUM | 1 | 1 | 4.105 | 0.45 | 0.2 | 0.36945
| B14 200X450 | CUM | 1 | 1 | 1.5 | 0.45 | 0.2 | 0.135
| B14 200X450 | CUM | 1 | 1 | 2.2 | 0.45 | 0.2 | 0.198
| B15 200X500 | CUM | 1 | 1 | 3.115 | 0.5 | 0.2 | 0.3115
| B16 200X350 | CUM | 1 | 3 | 1.02 | 0.35 | 0.2 | 0.2142
| B16 200X500 | CUM | 1 | 3 | 3.35 | 0.5 | 0.2 | 1.005
| B16 200X500 | CUM | 1 | 3 | 3.25 | 0.5 | 0.2 | 0.975
| B17 200X500 | CUM | 1 | 1 | 3.215 | 0.5 | 0.2 | 0.3215
| B18 230X500 | CUM | 1 | 1 | 2.76 | 0.5 | 0.23 | 0.3174
| B19 200X450 | CUM | 1 | 1 | 6.79 | 0.45 | 0.2 | 0.6111
| B20 200X350 | CUM | 1 | 1 | 2.41 | 0.35 | 0.2 | 0.1687
| B21 230X450 | CUM | 1 | 1 | 5.76 | 0.45 | 0.23 | 0.59616
| B22 200x450 | CUM | 1 | 1 | 4.69 | 0.45 | 0.2 | 0.4221
| B23 200X450 | CUM | 1 | 1 | 2.22 | 0.45 | 0.2 | 0.1998
| B24 200X450 | CUM | 1 | 1 | 5.63 | 0.45 | 0.2 | 0.5067
| B25 200X450 | CUM | 1 | 1 | 1.5 | 0.45 | 0.2 | 0.135
| B25 200X500 | CUM | 1 | 1 | 2.085 | 0.5 | 0.2 | 0.2085
| B25 200X450 BESIDE STAIRS | CUM | 1 | 1 | 5.63 | 0.45 | 0.2 | 0.5067
| B26 200X450 | CUM | 1 | 3 | 3.235 | 0.45 | 0.2 | 0.87345
| B26 200X450 | CUM | 1 | 3 | 4.72 | 0.45 | 0.2 | 1.2744
| B27 200X350 | CUM | 1 | 3 | 2.575 | 0.35 | 0.2 | 0.54075
| B27 200X500 | CUM | 1 | 3 | 3.165 | 0.5 | 0.2 | 0.9495
| B28 200X450 | CUM | 1 | 1 | 5.125 | 0.45 | 0.2 | 0.46125
| B29 200X450 | CUM | 1 | 1 | 1.9 | 0.45 | 0.2 | 0.171
| B29 200X450 | CUM | 1 | 1 | 1.9 | 0.45 | 0.2 | 0.171
| B29 200X450 | CUM | 1 | 1 | 1.4 | 0.45 | 0.2 | 0.126
| B30 200X350 | CUM | 1 | 1 | 2.93 | 0.35 | 0.2 | 0.2051
| B30 200X500 | CUM | 1 | 1 | 2.875 | 0.5 | 0.2 | 0.2875
| B30 200X450 | CUM | 1 | 1 | 3.95 | 0.45 | 0.2 | 0.3555
| B31 200X500 | CUM | 1 | 1 | 4.69 | 0.5 | 0.2 | 0.469
| B31 200X500 | CUM | 1 | 1 | 3.15 | 0.5 | 0.2 | 0.315
| B32 230X450 | CUM | 1 | 2 | 1.9 | 0.45 | 0.23 | 0.3933
| B33 200X350 | CUM | 1 | 1 | 5.235 | 0.35 | 0.2 | 0.36645
| B34 230X450 | CUM | 1 | 1 | 5.1 | 0.45 | 0.23 | 0.52785
| B34 230X450 | CUM | 1 | 1 | 5.1 | 0.45 | 0.23 | 0.52785
| B35 200X500 | CUM | 1 | 2 | 3.19 | 0.5 | 0.2 | 0.638
| B36 200X500 | CUM | 1 | 3 | 1.81 | 0.5 | 0.2 | 0.543
| B36 200X500 | CUM | 1 | 3 | 3.55 | 0.5 | 0.2 | 1.065
| B36 230X500 | CUM | 1 | 3 | 0.515 | 0.5 | 0.23 | 0.17767
| B37 200X450 | CUM | 1 | 3 | 3.86 | 0.45 | 0.2 | 1.0422
| B38 200X450 | CUM | 1 | 3 | 3.45 | 0.45 | 0.2 | 0.9315
| B39 200X450 | CUM | 1 | 3 | 2.91 | 0.45 | 0.2 | 0.7857
| B39 230X350 | CUM | 1 | 3 | 3.55 | 0.35 | 0.23 | 0.85732
| B40 200X450 | CUM | 1 | 2 | 3 | 0.45 | 0.2 | 0.54
| B40 200X350 | CUM | 1 | 2 | 2.065 | 0.35 | 0.2 | 0.2891
| B41 200X500 | CUM | 1 | 3 | 3.31 | 0.5 | 0.2 | 0.993
| B42 200X450 | CUM | 1 | 2 | 3 | 0.45 | 0.2 | 0.54
| B43 200X450 | CUM | 1 | 1 | 5.245 | 0.45 | 0.2 | 0.47205
| B44 200X450 | CUM | 1 | 1 | 3 | 0.45 | 0.2 | 0.27
| B44 200X350 | CUM | 1 | 1 | 1.95 | 0.35 | 0.2 | 0.1365
| B45 200X450 | CUM | 1 | 1 | 2.23 | 0.45 | 0.2 | 0.2007
| B46 200X500 | CUM | 1 | 1 | 5.145 | 0.5 | 0.2 | 0.5145
| B47 200X500 | CUM | 1 | 1 | 3.8 | 0.5 | 0.2 | 0.38
| B48 200X350 | CUM | 1 | 1 | 2.95 | 0.35 | 0.2 | 0.2065
| B49 200X450 | CUM | 1 | 1 | 4.55 | 0.45 | 0.2 | 0.4095
| B50 200X500 | CUM | 1 | 1 | 3.05 | 0.5 | 0.2 | 0.305
| B51 200X450 | CUM | 1 | 1 | 2.5 | 0.45 | 0.2 | 0.225
| B52 230X500 | CUM | 1 | 1 | 3.115 | 0.5 | 0.23 | 0.35823
| B53 200X350 | CUM | 1 | 1 | 2.335 | 0.35 | 0.2 | 0.16345
| B54 230X500 | CUM | 1 | 1 | 3.2 | 0.5 | 0.23 | 0.368
| B55 230X450 | CUM | 1 | 1 | 0.35 | 0.45 | 0.23 | 0.036225
| B56 200X450 | CUM | 1 | 1 | 1.96 | 0.45 | 0.2 | 0.1764
| B57 230X450 | CUM | 1 | 1 | 3.2 | 0.45 | 0.23 | 0.3312
| B57 200X450 | CUM | 1 | 1 | 2.335 | 0.45 | 0.2 | 0.21015
| B58 230X500 | CUM | 1 | 1 | 2.54 | 0.5 | 0.23 | 0.2921
| B58 230X450 | CUM | 1 | 1 | 3.43 | 0.45 | 0.23 | 0.35501
| B59 200X500 | CUM | 1 | 1 | 2.225 | 0.5 | 0.2 | 0.2225
| B60 200X450 | CUM | 1 | 1 | 3.14 | 0.45 | 0.2 | 0.2826
| B61 200X450 | CUM | 1 | 1 | 3.43 | 0.45 | 0.2 | 0.3087
| B61 230X450 | CUM | 1 | 1 | 1.99 | 0.45 | 0.23 | 0.20597
| B62 200X500 | CUM | 1 | 1 | 2.225 | 0.5 | 0.2 | 0.2225
| B63 200X450 | CUM | 1 | 2 | 3.06 | 0.45 | 0.2 | 0.5508
| B64 200X350 | CUM | 1 | 2 | 3.05 | 0.35 | 0.2 | 0.427
| B64 200X350 | CUM | 1 | 2 | 0.38 | 0.35 | 0.2 | 0.0532
| B65 200X450 | CUM | 1 | 2 | 3.385 | 0.45 | 0.2 | 0.6093
| B66 200X450 | CUM | 1 | 2 | 3.25 | 0.45 | 0.2 | 0.585
| B66 200X450 | CUM | 1 | 2 | 1.7 | 0.45 | 0.2 | 0.306
| B66 200X350 | CUM | 1 | 2 | 1.385 | 0.35 | 0.2 | 0.1939
| B67 200X450 | CUM | 1 | 2 | 3.05 | 0.45 | 0.2 | 0.549
| B67 200X450 | CUM | 1 | 2 | 1.7 | 0.45 | 0.2 | 0.306
| B68 200X350 | CUM | 1 | 1 | 3.17 | 0.35 | 0.2 | 0.2219
| B69 200X450 | CUM | 1 | 0.5 | 5.78 | 0.45 | 0.2 | 0.2601
39.8105
FLAT NO 9
| Bed room 1 | CUM | 1 | 1 | 3.575 | 3.55 | 0.135 | 1.7133
| Bed Room 2 | CUM | 1 | 1 | 3.55 | 3.2 | 0.135 | 1.5336
| Bed Room 3 | CUM | 1 | 1 | 3.145 | 3.05 | 0.125 | 1.199
|  | CUM | 1 | 1 | 0.9 | 0.4 | 0.125 | 0.045
| Service slab | CUM | 1 | 1 | 1.165 | 0.515 | 0.125 | 0.074997
| TOILET 1 | CUM | 1 | 1 | 3.575 | 1.57 | 0.125 | 0.70159
| TOILET 2 | CUM | 1 | 1 | 2.5 | 1.6 | 0.125 | 0.5
| PASSAGE | CUM | 1 | 1 | 2.785 | 1.2 | 0.125 | 0.41775
| Living | CUM | 1 | 1 | 6.365 | 3.72 | 0.15 | 3.5517
|  | CUM | 1 | 1 | 4.115 | 0.385 | 0.15 | 0.23764
| Entry/ Porch | CUM | 1 | 1 | 1.5 | 1.035 | 0.125 | 0.19406
| Kitchen | CUM | 1 | 1 | 2.85 | 2.335 | 0.135 | 0.89839
| Balcony 1 | CUM | 1 | 1 | 6.3 | 2 | 0.1825 | 2.2995
| Balcony 2 | CUM | 1 | 1 | 4.065 | 2 | 0.1825 | 1.4837
| Kitchen Balcony | CUM | 1 | 1 | 1.4 | 2 | 0.1825 | 0.511
|  | CUM | 1 | 1 | 1.185 | 0.435 | 0.2 | 0.1031
15.4644
| FLAT NO 8 | [6 empty] | 0
| B. ROOM 1 | CUM | 1 | 1 | 3.56 | 3.275 | 0.135 | 1.574
| B. ROOM 2 | CUM | 1 | 1 | 3.25 | 2.925 | 0.135 | 1.2833
| B. ROOM 3 | CUM | 1 | 1 | 3.58 | 3.05 | 0.135 | 1.4741
| PASSAGE | CUM | 1 | 1 | 2.925 | 1.7 | 0.125 | 0.62156
| KITCHEN | CUM | 1 | 1 | 3.25 | 2.365 | 0.135 | 1.0376
| LIVING | CUM | 1 | 1 | 5.23 | 3.33 | 0.15 | 2.6124
|  | CUM | 1 | 1 | 3.4 | 0.94 | 0.15 | 0.4794
|  | CUM | 1 | 1 | 2.55 | 1.47 | 0.15 | 0.56227
| DRESSING AREA | CUM | 1 | 1 | 2.41 | 1.43 | 0.125 | 0.43079
| TOILET 1 | CUM | 1 | 1 | 2.225 | 1.495 | 0.125 | 0.4158
| TOILET 2 | CUM | 1 | 1 | 3.385 | 1.425 | 0.125 | 0.60295
| TOILET 3 | CUM | 1 | 1 | 2.41 | 1.54 | 0.125 | 0.46393
| BALCONY 1 | CUM | 1 | 1 | 4.665 | 2 | 0.1825 | 1.7027
| BALCONY 2 | CUM | 1 | 1 | 5.105 | 2 | 0.1825 | 1.8633
| BALCONY 3 | CUM | 1 | 1 | 3.265 | 2 | 0.1825 | 1.1917
16.3159
| FLAT NO 7 | [6 empty] | 0
| B. ROOM 1 | CUM | 1 | 1 | 3.56 | 3.245 | 0.125 | 1.444
| B. ROOM 2 | CUM | 1 | 1 | 3.25 | 2.925 | 0.135 | 1.2833
| PASSAGE | CUM | 1 | 1 | 2.925 | 1.7 | 0.125 | 0.62156
| KITCHEN | CUM | 1 | 1 | 3.25 | 2.365 | 0.135 | 1.0376
| LIVING | CUM | 1 | 1 | 5.23 | 3.33 | 0.15 | 2.6124
|  | CUM | 1 | 1 | 3.4 | 0.94 | 0.15 | 0.4794
|  | CUM | 1 | 1 | 2.55 | 1.47 | 0.15 | 0.56227
| TOILET 1 | CUM | 1 | 1 | 2.225 | 1.495 | 0.125 | 0.4158
| TOILET 2 | CUM | 1 | 1 | 3.385 | 1.425 | 0.125 | 0.60295
| BALCONY 1 | CUM | 1 | 1 | 4.665 | 2 | 0.1825 | 1.7027
| BALCONY 2 | CUM | 1 | 1 | 5.105 | 2 | 0.1825 | 1.8633
12.6254
FLAT NO 10,11,12
| B. ROOM 1 |  | 3 | 1 | 3.86 | 3.25 | 0.135 | 5.0807
| B. ROOM 2 |  | 3 | 1 | 3.86 | 3.335 | 0.135 | 5.2136
| B. ROOM 3 |  | 3 | 1 | 3.55 | 3.265 | 0.125 | 4.3465
| Living |  | 3 | 1 | 6.245 | 3.315 | 0.15 | 9.316
|  |  | 3 | 1 | 3.17 | 1.91 | 0.15 | 2.7246
| KITCHEN |  | 3 | 1 | 3.435 | 2.345 | 0.135 | 3.2623
| TOILET 1 |  | 3 | 1 | 3.86 | 1.44 | 0.125 | 2.0844
| TOILET 2 |  | 3 | 1 | 3.55 | 1.425 | 0.125 | 1.897
| TOILET 3 |  | 3 | 1 | 3.55 | 1.425 | 0.125 | 1.897
| Service slab |  | 3 | 1 | 1.245 | 0.515 | 0.125 | 0.24044
| Service slab |  | 3 | 1 | 0.97 | 0.415 | 0.125 | 0.15096
| BALCONY 1 |  | 3 | 1 | 5.93 | 2 | 0.1825 | 6.4933
| BALCONY 2 |  | 3 | 1 | 3.565 | 2 | 0.1825 | 3.9037
| BALCONY 3 |  | 3 | 1 | 1.55 | 2 | 0.1825 | 1.6973
48.3079
| FLAT 7,8 & 9 LOBBY |  | 1 | 1 | 5.09 | 1.5 | 0.125 | 0.95437
|  |  | 1 | 1 | 3.14 | 0.955 | 0.125 | 0.37484
| LIFT LOBBY |  | 1 | 1 | 3.95 | 1.61 | 0.125 | 0.79494
|  |  | 1 | 1 | 5.635 | 2.44 | 0.125 | 1.7187
| FLAT 10,11,12 LOBBY |  | 1 | 1 | 4.79 | 3.19 | 0.125 | 1.91
|  |  | 1 | 1 | 1.4 | 0.655 | 0.125 | 0.11462
Main s/case (3 No)
| Half landing |  | 1 | 2 | 1.5 | 1.5 | 0.175 | 0.7875
| freight |  | 1 | 2 | 2.409 | 1.5 | 0.175 | 1.2647
| mid freight |  | 1 | 1 | 1.484 | 1.5 | 0.175 | 0.38955
| top landing |  | 1 | 1 | 3.96 | 0.26 | 0.175 | 0.18018
| landing beam 230x450 |  | 1 | 1 | 3.53 | 0.45 | 0.23 | 0.36536
Fire s/case (4 No)
| mid & full landing |  | 1 | 2 | 3.2 | 1.5 | 0.175 | 1.68
| freight |  | 1 | 2 | 3.343 | 1.5 | 0.175 | 1.7551
| landing beam 230x450 |  | 1 | 1 | 3.2 | 0.23 | 0.45 | 0.3312
12.621
COLUMN (22-43/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 31 | 1 | 0.3 | 0.6 | 0.45 | 2.511
2 | C4, C5 (300X750) | CUM | 15 | 1 | 0.3 | 0.7 | 0.45 | 1.4175
3 | C6, C11 (300X715) | CUM | 7 | 1 | 0.3 | 0.715 | 0.45 | 0.67568
4 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 0.45 | 0.216
5 | SW 1 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.067275
6 |  | CUM | 1 | 1 | 0.23 | 1.42 | 0.45 | 0.14697
7 | SW 2 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.067275
8 |  | CUM | 1 | 1 | 0.23 | 1.62 | 0.45 | 0.16767
9 | SW 3 (230x1000) | CUM | 1 | 1 | 0.23 | 1 | 0.45 | 0.1035
10 | SW 4 (230x1150) | CUM | 1 | 1 | 0.23 | 1.15 | 0.45 | 0.11903
11 | SW 5 (230x1700) | CUM | 2 | 1 | 0.23 | 1.7 | 0.45 | 0.3519
12 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 0.45 | 0.2453
13 | SW 7 (230x1855) | CUM | 1 | 1 | 0.23 | 1.855 | 0.45 | 0.19199
14 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 0.45 | 0.3726
15 | SW 9 (L-SHAPE) | CUM | 3 | 1 | 0.23 | 0.65 | 0.45 | 0.20183
16 |  | CUM | 3 | 1 | 0.23 | 1.62 | 0.45 | 0.50301
17 | SW 10 (230x3445) | CUM | 1 | 1 | 0.23 | 3.445 | 0.45 | 0.35656
18 | SW 11 (230x4065) | CUM | 1 | 1 | 0.23 | 4.065 | 0.45 | 0.42073
19 | SW 12 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.067275
20 |  | CUM | 1 | 1 | 0.23 | 1.305 | 0.45 | 0.13507
21 | SW 13 (200x3445) | CUM | 1 | 1 | 0.2 | 3.445 | 0.45 | 0.31005
8.6482
153.7933
| COLUMN (22-43/A-Q) FROM 1ST FLOOR LVL to 2nd floor LVL | [7 empty] | 10TH RA
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 31 | 1 | 0.3 | 0.6 | 2.5 | 13.95
2 | C4, C5 (300X750) | CUM | 15 | 1 | 0.3 | 0.7 | 2.5 | 7.875
3 | C6, C11 (300X715) | CUM | 7 | 1 | 0.3 | 0.715 | 2.5 | 3.7538
4 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 2.5 | 1.2
5 | SW 1 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 2.5 | 0.37375
6 |  | CUM | 1 | 1 | 0.23 | 1.42 | 2.5 | 0.8165
7 | SW 2 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 2.5 | 0.37375
8 |  | CUM | 1 | 1 | 0.23 | 1.62 | 2.5 | 0.9315
9 | SW 3 (230x1000) | CUM | 1 | 1 | 0.23 | 1 | 2.5 | 0.575
10 | SW 4 (230x1150) | CUM | 1 | 1 | 0.23 | 1.15 | 2.5 | 0.66125
11 | SW 5 (230x1700) | CUM | 2 | 1 | 0.23 | 1.7 | 2.5 | 1.955
12 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 2.5 | 1.3628
13 | SW 7 (230x1855) | CUM | 1 | 1 | 0.23 | 1.855 | 2.5 | 1.0666 |  | 143
14 | SW 8 (230x3600) | CUM | 0.5 | 1 | 0.23 | 3.6 | 2.5 | 1.035 |  | 103
15 | SW 9 (L-SHAPE) | CUM | 3 | 1 | 0.23 | 0.65 | 2.5 | 1.1213
16 |  | CUM | 3 | 1 | 0.23 | 1.62 | 2.5 | 2.7945
17 | SW 10 (230x3445) | CUM | 1 | 1 | 0.23 | 3.445 | 2.5 | 1.9809
18 | SW 11 (230x4065) | CUM | 1 | 1 | 0.23 | 4.065 | 2.5 | 2.3374
19 | SW 12 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 2.5 | 0.37375
20 |  | CUM | 1 | 1 | 0.23 | 1.305 | 2.5 | 0.75037
21 | SW 13 (200x3445) | CUM | 1 | 1 | 0.2 | 3.445 | 2.5 | 1.7225
[7 empty] | TOTAL | 47.0105
|  |  |  | Total RMC of 2nd floor lvl( grid 1-43) Column |  |  |  | 94.021
SLAB and Beam RCC(22to 43 &AtoQ
| B1 200X500 | CUM | 1 | 1 | 3.025 | 0.5 | 0.2 | 0.3025
| B1 200X500 | CUM | 1 | 1 | 2.8 | 0.5 | 0.2 | 0.28
| B2 200X500 | CUM | 1 | 1 | 3.3 | 0.5 | 0.2 | 0.33
| B3 AT GRID B-C/27-28 | CUM | 1 | 1 | 1.395 | 0.35 | 0.1 | 0.048825
| B3 AT GRID L-M/27-28 | CUM | 1 | 1 | 1.395 | 0.35 | 0.115 | 0.056149
| B3 AT GRID E/32-33 | CUM | 1 | 1 | 1.185 | 0.35 | 0.1 | 0.041475
| B3 AT GRID F/43 | CUM | 1 | 3 | 2.055 | 0.35 | 0.1 | 0.21578
| B3 AT GRID F/39-40 | CUM | 1 | 3 | 1.485 | 0.35 | 0.1 | 0.15593
| B3 AT GRID M & O/39-40 | CUM | 1 | 3 | 2.315 | 0.35 | 0.1 | 0.24307
| B3 AT GRID C,K/25 | CUM | 1 | 2 | 2.315 | 0.35 | 0.1 | 0.16205
| B4 200X350 | CUM | 1 | 2 | 1.395 | 0.35 | 0.2 | 0.1953
| B5 200X450 | CUM | 1 | 1 | 6.875 | 0.45 | 0.2 | 0.61875
| B6 230X350 | CUM | 1 | 1 | 3.16 | 0.35 | 0.23 | 0.25438
| B7 200X450 | CUM | 1 | 1 | 2.7 | 0.45 | 0.2 | 0.243
| B8 200X500 | CUM | 1 | 1 | 2.875 | 0.5 | 0.2 | 0.2875
| B8 200X350 | CUM | 1 | 1 | 2.93 | 0.35 | 0.2 | 0.2051
| B9 200X500 | CUM | 1 | 1 | 4.69 | 0.5 | 0.2 | 0.469
| B10 200X500 | CUM | 1 | 1 | 3.15 | 0.5 | 0.2 | 0.315
| B11 200X450 | CUM | 1 | 1 | 4.69 | 0.45 | 0.2 | 0.4221
| B12 200X450 | CUM | 1 | 1 | 5.76 | 0.45 | 0.2 | 0.5184
| B13 200X350 | CUM | 1 | 1 | 1.6 | 0.35 | 0.2 | 0.112
| B13 200X450 | CUM | 1 | 1 | 4.105 | 0.45 | 0.2 | 0.36945
| B14 200X450 | CUM | 1 | 1 | 1.5 | 0.45 | 0.2 | 0.135
| B14 200X450 | CUM | 1 | 1 | 2.2 | 0.45 | 0.2 | 0.198
| B15 200X500 | CUM | 1 | 1 | 3.115 | 0.5 | 0.2 | 0.3115
| B16 200X350 | CUM | 1 | 3 | 1.02 | 0.35 | 0.2 | 0.2142
| B16 200X500 | CUM | 1 | 3 | 3.35 | 0.5 | 0.2 | 1.005
| B16 200X500 | CUM | 1 | 3 | 3.25 | 0.5 | 0.2 | 0.975
| B17 200X500 | CUM | 1 | 1 | 3.215 | 0.5 | 0.2 | 0.3215
| B18 230X500 | CUM | 1 | 1 | 2.76 | 0.5 | 0.23 | 0.3174
| B19 200X450 | CUM | 1 | 1 | 6.79 | 0.45 | 0.2 | 0.6111
| B20 200X350 | CUM | 1 | 1 | 2.41 | 0.35 | 0.2 | 0.1687
| B21 230X450 | CUM | 1 | 1 | 5.76 | 0.45 | 0.23 | 0.59616
| B22 200x450 | CUM | 1 | 1 | 4.69 | 0.45 | 0.2 | 0.4221
| B23 200X450 | CUM | 1 | 1 | 2.22 | 0.45 | 0.2 | 0.1998
| B24 200X450 | CUM | 1 | 1 | 5.63 | 0.45 | 0.2 | 0.5067
| B25 200X450 | CUM | 1 | 1 | 1.5 | 0.45 | 0.2 | 0.135
| B25 200X500 | CUM | 1 | 1 | 2.085 | 0.5 | 0.2 | 0.2085
| B25 200X450 BESIDE STAIRS | CUM | 1 | 1 | 5.63 | 0.45 | 0.2 | 0.5067
| B26 200X450 | CUM | 1 | 3 | 3.235 | 0.45 | 0.2 | 0.87345
| B26 200X450 | CUM | 1 | 3 | 4.72 | 0.45 | 0.2 | 1.2744
| B27 200X350 | CUM | 1 | 3 | 2.575 | 0.35 | 0.2 | 0.54075
| B27 200X500 | CUM | 1 | 3 | 3.165 | 0.5 | 0.2 | 0.9495
| B28 200X450 | CUM | 1 | 1 | 5.125 | 0.45 | 0.2 | 0.46125
| B29 200X450 | CUM | 1 | 1 | 1.9 | 0.45 | 0.2 | 0.171
| B29 200X450 | CUM | 1 | 1 | 1.9 | 0.45 | 0.2 | 0.171
| B29 200X450 | CUM | 1 | 1 | 1.4 | 0.45 | 0.2 | 0.126
| B30 200X350 | CUM | 1 | 1 | 2.93 | 0.35 | 0.2 | 0.2051
| B30 200X500 | CUM | 1 | 1 | 2.875 | 0.5 | 0.2 | 0.2875
| B30 200X450 | CUM | 1 | 1 | 3.95 | 0.45 | 0.2 | 0.3555
| B31 200X500 | CUM | 1 | 1 | 4.69 | 0.5 | 0.2 | 0.469
| B31 200X500 | CUM | 1 | 1 | 3.15 | 0.5 | 0.2 | 0.315
| B32 230X450 | CUM | 1 | 2 | 1.9 | 0.45 | 0.23 | 0.3933
| B33 200X350 | CUM | 1 | 1 | 5.235 | 0.35 | 0.2 | 0.36645
| B34 230X450 | CUM | 1 | 1 | 5.1 | 0.45 | 0.23 | 0.52785
| B34 230X450 | CUM | 1 | 1 | 5.1 | 0.45 | 0.23 | 0.52785
| B35 200X500 | CUM | 1 | 2 | 3.19 | 0.5 | 0.2 | 0.638
| B36 200X500 | CUM | 1 | 3 | 1.81 | 0.5 | 0.2 | 0.543
| B36 200X500 | CUM | 1 | 3 | 3.55 | 0.5 | 0.2 | 1.065
| B36 230X500 | CUM | 1 | 3 | 0.515 | 0.5 | 0.23 | 0.17767
| B37 200X450 | CUM | 1 | 3 | 3.86 | 0.45 | 0.2 | 1.0422
| B38 200X450 | CUM | 1 | 3 | 3.45 | 0.45 | 0.2 | 0.9315
| B39 200X450 | CUM | 1 | 3 | 2.91 | 0.45 | 0.2 | 0.7857
| B39 230X350 | CUM | 1 | 3 | 3.55 | 0.35 | 0.23 | 0.85732
| B40 200X450 | CUM | 1 | 2 | 3 | 0.45 | 0.2 | 0.54
| B40 200X350 | CUM | 1 | 2 | 2.065 | 0.35 | 0.2 | 0.2891
| B41 200X500 | CUM | 1 | 3 | 3.31 | 0.5 | 0.2 | 0.993
| B42 200X450 | CUM | 1 | 2 | 3 | 0.45 | 0.2 | 0.54
| B43 200X450 | CUM | 1 | 1 | 5.245 | 0.45 | 0.2 | 0.47205
| B44 200X450 | CUM | 1 | 1 | 3 | 0.45 | 0.2 | 0.27
| B44 200X350 | CUM | 1 | 1 | 1.95 | 0.35 | 0.2 | 0.1365
| B45 200X450 | CUM | 1 | 1 | 2.23 | 0.45 | 0.2 | 0.2007
| B46 200X500 | CUM | 1 | 1 | 5.145 | 0.5 | 0.2 | 0.5145
| B47 200X500 | CUM | 1 | 1 | 3.8 | 0.5 | 0.2 | 0.38
| B48 200X350 | CUM | 1 | 1 | 2.95 | 0.35 | 0.2 | 0.2065
| B49 200X450 | CUM | 1 | 1 | 4.55 | 0.45 | 0.2 | 0.4095
| B50 200X500 | CUM | 1 | 1 | 3.05 | 0.5 | 0.2 | 0.305
| B51 200X450 | CUM | 1 | 1 | 2.5 | 0.45 | 0.2 | 0.225
| B52 230X500 | CUM | 1 | 1 | 3.115 | 0.5 | 0.23 | 0.35823
| B53 200X350 | CUM | 1 | 1 | 2.335 | 0.35 | 0.2 | 0.16345
| B54 230X500 | CUM | 1 | 1 | 3.2 | 0.5 | 0.23 | 0.368
| B55 230X450 | CUM | 1 | 1 | 0.35 | 0.45 | 0.23 | 0.036225
| B56 200X450 | CUM | 1 | 1 | 1.96 | 0.45 | 0.2 | 0.1764
| B57 230X450 | CUM | 1 | 1 | 3.2 | 0.45 | 0.23 | 0.3312
| B57 200X450 | CUM | 1 | 1 | 2.335 | 0.45 | 0.2 | 0.21015
| B58 230X500 | CUM | 1 | 1 | 2.54 | 0.5 | 0.23 | 0.2921
| B58 230X450 | CUM | 1 | 1 | 3.43 | 0.45 | 0.23 | 0.35501
| B59 200X500 | CUM | 1 | 1 | 2.225 | 0.5 | 0.2 | 0.2225
| B60 200X450 | CUM | 1 | 1 | 3.14 | 0.45 | 0.2 | 0.2826
| B61 200X450 | CUM | 1 | 1 | 3.43 | 0.45 | 0.2 | 0.3087
| B61 230X450 | CUM | 1 | 1 | 1.99 | 0.45 | 0.23 | 0.20597
| B62 200X500 | CUM | 1 | 1 | 2.225 | 0.5 | 0.2 | 0.2225
| B63 200X450 | CUM | 1 | 2 | 3.06 | 0.45 | 0.2 | 0.5508
| B64 200X350 | CUM | 1 | 2 | 3.05 | 0.35 | 0.2 | 0.427
| B64 200X350 | CUM | 1 | 2 | 0.38 | 0.35 | 0.2 | 0.0532
| B65 200X450 | CUM | 1 | 2 | 3.385 | 0.45 | 0.2 | 0.6093
| B66 200X450 | CUM | 1 | 2 | 3.25 | 0.45 | 0.2 | 0.585
| B66 200X450 | CUM | 1 | 2 | 1.7 | 0.45 | 0.2 | 0.306
| B66 200X350 | CUM | 1 | 2 | 1.385 | 0.35 | 0.2 | 0.1939
| B67 200X450 | CUM | 1 | 2 | 3.05 | 0.45 | 0.2 | 0.549
| B67 200X450 | CUM | 1 | 2 | 1.7 | 0.45 | 0.2 | 0.306
| B68 200X350 | CUM | 1 | 1 | 3.17 | 0.35 | 0.2 | 0.2219
| B69 200X450 | CUM | 1 | 0.5 | 5.78 | 0.45 | 0.2 | 0.2601
39.8105
FLAT NO 9
| Bed room 1 | CUM | 1 | 1 | 3.575 | 3.55 | 0.135 | 1.7133
| Bed Room 2 | CUM | 1 | 1 | 3.55 | 3.2 | 0.135 | 1.5336
| Bed Room 3 | CUM | 1 | 1 | 3.145 | 3.05 | 0.125 | 1.199
|  | CUM | 1 | 1 | 0.9 | 0.4 | 0.125 | 0.045
| Service slab | CUM | 1 | 1 | 1.165 | 0.515 | 0.125 | 0.074997
| TOILET 1 | CUM | 1 | 1 | 3.575 | 1.57 | 0.125 | 0.70159
| TOILET 2 | CUM | 1 | 1 | 2.5 | 1.6 | 0.125 | 0.5
| PASSAGE | CUM | 1 | 1 | 2.785 | 1.2 | 0.125 | 0.41775
| Living | CUM | 1 | 1 | 6.365 | 3.72 | 0.15 | 3.5517
|  | CUM | 1 | 1 | 4.115 | 0.385 | 0.15 | 0.23764
| Entry/ Porch | CUM | 1 | 1 | 1.5 | 1.035 | 0.125 | 0.19406
| Kitchen | CUM | 1 | 1 | 2.85 | 2.335 | 0.135 | 0.89839
| Balcony 1 | CUM | 1 | 1 | 6.3 | 2 | 0.1825 | 2.2995
| Balcony 2 | CUM | 1 | 1 | 4.065 | 2 | 0.1825 | 1.4837
| Kitchen Balcony | CUM | 1 | 1 | 1.4 | 2 | 0.1825 | 0.511
|  | CUM | 1 | 1 | 1.185 | 0.435 | 0.2 | 0.1031
15.4644
| FLAT NO 8 | [6 empty] | 0
| B. ROOM 1 | CUM | 1 | 1 | 3.56 | 3.275 | 0.135 | 1.574
| B. ROOM 2 | CUM | 1 | 1 | 3.25 | 2.925 | 0.135 | 1.2833
| B. ROOM 3 | CUM | 1 | 1 | 3.58 | 3.05 | 0.135 | 1.4741
| PASSAGE | CUM | 1 | 1 | 2.925 | 1.7 | 0.125 | 0.62156
| KITCHEN | CUM | 1 | 1 | 3.25 | 2.365 | 0.135 | 1.0376
| LIVING | CUM | 1 | 1 | 5.23 | 3.33 | 0.15 | 2.6124
|  | CUM | 1 | 1 | 3.4 | 0.94 | 0.15 | 0.4794
|  | CUM | 1 | 1 | 2.55 | 1.47 | 0.15 | 0.56227
| DRESSING AREA | CUM | 1 | 1 | 2.41 | 1.43 | 0.125 | 0.43079
| TOILET 1 | CUM | 1 | 1 | 2.225 | 1.495 | 0.125 | 0.4158
| TOILET 2 | CUM | 1 | 1 | 3.385 | 1.425 | 0.125 | 0.60295
| TOILET 3 | CUM | 1 | 1 | 2.41 | 1.54 | 0.125 | 0.46393
| BALCONY 1 | CUM | 1 | 1 | 4.665 | 2 | 0.1825 | 1.7027
| BALCONY 2 | CUM | 1 | 1 | 5.105 | 2 | 0.1825 | 1.8633
| BALCONY 3 | CUM | 1 | 1 | 3.265 | 2 | 0.1825 | 1.1917
16.3159
| FLAT NO 7 | [6 empty] | 0
| B. ROOM 1 | CUM | 1 | 1 | 3.56 | 3.245 | 0.125 | 1.444
| B. ROOM 2 | CUM | 1 | 1 | 3.25 | 2.925 | 0.135 | 1.2833
| PASSAGE | CUM | 1 | 1 | 2.925 | 1.7 | 0.125 | 0.62156
| KITCHEN | CUM | 1 | 1 | 3.25 | 2.365 | 0.135 | 1.0376
| LIVING | CUM | 1 | 1 | 5.23 | 3.33 | 0.15 | 2.6124
|  | CUM | 1 | 1 | 3.4 | 0.94 | 0.15 | 0.4794
|  | CUM | 1 | 1 | 2.55 | 1.47 | 0.15 | 0.56227
| TOILET 1 | CUM | 1 | 1 | 2.225 | 1.495 | 0.125 | 0.4158
| TOILET 2 | CUM | 1 | 1 | 3.385 | 1.425 | 0.125 | 0.60295
| BALCONY 1 | CUM | 1 | 1 | 4.665 | 2 | 0.1825 | 1.7027
| BALCONY 2 | CUM | 1 | 1 | 5.105 | 2 | 0.1825 | 1.8633
12.6254
FLAT NO 10,11,12
| B. ROOM 1 |  | 3 | 1 | 3.86 | 3.25 | 0.135 | 5.0807
| B. ROOM 2 |  | 3 | 1 | 3.86 | 3.335 | 0.135 | 5.2136
| B. ROOM 3 |  | 3 | 1 | 3.55 | 3.265 | 0.125 | 4.3465
| Living |  | 3 | 1 | 6.245 | 3.315 | 0.15 | 9.316
|  |  | 3 | 1 | 3.17 | 1.91 | 0.15 | 2.7246
| KITCHEN |  | 3 | 1 | 3.435 | 2.345 | 0.135 | 3.2623
| TOILET 1 |  | 3 | 1 | 3.86 | 1.44 | 0.125 | 2.0844
| TOILET 2 |  | 3 | 1 | 3.55 | 1.425 | 0.125 | 1.897
| TOILET 3 |  | 3 | 1 | 3.55 | 1.425 | 0.125 | 1.897
| Service slab |  | 3 | 1 | 1.245 | 0.515 | 0.125 | 0.24044
| Service slab |  | 3 | 1 | 0.97 | 0.415 | 0.125 | 0.15096
| BALCONY 1 |  | 3 | 1 | 5.93 | 2 | 0.1825 | 6.4933
| BALCONY 2 |  | 3 | 1 | 3.565 | 2 | 0.1825 | 3.9037
| BALCONY 3 |  | 3 | 1 | 1.55 | 2 | 0.1825 | 1.6973
48.3079
| FLAT 7,8 & 9 LOBBY |  | 1 | 1 | 5.09 | 1.5 | 0.125 | 0.95437
|  |  | 1 | 1 | 3.14 | 0.955 | 0.125 | 0.37484
| LIFT LOBBY |  | 1 | 1 | 3.95 | 1.61 | 0.125 | 0.79494
|  |  | 1 | 1 | 5.635 | 2.44 | 0.125 | 1.7187
| FLAT 10,11,12 LOBBY |  | 1 | 1 | 4.79 | 3.19 | 0.125 | 1.91
|  |  | 1 | 1 | 1.4 | 0.655 | 0.125 | 0.11462
Main s/case (3 No)
| Half landing |  | 1 | 2 | 1.5 | 1.5 | 0.175 | 0.7875
| freight |  | 1 | 2 | 2.409 | 1.5 | 0.175 | 1.2647
| mid freight |  | 1 | 1 | 1.484 | 1.5 | 0.175 | 0.38955
| top landing |  | 1 | 1 | 3.96 | 0.26 | 0.175 | 0.18018
| landing beam 230x450 |  | 1 | 1 | 3.53 | 0.45 | 0.23 | 0.36536 |  |  | 105.34
| Fire s/case (4 No) | [10 empty] | 145.15
| mid & full landing |  | 1 | 2 | 3.2 | 1.5 | 0.175 | 1.68 |  |  |  | 56.7
| freight |  | 1 | 2 | 3.343 | 1.5 | 0.175 | 1.7551
| landing beam 230x450 |  | 1 | 1 | 3.2 | 0.23 | 0.45 | 0.3312
12.621
COLUMN (22-43/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 31 | 1 | 0.3 | 0.6 | 0.45 | 2.511
2 | C4, C5 (300X750) | CUM | 15 | 1 | 0.3 | 0.7 | 0.45 | 1.4175
3 | C6, C11 (300X715) | CUM | 7 | 1 | 0.3 | 0.715 | 0.45 | 0.67568
4 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 0.45 | 0.216
5 | SW 1 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.067275
6 |  | CUM | 1 | 1 | 0.23 | 1.42 | 0.45 | 0.14697
7 | SW 2 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.067275
8 |  | CUM | 1 | 1 | 0.23 | 1.62 | 0.45 | 0.16767
9 | SW 3 (230x1000) | CUM | 1 | 1 | 0.23 | 1 | 0.45 | 0.1035
10 | SW 4 (230x1150) | CUM | 1 | 1 | 0.23 | 1.15 | 0.45 | 0.11903
11 | SW 5 (230x1700) | CUM | 2 | 1 | 0.23 | 1.7 | 0.45 | 0.3519
12 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 0.45 | 0.2453
13 | SW 7 (230x1855) | CUM | 1 | 1 | 0.23 | 1.855 | 0.45 | 0.19199
14 | SW 8 (230x3600) | CUM | 0.5 | 1 | 0.23 | 3.6 | 0.45 | 0.1863
15 | SW 9 (L-SHAPE) | CUM | 3 | 1 | 0.23 | 0.65 | 0.45 | 0.20183
16 |  | CUM | 3 | 1 | 0.23 | 1.62 | 0.45 | 0.50301
17 | SW 10 (230x3445) | CUM | 1 | 1 | 0.23 | 3.445 | 0.45 | 0.35656
18 | SW 11 (230x4065) | CUM | 1 | 1 | 0.23 | 4.065 | 0.45 | 0.42073
19 | SW 12 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.067275
20 |  | CUM | 1 | 1 | 0.23 | 1.305 | 0.45 | 0.13507
21 | SW 13 (200x3445) | CUM | 1 | 1 | 0.2 | 3.445 | 0.45 | 0.31005
8.4619
[5 empty] | Total RMC of 2nd floor ( grid 22to43)Slab And Beam |  |  | 153.607
| 2ND FLOOR LVL SLAB and Beam RCC(1- 22) &(A-Q) | [7 empty] | 11TH RA
| B1 200X500 | CUM | 1 | 1 | 3.025 | 0.5 | 0.2 | 0.3025
| B1 200X500 | CUM | 1 | 1 | 2.8 | 0.5 | 0.2 | 0.28
| B2 200X500 | CUM | 1 | 1 | 3.3 | 0.5 | 0.2 | 0.33
| B3 AT GRID B-C/27-28 | CUM | 1 | 1 | 1.395 | 0.35 | 0.1 | 0.048825
| B3 AT GRID L-M/27-28 | CUM | 1 | 1 | 1.395 | 0.35 | 0.115 | 0.056149
| B3 AT GRID E/32-33 | CUM | 1 | 1 | 1.185 | 0.35 | 0.1 | 0.041475
| B3 AT GRID F/43 | CUM | 1 | 3 | 2.055 | 0.35 | 0.1 | 0.21578
| B3 AT GRID F/39-40 | CUM | 1 | 3 | 1.485 | 0.35 | 0.1 | 0.15593
| B3 AT GRID M & O/39-40 | CUM | 1 | 3 | 2.315 | 0.35 | 0.1 | 0.24307
| B3 AT GRID C,K/25 | CUM | 1 | 2 | 2.315 | 0.35 | 0.1 | 0.16205
| B4 200X350 | CUM | 1 | 2 | 1.395 | 0.35 | 0.2 | 0.1953
| B5 200X450 | CUM | 1 | 1 | 6.875 | 0.45 | 0.2 | 0.61875
| B6 230X350 | CUM | 1 | 1 | 3.16 | 0.35 | 0.23 | 0.25438
| B7 200X450 | CUM | 1 | 1 | 2.7 | 0.45 | 0.2 | 0.243
| B8 200X500 | CUM | 1 | 1 | 2.875 | 0.5 | 0.2 | 0.2875
| B8 200X350 | CUM | 1 | 1 | 2.93 | 0.35 | 0.2 | 0.2051
| B9 200X500 | CUM | 1 | 1 | 4.69 | 0.5 | 0.2 | 0.469
| B10 200X500 | CUM | 1 | 1 | 3.15 | 0.5 | 0.2 | 0.315
| B11 200X450 | CUM | 1 | 1 | 4.69 | 0.45 | 0.2 | 0.4221
| B12 200X450 | CUM | 1 | 1 | 5.76 | 0.45 | 0.2 | 0.5184
| B13 200X350 | CUM | 1 | 1 | 1.6 | 0.35 | 0.2 | 0.112
| B13 200X450 | CUM | 1 | 1 | 4.105 | 0.45 | 0.2 | 0.36945
| B14 200X450 | CUM | 1 | 1 | 1.5 | 0.45 | 0.2 | 0.135
| B14 200X450 | CUM | 1 | 1 | 2.2 | 0.45 | 0.2 | 0.198
| B15 200X500 | CUM | 1 | 1 | 3.115 | 0.5 | 0.2 | 0.3115
| B16 200X350 | CUM | 1 | 3 | 1.02 | 0.35 | 0.2 | 0.2142
| B16 200X500 | CUM | 1 | 3 | 3.35 | 0.5 | 0.2 | 1.005
| B16 200X500 | CUM | 1 | 3 | 3.25 | 0.5 | 0.2 | 0.975
| B17 200X500 | CUM | 1 | 1 | 3.215 | 0.5 | 0.2 | 0.3215
| B18 230X500 | CUM | 1 | 1 | 2.76 | 0.5 | 0.23 | 0.3174
| B19 200X450 | CUM | 1 | 1 | 6.79 | 0.45 | 0.2 | 0.6111
| B20 200X350 | CUM | 1 | 1 | 2.41 | 0.35 | 0.2 | 0.1687
| B21 230X450 | CUM | 1 | 1 | 5.76 | 0.45 | 0.23 | 0.59616
| B22 200x450 | CUM | 1 | 1 | 4.69 | 0.45 | 0.2 | 0.4221
| B23 200X450 | CUM | 1 | 1 | 2.22 | 0.45 | 0.2 | 0.1998
| B24 200X450 | CUM | 1 | 1 | 5.63 | 0.45 | 0.2 | 0.5067
| B25 200X450 | CUM | 1 | 1 | 1.5 | 0.45 | 0.2 | 0.135
| B25 200X500 | CUM | 1 | 1 | 2.085 | 0.5 | 0.2 | 0.2085
| B25 200X450 BESIDE STAIRS | CUM | 1 | 1 | 5.63 | 0.45 | 0.2 | 0.5067
| B26 200X450 | CUM | 1 | 3 | 3.235 | 0.45 | 0.2 | 0.87345
| B26 200X450 | CUM | 1 | 3 | 4.72 | 0.45 | 0.2 | 1.2744
| B27 200X350 | CUM | 1 | 3 | 2.575 | 0.35 | 0.2 | 0.54075
| B27 200X500 | CUM | 1 | 3 | 3.165 | 0.5 | 0.2 | 0.9495
| B28 200X450 | CUM | 1 | 1 | 5.125 | 0.45 | 0.2 | 0.46125
| B29 200X450 | CUM | 1 | 1 | 1.9 | 0.45 | 0.2 | 0.171
| B29 200X450 | CUM | 1 | 1 | 1.9 | 0.45 | 0.2 | 0.171
| B29 200X450 | CUM | 1 | 1 | 1.4 | 0.45 | 0.2 | 0.126
| B30 200X350 | CUM | 1 | 1 | 2.93 | 0.35 | 0.2 | 0.2051
| B30 200X500 | CUM | 1 | 1 | 2.875 | 0.5 | 0.2 | 0.2875
| B30 200X450 | CUM | 1 | 1 | 3.95 | 0.45 | 0.2 | 0.3555
| B31 200X500 | CUM | 1 | 1 | 4.69 | 0.5 | 0.2 | 0.469
| B31 200X500 | CUM | 1 | 1 | 3.15 | 0.5 | 0.2 | 0.315
| B32 230X450 | CUM | 1 | 2 | 1.9 | 0.45 | 0.23 | 0.3933
| B33 200X350 | CUM | 1 | 1 | 5.235 | 0.35 | 0.2 | 0.36645
| B34 230X450 | CUM | 1 | 1 | 5.1 | 0.45 | 0.23 | 0.52785
| B34 230X450 | CUM | 1 | 1 | 5.1 | 0.45 | 0.23 | 0.52785
| B35 200X500 | CUM | 1 | 2 | 3.19 | 0.5 | 0.2 | 0.638
| B36 200X500 | CUM | 1 | 3 | 1.81 | 0.5 | 0.2 | 0.543
| B36 200X500 | CUM | 1 | 3 | 3.55 | 0.5 | 0.2 | 1.065
| B36 230X500 | CUM | 1 | 3 | 0.515 | 0.5 | 0.23 | 0.17767
| B37 200X450 | CUM | 1 | 3 | 3.86 | 0.45 | 0.2 | 1.0422
| B38 200X450 | CUM | 1 | 3 | 3.45 | 0.45 | 0.2 | 0.9315
| B39 200X450 | CUM | 1 | 3 | 2.91 | 0.45 | 0.2 | 0.7857
| B39 230X350 | CUM | 1 | 3 | 3.55 | 0.35 | 0.23 | 0.85732
| B40 200X450 | CUM | 1 | 2 | 3 | 0.45 | 0.2 | 0.54
| B40 200X350 | CUM | 1 | 2 | 2.065 | 0.35 | 0.2 | 0.2891
| B41 200X500 | CUM | 1 | 3 | 3.31 | 0.5 | 0.2 | 0.993
| B42 200X450 | CUM | 1 | 2 | 3 | 0.45 | 0.2 | 0.54
| B43 200X450 | CUM | 1 | 1 | 5.245 | 0.45 | 0.2 | 0.47205
| B44 200X450 | CUM | 1 | 1 | 3 | 0.45 | 0.2 | 0.27
| B44 200X350 | CUM | 1 | 1 | 1.95 | 0.35 | 0.2 | 0.1365
| B45 200X450 | CUM | 1 | 1 | 2.23 | 0.45 | 0.2 | 0.2007
| B46 200X500 | CUM | 1 | 1 | 5.145 | 0.5 | 0.2 | 0.5145
| B47 200X500 | CUM | 1 | 1 | 3.8 | 0.5 | 0.2 | 0.38
| B48 200X350 | CUM | 1 | 1 | 2.95 | 0.35 | 0.2 | 0.2065
| B49 200X450 | CUM | 1 | 1 | 4.55 | 0.45 | 0.2 | 0.4095
| B50 200X500 | CUM | 1 | 1 | 3.05 | 0.5 | 0.2 | 0.305
| B51 200X450 | CUM | 1 | 1 | 2.5 | 0.45 | 0.2 | 0.225
| B52 230X500 | CUM | 1 | 1 | 3.115 | 0.5 | 0.23 | 0.35823
| B53 200X350 | CUM | 1 | 1 | 2.335 | 0.35 | 0.2 | 0.16345
| B54 230X500 | CUM | 1 | 1 | 3.2 | 0.5 | 0.23 | 0.368
| B55 230X450 | CUM | 1 | 1 | 0.35 | 0.45 | 0.23 | 0.036225
| B56 200X450 | CUM | 1 | 1 | 1.96 | 0.45 | 0.2 | 0.1764
| B57 230X450 | CUM | 1 | 1 | 3.2 | 0.45 | 0.23 | 0.3312
| B57 200X450 | CUM | 1 | 1 | 2.335 | 0.45 | 0.2 | 0.21015
| B58 230X500 | CUM | 1 | 1 | 2.54 | 0.5 | 0.23 | 0.2921
| B58 230X450 | CUM | 1 | 1 | 3.43 | 0.45 | 0.23 | 0.35501
| B59 200X500 | CUM | 1 | 1 | 2.225 | 0.5 | 0.2 | 0.2225
| B60 200X450 | CUM | 1 | 1 | 3.14 | 0.45 | 0.2 | 0.2826
| B61 200X450 | CUM | 1 | 1 | 3.43 | 0.45 | 0.2 | 0.3087
| B61 230X450 | CUM | 1 | 1 | 1.99 | 0.45 | 0.23 | 0.20597
| B62 200X500 | CUM | 1 | 1 | 2.225 | 0.5 | 0.2 | 0.2225
| B63 200X450 | CUM | 1 | 2 | 3.06 | 0.45 | 0.2 | 0.5508
| B64 200X350 | CUM | 1 | 2 | 3.05 | 0.35 | 0.2 | 0.427
| B64 200X350 | CUM | 1 | 2 | 0.38 | 0.35 | 0.2 | 0.0532
| B65 200X450 | CUM | 1 | 2 | 3.385 | 0.45 | 0.2 | 0.6093
| B66 200X450 | CUM | 1 | 2 | 3.25 | 0.45 | 0.2 | 0.585
| B66 200X450 | CUM | 1 | 2 | 1.7 | 0.45 | 0.2 | 0.306
| B66 200X350 | CUM | 1 | 2 | 1.385 | 0.35 | 0.2 | 0.1939
| B67 200X450 | CUM | 1 | 2 | 3.05 | 0.45 | 0.2 | 0.549
| B67 200X450 | CUM | 1 | 2 | 1.7 | 0.45 | 0.2 | 0.306
| B68 200X350 | CUM | 1 | 1 | 3.17 | 0.35 | 0.2 | 0.2219
| B69 200X450 | CUM | 1 | 0.5 | 5.78 | 0.45 | 0.2 | 0.2601
| B66 200X450 | CUM | 1 | 1 | 5.78 | 0.45 | 0.2 | 0.5202
| B10 200X450 | CUM | 1 | 1 | 6.3 | 0.45 | 0.2 | 0.567
40.8977
FLAT NO 4
| Bed room 1 | CUM | 1 | 1 | 3.575 | 3.55 | 0.135 | 1.7133
| Bed Room 2 | CUM | 1 | 1 | 3.55 | 3.2 | 0.135 | 1.5336
| Bed Room 3 | CUM | 1 | 1 | 3.145 | 3.05 | 0.125 | 1.199
|  | CUM | 1 | 1 | 0.9 | 0.4 | 0.125 | 0.045
| Service slab | CUM | 1 | 1 | 1.165 | 0.515 | 0.125 | 0.074997
| TOILET 1 | CUM | 1 | 1 | 3.575 | 1.57 | 0.125 | 0.70159
| TOILET 2 | CUM | 1 | 1 | 2.5 | 1.6 | 0.125 | 0.5
| PASSAGE | CUM | 1 | 1 | 2.785 | 1.2 | 0.125 | 0.41775
| Living | CUM | 1 | 1 | 6.365 | 3.72 | 0.15 | 3.5517
|  | CUM | 1 | 1 | 4.115 | 0.385 | 0.15 | 0.23764
| Entry/ Porch | CUM | 1 | 1 | 1.5 | 1.035 | 0.125 | 0.19406
| Kitchen | CUM | 1 | 1 | 2.85 | 2.335 | 0.135 | 0.89839
| Balcony 1 | CUM | 1 | 1 | 6.3 | 2 | 0.1825 | 2.2995
| Balcony 2 | CUM | 1 | 1 | 4.065 | 2 | 0.1825 | 1.4837
| Kitchen Balcony | CUM | 1 | 1 | 1.4 | 2 | 0.1825 | 0.511
|  | CUM | 1 | 1 | 1.185 | 0.435 | 0.2 | 0.1031
15.4644
| FLAT NO 5 | [6 empty] | 0
| B. ROOM 1 | CUM | 1 | 1 | 3.56 | 3.275 | 0.135 | 1.574
| B. ROOM 2 | CUM | 1 | 1 | 3.25 | 2.925 | 0.135 | 1.2833
| B. ROOM 3 | CUM | 1 | 1 | 3.58 | 3.05 | 0.135 | 1.4741
| PASSAGE | CUM | 1 | 1 | 2.925 | 1.7 | 0.125 | 0.62156
| KITCHEN | CUM | 1 | 1 | 3.25 | 2.365 | 0.135 | 1.0376
| LIVING | CUM | 1 | 1 | 5.23 | 3.33 | 0.15 | 2.6124
|  | CUM | 1 | 1 | 3.4 | 0.94 | 0.15 | 0.4794
|  | CUM | 1 | 1 | 2.55 | 1.47 | 0.15 | 0.56227
| DRESSING AREA | CUM | 1 | 1 | 2.41 | 1.43 | 0.125 | 0.43079
| TOILET 1 | CUM | 1 | 1 | 2.225 | 1.495 | 0.125 | 0.4158
| TOILET 2 | CUM | 1 | 1 | 3.385 | 1.425 | 0.125 | 0.60295
| TOILET 3 | CUM | 1 | 1 | 2.41 | 1.54 | 0.125 | 0.46393
| BALCONY 1 | CUM | 1 | 1 | 4.665 | 2 | 0.1825 | 1.7027
| BALCONY 2 | CUM | 1 | 1 | 5.105 | 2 | 0.1825 | 1.8633
| BALCONY 3 | CUM | 1 | 1 | 3.265 | 2 | 0.1825 | 1.1917
16.3159
| FLAT NO 6 | [6 empty] | 0
| B. ROOM 1 | CUM | 1 | 1 | 3.56 | 3.245 | 0.125 | 1.444
| B. ROOM 2 | CUM | 1 | 1 | 3.25 | 2.925 | 0.135 | 1.2833
| PASSAGE | CUM | 1 | 1 | 2.925 | 1.7 | 0.125 | 0.62156
| KITCHEN | CUM | 1 | 1 | 3.25 | 2.365 | 0.135 | 1.0376
| LIVING | CUM | 1 | 1 | 5.23 | 3.33 | 0.15 | 2.6124
|  | CUM | 1 | 1 | 3.4 | 0.94 | 0.15 | 0.4794
|  | CUM | 1 | 1 | 2.55 | 1.47 | 0.15 | 0.56227
| TOILET 1 | CUM | 1 | 1 | 2.225 | 1.495 | 0.125 | 0.4158
| TOILET 2 | CUM | 1 | 1 | 3.385 | 1.425 | 0.125 | 0.60295
| BALCONY 1 | CUM | 1 | 1 | 4.665 | 2 | 0.1825 | 1.7027
| BALCONY 2 | CUM | 1 | 1 | 5.105 | 2 | 0.1825 | 1.8633
| BEDROOM | CUM | 1 | 2 | 3.58 | 3.05 | 0.135 | 2.9481
| BALCONY 3 | CUM | 1 | 2 | 3.05 | 2 | 0.1825 | 2.2265
17.8001
FLAT NO 1,2,3
| B. ROOM 1 |  | 3 | 1 | 3.86 | 3.25 | 0.135 | 5.0807
| B. ROOM 2 |  | 3 | 1 | 3.86 | 3.335 | 0.135 | 5.2136
| B. ROOM 3 |  | 3 | 1 | 3.55 | 3.265 | 0.125 | 4.3465
| Living |  | 3 | 1 | 6.245 | 3.315 | 0.15 | 9.316
|  |  | 3 | 1 | 3.17 | 1.91 | 0.15 | 2.7246
| KITCHEN |  | 3 | 1 | 3.435 | 2.345 | 0.135 | 3.2623
| TOILET 1 |  | 3 | 1 | 3.86 | 1.44 | 0.125 | 2.0844
| TOILET 2 |  | 3 | 1 | 3.55 | 1.425 | 0.125 | 1.897
| TOILET 3 |  | 3 | 1 | 3.55 | 1.425 | 0.125 | 1.897
| Service slab |  | 3 | 1 | 1.245 | 0.515 | 0.125 | 0.24044
| Service slab |  | 3 | 1 | 0.97 | 0.415 | 0.125 | 0.15096
| BALCONY 1 |  | 3 | 1 | 5.93 | 2 | 0.1825 | 6.4933
| BALCONY 2 |  | 3 | 1 | 3.565 | 2 | 0.1825 | 3.9037
| BALCONY 3 |  | 3 | 1 | 1.55 | 2 | 0.1825 | 1.6973
48.3079
| FLAT 6,5 & 4 LOBBY |  | 1 | 1 | 5.09 | 1.5 | 0.125 | 0.95437
|  |  | 1 | 1 | 3.14 | 0.955 | 0.125 | 0.37484
| LIFT LOBBY |  | 1 | 1 | 3.95 | 1.61 | 0.125 | 0.79494
|  |  | 1 | 1 | 5.635 | 2.44 | 0.125 | 1.7187
| FLAT 1,2,3 LOBBY |  | 1 | 1 | 4.79 | 3.19 | 0.125 | 1.91
|  |  | 1 | 1 | 1.4 | 0.655 | 0.125 | 0.11462
Main s/case (2 No)
| Half landing |  | 1 | 2 | 1.5 | 1.5 | 0.175 | 0.7875
| freight |  | 1 | 2 | 2.409 | 1.5 | 0.175 | 1.2647
| mid freight |  | 1 | 1 | 1.484 | 1.5 | 0.175 | 0.38955
| top landing |  | 1 | 1 | 3.96 | 0.26 | 0.175 | 0.18018
| landing beam 230x450 |  | 1 | 1 | 3.53 | 0.45 | 0.23 | 0.36536 |  |  | 105.34
| Fire s/case (1 No) | [10 empty] | 145.15
| mid & full landing |  | 1 | 2 | 3.2 | 1.5 | 0.175 | 1.68 |  |  |  | 56.7
| freight |  | 1 | 2 | 3.343 | 1.5 | 0.175 | 1.7551
| landing beam 230x450 |  | 1 | 1 | 3.2 | 0.23 | 0.45 | 0.3312
12.621
COLUMN JUNCTION (1-22/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 31 | 1 | 0.3 | 0.6 | 0.45 | 2.511
2 | C4, C5 (300X750) | CUM | 15 | 1 | 0.3 | 0.7 | 0.45 | 1.4175
3 | C6, C11 (300X715) | CUM | 7 | 1 | 0.3 | 0.715 | 0.45 | 0.67568
4 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 0.45 | 0.216
5 | SW 1 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.067275
6 |  | CUM | 1 | 1 | 0.23 | 1.42 | 0.45 | 0.14697
7 | SW 2 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.067275
8 |  | CUM | 1 | 1 | 0.23 | 1.62 | 0.45 | 0.16767
9 | SW 3 (230x1000) | CUM | 1 | 1 | 0.23 | 1 | 0.45 | 0.1035
10 | SW 4 (230x1150) | CUM | 1 | 1 | 0.23 | 1.15 | 0.45 | 0.11903
11 | SW 5 (230x1700) | CUM | 2 | 1 | 0.23 | 1.7 | 0.45 | 0.3519
12 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 0.45 | 0.2453
13 | SW 7 (230x1855) | CUM | 1 | 1 | 0.23 | 1.855 | 0.45 | 0.19199
14 | SW 8 (230x3600) | CUM | 0.5 | 1 | 0.23 | 3.6 | 0.45 | 0.1863
15 | SW 9 (L-SHAPE) | CUM | 3 | 1 | 0.23 | 0.65 | 0.45 | 0.20183
16 |  | CUM | 3 | 1 | 0.23 | 1.62 | 0.45 | 0.50301
17 | SW 10 (230x3445) | CUM | 1 | 1 | 0.23 | 3.445 | 0.45 | 0.35656
18 | SW 11 (230x4065) | CUM | 1 | 1 | 0.23 | 4.065 | 0.45 | 0.42073
19 | SW 12 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.067275
20 |  | CUM | 1 | 1 | 0.23 | 1.305 | 0.45 | 0.13507
21 | SW 13 (200x3445) | CUM | 1 | 1 | 0.2 | 3.445 | 0.45 | 0.31005
8.4619
[5 empty] | Total RMC of 2nd floor ( grid 22to43)Slab And Beam |  |  | 159.8688

## SHUTT. WORK SUMMARY
TOWER-E CENTERING & SHUTTERING WORK SUMMARY
|  |  | QTY | [9 empty] | TOTAL
3 | CENTRING AND SHUTTERING |  | 3rd RA | 4th RA | 5th RA | 6th RA | 7th RA | 8th RA | 9th RA | 10th RA | 11th RA
Providing and fixing plywood or steel plate shuttering and centring for structural concrete work in locations called for including strutting, propping, bracing, bolting, wedging, casing, striking, removal etc. complete for any size, section, thickness. Props shall consist of well designed steel pipes adequately braced (wooden ballies as props shall not be permitted). The item to include centering and shuttering at all heights and levels. Allow for forming grooves, drip course, chamfers, cut-outs, openings etc. where called for and for dressing with approved shuttering oil to prevent adhesion. Unexposed concrete surfaces subsequently left untreated (in the condition obtained on removal of form work) shall not constitute exposed concrete work and shall be measured under this item only Irregular shapes with sides (like circular, semi-circular, oval etc.) which may not be perpendicular to each other for shapes not conforming to rectangle or square, and circular shuttering shall not be paid separately. Joints of soffits of the slab shall be made clean after concreting and de-shuttering. (quoted rate to include all staging upto 3.50 mtr height). Note:- Contractor shall take necessary precautions such as watertight shuttering. This is inclusive of RCC members, leaving shuttering & centring for pour strip, slab in slope, RCC members in curved (in plan), etc., nothing is payable extra on this account.
3.1.1. | Foundation, column footings, raft slab, raft beams, plinth beam, lift pits, sump pits, pedestals / bases of column, column up to plinth, swimming pool, Retaining wall foundations, grade slab etc. | SQM | QTY 3rd RA: 93.6125; QTY 4th RA: 82.707; QTY 5th RA: 619.2036; QTY 7th RA: 849.9743 |  | 1645.4974
3.1.2. | Suspended floors, roofs, balconies, shelves/ counters, stair waist slabs, folded plate stairs and landings, swimming pool slab, lintel and floor beams, landing beams, girders (deep beams), RCC bands, swimming pool beam, cantilever projections, coping, cills, slab of tank etc at all levels.
3.1.2.1. | Stilt Floor level to 7th Floor level | SQM | QTY 8th RA: 1195.8149; QTY 9th RA: 1195.8149; QTY 10th RA: 1195.8149; QTY 11th RA: 1349.0173 |  | 4936.4622
3.1.2.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | [10 empty] | 0
3.1.2..3 | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | SQM | [10 empty] | 0
3.2. | Columns, Wall, pillars, piers, abutments, posts and struts, offset and projection of columns, water tank walls, lift walls, Retaining Wall, swimming pool, Parapets, planters, vertical projection of pergolas, wall and ramp walls etc. at all levels.
3.2.1. | Stilt Floor level to 7th Floor level | SQM | QTY 7th RA: 246.825; QTY 8th RA: 751.279; QTY 10th RA: 949; QTY 11th RA: 474.5 |  | 2421.604
3.2.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | [10 empty] | 0
3.2.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | SQM | [10 empty] | 0
3.3. | Extra for additional height in centring, shuttering where ever required with adequate bracing, propping etc. including cost of de-shuttering and decentring at all levels, over and above height of 3.50 mtr (Plan area to be measured and shall be paid proportionately on actual height) – for every 1.0 mtr. height | SQM | [10 empty] | 0
|  |  | 93.6125 | 82.707 | 619.2036 | 0 | 1096.7993 | 1947.0939 | 1195.8149 | 2144.8149 | 1823.5173 | TOTAL | 9003.5635

## SHUTTERING WORK MB
COMPANY- OMAXE PANCHAM REALCON PVT LTD
PROJECT- TOWER-E
LOCATION- NAINI, PRAYAGRAJ
MB SHEET- SHUTTERING WORK
S.NO. | DESCRIPTION | UNIT | NOS | NOS | MEASUREMENT |  |  | QTY. | REMARKS
[5 empty] | L | B | H/T
PCC SHUTTERING
1 | GRID (26'/Q') | SQM | 1 | 1 | 0.7 |  | 0.1 | 0.07 |  | 3rd RA
2 | GRID (26'-43'/Q') | SQM | 1 | 1 | 26.92 |  | 0.1 | 2.692
3 | GRID (43'/E'-Q') | SQM | 1 | 1 | 21.65 |  | 0.1 | 2.165
4 | GRID (38'-43'/E') | SQM | 1 | 1 | 11.09 |  | 0.1 | 1.109
5 | GRID (38'/A-E') | SQM | 1 | 1 | 10.285 |  | 0.1 | 1.0285
6 | GRID (30-38'/A) | SQM | 1 | 1 | 8.875 |  | 0.1 | 0.8875
7 | GRID (30/A-A') | SQM | 1 | 1 | 1.5 |  | 0.1 | 0.15
8 | GRID (27'-30/A') | SQM | 1 | 1 | 3.95 |  | 0.1 | 0.395
9 | GRID (27'/A'-B) | SQM | 1 | 1 | 0.815 |  | 0.1 | 0.0815
10 | GRID (26'-27'/B) | SQM | 1 | 1 | 1.695 |  | 0.1 | 0.1695
11 | GRID (26'/B-B') | SQM | 1 | 1 | 1.405 |  | 0.1 | 0.1405
12 | GRID (22'-26'/B') | SQM | 1 | 1 | 2.285 |  | 0.1 | 0.2285 | -9mtr as per JMR
RAFT SHUTTERING
1 | GRID (22'-26'/M') | SQM | 1 | 1 | 11.005 |  | 0.55 | 6.0528
2 | GRID (26/M'-Q) | SQM | 1 | 1 | 12.415 |  | 0.55 | 6.8282
3 | GRID (26'-43'/Q') | SQM | 1 | 1 | 26.92 |  | 0.55 | 14.806
4 | GRID (43'/E'-Q') | SQM | 1 | 1 | 21.65 |  | 0.55 | 11.9075
5 | GRID (38'-43'/E') | SQM | 1 | 1 | 11.09 |  | 0.55 | 6.0995
6 | GRID (38'/A-E') | SQM | 1 | 1 | 10.285 |  | 0.55 | 5.6568
7 | GRID (30-38'/A) | SQM | 1 | 1 | 8.875 |  | 0.55 | 4.8813
8 | GRID (30/A-A') | SQM | 1 | 1 | 1.5 |  | 0.55 | 0.825
9 | GRID (27'-30/A') | SQM | 1 | 1 | 3.95 |  | 0.55 | 2.1725
10 | GRID (27'/A'-B) | SQM | 1 | 1 | 0.815 |  | 0.55 | 0.44825
11 | GRID (26'-27'/B) | SQM | 1 | 1 | 1.695 |  | 0.55 | 0.93225
12 | GRID (26'/B-B') | SQM | 1 | 1 | 1.405 |  | 0.55 | 0.77275
13 | GRID (22'-26'/B') | SQM | 1 | 1 | 11.285 |  | 0.55 | 6.2068
14 | GRID (22'-26'/B') | SQM | 1 | 1 | 15.8 |  | 1.07 | 16.906
[7 empty] | TOTAL | 93.6125
PCC SHUTTERING
1 | GRID (5'-20/A-C') (DETAILS IN JMR) | SQM | 1 | 1 | 1.5 |  | 0.1 | 0.15 |  | 4th RA
2 |  | SQM | 1 | 1 | 8.875 |  | 0.1 | 0.8875
3 |  | SQM | 1 | 1 | 1.5 |  | 0.1 | 0.15
4 |  | SQM | 1 | 1 | 3.95 |  | 0.1 | 0.395
5 |  | SQM | 1 | 1 | 0.815 |  | 0.1 | 0.0815
6 |  | SQM | 1 | 1 | 1.695 |  | 0.1 | 0.1695
7 |  | SQM | 1 | 1 | 1.405 |  | 0.1 | 0.1405
8 |  | SQM | 1 | 1 | 1.98 |  | 0.1 | 0.198
9 |  | SQM | 1 | 1 | 1 |  | 0.1 | 0.1
10 | GRID (1-18/M'-Q') (DETAILS IN JMR) | SQM | 1 | 1 | 11.03 |  | 0.1 | 1.103
11 |  | SQM | 1 | 1 | 8.67 |  | 0.1 | 0.867
12 |  | SQM | 1 | 1 | 0.515 |  | 0.1 | 0.0515
13 |  | SQM | 1 | 1 | 8.78 |  | 0.1 | 0.878
14 |  | SQM | 1 | 1 | 0.515 |  | 0.1 | 0.0515
15 |  | SQM | 1 | 1 | 9.72 |  | 0.1 | 0.972
16 |  | SQM | 1 | 1 | 3.27 |  | 0.1 | 0.327
RAFT SHUTTERING
1 | GRID (17'-22'/M') | SQM | 1 | 1 | 14.275 |  | 0.55 | 7.8513
2 | GRID (17'/M'-Q) | SQM | 1 | 1 | 12.415 |  | 0.55 | 6.8282
3 | GRID (1-17'/Q') | SQM | 1 | 1 | 26.92 |  | 0.55 | 14.806
4 | GRID (1-5'/E') | SQM | 1 | 1 | 11.09 |  | 0.55 | 6.0995
5 | GRID (5'/A-E') | SQM | 1 | 1 | 10.285 |  | 0.55 | 5.6568
6 | GRID (5'-14'/A) | SQM | 1 | 1 | 8.875 |  | 0.55 | 4.8813
7 | GRID (14'/A-A') | SQM | 1 | 1 | 1.5 |  | 0.55 | 0.825
8 | GRID (14'-16'/A') | SQM | 1 | 1 | 3.95 |  | 0.55 | 2.1725
9 | GRID (16'/A'-B) | SQM | 1 | 1 | 0.815 |  | 0.55 | 0.44825
10 | GRID (16'-17'/B) | SQM | 1 | 1 | 1.695 |  | 0.55 | 0.93225
11 | GRID (17'/B-B') | SQM | 1 | 1 | 1.405 |  | 0.55 | 0.77275
12 | GRID (17'-22'/B') | SQM | 1 | 1 | 14.555 |  | 0.55 | 8.0053
13 | GRID (22'-26'/B') | SQM | 1 | 1 | 15.8 |  | 1.07 | 16.906
[7 empty] | TOTAL | 82.707
COMPENSATORY STRIP
1 | GRID (22-23/B'-L') | SQM | 1 | 2 |  | 0.9 | 0.85 | 1.53 |  | 5th RA
PADESTIAL GRID (1-43/A-Q)
1 | C1, C2, C3, C8 (300X600) | SQM | 46 | 1 | 0.3 | 0.6 | 1.48 | 122.544
2 | C1 (300X600) | SQM | 6 | 1 | 0.3 | 0.6 | 1.68 | 18.144
3 | C2 (300X600) | SQM | 6 | 1 | 0.3 | 0.6 | 1.68 | 18.144
4 | C3 (300X600) | SQM | 2 | 1 | 0.3 | 0.6 | 1.68 | 6.048
5 | C3 (300X600) | SQM | 2 | 1 | 0.3 | 0.6 | 1.68 | 6.048
6 | C4, C5 (300X750) | SQM | 24 | 1 | 0.3 | 0.7 | 1.48 | 71.04
7 | C4 (300X750) | SQM | 4 | 1 | 0.3 | 0.7 | 1.68 | 13.44
8 | C5 (300X750) | SQM | 2 | 1 | 0.3 | 0.7 | 1.68 | 6.72
9 | C6 (300X715) | SQM | 14 | 1 | 0.3 | 0.715 | 1.48 | 42.0616
10 | C7 (300X800) | SQM | 2 | 1 | 0.3 | 0.8 | 1.48 | 6.512
11 | C7 (300X800) | SQM | 2 | 1 | 0.3 | 0.8 | 1.68 | 7.392
12 | SW 1 (L-SHAPE) | SQM | 2 | 1 | 0.23 | 0.65 | 1.48 | 5.2096
13 |  | SQM | 2 | 1 | 0 | 1.42 | 1.48 | 8.4064
14 | SW 2 (L-SHAPE) | SQM | 2 | 1 | 0.23 | 0.65 | 1.48 | 5.2096
15 |  | SQM | 2 | 1 | 0 | 1.62 | 1.48 | 9.5904
16 | SW 3 (230x1000) | SQM | 2 | 1 | 0.23 | 1 | 1.48 | 7.2816
17 | SW 4 (230x1150) | SQM | 2 | 1 | 0.23 | 1.15 | 1.48 | 8.1696
18 | SW 5 (230x1700) | SQM | 4 | 1 | 0.23 | 1.7 | 1.68 | 25.9392
19 | SW 6 (230x1185) | SQM | 2 | 1 | 0.23 | 1.185 | 1.48 | 8.3768
20 | SW 6 (230x1185) | SQM | 2 | 1 | 0.23 | 1.185 | 1.68 | 9.5088
21 | SW 7 (230x1855) | SQM | 2 | 1 | 0.23 | 1.855 | 1.48 | 12.3432
22 | SW 8 (230x3600) | SQM | 1 | 1 | 0.23 | 3.6 | 1.48 | 11.3368
23 | SW 9 (L-SHAPE) | SQM | 6 | 1 | 0.23 | 0.65 | 1.48 | 15.6288
24 |  | SQM | 6 | 1 | 0 | 1.62 | 1.48 | 28.7712
25 | SW 10 (230x3445) | SQM | 2 | 1 | 0.23 | 3.445 | 1.68 | 24.696
26 | SW 11 (230x4065) | SQM | 2 | 1 | 0.23 | 4.065 | 1.68 | 28.8624
27 | SW 12 (L-SHAPE) | SQM | 2 | 1 | 0.23 | 0.65 | 1.68 | 5.9136
28 |  | SQM | 2 | 1 | 0 | 1.305 | 1.68 | 8.7696
29 | SW 13 (200x3445) | SQM | 2 | 1 | 0.2 | 3.445 | 1.68 | 24.4944
30 | LIFT WALL | SQM | 8 | 1 | 0 | 1.9 | 1.68 | 51.072
[7 empty] | TOTAL | 619.2036
PLINTH BEAM (1-43/A-Q)
| PB1 | SQM | 4 |  | 3.025 |  | 0.335 | 4.0535 |  | 7th RA
|  | SQM | 4 |  | 2.8 |  | 0.335 | 3.752
| BOTTOM | SQM | 2 |  | 3.025 |  | 0.2 | 1.21
|  | SQM | 2 |  | 2.8 |  | 0.2 | 1.12
| PB2 | SQM | 4 |  | 3.3 |  | 0.335 | 4.422
| BOTTOM | SQM | 2 |  | 3.3 |  | 0.2 | 1.32
| PB3 | SQM | 8 |  | 1.395 |  | 0.335 | 3.7386
| BOTTOM | SQM | 4 |  | 1.395 |  | 0.1 | 0.558
| PB3 | SQM | 12 |  | 1.4 |  | 0.335 | 5.628
| BOTTOM | SQM | 6 |  | 1.4 |  | 0.1 | 0.84
| PB3 | SQM | 4 |  | 1.2 |  | 0.335 | 1.608
| BOTTOM | SQM | 2 |  | 1.2 |  | 0.1 | 0.24
| PB3 | SQM | 12 |  | 1.55 |  | 0.335 | 6.231
| BOTTOM | SQM | 6 |  | 1.55 |  | 0.1 | 0.93
| PB3 | SQM | 12 |  | 0.97 |  | 0.335 | 3.8994
| BOTTOM | SQM | 6 |  | 0.97 |  | 0.1 | 0.582
| PB4 | SQM | 4 |  | 1.395 |  | 0.335 | 1.8693
| BOTTOM | SQM | 6 |  | 1.395 |  | 0.2 | 1.674
| PB5 | SQM | 4 |  | 3.1 |  | 0.335 | 4.154
| BOTTOM | SQM | 2 |  | 3.1 |  | 0.2 | 1.24
| PB6 | SQM | 1 |  | 16.51 |  | 0.335 | 5.5309
| BOTTOM | SQM | 1 |  | 16.51 |  | 0.2 | 3.302
| PB7 | SQM | 4 |  | 2.875 |  | 0.335 | 3.8525
| BOTTOM | SQM | 2 |  | 2.875 |  | 0.2 | 1.15
| PB7 | SQM | 4 |  | 2.93 |  | 0.335 | 3.9262
| BOTTOM | SQM | 2 |  | 2.93 |  | 0.2 | 1.172
| PB8 | SQM | 4 |  | 3.16 |  | 0.335 | 4.2344
| BOTTOM | SQM | 2 |  | 3.16 |  | 0.2 | 1.264
| PB9 | SQM | 4 |  | 5.635 |  | 0.335 | 7.5509
| BOTTOM | SQM | 2 |  | 5.635 |  | 0.2 | 2.254
| PB10 | SQM | 4 |  | 4.69 |  | 0.335 | 6.2846
| BOTTOM | SQM | 2 |  | 4.69 |  | 0.2 | 1.876
| PB11 | SQM | 4 |  | 5.76 |  | 0.335 | 7.7184
| BOTTOM | SQM | 2 |  | 5.76 |  | 0.2 | 2.304
| PB12 | SQM | 4 |  | 2.22 |  | 0.335 | 2.9748
| BOTTOM | SQM | 2 |  | 2.22 |  | 0.2 | 0.888
| PB13 | SQM | 4 |  | 3.115 |  | 0.335 | 4.1741
| BOTTOM | SQM | 2 |  | 3.115 |  | 0.2 | 1.246
| PB14 | SQM | 12 |  | 7.605 |  | 0.335 | 30.5721
| BOTTOM | SQM | 6 |  | 7.605 |  | 0.2 | 9.126
| PB15 | SQM | 4 |  | 3.215 |  | 0.335 | 4.3081
| BOTTOM | SQM | 2 |  | 3.215 |  | 0.2 | 1.286
| PB16 | SQM | 4 |  | 2.76 |  | 0.335 | 3.6984
| BOTTOM | SQM | 2 |  | 2.76 |  | 0.23 | 1.2696
| PB17 | SQM | 4 |  | 15.345 |  | 0.335 | 20.5623
| BOTTOM | SQM | 2 |  | 15.345 |  | 0.23 | 7.0587
| PB18 | SQM | 4 |  | 8.02 |  | 0.335 | 10.7468
| BOTTOM | SQM | 2 |  | 8.02 |  | 0.2 | 3.208
| PB19 | SQM | 4 |  | 5.72 |  | 0.335 | 7.6648
| BOTTOM | SQM | 2 |  | 5.72 |  | 0.2 | 2.288
| PB20 | SQM | 4 |  | 7.77 |  | 0.335 | 10.4118
| BOTTOM | SQM | 2 |  | 7.77 |  | 0.2 | 3.108
| PB21 | SQM | 12 |  | 7.955 |  | 0.335 | 31.9791
| BOTTOM | SQM | 6 |  | 7.955 |  | 0.2 | 9.546
| PB22 | SQM | 12 |  | 5.745 |  | 0.335 | 23.0949
| BOTTOM | SQM | 6 |  | 5.745 |  | 0.2 | 6.894
| PB23 | SQM | 4 |  | 5.125 |  | 0.335 | 6.8675
| BOTTOM | SQM | 2 |  | 5.125 |  | 0.2 | 2.05
| PB24 | SQM | 4 |  | 1.4 |  | 0.335 | 1.876
| BOTTOM | SQM | 2 |  | 1.4 |  | 0.23 | 0.644
| PB25 | SQM | 4 |  | 6.825 |  | 0.335 | 9.1455
| BOTTOM | SQM | 2 |  | 6.825 |  | 0.2 | 2.73
| PB25 | SQM | 4 |  | 2.93 |  | 0.335 | 3.9262
| BOTTOM | SQM | 2 |  | 2.93 |  | 0.23 | 1.3478
| PB26 | SQM | 2 |  | 16.51 |  | 0.335 | 11.0617
| BOTTOM | SQM | 1 |  | 16.51 |  | 0.23 | 3.7973
| PB27 | SQM | 4 |  | 3.53 |  | 0.335 | 4.7302
| BOTTOM | SQM | 2 |  | 3.53 |  | 0.23 | 1.6238
| PB28 | SQM | 4 |  | 3.03 |  | 0.335 | 4.0602
| BOTTOM | SQM | 2 |  | 3.03 |  | 0.2 | 1.212
| PB29 | SQM | 4 |  | 10.2 |  | 0.335 | 13.668
| BOTTOM | SQM | 2 |  | 10.2 |  | 0.2 | 4.08
| PB30 | SQM | 4 |  | 6.38 |  | 0.335 | 8.5492
| BOTTOM | SQM | 2 |  | 6.38 |  | 0.2 | 2.552
| PB31 | SQM | 12 |  | 5.36 |  | 0.335 | 21.5472
| BOTTOM | SQM | 6 |  | 5.36 |  | 0.2 | 6.432
| PB32 | SQM | 40 |  | 0.515 |  | 0.335 | 6.901
| BOTTOM | SQM | 20 |  | 0.515 |  | 0.1 | 1.03
| PB33 | SQM | 12 |  | 3.45 |  | 0.335 | 13.869
| BOTTOM | SQM | 6 |  | 3.45 |  | 0.2 | 4.14
| PB34 | SQM | 12 |  | 2.91 |  | 0.335 | 11.6982
| BOTTOM | SQM | 6 |  | 2.91 |  | 0.2 | 3.492
| PB35 | SQM | 4 |  | 6.38 |  | 0.335 | 8.5492
| BOTTOM | SQM | 2 |  | 6.38 |  | 0.2 | 2.552
| PB36 | SQM | 12 |  | 3.31 |  | 0.335 | 13.3062
| BOTTOM | SQM | 6 |  | 3.31 |  | 0.2 | 3.972
| PB37 | SQM | 8 |  | 2.195 |  | 0.335 | 5.8826
| BOTTOM | SQM | 4 |  | 2.195 |  | 0.2 | 1.756
| PB38 | SQM | 4 |  | 5.245 |  | 0.335 | 7.0283
| BOTTOM | SQM | 2 |  | 5.245 |  | 0.2 | 2.098
| PB39 | SQM | 4 |  | 2.23 |  | 0.335 | 2.9882
| BOTTOM | SQM | 2 |  | 2.23 |  | 0.2 | 0.892
| PB40 | SQM | 4 |  | 4.9 |  | 0.335 | 6.566
| BOTTOM | SQM | 2 |  | 4.9 |  | 0.2 | 1.96
| PB41 | SQM | 4 |  | 5.145 |  | 0.335 | 6.8943
| BOTTOM | SQM | 2 |  | 5.145 |  | 0.2 | 2.058
| PB42 | SQM | 4 |  | 3.2 |  | 0.335 | 4.288
| BOTTOM | SQM | 2 |  | 3.2 |  | 0.23 | 1.472
| PB43 | SQM | 4 |  | 2.95 |  | 0.335 | 3.953
| BOTTOM | SQM | 2 |  | 2.95 |  | 0.2 | 1.18
| PB44 | SQM | 4 |  | 3.8 |  | 0.335 | 5.092
| BOTTOM | SQM | 2 |  | 3.8 |  | 0.2 | 1.52
| PB45 | SQM | 4 |  | 4.55 |  | 0.335 | 6.097
| BOTTOM | SQM | 2 |  | 4.55 |  | 0.2 | 1.82
| PB46 | SQM | 4 |  | 3.05 |  | 0.335 | 4.087
| BOTTOM | SQM | 2 |  | 3.05 |  | 0.2 | 1.22
| PB47 | SQM | 4 |  | 3.115 |  | 0.335 | 4.1741
| BOTTOM | SQM | 2 |  | 3.115 |  | 0.2 | 1.246
| PB48 | SQM | 4 |  | 1.41 |  | 0.335 | 1.8894
| BOTTOM | SQM | 2 |  | 1.41 |  | 0.2 | 0.564
| PB49 | SQM | 4 |  | 0.35 |  | 0.335 | 0.469
| BOTTOM | SQM | 2 |  | 0.35 |  | 0.2 | 0.14
| PB50 | SQM | 4 |  | 2.37 |  | 0.335 | 3.1758
| BOTTOM | SQM | 2 |  | 2.37 |  | 0.2 | 0.948
| PB51 | SQM | 4 |  | 3.2 |  | 0.335 | 4.288
| BOTTOM | SQM | 2 |  | 3.2 |  | 0.2 | 1.28
| PB52 | SQM | 4 |  | 14.53 |  | 0.335 | 19.4702
| BOTTOM | SQM | 2 |  | 14.53 |  | 0.2 | 5.812
| PB53 | SQM | 8 |  | 2.225 |  | 0.335 | 5.963
| BOTTOM | SQM | 4 |  | 2.225 |  | 0.2 | 1.78
| PB54 | SQM | 4 |  | 3.06 |  | 0.335 | 4.1004
| BOTTOM | SQM | 2 |  | 3.06 |  | 0.2 | 1.224
| PB55 | SQM | 4 |  | 3.06 |  | 0.335 | 4.1004
| BOTTOM | SQM | 2 |  | 3.06 |  | 0.2 | 1.224
| PB56 | SQM | 4 |  | 1.6 |  | 0.335 | 2.144
| BOTTOM | SQM | 2 |  | 1.6 |  | 0.2 | 0.64
| PB57 | SQM | 8 |  | 3.05 |  | 0.335 | 8.174
| BOTTOM | SQM | 4 |  | 3.05 |  | 0.2 | 2.44
| PB58 | SQM | 4 |  | 6.54 |  | 0.335 | 8.7636
| BOTTOM | SQM | 2 |  | 6.54 |  | 0.2 | 2.616
| PB59 | SQM | 4 |  | 6.17 |  | 0.335 | 8.2678
| BOTTOM | SQM | 2 |  | 6.17 |  | 0.2 | 2.468
| PB60 | SQM | 8 |  | 3.05 |  | 0.335 | 8.174
| BOTTOM | SQM | 4 |  | 3.05 |  | 0.2 | 2.44
| PB60 | SQM | 8 |  | 1.7 |  | 0.335 | 4.556
| BOTTOM | SQM | 4 |  | 1.7 |  | 0.2 | 1.36
| PB61 | SQM | 4 |  | 3.17 |  | 0.335 | 4.2478
| BOTTOM | SQM | 2 |  | 3.17 |  | 0.2 | 1.268
COLUMN JUNCTION (1-43/A-Q) AT PLINTH BEAM LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | SQM | 62 | 1 | 0.3 | 0.6 | 0.45 | 50.22
2 | C4, C5 (300X750) | SQM | 30 | 1 | 0.3 | 0.7 | 0.45 | 27
3 | C6, C11 (300X715) | SQM | 14 | 1 | 0.3 | 0.715 | 0.45 | 12.789
4 | C7 (300X800) | SQM | 4 | 1 | 0.3 | 0.8 | 0.45 | 3.96
5 | SW 1 (L-SHAPE) | SQM | 2 | 1 | 0.23 | 0.65 | 0.45 | 1.584
6 |  | SQM | 2 | 1 | 0.23 | 1.42 | 0.45 | 2.97
7 | SW 2 (L-SHAPE) | SQM | 2 | 1 | 0.23 | 0.65 | 0.45 | 1.584
8 |  | SQM | 2 | 1 | 0.23 | 1.62 | 0.45 | 3.33
9 | SW 3 (230x1000) | SQM | 2 | 1 | 0.23 | 1 | 0.45 | 2.214
10 | SW 4 (230x1150) | SQM | 2 | 1 | 0.23 | 1.15 | 0.45 | 2.484
11 | SW 5 (230x1700) | SQM | 4 | 1 | 0.23 | 1.7 | 0.45 | 6.948
12 | SW 6 (230x1185) | SQM | 4 | 1 | 0.23 | 1.185 | 0.45 | 5.094
13 | SW 7 (230x1855) | SQM | 2 | 1 | 0.23 | 1.855 | 0.45 | 3.753
14 | SW 8 (230x3600) | SQM | 1 | 1 | 0.23 | 3.6 | 0.45 | 3.447
15 | SW 9 (L-SHAPE) | SQM | 6 | 1 | 0.23 | 0.65 | 0.45 | 4.752
16 |  | SQM | 6 | 1 | 0.23 | 1.62 | 0.45 | 9.99
17 | SW 10 (230x3445) | SQM | 2 | 1 | 0.23 | 3.445 | 0.45 | 6.615
18 | SW 11 (230x4065) | SQM | 2 | 1 | 0.23 | 4.065 | 0.45 | 7.731
19 | SW 12 (L-SHAPE) | SQM | 2 | 1 | 0.23 | 0.65 | 0.45 | 1.584
20 |  | SQM | 2 | 1 | 0.23 | 1.305 | 0.45 | 2.763
21 | SW 13 (200x3445) | SQM | 2 | 1 | 0.2 | 3.445 | 0.45 | 6.561
22 | LIFT WALL | SQM | 8 | 1 | 0.23 | 1.9 | 0.45 | 15.336
[7 empty] | TOTAL | 849.9743
COLUMN (22-43/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | SQM | 31 | 0.5 | 0.3 | 0.6 | 2.5 | 69.75
2 | C4, C5 (300X750) | SQM | 15 | 0.5 | 0.3 | 0.7 | 2.5 | 37.5
3 | C6, C11 (300X715) | SQM | 7 | 0.5 | 0.3 | 0.715 | 2.5 | 17.7625
4 | C7 (300X800) | SQM | 2 | 0.5 | 0.3 | 0.8 | 2.5 | 5.5
5 | SW 1 (L-SHAPE) | SQM | 1 | 0.5 | 0.23 | 0.65 | 2.5 | 2.2
6 |  | SQM | 1 | 0.5 | 0.23 | 1.42 | 2.5 | 4.125
7 | SW 2 (L-SHAPE) | SQM | 1 | 0.5 | 0.23 | 0.65 | 2.5 | 2.2
8 |  | SQM | 1 | 0.5 | 0.23 | 1.62 | 2.5 | 4.625
9 | SW 3 (230x1000) | SQM | 1 | 0.5 | 0.23 | 1 | 2.5 | 3.075
10 | SW 4 (230x1150) | SQM | 1 | 0.5 | 0.23 | 1.15 | 2.5 | 3.45
11 | SW 5 (230x1700) | SQM | 2 | 0.5 | 0.23 | 1.7 | 2.5 | 9.65
12 | SW 6 (230x1185) | SQM | 2 | 0.5 | 0.23 | 1.185 | 2.5 | 7.075
13 | SW 7 (230x1855) | SQM | 1 | 0.5 | 0.23 | 1.855 | 2.5 | 5.2125
14 | SW 8 (230x3600) | SQM | 1 | 1 | 0.23 | 3.6 | 2.5 | 19.15
15 | SW 9 (L-SHAPE) | SQM | 3 | 0.5 | 0.23 | 0.65 | 2.5 | 6.6
16 |  | SQM | 3 | 0.5 | 0.23 | 1.62 | 2.5 | 13.875
17 | SW 10 (230x3445) | SQM | 1 | 0.5 | 0.23 | 3.445 | 2.5 | 9.1875
18 | SW 11 (230x4065) | SQM | 1 | 0.5 | 0.23 | 4.065 | 2.5 | 10.7375
19 | SW 12 (L-SHAPE) | SQM | 1 | 0.5 | 0.23 | 0.65 | 2.5 | 2.2
20 |  | SQM | 1 | 0.5 | 0.23 | 1.305 | 2.5 | 3.8375
21 | SW 13 (200x3445) | SQM | 1 | 0.5 | 0.2 | 3.445 | 2.5 | 9.1125
[7 empty] | TOTAL | 246.825
| COLUMN (22-43/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL | [8 empty] | 8th RA
1 | C1, C2, C3, C8, C9, C10 (300X600) | SQM | 31 | 0.5 | 0.3 | 0.6 | 2.5 | 69.75
2 | C4, C5 (300X750) | SQM | 15 | 0.5 | 0.3 | 0.7 | 2.5 | 37.5
3 | C6, C11 (300X715) | SQM | 7 | 0.5 | 0.3 | 0.715 | 2.5 | 17.7625
4 | C7 (300X800) | SQM | 2 | 0.5 | 0.3 | 0.8 | 2.5 | 5.5
5 | SW 1 (L-SHAPE) | SQM | 1 | 0.5 | 0.23 | 0.65 | 2.5 | 2.2
6 |  | SQM | 1 | 0.5 | 0.23 | 1.42 | 2.5 | 4.125
7 | SW 2 (L-SHAPE) | SQM | 1 | 0.5 | 0.23 | 0.65 | 2.5 | 2.2
8 |  | SQM | 1 | 0.5 | 0.23 | 1.62 | 2.5 | 4.625
9 | SW 3 (230x1000) | SQM | 1 | 0.5 | 0.23 | 1 | 2.5 | 3.075
10 | SW 4 (230x1150) | SQM | 1 | 0.5 | 0.23 | 1.15 | 2.5 | 3.45
11 | SW 5 (230x1700) | SQM | 2 | 0.5 | 0.23 | 1.7 | 2.5 | 9.65
12 | SW 6 (230x1185) | SQM | 2 | 0.5 | 0.23 | 1.185 | 2.5 | 7.075
13 | SW 7 (230x1855) | SQM | 1 | 0.5 | 0.23 | 1.855 | 2.5 | 5.2125
14 | SW 8 (230x3600) | SQM | 1 | 1 | 0.23 | 3.6 | 2.5 | 19.15
15 | SW 9 (L-SHAPE) | SQM | 3 | 0.5 | 0.23 | 0.65 | 2.5 | 6.6
16 |  | SQM | 3 | 0.5 | 0.23 | 1.62 | 2.5 | 13.875
17 | SW 10 (230x3445) | SQM | 1 | 0.5 | 0.23 | 3.445 | 2.5 | 9.1875
18 | SW 11 (230x4065) | SQM | 1 | 0.5 | 0.23 | 4.065 | 2.5 | 10.7375
19 | SW 12 (L-SHAPE) | SQM | 1 | 0.5 | 0.23 | 0.65 | 2.5 | 2.2
20 |  | SQM | 1 | 0.5 | 0.23 | 1.305 | 2.5 | 3.8375
21 | SW 13 (200x3445) | SQM | 1 | 0.5 | 0.2 | 3.445 | 2.5 | 9.1125
COLUMN (1-22/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | SQM | 31 | 1 | 0.3 | 0.6 | 2.5 | 139.5
2 | C4, C5 (300X750) | SQM | 15 | 1 | 0.3 | 0.7 | 2.5 | 75
3 | C6, C11 (300X715) | SQM | 7 | 1 | 0.3 | 0.715 | 2.5 | 35.525
4 | C7 (300X800) | SQM | 2 | 1 | 0.3 | 0.8 | 2.5 | 11
5 | SW 1 (L-SHAPE) | SQM | 1 | 1 | 0.23 | 0.65 | 2.5 | 4.4
6 |  | SQM | 1 | 1 | 0.23 | 1.42 | 2.5 | 8.25
7 | SW 2 (L-SHAPE) | SQM | 1 | 1 | 0.23 | 0.65 | 2.5 | 4.4
8 |  | SQM | 1 | 1 | 0.23 | 1.62 | 2.5 | 9.25
9 | SW 3 (230x1000) | SQM | 1 | 1 | 0.23 | 1 | 2.5 | 6.15
10 | SW 4 (230x1150) | SQM | 1 | 1 | 0.23 | 1.15 | 2.5 | 6.9
11 | SW 5 (230x1700) | SQM | 2 | 1 | 0.23 | 1.7 | 2.5 | 19.3
12 | SW 6 (230x1185) | SQM | 2 | 1 | 0.23 | 1.185 | 2.5 | 14.15
13 | SW 7 (230x1855) | SQM | 1 | 1 | 0.23 | 1.855 | 2.5 | 10.425
14 | SW 8 (230x3600) | SQM | 0 | 0 | 0.23 | 3.6 | 2.5 | 0
15 | SW 9 (L-SHAPE) | SQM | 3 | 1 | 0.23 | 0.65 | 2.5 | 13.2
16 |  | SQM | 3 | 1 | 0.23 | 1.62 | 2.5 | 27.75
17 | SW 10 (230x3445) | SQM | 1 | 1 | 0.23 | 3.445 | 2.5 | 18.375
18 | SW 11 (230x4065) | SQM | 1 | 1 | 0.23 | 4.065 | 2.5 | 21.475
19 | SW 12 (L-SHAPE) | SQM | 1 | 1 | 0.23 | 0.65 | 2.5 | 4.4
20 |  | SQM | 1 | 1 | 0.23 | 1.305 | 2.5 | 7.675
21 | SW 13 (200x3445) | SQM | 1 | 1 | 0.2 | 3.445 | 2.5 | 18.225
COLUMN (1-43/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8 (300X600) | CUM | 46 | 1 | 0.3 | 0.6 | 0.2 | 16.56
2 | C4, C5 (300X750) | CUM | 22 | 1 | 0.3 | 0.7 | 0.2 | 8.8
3 | C6 (300X715) | CUM | 14 | 1 | 0.3 | 0.715 | 0.2 | 5.684
4 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 0.2 | 0.88
5 | SW 1 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.2 | 0.704
6 |  | CUM | 2 | 1 | 0.23 | 1.42 | 0.2 | 1.32
7 | SW 2 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.2 | 0.704
8 |  | CUM | 2 | 1 | 0.23 | 1.62 | 0.2 | 1.48
9 | SW 3 (230x1000) | CUM | 2 | 1 | 0.23 | 1 | 0.2 | 0.984
10 | SW 4 (230x1150) | CUM | 2 | 1 | 0.23 | 1.15 | 0.2 | 1.104
11 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 0.2 | 1.132
12 | SW 7 (230x1855) | CUM | 2 | 1 | 0.23 | 1.855 | 0.2 | 1.668
13 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 0.2 | 1.532
14 | SW 9 (L-SHAPE) | CUM | 6 | 1 | 0.23 | 0.65 | 0.2 | 2.112
15 |  | CUM | 6 | 1 | 0.23 | 1.62 | 0.2 | 4.44
49.104
[7 empty] | TOTAL | 751.279
SLAB SHUTTERING
| B1 200X500 | SQM | 1 | 1 | 3.025 |  | 0.2 | 0.605
| SIDE | SQM | 1 | 1 | 3.025 |  | 0.3 | 0.9075
| SIDE | SQM | 1 | 1 | 3.025 |  | 0.365 | 1.1041
| B1 200X500 | SQM | 1 | 1 | 2.8 | 0.5 | 0.2 | 0.28
| SIDE | SQM | 1 | 1 | 2.8 |  | 0.3 | 0.84
| SIDE | SQM | 1 | 1 | 2.8 |  | 0.365 | 1.022
| B2 200X500 | SQM | 1 | 1 | 3.3 |  | 0.2 | 0.66
| SIDE | SQM | 1 | 1 | 3.3 |  | 0.3 | 0.99
| SIDE | SQM | 1 | 1 | 3.3 |  | 0.35 | 1.155
| B3 AT GRID B-C/27-28 | SQM | 1 | 1 | 1.395 |  | 0.1 | 0.1395
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.35 | 0.9765
| B3 AT GRID L-M/27-28 | SQM | 1 | 1 | 1.395 |  | 0.115 | 0.16043
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.35 | 0.9765
| B3 AT GRID E/32-33 | SQM | 1 | 1 | 1.185 |  | 0.1 | 0.1185
| SIDE | SQM | 1 | 2 | 1.185 |  | 0.35 | 0.8295
| B3 AT GRID F/43 | SQM | 3 | 1 | 2.055 |  | 0.1 | 0.6165
| SIDE | SQM | 3 | 2 | 2.055 |  | 0.35 | 4.3155
| B3 AT GRID F/39-40 | SQM | 3 | 1 | 1.485 |  | 0.1 | 0.4455
| SIDE | SQM | 3 | 2 | 1.485 |  | 0.35 | 3.1185
| B3 AT GRID M & O/39-40 | SQM | 3 | 1 | 2.315 |  | 0.1 | 0.6945
| SIDE | SQM | 3 | 2 | 2.315 |  | 0.35 | 4.8615
| B3 AT GRID C,K/25 | SQM | 2 | 1 | 2.315 |  | 0.1 | 0.463
| SIDE | SQM | 2 | 2 | 2.315 |  | 0.35 | 3.241
| B4 200X350 | SQM | 1 | 2 | 1.395 |  | 0.2 | 0.558
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.35 | 0.9765
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.225 | 0.62775
| B5 200X450 | SQM | 1 | 1 | 6.875 |  | 0.2 | 1.375
| SIDE | SQM | 1 | 1 | 6.875 |  | 0.315 | 2.1656
| SIDE | SQM | 1 | 1 | 6.875 |  | 0.325 | 2.2344
| B6 230X350 | SQM | 1 | 1 | 3.16 |  | 0.23 | 0.7268
| SIDE | SQM | 1 | 1 | 3.16 |  | 0.225 | 0.711
| SIDE | SQM | 1 | 1 | 2.145 |  | 0.225 | 0.48262
| SIDE | SQM | 1 | 1 | 1.015 |  | 0.35 | 0.35525
| B7 200X450 | SQM | 1 | 1 | 2.7 |  | 0.2 | 0.54
| SIDE | SQM | 1 | 1 | 2.7 |  | 0.325 | 0.8775
| SIDE | SQM | 1 | 1 | 2.7 |  | 0.325 | 0.8775
| B8 200X500 | SQM | 1 | 1 | 2.875 |  | 0.2 | 0.575
| SIDE | SQM | 1 | 1 | 2.875 |  | 0.365 | 1.0494
| SIDE | SQM | 1 | 1 | 1.55 |  | 0.3 | 0.465
| SIDE | SQM | 1 | 1 | 1.325 |  | 0.375 | 0.49687
| B8 200X350 | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 2.615 |  | 0.15 | 0.39225
| SIDE | SQM | 1 | 1 | 0.315 |  | 0.35 | 0.11025
| B9 200X500 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.3 | 1.407
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.365 | 1.7119
| B10 200X500 | SQM | 1 | 1 | 3.15 |  | 0.2 | 0.63
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.3 | 0.945
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.365 | 1.1498
| B11 200X450 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.315 | 1.4774
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.325 | 1.5243
| B12 200X450 | SQM | 1 | 1 | 5.76 |  | 0.2 | 1.152
| SIDE | SQM | 1 | 1 | 3.035 |  | 0.315 | 0.95603
| SIDE | SQM | 1 | 1 | 2.725 |  | 0.325 | 0.88563
| SIDE | SQM | 1 | 1 | 2.61 |  | 0.325 | 0.84825
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.45 | 1.4175
| B13 200X350 | SQM | 1 | 1 | 1.6 |  | 0.2 | 0.32
| SIDE | SQM | 1 | 1 | 1.6 |  | 0.225 | 0.36
| SIDE | SQM | 1 | 1 | 1.6 |  | 0.35 | 0.56
| B13 200X450 | SQM | 1 | 1 | 4.105 |  | 0.2 | 0.821
| SIDE | SQM | 1 | 1 | 4.105 |  | 0.3 | 1.2315
| SIDE | SQM | 1 | 1 | 4.105 |  | 0.325 | 1.3341
| SIDE | SQM | 1 | 1 | 4.105 |  | 0.315 | 1.2931
| B14 200X450 | SQM | 1 | 1 | 1.5 |  | 0.2 | 0.3
| SIDE | SQM | 1 | 1 | 1.5 |  | 0.325 | 0.4875
| SIDE | SQM | 1 | 1 | 1.5 |  | 0.325 | 0.4875
| B14 200X450 | SQM | 1 | 1 | 2.2 |  | 0.2 | 0.44
| SIDE | SQM | 1 | 1 | 2.2 |  | 0.315 | 0.693
| SIDE | SQM | 1 | 1 | 2.2 |  | 0.3 | 0.66
| B15 200X500 | SQM | 1 | 1 | 3.115 |  | 0.2 | 0.623
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.375 | 1.1681
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.5 | 1.5575
| B16 200X350 | SQM | 1 | 3 | 1.02 |  | 0.2 | 0.612
| SIDE | SQM | 1 | 3 | 1.02 |  | 0.225 | 0.6885
| SIDE | SQM | 1 | 3 | 1.02 |  | 0.35 | 1.071
| B16 200X500 | SQM | 1 | 3 | 3.35 |  | 0.2 | 2.01
| SIDE | SQM | 1 | 3 | 3.35 |  | 0.3 | 3.015
| SIDE | SQM | 1 | 3 | 3.35 |  | 0.365 | 3.6683
| B16 200X500 | SQM | 1 | 3 | 3.25 |  | 0.2 | 1.95
| SIDE | SQM | 1 | 3 | 3.25 |  | 0.365 | 3.5587
| SIDE | SQM | 1 | 3 | 2.28 |  | 0.3 | 2.052
| SIDE | SQM | 1 | 3 | 0.97 |  | 0.5 | 1.455
| B17 200X500 | SQM | 1 | 1 | 3.215 |  | 0.2 | 0.643
| SIDE | SQM | 1 | 1 | 3.215 |  | 0.35 | 1.1252
| SIDE | SQM | 1 | 1 | 3.215 |  | 0.3 | 0.9645
| B18 230X500 | SQM | 1 | 1 | 2.76 |  | 0.23 | 0.6348
| SIDE | SQM | 1 | 1 | 2.76 |  | 0.365 | 1.0074
| SIDE | SQM | 1 | 1 | 2.76 |  | 0.5 | 1.38
| B19 200X450 | SQM | 1 | 1 | 6.79 |  | 0.2 | 1.358
| SIDE | SQM | 1 | 1 | 6.79 |  | 0.3 | 2.037
| SIDE | SQM | 1 | 1 | 6.79 |  | 0.3 | 2.037
| B20 200X350 | SQM | 1 | 1 | 2.41 |  | 0.2 | 0.482
| SIDE | SQM | 1 | 1 | 2.41 |  | 0.35 | 0.8435
| SIDE | SQM | 1 | 1 | 2.41 |  | 0.35 | 0.8435
| B21 230X450 | SQM | 1 | 1 | 5.76 |  | 0.23 | 1.3248
| SIDE | SQM | 1 | 1 | 2.61 |  | 0.325 | 0.84825
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.45 | 1.4175
| SIDE | SQM | 1 | 1 | 3.035 |  | 0.45 | 1.3658
| SIDE | SQM | 1 | 1 | 2.725 |  | 0.325 | 0.88563
| B22 200x450 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.325 | 1.5243
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.315 | 1.4774
| B23 200X450 | SQM | 1 | 1 | 2.22 |  | 0.2 | 0.444
| SIDE | SQM | 1 | 1 | 2.22 |  | 0.325 | 0.7215
| SIDE | SQM | 1 | 1 | 2.22 |  | 0.3 | 0.666
| B24 200X450 | SQM | 1 | 1 | 5.63 |  | 0.2 | 1.126
| SIDE | SQM | 1 | 2 | 5.63 |  | 0.45 | 5.067
| B25 200X450 | SQM | 1 | 1 | 1.5 |  | 0.2 | 0.3
| SIDE | SQM | 1 | 2 | 1.5 |  | 0.325 | 0.975
| B25 200X500 | SQM | 1 | 1 | 2.085 |  | 0.2 | 0.417
| SIDE | SQM | 1 | 2 | 2.085 |  | 0.325 | 1.3553
| B25 200X450 BESIDE STAIRS | SQM | 1 | 1 | 5.63 |  | 0.2 | 1.126
| SIDE | SQM | 1 | 1 | 5.63 |  | 0.45 | 2.5335
| SIDE | SQM | 1 | 1 | 5.63 |  | 0.325 | 1.8297
| B26 200X450 | SQM | 1 | 3 | 3.235 |  | 0.2 | 1.941
| SIDE | SQM | 1 | 3 | 3.235 |  | 0.315 | 3.0571
| SIDE | SQM | 1 | 3 | 1.61 |  | 0.3 | 1.449
| SIDE | SQM | 1 | 3 | 1.625 |  | 0.325 | 1.5844
| B26 200X450 | SQM | 1 | 3 | 4.72 |  | 0.2 | 2.832
| SIDE | SQM | 1 | 3 | 3.15 |  | 0.315 | 2.9768
| SIDE | SQM | 1 | 3 | 1.57 |  | 0.325 | 1.5308
| SIDE | SQM | 1 | 3 | 4.72 |  | 0.325 | 4.602
| B27 200X350 | SQM | 1 | 3 | 2.575 |  | 0.2 | 1.545
| SIDE | SQM | 1 | 3 | 2.575 |  | 0.225 | 1.7381
| SIDE | SQM | 1 | 3 | 2.575 |  | 0.35 | 2.7037
| B27 200X500 | SQM | 1 | 3 | 3.165 |  | 0.2 | 1.899
| SIDE | SQM | 1 | 3 | 3.165 |  | 0.375 | 3.5606
| SIDE | SQM | 1 | 3 | 3.165 |  | 0.5 | 4.7475
| B28 200X450 | SQM | 1 | 1 | 5.125 |  | 0.2 | 1.025
| SIDE | SQM | 1 | 1 | 5.125 |  | 0.3 | 1.5375
| SIDE | SQM | 1 | 1 | 1.69 |  | 0.325 | 0.54925
| SIDE | SQM | 1 | 1 | 3.435 |  | 0.315 | 1.082
| B29 200X450 | SQM | 1 | 1 | 1.9 |  | 0.2 | 0.38
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.325 | 0.6175
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.45 | 0.855
| B29 200X450 | SQM | 1 | 1 | 1.9 |  | 0.2 | 0.38
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.325 | 0.6175
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.45 | 0.855
| B29 200X450 | SQM | 1 | 1 | 1.4 |  | 0.2 | 0.28
| SIDE | SQM | 1 | 2 | 1.4 |  | 0.325 | 0.91
| B30 200X350 | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 0.315 |  | 0.35 | 0.11025
| SIDE | SQM | 1 | 1 | 2.615 |  | 0.15 | 0.39225
| B30 200X500 | SQM | 1 | 1 | 2.875 |  | 0.2 | 0.575
| SIDE | SQM | 1 | 1 | 1.55 |  | 0.3 | 0.465
| SIDE | SQM | 1 | 1 | 1.325 |  | 0.375 | 0.49687
| SIDE | SQM | 1 | 1 | 2.875 |  | 0.375 | 1.0781
| B30 200X450 | SQM | 1 | 1 | 3.95 |  | 0.2 | 0.79
| SIDE | SQM | 1 | 1 | 3.95 |  | 0.325 | 1.2838
| SIDE | SQM | 1 | 1 | 3.95 |  | 0.325 | 1.2838
| B31 200X500 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.365 | 1.7119
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.3 | 1.407
| B31 200X500 | SQM | 1 | 1 | 3.15 |  | 0.2 | 0.63
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.5 | 1.575
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.5 | 1.575
| B32 230X450 | SQM | 1 | 2 | 1.9 |  | 0.23 | 0.874
| SIDE | SQM | 1 | 2 | 1.9 |  | 0.325 | 1.235
| SIDE | SQM | 1 | 2 | 1.9 |  | 0.45 | 1.71
| B33 200X350 | SQM | 1 | 1 | 5.235 |  | 0.2 | 1.047
| SIDE | SQM | 1 | 2 | 3.235 |  | 0.215 | 1.391
| SIDE | SQM | 1 | 2 | 2 |  | 0.168 | 0.672
| B34 230X450 | SQM | 1 | 1 | 5.1 |  | 0.23 | 1.173
| SIDE | SQM | 1 | 1 | 5.1 |  | 0.3 | 1.53
| SIDE | SQM | 1 | 1 | 3.475 |  | 0.315 | 1.0946
| SIDE | SQM | 1 | 1 | 1.625 |  | 0.325 | 0.52812
| B34 230X450 | SQM | 1 | 1 | 5.1 |  | 0.23 | 1.173
| SIDE | SQM | 1 | 1 | 5.1 |  | 0.3 | 1.53
| SIDE | SQM | 1 | 1 | 3.475 |  | 0.315 | 1.0946
| SIDE | SQM | 1 | 1 | 1.625 |  | 0.325 | 0.52812
| B35 200X500 | SQM | 1 | 2 | 3.19 |  | 0.2 | 1.276
| SIDE | SQM | 1 | 2 | 3.19 |  | 0.3 | 1.914
| SIDE | SQM | 1 | 2 | 3.19 |  | 0.35 | 2.233
| B36 200X500 | SQM | 1 | 3 | 1.81 |  | 0.2 | 1.086
| SIDE | SQM | 1 | 3 | 1.81 |  | 0.375 | 2.0362
| SIDE | SQM | 1 | 3 | 1.81 |  | 0.5 | 2.715
| B36 200X500 | SQM | 1 | 3 | 3.55 |  | 0.2 | 2.13
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.375 | 3.9937
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.5 | 5.325
| B36 230X500 | SQM | 1 | 3 | 0.515 |  | 0.23 | 0.35535
| SIDE | SQM | 1 | 3 | 0.515 |  | 0.5 | 0.7725
| SIDE | SQM | 1 | 3 | 0.515 |  | 0.5 | 0.7725
| B37 200X450 | SQM | 1 | 3 | 3.86 |  | 0.2 | 2.316
| SIDE | SQM | 1 | 3 | 3.86 |  | 0.315 | 3.6477
| SIDE | SQM | 1 | 3 | 3.86 |  | 0.325 | 3.7635
| B38 200X450 | SQM | 3 | 1 | 3.45 |  | 0.2 | 2.07
| SIDE | SQM | 3 | 2 | 3.45 |  | 0.325 | 6.7275
| B39 200X450 | SQM | 1 | 3 | 2.91 |  | 0.2 | 1.746
| SIDE | SQM | 1 | 3 | 2.91 |  | 0.315 | 2.75
| SIDE | SQM | 1 | 3 | 2.91 |  | 0.315 | 2.75
| B39 230X350 | SQM | 1 | 3 | 3.55 |  | 0.23 | 2.4495
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.225 | 2.3962
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.225 | 2.3962
| B40 200X450 | SQM | 1 | 2 | 3 |  | 0.2 | 1.2
| SIDE | SQM | 1 | 2 | 3 |  | 0.3 | 1.8
| SIDE | SQM | 1 | 2 | 3 |  | 0.325 | 1.95
| B40 200X350 | SQM | 1 | 2 | 2.065 |  | 0.2 | 0.826
| SIDE | SQM | 1 | 2 | 2.065 |  | 0.215 | 0.88795
| SIDE | SQM | 1 | 2 | 2.065 |  | 0.15 | 0.6195
| B41 200X500 | SQM | 1 | 3 | 3.31 |  | 0.2 | 1.986
| SIDE | SQM | 1 | 3 | 3.31 |  | 0.35 | 3.4755
| SIDE | SQM | 1 | 3 | 3.31 |  | 0.365 | 3.6244
| B42 200X450 | SQM | 1 | 2 | 3 |  | 0.2 | 1.2
| SIDE | SQM | 1 | 2 | 3 |  | 0.325 | 1.95
| SIDE | SQM | 1 | 2 | 3 |  | 0.315 | 1.89
| B43 200X450 | SQM | 1 | 1 | 5.245 |  | 0.2 | 1.049
| SIDE | SQM | 1 | 2 | 5.245 |  | 0.3 | 3.147
| B44 200X450 | SQM | 1 | 1 | 3 |  | 0.2 | 0.6
| SIDE | SQM | 1 | 1 | 3 |  | 0.3 | 0.9
| SIDE | SQM | 1 | 1 | 3 |  | 0.325 | 0.975
| B44 200X350 | SQM | 1 | 1 | 1.95 |  | 0.2 | 0.39
| SIDE | SQM | 1 | 1 | 1.95 |  | 0.15 | 0.2925
| SIDE | SQM | 1 | 1 | 1.95 |  | 0.215 | 0.41925
| B45 200X450 | SQM | 1 | 1 | 2.23 |  | 0.2 | 0.446
| SIDE | SQM | 1 | 1 | 2.23 |  | 0.315 | 0.70245
| SIDE | SQM | 1 | 1 | 2.23 |  | 0.325 | 0.72475
| B46 200X500 | SQM | 1 | 1 | 5.145 |  | 0.2 | 1.029
| SIDE | SQM | 1 | 1 | 5.145 |  | 0.35 | 1.8007
| SIDE | SQM | 1 | 1 | 2.775 |  | 0.375 | 1.0406
| SIDE | SQM | 1 | 1 | 2.37 |  | 0.5 | 1.185
| B47 200X500 | SQM | 1 | 1 | 3.8 |  | 0.2 | 0.76
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.375 | 0.6375
| SIDE | SQM | 1 | 1 | 2.1 |  | 0.365 | 0.7665
| SIDE | SQM | 1 | 1 | 3.8 |  | 0.5 | 1.9
| B48 200X350 | SQM | 1 | 1 | 2.95 |  | 0.2 | 0.59
| SIDE | SQM | 1 | 1 | 2.95 |  | 0.225 | 0.66375
| SIDE | SQM | 1 | 1 | 2.95 |  | 0.35 | 1.0325
| B49 200X450 | SQM | 1 | 1 | 4.55 |  | 0.2 | 0.91
| SIDE | SQM | 1 | 2 | 3.15 |  | 0.315 | 1.9845
| SIDE | SQM | 1 | 2 | 1.4 |  | 0.325 | 0.91
| B50 200X500 | SQM | 1 | 1 | 3.05 |  | 0.2 | 0.61
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.365 | 1.1132
| SIDE | SQM | 1 | 1 | 1.85 |  | 0.35 | 0.6475
| SIDE | SQM | 1 | 1 | 1.2 |  | 0.3 | 0.36
| B51 200X450 | SQM | 1 | 1 | 2.5 |  | 0.2 | 0.5
| SIDE | SQM | 1 | 2 | 2.5 |  | 0.325 | 1.625
| B52 230X500 | SQM | 1 | 1 | 3.115 |  | 0.23 | 0.71645
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.35 | 1.0902
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.375 | 1.1681
| B53 200X350 | SQM | 1 | 1 | 2.335 |  | 0.2 | 0.467
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.15 | 0.35025
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.215 | 0.50202
| B54 230X500 | SQM | 1 | 1 | 3.2 |  | 0.23 | 0.736
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.325 | 1.04
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.5 | 1.6
| B55 230X450 | SQM | 1 | 1 | 0.35 |  | 0.23 | 0.0805
| SIDE | SQM | 1 | 2 | 0.35 |  | 0.45 | 0.315
| B56 200X450 | SQM | 1 | 1 | 1.96 |  | 0.2 | 0.392
| SIDE | SQM | 1 | 2 | 1.96 |  | 0.325 | 1.274
| B57 230X450 | SQM | 1 | 1 | 3.2 |  | 0.23 | 0.736
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.325 | 1.04
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.45 | 1.44
| B57 200X450 | SQM | 1 | 1 | 2.335 |  | 0.2 | 0.467
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.315 | 0.73552
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.325 | 0.75887
| B58 230X500 | SQM | 1 | 1 | 2.54 |  | 0.23 | 0.5842
| SIDE | SQM | 1 | 1 | 2.54 |  | 0.375 | 0.9525
| SIDE | SQM | 1 | 1 | 2.54 |  | 0.5 | 1.27
| B58 230X450 | SQM | 1 | 1 | 3.43 |  | 0.23 | 0.7889
| SIDE | SQM | 1 | 2 | 3.43 |  | 0.325 | 2.2295
| B59 200X500 | SQM | 1 | 1 | 2.225 |  | 0.2 | 0.445
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.318 | 0.70755
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.375 | 0.83438
| B60 200X450 | SQM | 1 | 1 | 3.14 |  | 0.2 | 0.628
| SIDE | SQM | 1 | 1 | 3.14 |  | 0.3 | 0.942
| SIDE | SQM | 1 | 1 | 3.14 |  | 0.325 | 1.0205
| B61 200X450 | SQM | 1 | 1 | 3.43 |  | 0.2 | 0.686
| SIDE | SQM | 1 | 1 | 3.43 |  | 0.315 | 1.0805
| SIDE | SQM | 1 | 1 | 1.205 |  | 0.325 | 0.39163
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.3 | 0.6675
| B61 230X450 | SQM | 1 | 1 | 1.99 |  | 0.23 | 0.4577
| SIDE | SQM | 1 | 1 | 1.99 |  | 0.325 | 0.64675
| SIDE | SQM | 1 | 1 | 1.99 |  | 0.3 | 0.597
| B62 200X500 | SQM | 1 | 1 | 2.225 |  | 0.2 | 0.445
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.318 | 0.70755
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.375 | 0.83438
| B63 200X450 | SQM | 1 | 1 | 3.06 |  | 0.2 | 0.612
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.3 | 0.918
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.315 | 0.9639
| B63 200X450 | SQM | 1 | 1 | 3.06 |  | 0.2 | 0.612
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.3 | 0.918
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.325 | 0.9945
| B64 200X350 | SQM | 1 | 2 | 3.05 |  | 0.2 | 1.22
| SIDE | SQM | 1 | 2 | 3.05 |  | 0.215 | 1.3115
| SIDE | SQM | 1 | 2 | 1.32 |  | 0.35 | 0.924
| SIDE | SQM | 1 | 2 | 1.73 |  | 0.2 | 0.692
| B64 200X350 | SQM | 1 | 2 | 0.38 |  | 0.2 | 0.152
| SIDE | SQM | 1 | 2 | 0.38 |  | 0.35 | 0.266
| B65 200X450 | SQM | 1 | 2 | 3.385 |  | 0.2 | 1.354
| SIDE | SQM | 1 | 2 | 3.385 |  | 0.325 | 2.2003
| SIDE | SQM | 1 | 2 | 3.385 |  | 0.3 | 2.031
| B66 200X450 | SQM | 2 | 1 | 3.25 |  | 0.2 | 1.3
| SIDE | SQM | 2 | 2 | 3.25 |  | 0.315 | 4.095
| B66 200X450 | SQM | 2 | 1 | 1.7 |  | 0.2 | 0.68
| SIDE | SQM | 2 | 2 | 1.7 |  | 0.325 | 2.21
| B66 200X350 | SQM | 1 | 2 | 1.385 |  | 0.2 | 0.554
| SIDE | SQM | 1 | 2 | 1.385 |  | 0.225 | 0.62325
| SIDE | SQM | 1 | 2 | 1.385 |  | 0.35 | 0.9695
| B67 200X450 | SQM | 1 | 1 | 3.05 |  | 0.2 | 0.61
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.315 | 0.96075
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.45 | 1.3725
| B67 200X450 | SQM | 1 | 1 | 1.7 |  | 0.2 | 0.34
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.325 | 0.5525
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.45 | 0.765
| B67 200X450 | SQM | 1 | 1 | 3.05 |  | 0.2 | 0.61
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.315 | 0.96075
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.315 | 0.96075
| B67 200X450 | SQM | 1 | 1 | 1.7 |  | 0.2 | 0.34
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.325 | 0.5525
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.325 | 0.5525
| B68 200X350 | SQM | 1 | 1 | 3.17 |  | 0.2 | 0.634
| SIDE | SQM | 1 | 1 | 3.17 |  | 0.225 | 0.71325
| SIDE | SQM | 1 | 1 | 3.17 |  | 0.35 | 1.1095
| B69 200X450 | SQM | 1 | 0.5 | 5.78 |  | 0.2 | 0.578
| SIDE | SQM | 1 | 0.5 | 3.78 |  | 0.315 | 0.59535
| SIDE | SQM | 1 | 0.5 | 3.78 |  | 0.315 | 0.59535
| SIDE | SQM | 1 | 0.5 | 2 |  | 0.268 | 0.268
| SIDE | SQM | 1 | 0.5 | 2 |  | 0.268 | 0.268
389.2135
FLAT NO 9
| Bed room 1 | CUM | 1 | 1 | 3.575 | 3.55 |  | 12.6913
| Bed Room 2 | CUM | 1 | 1 | 3.55 | 3.2 |  | 11.36
| Bed Room 3 | CUM | 1 | 1 | 3.145 | 3.05 |  | 9.5922
|  | CUM | 1 | 1 | 0.9 | 0.4 |  | 0.36
| Service slab | CUM | 1 | 1 | 1.165 | 0.515 |  | 0.59998
| TOILET 1 | CUM | 1 | 1 | 3.575 | 1.57 |  | 5.6128
| TOILET 2 | CUM | 1 | 1 | 2.5 | 1.6 |  | 4
| PASSAGE | CUM | 1 | 1 | 2.785 | 1.2 |  | 3.342
| Living | CUM | 1 | 1 | 6.365 | 3.72 |  | 23.6778
|  | CUM | 1 | 1 | 4.115 | 0.385 |  | 1.5843
| Entry/ Porch | CUM | 1 | 1 | 1.5 | 1.035 |  | 1.5525
| Kitchen | CUM | 1 | 1 | 2.85 | 2.335 |  | 6.6547
| Balcony 1 | CUM | 1 | 1 | 6.3 | 2 |  | 12.6
| Balcony 2 | CUM | 1 | 1 | 4.065 | 2 |  | 8.13
| Kitchen Balcony | CUM | 1 | 1 | 1.4 | 2 |  | 2.8
|  | CUM | 1 | 1 | 1.185 | 0.435 |  | 0.51548
105.073
| FLAT NO 8 | [6 empty] | 0
| B. ROOM 1 | CUM | 1 | 1 | 3.56 | 3.275 |  | 11.659
| B. ROOM 2 | CUM | 1 | 1 | 3.25 | 2.925 |  | 9.5062
| B. ROOM 3 | CUM | 1 | 1 | 3.58 | 3.05 |  | 10.919
| PASSAGE | CUM | 1 | 1 | 2.925 | 1.7 |  | 4.9725
| KITCHEN | CUM | 1 | 1 | 3.25 | 2.365 |  | 7.6863
| LIVING | CUM | 1 | 1 | 5.23 | 3.33 |  | 17.4159
|  | CUM | 1 | 1 | 3.4 | 0.94 |  | 3.196
|  | CUM | 1 | 1 | 2.55 | 1.47 |  | 3.7485
| DRESSING AREA | CUM | 1 | 1 | 2.41 | 1.43 |  | 3.4463
| TOILET 1 | CUM | 1 | 1 | 2.225 | 1.495 |  | 3.3264
| TOILET 2 | CUM | 1 | 1 | 3.385 | 1.425 |  | 4.8236
| TOILET 3 | CUM | 1 | 1 | 2.41 | 1.54 |  | 3.7114
| BALCONY 1 | CUM | 1 | 1 | 4.665 | 2 |  | 9.33
| BALCONY 2 | CUM | 1 | 1 | 5.105 | 2 |  | 10.21
| BALCONY 3 | CUM | 1 | 1 | 3.265 | 2 |  | 6.53
110.4811
| FLAT NO 7 | [6 empty] | 0
| B. ROOM 1 | CUM | 1 | 1 | 3.56 | 3.245 |  | 11.5522
| B. ROOM 2 | CUM | 1 | 1 | 3.25 | 2.925 |  | 9.5062
| PASSAGE | CUM | 1 | 1 | 2.925 | 1.7 |  | 4.9725
| KITCHEN | CUM | 1 | 1 | 3.25 | 2.365 |  | 7.6863
| LIVING | CUM | 1 | 1 | 5.23 | 3.33 |  | 17.4159
|  | CUM | 1 | 1 | 3.4 | 0.94 |  | 3.196
|  | CUM | 1 | 1 | 2.55 | 1.47 |  | 3.7485
| TOILET 1 | CUM | 1 | 1 | 2.225 | 1.495 |  | 3.3264
| TOILET 2 | CUM | 1 | 1 | 3.385 | 1.425 |  | 4.8236
| BALCONY 1 | CUM | 1 | 1 | 4.665 | 2 |  | 9.33
| BALCONY 2 | CUM | 1 | 1 | 5.105 | 2 |  | 10.21
85.7676
FLAT NO 10,11,12
| B. ROOM 1 |  | 3 | 1 | 3.86 | 3.25 |  | 37.635
| B. ROOM 2 |  | 3 | 1 | 3.86 | 3.335 |  | 38.6193
| B. ROOM 3 |  | 3 | 1 | 3.55 | 3.265 |  | 34.7722
| Living |  | 3 | 1 | 6.245 | 3.315 |  | 62.1065
|  |  | 3 | 1 | 3.17 | 1.91 |  | 18.1641
| KITCHEN |  | 3 | 1 | 3.435 | 2.345 |  | 24.1652
| TOILET 1 |  | 3 | 1 | 3.86 | 1.44 |  | 16.6752
| TOILET 2 |  | 3 | 1 | 3.55 | 1.425 |  | 15.1762
| TOILET 3 |  | 3 | 1 | 3.55 | 1.425 |  | 15.1762
| Service slab |  | 3 | 1 | 1.245 | 0.515 |  | 1.9235
| Service slab |  | 3 | 1 | 0.97 | 0.415 |  | 1.2076
| BALCONY 1 |  | 3 | 1 | 5.93 | 2 |  | 35.58
| BALCONY 2 |  | 3 | 1 | 3.565 | 2 |  | 21.39
| BALCONY 3 |  | 3 | 1 | 1.55 | 2 |  | 9.3
331.8913
| FLAT 7,8 & 9 LOBBY |  | 1 | 1 | 5.09 | 1.5 |  | 7.635
|  |  | 1 | 1 | 3.14 | 0.955 |  | 2.9987
| LIFT LOBBY |  | 1 | 1 | 3.95 | 1.61 |  | 6.3595
|  |  | 1 | 1 | 5.635 | 2.44 |  | 13.7494
| FLAT 10,11,12 LOBBY |  | 1 | 1 | 4.79 | 3.19 |  | 15.2801
|  |  | 1 | 1 | 1.4 | 0.655 |  | 0.917
Main s/case (2 No)
| Half landing |  | 1 | 2 | 1.5 | 1.5 |  | 4.5
| freight |  | 1 | 2 | 2.409 | 1.5 |  | 7.227
| mid freight |  | 1 | 1 | 1.484 | 1.5 |  | 2.226
| top landing |  | 1 | 1 | 3.96 | 0.26 |  | 1.0296
| landing beam 230x450 |  | 1 | 1 | 3.53 | 0.23 |  | 0.8119
| SIDE |  | 1 | 1 | 3.53 | 0.275 |  | 0.97075
| SIDE |  | 1 | 1 | 3.53 | 0.45 |  | 1.5885
Fire s/case (4 No)
| mid & full landing |  | 1 | 2 | 3.2 | 1.5 |  | 9.6
| freight |  | 1 | 2 | 3.343 | 1.5 |  | 10.029
| landing beam 230x450 |  | 1 | 1 | 3.2 | 0.23 |  | 0.736
| SIDE |  | 1 | 1 | 3.2 | 0.275 |  | 0.88
| SIDE |  | 1 | 1 | 3.2 | 0.45 |  | 1.44
87.9784
COLUMN (22-43/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 31 | 1 | 0.3 | 0.6 | 0.45 | 25.11
2 | C4, C5 (300X750) | CUM | 15 | 1 | 0.3 | 0.7 | 0.45 | 13.5
3 | C6, C11 (300X715) | CUM | 7 | 1 | 0.3 | 0.715 | 0.45 | 6.3945
4 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 0.45 | 1.98
5 | SW 1 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.792
6 |  | CUM | 1 | 1 | 0.23 | 1.42 | 0.45 | 1.485
7 | SW 2 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.792
8 |  | CUM | 1 | 1 | 0.23 | 1.62 | 0.45 | 1.665
9 | SW 3 (230x1000) | CUM | 1 | 1 | 0.23 | 1 | 0.45 | 1.107
10 | SW 4 (230x1150) | CUM | 1 | 1 | 0.23 | 1.15 | 0.45 | 1.242
11 | SW 5 (230x1700) | CUM | 2 | 1 | 0.23 | 1.7 | 0.45 | 3.474
12 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 0.45 | 2.547
13 | SW 7 (230x1855) | CUM | 1 | 1 | 0.23 | 1.855 | 0.45 | 1.8765
14 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 0.45 | 3.447
15 | SW 9 (L-SHAPE) | CUM | 3 | 1 | 0.23 | 0.65 | 0.45 | 2.376
16 |  | CUM | 3 | 1 | 0.23 | 1.62 | 0.45 | 4.995
17 | SW 10 (230x3445) | CUM | 1 | 1 | 0.23 | 3.445 | 0.45 | 3.3075
18 | SW 11 (230x4065) | CUM | 1 | 1 | 0.23 | 4.065 | 0.45 | 3.8655
19 | SW 12 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.792
20 |  | CUM | 1 | 1 | 0.23 | 1.305 | 0.45 | 1.3815
21 | SW 13 (200x3445) | CUM | 1 | 1 | 0.2 | 3.445 | 0.45 | 3.2805
85.41
1195.8149
| SLAB SHUTTERING | [8 empty] | 9TH RA
| B1 200X500 | SQM | 1 | 1 | 3.025 |  | 0.2 | 0.605
| SIDE | SQM | 1 | 1 | 3.025 |  | 0.3 | 0.9075
| SIDE | SQM | 1 | 1 | 3.025 |  | 0.365 | 1.1041
| B1 200X500 | SQM | 1 | 1 | 2.8 | 0.5 | 0.2 | 0.28
| SIDE | SQM | 1 | 1 | 2.8 |  | 0.3 | 0.84
| SIDE | SQM | 1 | 1 | 2.8 |  | 0.365 | 1.022
| B2 200X500 | SQM | 1 | 1 | 3.3 |  | 0.2 | 0.66
| SIDE | SQM | 1 | 1 | 3.3 |  | 0.3 | 0.99
| SIDE | SQM | 1 | 1 | 3.3 |  | 0.35 | 1.155
| B3 AT GRID B-C/27-28 | SQM | 1 | 1 | 1.395 |  | 0.1 | 0.1395
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.35 | 0.9765
| B3 AT GRID L-M/27-28 | SQM | 1 | 1 | 1.395 |  | 0.115 | 0.16043
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.35 | 0.9765
| B3 AT GRID E/32-33 | SQM | 1 | 1 | 1.185 |  | 0.1 | 0.1185
| SIDE | SQM | 1 | 2 | 1.185 |  | 0.35 | 0.8295
| B3 AT GRID F/43 | SQM | 3 | 1 | 2.055 |  | 0.1 | 0.6165
| SIDE | SQM | 3 | 2 | 2.055 |  | 0.35 | 4.3155
| B3 AT GRID F/39-40 | SQM | 3 | 1 | 1.485 |  | 0.1 | 0.4455
| SIDE | SQM | 3 | 2 | 1.485 |  | 0.35 | 3.1185
| B3 AT GRID M & O/39-40 | SQM | 3 | 1 | 2.315 |  | 0.1 | 0.6945
| SIDE | SQM | 3 | 2 | 2.315 |  | 0.35 | 4.8615
| B3 AT GRID C,K/25 | SQM | 2 | 1 | 2.315 |  | 0.1 | 0.463
| SIDE | SQM | 2 | 2 | 2.315 |  | 0.35 | 3.241
| B4 200X350 | SQM | 1 | 2 | 1.395 |  | 0.2 | 0.558
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.35 | 0.9765
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.225 | 0.62775
| B5 200X450 | SQM | 1 | 1 | 6.875 |  | 0.2 | 1.375
| SIDE | SQM | 1 | 1 | 6.875 |  | 0.315 | 2.1656
| SIDE | SQM | 1 | 1 | 6.875 |  | 0.325 | 2.2344
| B6 230X350 | SQM | 1 | 1 | 3.16 |  | 0.23 | 0.7268
| SIDE | SQM | 1 | 1 | 3.16 |  | 0.225 | 0.711
| SIDE | SQM | 1 | 1 | 2.145 |  | 0.225 | 0.48262
| SIDE | SQM | 1 | 1 | 1.015 |  | 0.35 | 0.35525
| B7 200X450 | SQM | 1 | 1 | 2.7 |  | 0.2 | 0.54
| SIDE | SQM | 1 | 1 | 2.7 |  | 0.325 | 0.8775
| SIDE | SQM | 1 | 1 | 2.7 |  | 0.325 | 0.8775
| B8 200X500 | SQM | 1 | 1 | 2.875 |  | 0.2 | 0.575
| SIDE | SQM | 1 | 1 | 2.875 |  | 0.365 | 1.0494
| SIDE | SQM | 1 | 1 | 1.55 |  | 0.3 | 0.465
| SIDE | SQM | 1 | 1 | 1.325 |  | 0.375 | 0.49687
| B8 200X350 | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 2.615 |  | 0.15 | 0.39225
| SIDE | SQM | 1 | 1 | 0.315 |  | 0.35 | 0.11025
| B9 200X500 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.3 | 1.407
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.365 | 1.7119
| B10 200X500 | SQM | 1 | 1 | 3.15 |  | 0.2 | 0.63
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.3 | 0.945
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.365 | 1.1498
| B11 200X450 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.315 | 1.4774
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.325 | 1.5243
| B12 200X450 | SQM | 1 | 1 | 5.76 |  | 0.2 | 1.152
| SIDE | SQM | 1 | 1 | 3.035 |  | 0.315 | 0.95603
| SIDE | SQM | 1 | 1 | 2.725 |  | 0.325 | 0.88563
| SIDE | SQM | 1 | 1 | 2.61 |  | 0.325 | 0.84825
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.45 | 1.4175
| B13 200X350 | SQM | 1 | 1 | 1.6 |  | 0.2 | 0.32
| SIDE | SQM | 1 | 1 | 1.6 |  | 0.225 | 0.36
| SIDE | SQM | 1 | 1 | 1.6 |  | 0.35 | 0.56
| B13 200X450 | SQM | 1 | 1 | 4.105 |  | 0.2 | 0.821
| SIDE | SQM | 1 | 1 | 4.105 |  | 0.3 | 1.2315
| SIDE | SQM | 1 | 1 | 4.105 |  | 0.325 | 1.3341
| SIDE | SQM | 1 | 1 | 4.105 |  | 0.315 | 1.2931
| B14 200X450 | SQM | 1 | 1 | 1.5 |  | 0.2 | 0.3
| SIDE | SQM | 1 | 1 | 1.5 |  | 0.325 | 0.4875
| SIDE | SQM | 1 | 1 | 1.5 |  | 0.325 | 0.4875
| B14 200X450 | SQM | 1 | 1 | 2.2 |  | 0.2 | 0.44
| SIDE | SQM | 1 | 1 | 2.2 |  | 0.315 | 0.693
| SIDE | SQM | 1 | 1 | 2.2 |  | 0.3 | 0.66
| B15 200X500 | SQM | 1 | 1 | 3.115 |  | 0.2 | 0.623
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.375 | 1.1681
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.5 | 1.5575
| B16 200X350 | SQM | 1 | 3 | 1.02 |  | 0.2 | 0.612
| SIDE | SQM | 1 | 3 | 1.02 |  | 0.225 | 0.6885
| SIDE | SQM | 1 | 3 | 1.02 |  | 0.35 | 1.071
| B16 200X500 | SQM | 1 | 3 | 3.35 |  | 0.2 | 2.01
| SIDE | SQM | 1 | 3 | 3.35 |  | 0.3 | 3.015
| SIDE | SQM | 1 | 3 | 3.35 |  | 0.365 | 3.6683
| B16 200X500 | SQM | 1 | 3 | 3.25 |  | 0.2 | 1.95
| SIDE | SQM | 1 | 3 | 3.25 |  | 0.365 | 3.5587
| SIDE | SQM | 1 | 3 | 2.28 |  | 0.3 | 2.052
| SIDE | SQM | 1 | 3 | 0.97 |  | 0.5 | 1.455
| B17 200X500 | SQM | 1 | 1 | 3.215 |  | 0.2 | 0.643
| SIDE | SQM | 1 | 1 | 3.215 |  | 0.35 | 1.1252
| SIDE | SQM | 1 | 1 | 3.215 |  | 0.3 | 0.9645
| B18 230X500 | SQM | 1 | 1 | 2.76 |  | 0.23 | 0.6348
| SIDE | SQM | 1 | 1 | 2.76 |  | 0.365 | 1.0074
| SIDE | SQM | 1 | 1 | 2.76 |  | 0.5 | 1.38
| B19 200X450 | SQM | 1 | 1 | 6.79 |  | 0.2 | 1.358
| SIDE | SQM | 1 | 1 | 6.79 |  | 0.3 | 2.037
| SIDE | SQM | 1 | 1 | 6.79 |  | 0.3 | 2.037
| B20 200X350 | SQM | 1 | 1 | 2.41 |  | 0.2 | 0.482
| SIDE | SQM | 1 | 1 | 2.41 |  | 0.35 | 0.8435
| SIDE | SQM | 1 | 1 | 2.41 |  | 0.35 | 0.8435
| B21 230X450 | SQM | 1 | 1 | 5.76 |  | 0.23 | 1.3248
| SIDE | SQM | 1 | 1 | 2.61 |  | 0.325 | 0.84825
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.45 | 1.4175
| SIDE | SQM | 1 | 1 | 3.035 |  | 0.45 | 1.3658
| SIDE | SQM | 1 | 1 | 2.725 |  | 0.325 | 0.88563
| B22 200x450 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.325 | 1.5243
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.315 | 1.4774
| B23 200X450 | SQM | 1 | 1 | 2.22 |  | 0.2 | 0.444
| SIDE | SQM | 1 | 1 | 2.22 |  | 0.325 | 0.7215
| SIDE | SQM | 1 | 1 | 2.22 |  | 0.3 | 0.666
| B24 200X450 | SQM | 1 | 1 | 5.63 |  | 0.2 | 1.126
| SIDE | SQM | 1 | 2 | 5.63 |  | 0.45 | 5.067
| B25 200X450 | SQM | 1 | 1 | 1.5 |  | 0.2 | 0.3
| SIDE | SQM | 1 | 2 | 1.5 |  | 0.325 | 0.975
| B25 200X500 | SQM | 1 | 1 | 2.085 |  | 0.2 | 0.417
| SIDE | SQM | 1 | 2 | 2.085 |  | 0.325 | 1.3553
| B25 200X450 BESIDE STAIRS | SQM | 1 | 1 | 5.63 |  | 0.2 | 1.126
| SIDE | SQM | 1 | 1 | 5.63 |  | 0.45 | 2.5335
| SIDE | SQM | 1 | 1 | 5.63 |  | 0.325 | 1.8297
| B26 200X450 | SQM | 1 | 3 | 3.235 |  | 0.2 | 1.941
| SIDE | SQM | 1 | 3 | 3.235 |  | 0.315 | 3.0571
| SIDE | SQM | 1 | 3 | 1.61 |  | 0.3 | 1.449
| SIDE | SQM | 1 | 3 | 1.625 |  | 0.325 | 1.5844
| B26 200X450 | SQM | 1 | 3 | 4.72 |  | 0.2 | 2.832
| SIDE | SQM | 1 | 3 | 3.15 |  | 0.315 | 2.9768
| SIDE | SQM | 1 | 3 | 1.57 |  | 0.325 | 1.5308
| SIDE | SQM | 1 | 3 | 4.72 |  | 0.325 | 4.602
| B27 200X350 | SQM | 1 | 3 | 2.575 |  | 0.2 | 1.545
| SIDE | SQM | 1 | 3 | 2.575 |  | 0.225 | 1.7381
| SIDE | SQM | 1 | 3 | 2.575 |  | 0.35 | 2.7037
| B27 200X500 | SQM | 1 | 3 | 3.165 |  | 0.2 | 1.899
| SIDE | SQM | 1 | 3 | 3.165 |  | 0.375 | 3.5606
| SIDE | SQM | 1 | 3 | 3.165 |  | 0.5 | 4.7475
| B28 200X450 | SQM | 1 | 1 | 5.125 |  | 0.2 | 1.025
| SIDE | SQM | 1 | 1 | 5.125 |  | 0.3 | 1.5375
| SIDE | SQM | 1 | 1 | 1.69 |  | 0.325 | 0.54925
| SIDE | SQM | 1 | 1 | 3.435 |  | 0.315 | 1.082
| B29 200X450 | SQM | 1 | 1 | 1.9 |  | 0.2 | 0.38
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.325 | 0.6175
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.45 | 0.855
| B29 200X450 | SQM | 1 | 1 | 1.9 |  | 0.2 | 0.38
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.325 | 0.6175
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.45 | 0.855
| B29 200X450 | SQM | 1 | 1 | 1.4 |  | 0.2 | 0.28
| SIDE | SQM | 1 | 2 | 1.4 |  | 0.325 | 0.91
| B30 200X350 | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 0.315 |  | 0.35 | 0.11025
| SIDE | SQM | 1 | 1 | 2.615 |  | 0.15 | 0.39225
| B30 200X500 | SQM | 1 | 1 | 2.875 |  | 0.2 | 0.575
| SIDE | SQM | 1 | 1 | 1.55 |  | 0.3 | 0.465
| SIDE | SQM | 1 | 1 | 1.325 |  | 0.375 | 0.49687
| SIDE | SQM | 1 | 1 | 2.875 |  | 0.375 | 1.0781
| B30 200X450 | SQM | 1 | 1 | 3.95 |  | 0.2 | 0.79
| SIDE | SQM | 1 | 1 | 3.95 |  | 0.325 | 1.2838
| SIDE | SQM | 1 | 1 | 3.95 |  | 0.325 | 1.2838
| B31 200X500 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.365 | 1.7119
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.3 | 1.407
| B31 200X500 | SQM | 1 | 1 | 3.15 |  | 0.2 | 0.63
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.5 | 1.575
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.5 | 1.575
| B32 230X450 | SQM | 1 | 2 | 1.9 |  | 0.23 | 0.874
| SIDE | SQM | 1 | 2 | 1.9 |  | 0.325 | 1.235
| SIDE | SQM | 1 | 2 | 1.9 |  | 0.45 | 1.71
| B33 200X350 | SQM | 1 | 1 | 5.235 |  | 0.2 | 1.047
| SIDE | SQM | 1 | 2 | 3.235 |  | 0.215 | 1.391
| SIDE | SQM | 1 | 2 | 2 |  | 0.168 | 0.672
| B34 230X450 | SQM | 1 | 1 | 5.1 |  | 0.23 | 1.173
| SIDE | SQM | 1 | 1 | 5.1 |  | 0.3 | 1.53
| SIDE | SQM | 1 | 1 | 3.475 |  | 0.315 | 1.0946
| SIDE | SQM | 1 | 1 | 1.625 |  | 0.325 | 0.52812
| B34 230X450 | SQM | 1 | 1 | 5.1 |  | 0.23 | 1.173
| SIDE | SQM | 1 | 1 | 5.1 |  | 0.3 | 1.53
| SIDE | SQM | 1 | 1 | 3.475 |  | 0.315 | 1.0946
| SIDE | SQM | 1 | 1 | 1.625 |  | 0.325 | 0.52812
| B35 200X500 | SQM | 1 | 2 | 3.19 |  | 0.2 | 1.276
| SIDE | SQM | 1 | 2 | 3.19 |  | 0.3 | 1.914
| SIDE | SQM | 1 | 2 | 3.19 |  | 0.35 | 2.233
| B36 200X500 | SQM | 1 | 3 | 1.81 |  | 0.2 | 1.086
| SIDE | SQM | 1 | 3 | 1.81 |  | 0.375 | 2.0362
| SIDE | SQM | 1 | 3 | 1.81 |  | 0.5 | 2.715
| B36 200X500 | SQM | 1 | 3 | 3.55 |  | 0.2 | 2.13
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.375 | 3.9937
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.5 | 5.325
| B36 230X500 | SQM | 1 | 3 | 0.515 |  | 0.23 | 0.35535
| SIDE | SQM | 1 | 3 | 0.515 |  | 0.5 | 0.7725
| SIDE | SQM | 1 | 3 | 0.515 |  | 0.5 | 0.7725
| B37 200X450 | SQM | 1 | 3 | 3.86 |  | 0.2 | 2.316
| SIDE | SQM | 1 | 3 | 3.86 |  | 0.315 | 3.6477
| SIDE | SQM | 1 | 3 | 3.86 |  | 0.325 | 3.7635
| B38 200X450 | SQM | 3 | 1 | 3.45 |  | 0.2 | 2.07
| SIDE | SQM | 3 | 2 | 3.45 |  | 0.325 | 6.7275
| B39 200X450 | SQM | 1 | 3 | 2.91 |  | 0.2 | 1.746
| SIDE | SQM | 1 | 3 | 2.91 |  | 0.315 | 2.75
| SIDE | SQM | 1 | 3 | 2.91 |  | 0.315 | 2.75
| B39 230X350 | SQM | 1 | 3 | 3.55 |  | 0.23 | 2.4495
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.225 | 2.3962
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.225 | 2.3962
| B40 200X450 | SQM | 1 | 2 | 3 |  | 0.2 | 1.2
| SIDE | SQM | 1 | 2 | 3 |  | 0.3 | 1.8
| SIDE | SQM | 1 | 2 | 3 |  | 0.325 | 1.95
| B40 200X350 | SQM | 1 | 2 | 2.065 |  | 0.2 | 0.826
| SIDE | SQM | 1 | 2 | 2.065 |  | 0.215 | 0.88795
| SIDE | SQM | 1 | 2 | 2.065 |  | 0.15 | 0.6195
| B41 200X500 | SQM | 1 | 3 | 3.31 |  | 0.2 | 1.986
| SIDE | SQM | 1 | 3 | 3.31 |  | 0.35 | 3.4755
| SIDE | SQM | 1 | 3 | 3.31 |  | 0.365 | 3.6244
| B42 200X450 | SQM | 1 | 2 | 3 |  | 0.2 | 1.2
| SIDE | SQM | 1 | 2 | 3 |  | 0.325 | 1.95
| SIDE | SQM | 1 | 2 | 3 |  | 0.315 | 1.89
| B43 200X450 | SQM | 1 | 1 | 5.245 |  | 0.2 | 1.049
| SIDE | SQM | 1 | 2 | 5.245 |  | 0.3 | 3.147
| B44 200X450 | SQM | 1 | 1 | 3 |  | 0.2 | 0.6
| SIDE | SQM | 1 | 1 | 3 |  | 0.3 | 0.9
| SIDE | SQM | 1 | 1 | 3 |  | 0.325 | 0.975
| B44 200X350 | SQM | 1 | 1 | 1.95 |  | 0.2 | 0.39
| SIDE | SQM | 1 | 1 | 1.95 |  | 0.15 | 0.2925
| SIDE | SQM | 1 | 1 | 1.95 |  | 0.215 | 0.41925
| B45 200X450 | SQM | 1 | 1 | 2.23 |  | 0.2 | 0.446
| SIDE | SQM | 1 | 1 | 2.23 |  | 0.315 | 0.70245
| SIDE | SQM | 1 | 1 | 2.23 |  | 0.325 | 0.72475
| B46 200X500 | SQM | 1 | 1 | 5.145 |  | 0.2 | 1.029
| SIDE | SQM | 1 | 1 | 5.145 |  | 0.35 | 1.8007
| SIDE | SQM | 1 | 1 | 2.775 |  | 0.375 | 1.0406
| SIDE | SQM | 1 | 1 | 2.37 |  | 0.5 | 1.185
| B47 200X500 | SQM | 1 | 1 | 3.8 |  | 0.2 | 0.76
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.375 | 0.6375
| SIDE | SQM | 1 | 1 | 2.1 |  | 0.365 | 0.7665
| SIDE | SQM | 1 | 1 | 3.8 |  | 0.5 | 1.9
| B48 200X350 | SQM | 1 | 1 | 2.95 |  | 0.2 | 0.59
| SIDE | SQM | 1 | 1 | 2.95 |  | 0.225 | 0.66375
| SIDE | SQM | 1 | 1 | 2.95 |  | 0.35 | 1.0325
| B49 200X450 | SQM | 1 | 1 | 4.55 |  | 0.2 | 0.91
| SIDE | SQM | 1 | 2 | 3.15 |  | 0.315 | 1.9845
| SIDE | SQM | 1 | 2 | 1.4 |  | 0.325 | 0.91
| B50 200X500 | SQM | 1 | 1 | 3.05 |  | 0.2 | 0.61
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.365 | 1.1132
| SIDE | SQM | 1 | 1 | 1.85 |  | 0.35 | 0.6475
| SIDE | SQM | 1 | 1 | 1.2 |  | 0.3 | 0.36
| B51 200X450 | SQM | 1 | 1 | 2.5 |  | 0.2 | 0.5
| SIDE | SQM | 1 | 2 | 2.5 |  | 0.325 | 1.625
| B52 230X500 | SQM | 1 | 1 | 3.115 |  | 0.23 | 0.71645
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.35 | 1.0902
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.375 | 1.1681
| B53 200X350 | SQM | 1 | 1 | 2.335 |  | 0.2 | 0.467
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.15 | 0.35025
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.215 | 0.50202
| B54 230X500 | SQM | 1 | 1 | 3.2 |  | 0.23 | 0.736
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.325 | 1.04
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.5 | 1.6
| B55 230X450 | SQM | 1 | 1 | 0.35 |  | 0.23 | 0.0805
| SIDE | SQM | 1 | 2 | 0.35 |  | 0.45 | 0.315
| B56 200X450 | SQM | 1 | 1 | 1.96 |  | 0.2 | 0.392
| SIDE | SQM | 1 | 2 | 1.96 |  | 0.325 | 1.274
| B57 230X450 | SQM | 1 | 1 | 3.2 |  | 0.23 | 0.736
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.325 | 1.04
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.45 | 1.44
| B57 200X450 | SQM | 1 | 1 | 2.335 |  | 0.2 | 0.467
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.315 | 0.73552
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.325 | 0.75887
| B58 230X500 | SQM | 1 | 1 | 2.54 |  | 0.23 | 0.5842
| SIDE | SQM | 1 | 1 | 2.54 |  | 0.375 | 0.9525
| SIDE | SQM | 1 | 1 | 2.54 |  | 0.5 | 1.27
| B58 230X450 | SQM | 1 | 1 | 3.43 |  | 0.23 | 0.7889
| SIDE | SQM | 1 | 2 | 3.43 |  | 0.325 | 2.2295
| B59 200X500 | SQM | 1 | 1 | 2.225 |  | 0.2 | 0.445
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.318 | 0.70755
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.375 | 0.83438
| B60 200X450 | SQM | 1 | 1 | 3.14 |  | 0.2 | 0.628
| SIDE | SQM | 1 | 1 | 3.14 |  | 0.3 | 0.942
| SIDE | SQM | 1 | 1 | 3.14 |  | 0.325 | 1.0205
| B61 200X450 | SQM | 1 | 1 | 3.43 |  | 0.2 | 0.686
| SIDE | SQM | 1 | 1 | 3.43 |  | 0.315 | 1.0805
| SIDE | SQM | 1 | 1 | 1.205 |  | 0.325 | 0.39163
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.3 | 0.6675
| B61 230X450 | SQM | 1 | 1 | 1.99 |  | 0.23 | 0.4577
| SIDE | SQM | 1 | 1 | 1.99 |  | 0.325 | 0.64675
| SIDE | SQM | 1 | 1 | 1.99 |  | 0.3 | 0.597
| B62 200X500 | SQM | 1 | 1 | 2.225 |  | 0.2 | 0.445
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.318 | 0.70755
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.375 | 0.83438
| B63 200X450 | SQM | 1 | 1 | 3.06 |  | 0.2 | 0.612
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.3 | 0.918
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.315 | 0.9639
| B63 200X450 | SQM | 1 | 1 | 3.06 |  | 0.2 | 0.612
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.3 | 0.918
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.325 | 0.9945
| B64 200X350 | SQM | 1 | 2 | 3.05 |  | 0.2 | 1.22
| SIDE | SQM | 1 | 2 | 3.05 |  | 0.215 | 1.3115
| SIDE | SQM | 1 | 2 | 1.32 |  | 0.35 | 0.924
| SIDE | SQM | 1 | 2 | 1.73 |  | 0.2 | 0.692
| B64 200X350 | SQM | 1 | 2 | 0.38 |  | 0.2 | 0.152
| SIDE | SQM | 1 | 2 | 0.38 |  | 0.35 | 0.266
| B65 200X450 | SQM | 1 | 2 | 3.385 |  | 0.2 | 1.354
| SIDE | SQM | 1 | 2 | 3.385 |  | 0.325 | 2.2003
| SIDE | SQM | 1 | 2 | 3.385 |  | 0.3 | 2.031
| B66 200X450 | SQM | 2 | 1 | 3.25 |  | 0.2 | 1.3
| SIDE | SQM | 2 | 2 | 3.25 |  | 0.315 | 4.095
| B66 200X450 | SQM | 2 | 1 | 1.7 |  | 0.2 | 0.68
| SIDE | SQM | 2 | 2 | 1.7 |  | 0.325 | 2.21
| B66 200X350 | SQM | 1 | 2 | 1.385 |  | 0.2 | 0.554
| SIDE | SQM | 1 | 2 | 1.385 |  | 0.225 | 0.62325
| SIDE | SQM | 1 | 2 | 1.385 |  | 0.35 | 0.9695
| B67 200X450 | SQM | 1 | 1 | 3.05 |  | 0.2 | 0.61
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.315 | 0.96075
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.45 | 1.3725
| B67 200X450 | SQM | 1 | 1 | 1.7 |  | 0.2 | 0.34
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.325 | 0.5525
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.45 | 0.765
| B67 200X450 | SQM | 1 | 1 | 3.05 |  | 0.2 | 0.61
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.315 | 0.96075
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.315 | 0.96075
| B67 200X450 | SQM | 1 | 1 | 1.7 |  | 0.2 | 0.34
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.325 | 0.5525
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.325 | 0.5525
| B68 200X350 | SQM | 1 | 1 | 3.17 |  | 0.2 | 0.634
| SIDE | SQM | 1 | 1 | 3.17 |  | 0.225 | 0.71325
| SIDE | SQM | 1 | 1 | 3.17 |  | 0.35 | 1.1095
| B69 200X450 | SQM | 1 | 0.5 | 5.78 |  | 0.2 | 0.578
| SIDE | SQM | 1 | 0.5 | 3.78 |  | 0.315 | 0.59535
| SIDE | SQM | 1 | 0.5 | 3.78 |  | 0.315 | 0.59535
| SIDE | SQM | 1 | 0.5 | 2 |  | 0.268 | 0.268
| SIDE | SQM | 1 | 0.5 | 2 |  | 0.268 | 0.268
389.2135
FLAT NO 9
| Bed room 1 | CUM | 1 | 1 | 3.575 | 3.55 |  | 12.6913
| Bed Room 2 | CUM | 1 | 1 | 3.55 | 3.2 |  | 11.36
| Bed Room 3 | CUM | 1 | 1 | 3.145 | 3.05 |  | 9.5922
|  | CUM | 1 | 1 | 0.9 | 0.4 |  | 0.36
| Service slab | CUM | 1 | 1 | 1.165 | 0.515 |  | 0.59998
| TOILET 1 | CUM | 1 | 1 | 3.575 | 1.57 |  | 5.6128
| TOILET 2 | CUM | 1 | 1 | 2.5 | 1.6 |  | 4
| PASSAGE | CUM | 1 | 1 | 2.785 | 1.2 |  | 3.342
| Living | CUM | 1 | 1 | 6.365 | 3.72 |  | 23.6778
|  | CUM | 1 | 1 | 4.115 | 0.385 |  | 1.5843
| Entry/ Porch | CUM | 1 | 1 | 1.5 | 1.035 |  | 1.5525
| Kitchen | CUM | 1 | 1 | 2.85 | 2.335 |  | 6.6547
| Balcony 1 | CUM | 1 | 1 | 6.3 | 2 |  | 12.6
| Balcony 2 | CUM | 1 | 1 | 4.065 | 2 |  | 8.13
| Kitchen Balcony | CUM | 1 | 1 | 1.4 | 2 |  | 2.8
|  | CUM | 1 | 1 | 1.185 | 0.435 |  | 0.51548
105.073
| FLAT NO 8 | [6 empty] | 0
| B. ROOM 1 | CUM | 1 | 1 | 3.56 | 3.275 |  | 11.659
| B. ROOM 2 | CUM | 1 | 1 | 3.25 | 2.925 |  | 9.5062
| B. ROOM 3 | CUM | 1 | 1 | 3.58 | 3.05 |  | 10.919
| PASSAGE | CUM | 1 | 1 | 2.925 | 1.7 |  | 4.9725
| KITCHEN | CUM | 1 | 1 | 3.25 | 2.365 |  | 7.6863
| LIVING | CUM | 1 | 1 | 5.23 | 3.33 |  | 17.4159
|  | CUM | 1 | 1 | 3.4 | 0.94 |  | 3.196
|  | CUM | 1 | 1 | 2.55 | 1.47 |  | 3.7485
| DRESSING AREA | CUM | 1 | 1 | 2.41 | 1.43 |  | 3.4463
| TOILET 1 | CUM | 1 | 1 | 2.225 | 1.495 |  | 3.3264
| TOILET 2 | CUM | 1 | 1 | 3.385 | 1.425 |  | 4.8236
| TOILET 3 | CUM | 1 | 1 | 2.41 | 1.54 |  | 3.7114
| BALCONY 1 | CUM | 1 | 1 | 4.665 | 2 |  | 9.33
| BALCONY 2 | CUM | 1 | 1 | 5.105 | 2 |  | 10.21
| BALCONY 3 | CUM | 1 | 1 | 3.265 | 2 |  | 6.53
110.4811
| FLAT NO 7 | [6 empty] | 0
| B. ROOM 1 | CUM | 1 | 1 | 3.56 | 3.245 |  | 11.5522
| B. ROOM 2 | CUM | 1 | 1 | 3.25 | 2.925 |  | 9.5062
| PASSAGE | CUM | 1 | 1 | 2.925 | 1.7 |  | 4.9725
| KITCHEN | CUM | 1 | 1 | 3.25 | 2.365 |  | 7.6863
| LIVING | CUM | 1 | 1 | 5.23 | 3.33 |  | 17.4159
|  | CUM | 1 | 1 | 3.4 | 0.94 |  | 3.196
|  | CUM | 1 | 1 | 2.55 | 1.47 |  | 3.7485
| TOILET 1 | CUM | 1 | 1 | 2.225 | 1.495 |  | 3.3264
| TOILET 2 | CUM | 1 | 1 | 3.385 | 1.425 |  | 4.8236
| BALCONY 1 | CUM | 1 | 1 | 4.665 | 2 |  | 9.33
| BALCONY 2 | CUM | 1 | 1 | 5.105 | 2 |  | 10.21
85.7676
FLAT NO 10,11,12
| B. ROOM 1 |  | 3 | 1 | 3.86 | 3.25 |  | 37.635
| B. ROOM 2 |  | 3 | 1 | 3.86 | 3.335 |  | 38.6193
| B. ROOM 3 |  | 3 | 1 | 3.55 | 3.265 |  | 34.7722
| Living |  | 3 | 1 | 6.245 | 3.315 |  | 62.1065
|  |  | 3 | 1 | 3.17 | 1.91 |  | 18.1641
| KITCHEN |  | 3 | 1 | 3.435 | 2.345 |  | 24.1652
| TOILET 1 |  | 3 | 1 | 3.86 | 1.44 |  | 16.6752
| TOILET 2 |  | 3 | 1 | 3.55 | 1.425 |  | 15.1762
| TOILET 3 |  | 3 | 1 | 3.55 | 1.425 |  | 15.1762
| Service slab |  | 3 | 1 | 1.245 | 0.515 |  | 1.9235
| Service slab |  | 3 | 1 | 0.97 | 0.415 |  | 1.2076
| BALCONY 1 |  | 3 | 1 | 5.93 | 2 |  | 35.58
| BALCONY 2 |  | 3 | 1 | 3.565 | 2 |  | 21.39
| BALCONY 3 |  | 3 | 1 | 1.55 | 2 |  | 9.3
331.8913
| FLAT 7,8 & 9 LOBBY |  | 1 | 1 | 5.09 | 1.5 |  | 7.635
|  |  | 1 | 1 | 3.14 | 0.955 |  | 2.9987
| LIFT LOBBY |  | 1 | 1 | 3.95 | 1.61 |  | 6.3595
|  |  | 1 | 1 | 5.635 | 2.44 |  | 13.7494
| FLAT 10,11,12 LOBBY |  | 1 | 1 | 4.79 | 3.19 |  | 15.2801
|  |  | 1 | 1 | 1.4 | 0.655 |  | 0.917
Main s/case (2 No)
| Half landing |  | 1 | 2 | 1.5 | 1.5 |  | 4.5
| freight |  | 1 | 2 | 2.409 | 1.5 |  | 7.227
| mid freight |  | 1 | 1 | 1.484 | 1.5 |  | 2.226
| top landing |  | 1 | 1 | 3.96 | 0.26 |  | 1.0296
| landing beam 230x450 |  | 1 | 1 | 3.53 | 0.23 |  | 0.8119
| SIDE |  | 1 | 1 | 3.53 | 0.275 |  | 0.97075
| SIDE |  | 1 | 1 | 3.53 | 0.45 |  | 1.5885
Fire s/case (4 No)
| mid & full landing |  | 1 | 2 | 3.2 | 1.5 |  | 9.6
| freight |  | 1 | 2 | 3.343 | 1.5 |  | 10.029
| landing beam 230x450 |  | 1 | 1 | 3.2 | 0.23 |  | 0.736
| SIDE |  | 1 | 1 | 3.2 | 0.275 |  | 0.88
| SIDE |  | 1 | 1 | 3.2 | 0.45 |  | 1.44
87.9784
COLUMN (22-43/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 31 | 1 | 0.3 | 0.6 | 0.45 | 25.11
2 | C4, C5 (300X750) | CUM | 15 | 1 | 0.3 | 0.7 | 0.45 | 13.5
3 | C6, C11 (300X715) | CUM | 7 | 1 | 0.3 | 0.715 | 0.45 | 6.3945
4 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 0.45 | 1.98
5 | SW 1 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.792
6 |  | CUM | 1 | 1 | 0.23 | 1.42 | 0.45 | 1.485
7 | SW 2 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.792
8 |  | CUM | 1 | 1 | 0.23 | 1.62 | 0.45 | 1.665
9 | SW 3 (230x1000) | CUM | 1 | 1 | 0.23 | 1 | 0.45 | 1.107
10 | SW 4 (230x1150) | CUM | 1 | 1 | 0.23 | 1.15 | 0.45 | 1.242
11 | SW 5 (230x1700) | CUM | 2 | 1 | 0.23 | 1.7 | 0.45 | 3.474
12 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 0.45 | 2.547
13 | SW 7 (230x1855) | CUM | 1 | 1 | 0.23 | 1.855 | 0.45 | 1.8765
14 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 0.45 | 3.447
15 | SW 9 (L-SHAPE) | CUM | 3 | 1 | 0.23 | 0.65 | 0.45 | 2.376
16 |  | CUM | 3 | 1 | 0.23 | 1.62 | 0.45 | 4.995
17 | SW 10 (230x3445) | CUM | 1 | 1 | 0.23 | 3.445 | 0.45 | 3.3075
18 | SW 11 (230x4065) | CUM | 1 | 1 | 0.23 | 4.065 | 0.45 | 3.8655
19 | SW 12 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.792
20 |  | CUM | 1 | 1 | 0.23 | 1.305 | 0.45 | 1.3815
21 | SW 13 (200x3445) | CUM | 1 | 1 | 0.2 | 3.445 | 0.45 | 3.2805
85.41
1195.8149
| COLUMN (1-22/A-Q) FROM 1ST FLOOR LVL to 2nd floor LVL | [7 empty] | 10TH RA
1 | C1, C2, C3, C8, C9, C10 (300X600) | SQM | 31 | 1 | 0.3 | 0.6 | 2.5 | 139.5
2 | C4, C5 (300X750) | SQM | 15 | 1 | 0.3 | 0.7 | 2.5 | 75
3 | C6, C11 (300X715) | SQM | 7 | 1 | 0.3 | 0.715 | 2.5 | 35.525
4 | C7 (300X800) | SQM | 2 | 1 | 0.3 | 0.8 | 2.5 | 11
5 | SW 1 (L-SHAPE) | SQM | 1 | 1 | 0.23 | 0.65 | 2.5 | 4.4
6 |  | SQM | 1 | 1 | 0.23 | 1.42 | 2.5 | 8.25
7 | SW 2 (L-SHAPE) | SQM | 1 | 1 | 0.23 | 0.65 | 2.5 | 4.4
8 |  | SQM | 1 | 1 | 0.23 | 1.62 | 2.5 | 9.25
9 | SW 3 (230x1000) | SQM | 1 | 1 | 0.23 | 1 | 2.5 | 6.15
10 | SW 4 (230x1150) | SQM | 1 | 1 | 0.23 | 1.15 | 2.5 | 6.9
11 | SW 5 (230x1700) | SQM | 2 | 1 | 0.23 | 1.7 | 2.5 | 19.3
12 | SW 6 (230x1185) | SQM | 2 | 1 | 0.23 | 1.185 | 2.5 | 14.15
13 | SW 7 (230x1855) | SQM | 1 | 1 | 0.23 | 1.855 | 2.5 | 10.425
14 | SW 8 (230x3600) | SQM | 0 | 0 | 0.23 | 3.6 | 2.5 | 0
15 | SW 9 (L-SHAPE) | SQM | 3 | 1 | 0.23 | 0.65 | 2.5 | 13.2
16 |  | SQM | 3 | 1 | 0.23 | 1.62 | 2.5 | 27.75
17 | SW 10 (230x3445) | SQM | 1 | 1 | 0.23 | 3.445 | 2.5 | 18.375
18 | SW 11 (230x4065) | SQM | 1 | 1 | 0.23 | 4.065 | 2.5 | 21.475
19 | SW 12 (L-SHAPE) | SQM | 1 | 1 | 0.23 | 0.65 | 2.5 | 4.4
20 |  | SQM | 1 | 1 | 0.23 | 1.305 | 2.5 | 7.675
21 | SW 13 (200x3445) | SQM | 1 | 1 | 0.2 | 3.445 | 2.5 | 18.225
COLUMN (22-43/A-Q) FROM 1ST FLOOR LVL to 2nd floor LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | SQM | 31 | 1 | 0.3 | 0.6 | 2.5 | 139.5
2 | C4, C5 (300X750) | SQM | 15 | 1 | 0.3 | 0.7 | 2.5 | 75
3 | C6, C11 (300X715) | SQM | 7 | 1 | 0.3 | 0.715 | 2.5 | 35.525
4 | C7 (300X800) | SQM | 2 | 1 | 0.3 | 0.8 | 2.5 | 11
5 | SW 1 (L-SHAPE) | SQM | 1 | 1 | 0.23 | 0.65 | 2.5 | 4.4
6 |  | SQM | 1 | 1 | 0.23 | 1.42 | 2.5 | 8.25
7 | SW 2 (L-SHAPE) | SQM | 1 | 1 | 0.23 | 0.65 | 2.5 | 4.4
8 |  | SQM | 1 | 1 | 0.23 | 1.62 | 2.5 | 9.25
9 | SW 3 (230x1000) | SQM | 1 | 1 | 0.23 | 1 | 2.5 | 6.15
10 | SW 4 (230x1150) | SQM | 1 | 1 | 0.23 | 1.15 | 2.5 | 6.9
11 | SW 5 (230x1700) | SQM | 2 | 1 | 0.23 | 1.7 | 2.5 | 19.3
12 | SW 6 (230x1185) | SQM | 2 | 1 | 0.23 | 1.185 | 2.5 | 14.15
13 | SW 7 (230x1855) | SQM | 1 | 1 | 0.23 | 1.855 | 2.5 | 10.425
14 | SW 8 (230x3600) | SQM | 1 | 2 | 0.23 | 3.6 | 2.5 | 38.3
15 | SW 9 (L-SHAPE) | SQM | 3 | 1 | 0.23 | 0.65 | 2.5 | 13.2
16 |  | SQM | 3 | 1 | 0.23 | 1.62 | 2.5 | 27.75
17 | SW 10 (230x3445) | SQM | 1 | 1 | 0.23 | 3.445 | 2.5 | 18.375
18 | SW 11 (230x4065) | SQM | 1 | 1 | 0.23 | 4.065 | 2.5 | 21.475
19 | SW 12 (L-SHAPE) | SQM | 1 | 1 | 0.23 | 0.65 | 2.5 | 4.4
20 |  | SQM | 1 | 1 | 0.23 | 1.305 | 2.5 | 7.675
21 | SW 13 (200x3445) | SQM | 1 | 1 | 0.2 | 3.445 | 2.5 | 18.225
[6 empty] | Total of 2nd floor LVL column shuttering |  | 949
SLAB SHUTTERING
| B1 200X500 | SQM | 1 | 1 | 3.025 |  | 0.2 | 0.605
| SIDE | SQM | 1 | 1 | 3.025 |  | 0.3 | 0.9075
| SIDE | SQM | 1 | 1 | 3.025 |  | 0.365 | 1.1041
| B1 200X500 | SQM | 1 | 1 | 2.8 | 0.5 | 0.2 | 0.28
| SIDE | SQM | 1 | 1 | 2.8 |  | 0.3 | 0.84
| SIDE | SQM | 1 | 1 | 2.8 |  | 0.365 | 1.022
| B2 200X500 | SQM | 1 | 1 | 3.3 |  | 0.2 | 0.66
| SIDE | SQM | 1 | 1 | 3.3 |  | 0.3 | 0.99
| SIDE | SQM | 1 | 1 | 3.3 |  | 0.35 | 1.155
| B3 AT GRID B-C/27-28 | SQM | 1 | 1 | 1.395 |  | 0.1 | 0.1395
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.35 | 0.9765
| B3 AT GRID L-M/27-28 | SQM | 1 | 1 | 1.395 |  | 0.115 | 0.16043
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.35 | 0.9765
| B3 AT GRID E/32-33 | SQM | 1 | 1 | 1.185 |  | 0.1 | 0.1185
| SIDE | SQM | 1 | 2 | 1.185 |  | 0.35 | 0.8295
| B3 AT GRID F/43 | SQM | 3 | 1 | 2.055 |  | 0.1 | 0.6165
| SIDE | SQM | 3 | 2 | 2.055 |  | 0.35 | 4.3155
| B3 AT GRID F/39-40 | SQM | 3 | 1 | 1.485 |  | 0.1 | 0.4455
| SIDE | SQM | 3 | 2 | 1.485 |  | 0.35 | 3.1185
| B3 AT GRID M & O/39-40 | SQM | 3 | 1 | 2.315 |  | 0.1 | 0.6945
| SIDE | SQM | 3 | 2 | 2.315 |  | 0.35 | 4.8615
| B3 AT GRID C,K/25 | SQM | 2 | 1 | 2.315 |  | 0.1 | 0.463
| SIDE | SQM | 2 | 2 | 2.315 |  | 0.35 | 3.241
| B4 200X350 | SQM | 1 | 2 | 1.395 |  | 0.2 | 0.558
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.35 | 0.9765
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.225 | 0.62775
| B5 200X450 | SQM | 1 | 1 | 6.875 |  | 0.2 | 1.375
| SIDE | SQM | 1 | 1 | 6.875 |  | 0.315 | 2.1656
| SIDE | SQM | 1 | 1 | 6.875 |  | 0.325 | 2.2344
| B6 230X350 | SQM | 1 | 1 | 3.16 |  | 0.23 | 0.7268
| SIDE | SQM | 1 | 1 | 3.16 |  | 0.225 | 0.711
| SIDE | SQM | 1 | 1 | 2.145 |  | 0.225 | 0.48262
| SIDE | SQM | 1 | 1 | 1.015 |  | 0.35 | 0.35525
| B7 200X450 | SQM | 1 | 1 | 2.7 |  | 0.2 | 0.54
| SIDE | SQM | 1 | 1 | 2.7 |  | 0.325 | 0.8775
| SIDE | SQM | 1 | 1 | 2.7 |  | 0.325 | 0.8775
| B8 200X500 | SQM | 1 | 1 | 2.875 |  | 0.2 | 0.575
| SIDE | SQM | 1 | 1 | 2.875 |  | 0.365 | 1.0494
| SIDE | SQM | 1 | 1 | 1.55 |  | 0.3 | 0.465
| SIDE | SQM | 1 | 1 | 1.325 |  | 0.375 | 0.49687
| B8 200X350 | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 2.615 |  | 0.15 | 0.39225
| SIDE | SQM | 1 | 1 | 0.315 |  | 0.35 | 0.11025
| B9 200X500 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.3 | 1.407
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.365 | 1.7119
| B10 200X500 | SQM | 1 | 1 | 3.15 |  | 0.2 | 0.63
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.3 | 0.945
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.365 | 1.1498
| B11 200X450 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.315 | 1.4774
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.325 | 1.5243
| B12 200X450 | SQM | 1 | 1 | 5.76 |  | 0.2 | 1.152
| SIDE | SQM | 1 | 1 | 3.035 |  | 0.315 | 0.95603
| SIDE | SQM | 1 | 1 | 2.725 |  | 0.325 | 0.88563
| SIDE | SQM | 1 | 1 | 2.61 |  | 0.325 | 0.84825
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.45 | 1.4175
| B13 200X350 | SQM | 1 | 1 | 1.6 |  | 0.2 | 0.32
| SIDE | SQM | 1 | 1 | 1.6 |  | 0.225 | 0.36
| SIDE | SQM | 1 | 1 | 1.6 |  | 0.35 | 0.56
| B13 200X450 | SQM | 1 | 1 | 4.105 |  | 0.2 | 0.821
| SIDE | SQM | 1 | 1 | 4.105 |  | 0.3 | 1.2315
| SIDE | SQM | 1 | 1 | 4.105 |  | 0.325 | 1.3341
| SIDE | SQM | 1 | 1 | 4.105 |  | 0.315 | 1.2931
| B14 200X450 | SQM | 1 | 1 | 1.5 |  | 0.2 | 0.3
| SIDE | SQM | 1 | 1 | 1.5 |  | 0.325 | 0.4875
| SIDE | SQM | 1 | 1 | 1.5 |  | 0.325 | 0.4875
| B14 200X450 | SQM | 1 | 1 | 2.2 |  | 0.2 | 0.44
| SIDE | SQM | 1 | 1 | 2.2 |  | 0.315 | 0.693
| SIDE | SQM | 1 | 1 | 2.2 |  | 0.3 | 0.66
| B15 200X500 | SQM | 1 | 1 | 3.115 |  | 0.2 | 0.623
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.375 | 1.1681
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.5 | 1.5575
| B16 200X350 | SQM | 1 | 3 | 1.02 |  | 0.2 | 0.612
| SIDE | SQM | 1 | 3 | 1.02 |  | 0.225 | 0.6885
| SIDE | SQM | 1 | 3 | 1.02 |  | 0.35 | 1.071
| B16 200X500 | SQM | 1 | 3 | 3.35 |  | 0.2 | 2.01
| SIDE | SQM | 1 | 3 | 3.35 |  | 0.3 | 3.015
| SIDE | SQM | 1 | 3 | 3.35 |  | 0.365 | 3.6683
| B16 200X500 | SQM | 1 | 3 | 3.25 |  | 0.2 | 1.95
| SIDE | SQM | 1 | 3 | 3.25 |  | 0.365 | 3.5587
| SIDE | SQM | 1 | 3 | 2.28 |  | 0.3 | 2.052
| SIDE | SQM | 1 | 3 | 0.97 |  | 0.5 | 1.455
| B17 200X500 | SQM | 1 | 1 | 3.215 |  | 0.2 | 0.643
| SIDE | SQM | 1 | 1 | 3.215 |  | 0.35 | 1.1252
| SIDE | SQM | 1 | 1 | 3.215 |  | 0.3 | 0.9645
| B18 230X500 | SQM | 1 | 1 | 2.76 |  | 0.23 | 0.6348
| SIDE | SQM | 1 | 1 | 2.76 |  | 0.365 | 1.0074
| SIDE | SQM | 1 | 1 | 2.76 |  | 0.5 | 1.38
| B19 200X450 | SQM | 1 | 1 | 6.79 |  | 0.2 | 1.358
| SIDE | SQM | 1 | 1 | 6.79 |  | 0.3 | 2.037
| SIDE | SQM | 1 | 1 | 6.79 |  | 0.3 | 2.037
| B20 200X350 | SQM | 1 | 1 | 2.41 |  | 0.2 | 0.482
| SIDE | SQM | 1 | 1 | 2.41 |  | 0.35 | 0.8435
| SIDE | SQM | 1 | 1 | 2.41 |  | 0.35 | 0.8435
| B21 230X450 | SQM | 1 | 1 | 5.76 |  | 0.23 | 1.3248
| SIDE | SQM | 1 | 1 | 2.61 |  | 0.325 | 0.84825
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.45 | 1.4175
| SIDE | SQM | 1 | 1 | 3.035 |  | 0.45 | 1.3658
| SIDE | SQM | 1 | 1 | 2.725 |  | 0.325 | 0.88563
| B22 200x450 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.325 | 1.5243
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.315 | 1.4774
| B23 200X450 | SQM | 1 | 1 | 2.22 |  | 0.2 | 0.444
| SIDE | SQM | 1 | 1 | 2.22 |  | 0.325 | 0.7215
| SIDE | SQM | 1 | 1 | 2.22 |  | 0.3 | 0.666
| B24 200X450 | SQM | 1 | 1 | 5.63 |  | 0.2 | 1.126
| SIDE | SQM | 1 | 2 | 5.63 |  | 0.45 | 5.067
| B25 200X450 | SQM | 1 | 1 | 1.5 |  | 0.2 | 0.3
| SIDE | SQM | 1 | 2 | 1.5 |  | 0.325 | 0.975
| B25 200X500 | SQM | 1 | 1 | 2.085 |  | 0.2 | 0.417
| SIDE | SQM | 1 | 2 | 2.085 |  | 0.325 | 1.3553
| B25 200X450 BESIDE STAIRS | SQM | 1 | 1 | 5.63 |  | 0.2 | 1.126
| SIDE | SQM | 1 | 1 | 5.63 |  | 0.45 | 2.5335
| SIDE | SQM | 1 | 1 | 5.63 |  | 0.325 | 1.8297
| B26 200X450 | SQM | 1 | 3 | 3.235 |  | 0.2 | 1.941
| SIDE | SQM | 1 | 3 | 3.235 |  | 0.315 | 3.0571
| SIDE | SQM | 1 | 3 | 1.61 |  | 0.3 | 1.449
| SIDE | SQM | 1 | 3 | 1.625 |  | 0.325 | 1.5844
| B26 200X450 | SQM | 1 | 3 | 4.72 |  | 0.2 | 2.832
| SIDE | SQM | 1 | 3 | 3.15 |  | 0.315 | 2.9768
| SIDE | SQM | 1 | 3 | 1.57 |  | 0.325 | 1.5308
| SIDE | SQM | 1 | 3 | 4.72 |  | 0.325 | 4.602
| B27 200X350 | SQM | 1 | 3 | 2.575 |  | 0.2 | 1.545
| SIDE | SQM | 1 | 3 | 2.575 |  | 0.225 | 1.7381
| SIDE | SQM | 1 | 3 | 2.575 |  | 0.35 | 2.7037
| B27 200X500 | SQM | 1 | 3 | 3.165 |  | 0.2 | 1.899
| SIDE | SQM | 1 | 3 | 3.165 |  | 0.375 | 3.5606
| SIDE | SQM | 1 | 3 | 3.165 |  | 0.5 | 4.7475
| B28 200X450 | SQM | 1 | 1 | 5.125 |  | 0.2 | 1.025
| SIDE | SQM | 1 | 1 | 5.125 |  | 0.3 | 1.5375
| SIDE | SQM | 1 | 1 | 1.69 |  | 0.325 | 0.54925
| SIDE | SQM | 1 | 1 | 3.435 |  | 0.315 | 1.082
| B29 200X450 | SQM | 1 | 1 | 1.9 |  | 0.2 | 0.38
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.325 | 0.6175
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.45 | 0.855
| B29 200X450 | SQM | 1 | 1 | 1.9 |  | 0.2 | 0.38
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.325 | 0.6175
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.45 | 0.855
| B29 200X450 | SQM | 1 | 1 | 1.4 |  | 0.2 | 0.28
| SIDE | SQM | 1 | 2 | 1.4 |  | 0.325 | 0.91
| B30 200X350 | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 0.315 |  | 0.35 | 0.11025
| SIDE | SQM | 1 | 1 | 2.615 |  | 0.15 | 0.39225
| B30 200X500 | SQM | 1 | 1 | 2.875 |  | 0.2 | 0.575
| SIDE | SQM | 1 | 1 | 1.55 |  | 0.3 | 0.465
| SIDE | SQM | 1 | 1 | 1.325 |  | 0.375 | 0.49687
| SIDE | SQM | 1 | 1 | 2.875 |  | 0.375 | 1.0781
| B30 200X450 | SQM | 1 | 1 | 3.95 |  | 0.2 | 0.79
| SIDE | SQM | 1 | 1 | 3.95 |  | 0.325 | 1.2838
| SIDE | SQM | 1 | 1 | 3.95 |  | 0.325 | 1.2838
| B31 200X500 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.365 | 1.7119
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.3 | 1.407
| B31 200X500 | SQM | 1 | 1 | 3.15 |  | 0.2 | 0.63
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.5 | 1.575
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.5 | 1.575
| B32 230X450 | SQM | 1 | 2 | 1.9 |  | 0.23 | 0.874
| SIDE | SQM | 1 | 2 | 1.9 |  | 0.325 | 1.235
| SIDE | SQM | 1 | 2 | 1.9 |  | 0.45 | 1.71
| B33 200X350 | SQM | 1 | 1 | 5.235 |  | 0.2 | 1.047
| SIDE | SQM | 1 | 2 | 3.235 |  | 0.215 | 1.391
| SIDE | SQM | 1 | 2 | 2 |  | 0.168 | 0.672
| B34 230X450 | SQM | 1 | 1 | 5.1 |  | 0.23 | 1.173
| SIDE | SQM | 1 | 1 | 5.1 |  | 0.3 | 1.53
| SIDE | SQM | 1 | 1 | 3.475 |  | 0.315 | 1.0946
| SIDE | SQM | 1 | 1 | 1.625 |  | 0.325 | 0.52812
| B34 230X450 | SQM | 1 | 1 | 5.1 |  | 0.23 | 1.173
| SIDE | SQM | 1 | 1 | 5.1 |  | 0.3 | 1.53
| SIDE | SQM | 1 | 1 | 3.475 |  | 0.315 | 1.0946
| SIDE | SQM | 1 | 1 | 1.625 |  | 0.325 | 0.52812
| B35 200X500 | SQM | 1 | 2 | 3.19 |  | 0.2 | 1.276
| SIDE | SQM | 1 | 2 | 3.19 |  | 0.3 | 1.914
| SIDE | SQM | 1 | 2 | 3.19 |  | 0.35 | 2.233
| B36 200X500 | SQM | 1 | 3 | 1.81 |  | 0.2 | 1.086
| SIDE | SQM | 1 | 3 | 1.81 |  | 0.375 | 2.0362
| SIDE | SQM | 1 | 3 | 1.81 |  | 0.5 | 2.715
| B36 200X500 | SQM | 1 | 3 | 3.55 |  | 0.2 | 2.13
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.375 | 3.9937
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.5 | 5.325
| B36 230X500 | SQM | 1 | 3 | 0.515 |  | 0.23 | 0.35535
| SIDE | SQM | 1 | 3 | 0.515 |  | 0.5 | 0.7725
| SIDE | SQM | 1 | 3 | 0.515 |  | 0.5 | 0.7725
| B37 200X450 | SQM | 1 | 3 | 3.86 |  | 0.2 | 2.316
| SIDE | SQM | 1 | 3 | 3.86 |  | 0.315 | 3.6477
| SIDE | SQM | 1 | 3 | 3.86 |  | 0.325 | 3.7635
| B38 200X450 | SQM | 3 | 1 | 3.45 |  | 0.2 | 2.07
| SIDE | SQM | 3 | 2 | 3.45 |  | 0.325 | 6.7275
| B39 200X450 | SQM | 1 | 3 | 2.91 |  | 0.2 | 1.746
| SIDE | SQM | 1 | 3 | 2.91 |  | 0.315 | 2.75
| SIDE | SQM | 1 | 3 | 2.91 |  | 0.315 | 2.75
| B39 230X350 | SQM | 1 | 3 | 3.55 |  | 0.23 | 2.4495
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.225 | 2.3962
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.225 | 2.3962
| B40 200X450 | SQM | 1 | 2 | 3 |  | 0.2 | 1.2
| SIDE | SQM | 1 | 2 | 3 |  | 0.3 | 1.8
| SIDE | SQM | 1 | 2 | 3 |  | 0.325 | 1.95
| B40 200X350 | SQM | 1 | 2 | 2.065 |  | 0.2 | 0.826
| SIDE | SQM | 1 | 2 | 2.065 |  | 0.215 | 0.88795
| SIDE | SQM | 1 | 2 | 2.065 |  | 0.15 | 0.6195
| B41 200X500 | SQM | 1 | 3 | 3.31 |  | 0.2 | 1.986
| SIDE | SQM | 1 | 3 | 3.31 |  | 0.35 | 3.4755
| SIDE | SQM | 1 | 3 | 3.31 |  | 0.365 | 3.6244
| B42 200X450 | SQM | 1 | 2 | 3 |  | 0.2 | 1.2
| SIDE | SQM | 1 | 2 | 3 |  | 0.325 | 1.95
| SIDE | SQM | 1 | 2 | 3 |  | 0.315 | 1.89
| B43 200X450 | SQM | 1 | 1 | 5.245 |  | 0.2 | 1.049
| SIDE | SQM | 1 | 2 | 5.245 |  | 0.3 | 3.147
| B44 200X450 | SQM | 1 | 1 | 3 |  | 0.2 | 0.6
| SIDE | SQM | 1 | 1 | 3 |  | 0.3 | 0.9
| SIDE | SQM | 1 | 1 | 3 |  | 0.325 | 0.975
| B44 200X350 | SQM | 1 | 1 | 1.95 |  | 0.2 | 0.39
| SIDE | SQM | 1 | 1 | 1.95 |  | 0.15 | 0.2925
| SIDE | SQM | 1 | 1 | 1.95 |  | 0.215 | 0.41925
| B45 200X450 | SQM | 1 | 1 | 2.23 |  | 0.2 | 0.446
| SIDE | SQM | 1 | 1 | 2.23 |  | 0.315 | 0.70245
| SIDE | SQM | 1 | 1 | 2.23 |  | 0.325 | 0.72475
| B46 200X500 | SQM | 1 | 1 | 5.145 |  | 0.2 | 1.029
| SIDE | SQM | 1 | 1 | 5.145 |  | 0.35 | 1.8007
| SIDE | SQM | 1 | 1 | 2.775 |  | 0.375 | 1.0406
| SIDE | SQM | 1 | 1 | 2.37 |  | 0.5 | 1.185
| B47 200X500 | SQM | 1 | 1 | 3.8 |  | 0.2 | 0.76
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.375 | 0.6375
| SIDE | SQM | 1 | 1 | 2.1 |  | 0.365 | 0.7665
| SIDE | SQM | 1 | 1 | 3.8 |  | 0.5 | 1.9
| B48 200X350 | SQM | 1 | 1 | 2.95 |  | 0.2 | 0.59
| SIDE | SQM | 1 | 1 | 2.95 |  | 0.225 | 0.66375
| SIDE | SQM | 1 | 1 | 2.95 |  | 0.35 | 1.0325
| B49 200X450 | SQM | 1 | 1 | 4.55 |  | 0.2 | 0.91
| SIDE | SQM | 1 | 2 | 3.15 |  | 0.315 | 1.9845
| SIDE | SQM | 1 | 2 | 1.4 |  | 0.325 | 0.91
| B50 200X500 | SQM | 1 | 1 | 3.05 |  | 0.2 | 0.61
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.365 | 1.1132
| SIDE | SQM | 1 | 1 | 1.85 |  | 0.35 | 0.6475
| SIDE | SQM | 1 | 1 | 1.2 |  | 0.3 | 0.36
| B51 200X450 | SQM | 1 | 1 | 2.5 |  | 0.2 | 0.5
| SIDE | SQM | 1 | 2 | 2.5 |  | 0.325 | 1.625
| B52 230X500 | SQM | 1 | 1 | 3.115 |  | 0.23 | 0.71645
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.35 | 1.0902
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.375 | 1.1681
| B53 200X350 | SQM | 1 | 1 | 2.335 |  | 0.2 | 0.467
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.15 | 0.35025
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.215 | 0.50202
| B54 230X500 | SQM | 1 | 1 | 3.2 |  | 0.23 | 0.736
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.325 | 1.04
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.5 | 1.6
| B55 230X450 | SQM | 1 | 1 | 0.35 |  | 0.23 | 0.0805
| SIDE | SQM | 1 | 2 | 0.35 |  | 0.45 | 0.315
| B56 200X450 | SQM | 1 | 1 | 1.96 |  | 0.2 | 0.392
| SIDE | SQM | 1 | 2 | 1.96 |  | 0.325 | 1.274
| B57 230X450 | SQM | 1 | 1 | 3.2 |  | 0.23 | 0.736
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.325 | 1.04
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.45 | 1.44
| B57 200X450 | SQM | 1 | 1 | 2.335 |  | 0.2 | 0.467
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.315 | 0.73552
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.325 | 0.75887
| B58 230X500 | SQM | 1 | 1 | 2.54 |  | 0.23 | 0.5842
| SIDE | SQM | 1 | 1 | 2.54 |  | 0.375 | 0.9525
| SIDE | SQM | 1 | 1 | 2.54 |  | 0.5 | 1.27
| B58 230X450 | SQM | 1 | 1 | 3.43 |  | 0.23 | 0.7889
| SIDE | SQM | 1 | 2 | 3.43 |  | 0.325 | 2.2295
| B59 200X500 | SQM | 1 | 1 | 2.225 |  | 0.2 | 0.445
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.318 | 0.70755
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.375 | 0.83438
| B60 200X450 | SQM | 1 | 1 | 3.14 |  | 0.2 | 0.628
| SIDE | SQM | 1 | 1 | 3.14 |  | 0.3 | 0.942
| SIDE | SQM | 1 | 1 | 3.14 |  | 0.325 | 1.0205
| B61 200X450 | SQM | 1 | 1 | 3.43 |  | 0.2 | 0.686
| SIDE | SQM | 1 | 1 | 3.43 |  | 0.315 | 1.0805
| SIDE | SQM | 1 | 1 | 1.205 |  | 0.325 | 0.39163
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.3 | 0.6675
| B61 230X450 | SQM | 1 | 1 | 1.99 |  | 0.23 | 0.4577
| SIDE | SQM | 1 | 1 | 1.99 |  | 0.325 | 0.64675
| SIDE | SQM | 1 | 1 | 1.99 |  | 0.3 | 0.597
| B62 200X500 | SQM | 1 | 1 | 2.225 |  | 0.2 | 0.445
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.318 | 0.70755
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.375 | 0.83438
| B63 200X450 | SQM | 1 | 1 | 3.06 |  | 0.2 | 0.612
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.3 | 0.918
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.315 | 0.9639
| B63 200X450 | SQM | 1 | 1 | 3.06 |  | 0.2 | 0.612
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.3 | 0.918
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.325 | 0.9945
| B64 200X350 | SQM | 1 | 2 | 3.05 |  | 0.2 | 1.22
| SIDE | SQM | 1 | 2 | 3.05 |  | 0.215 | 1.3115
| SIDE | SQM | 1 | 2 | 1.32 |  | 0.35 | 0.924
| SIDE | SQM | 1 | 2 | 1.73 |  | 0.2 | 0.692
| B64 200X350 | SQM | 1 | 2 | 0.38 |  | 0.2 | 0.152
| SIDE | SQM | 1 | 2 | 0.38 |  | 0.35 | 0.266
| B65 200X450 | SQM | 1 | 2 | 3.385 |  | 0.2 | 1.354
| SIDE | SQM | 1 | 2 | 3.385 |  | 0.325 | 2.2003
| SIDE | SQM | 1 | 2 | 3.385 |  | 0.3 | 2.031
| B66 200X450 | SQM | 2 | 1 | 3.25 |  | 0.2 | 1.3
| SIDE | SQM | 2 | 2 | 3.25 |  | 0.315 | 4.095
| B66 200X450 | SQM | 2 | 1 | 1.7 |  | 0.2 | 0.68
| SIDE | SQM | 2 | 2 | 1.7 |  | 0.325 | 2.21
| B66 200X350 | SQM | 1 | 2 | 1.385 |  | 0.2 | 0.554
| SIDE | SQM | 1 | 2 | 1.385 |  | 0.225 | 0.62325
| SIDE | SQM | 1 | 2 | 1.385 |  | 0.35 | 0.9695
| B67 200X450 | SQM | 1 | 1 | 3.05 |  | 0.2 | 0.61
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.315 | 0.96075
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.45 | 1.3725
| B67 200X450 | SQM | 1 | 1 | 1.7 |  | 0.2 | 0.34
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.325 | 0.5525
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.45 | 0.765
| B67 200X450 | SQM | 1 | 1 | 3.05 |  | 0.2 | 0.61
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.315 | 0.96075
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.315 | 0.96075
| B67 200X450 | SQM | 1 | 1 | 1.7 |  | 0.2 | 0.34
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.325 | 0.5525
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.325 | 0.5525
| B68 200X350 | SQM | 1 | 1 | 3.17 |  | 0.2 | 0.634
| SIDE | SQM | 1 | 1 | 3.17 |  | 0.225 | 0.71325
| SIDE | SQM | 1 | 1 | 3.17 |  | 0.35 | 1.1095
| B69 200X450 | SQM | 1 | 0.5 | 5.78 |  | 0.2 | 0.578
| SIDE | SQM | 1 | 0.5 | 3.78 |  | 0.315 | 0.59535
| SIDE | SQM | 1 | 0.5 | 3.78 |  | 0.315 | 0.59535
| SIDE | SQM | 1 | 0.5 | 2 |  | 0.268 | 0.268
| SIDE | SQM | 1 | 0.5 | 2 |  | 0.268 | 0.268
389.2135
FLAT NO 9
| Bed room 1 | CUM | 1 | 1 | 3.575 | 3.55 |  | 12.6913
| Bed Room 2 | CUM | 1 | 1 | 3.55 | 3.2 |  | 11.36
| Bed Room 3 | CUM | 1 | 1 | 3.145 | 3.05 |  | 9.5922
|  | CUM | 1 | 1 | 0.9 | 0.4 |  | 0.36
| Service slab | CUM | 1 | 1 | 1.165 | 0.515 |  | 0.59998
| TOILET 1 | CUM | 1 | 1 | 3.575 | 1.57 |  | 5.6128
| TOILET 2 | CUM | 1 | 1 | 2.5 | 1.6 |  | 4
| PASSAGE | CUM | 1 | 1 | 2.785 | 1.2 |  | 3.342
| Living | CUM | 1 | 1 | 6.365 | 3.72 |  | 23.6778
|  | CUM | 1 | 1 | 4.115 | 0.385 |  | 1.5843
| Entry/ Porch | CUM | 1 | 1 | 1.5 | 1.035 |  | 1.5525
| Kitchen | CUM | 1 | 1 | 2.85 | 2.335 |  | 6.6547
| Balcony 1 | CUM | 1 | 1 | 6.3 | 2 |  | 12.6
| Balcony 2 | CUM | 1 | 1 | 4.065 | 2 |  | 8.13
| Kitchen Balcony | CUM | 1 | 1 | 1.4 | 2 |  | 2.8
|  | CUM | 1 | 1 | 1.185 | 0.435 |  | 0.51548
105.073
| FLAT NO 8 | [6 empty] | 0
| B. ROOM 1 | CUM | 1 | 1 | 3.56 | 3.275 |  | 11.659
| B. ROOM 2 | CUM | 1 | 1 | 3.25 | 2.925 |  | 9.5062
| B. ROOM 3 | CUM | 1 | 1 | 3.58 | 3.05 |  | 10.919
| PASSAGE | CUM | 1 | 1 | 2.925 | 1.7 |  | 4.9725
| KITCHEN | CUM | 1 | 1 | 3.25 | 2.365 |  | 7.6863
| LIVING | CUM | 1 | 1 | 5.23 | 3.33 |  | 17.4159
|  | CUM | 1 | 1 | 3.4 | 0.94 |  | 3.196
|  | CUM | 1 | 1 | 2.55 | 1.47 |  | 3.7485
| DRESSING AREA | CUM | 1 | 1 | 2.41 | 1.43 |  | 3.4463
| TOILET 1 | CUM | 1 | 1 | 2.225 | 1.495 |  | 3.3264
| TOILET 2 | CUM | 1 | 1 | 3.385 | 1.425 |  | 4.8236
| TOILET 3 | CUM | 1 | 1 | 2.41 | 1.54 |  | 3.7114
| BALCONY 1 | CUM | 1 | 1 | 4.665 | 2 |  | 9.33
| BALCONY 2 | CUM | 1 | 1 | 5.105 | 2 |  | 10.21
| BALCONY 3 | CUM | 1 | 1 | 3.265 | 2 |  | 6.53
110.4811
| FLAT NO 7 | [6 empty] | 0
| B. ROOM 1 | CUM | 1 | 1 | 3.56 | 3.245 |  | 11.5522
| B. ROOM 2 | CUM | 1 | 1 | 3.25 | 2.925 |  | 9.5062
| PASSAGE | CUM | 1 | 1 | 2.925 | 1.7 |  | 4.9725
| KITCHEN | CUM | 1 | 1 | 3.25 | 2.365 |  | 7.6863
| LIVING | CUM | 1 | 1 | 5.23 | 3.33 |  | 17.4159
|  | CUM | 1 | 1 | 3.4 | 0.94 |  | 3.196
|  | CUM | 1 | 1 | 2.55 | 1.47 |  | 3.7485
| TOILET 1 | CUM | 1 | 1 | 2.225 | 1.495 |  | 3.3264
| TOILET 2 | CUM | 1 | 1 | 3.385 | 1.425 |  | 4.8236
| BALCONY 1 | CUM | 1 | 1 | 4.665 | 2 |  | 9.33
| BALCONY 2 | CUM | 1 | 1 | 5.105 | 2 |  | 10.21
85.7676
FLAT NO 10,11,12
| B. ROOM 1 |  | 3 | 1 | 3.86 | 3.25 |  | 37.635
| B. ROOM 2 |  | 3 | 1 | 3.86 | 3.335 |  | 38.6193
| B. ROOM 3 |  | 3 | 1 | 3.55 | 3.265 |  | 34.7722
| Living |  | 3 | 1 | 6.245 | 3.315 |  | 62.1065
|  |  | 3 | 1 | 3.17 | 1.91 |  | 18.1641
| KITCHEN |  | 3 | 1 | 3.435 | 2.345 |  | 24.1652
| TOILET 1 |  | 3 | 1 | 3.86 | 1.44 |  | 16.6752
| TOILET 2 |  | 3 | 1 | 3.55 | 1.425 |  | 15.1762
| TOILET 3 |  | 3 | 1 | 3.55 | 1.425 |  | 15.1762
| Service slab |  | 3 | 1 | 1.245 | 0.515 |  | 1.9235
| Service slab |  | 3 | 1 | 0.97 | 0.415 |  | 1.2076
| BALCONY 1 |  | 3 | 1 | 5.93 | 2 |  | 35.58
| BALCONY 2 |  | 3 | 1 | 3.565 | 2 |  | 21.39
| BALCONY 3 |  | 3 | 1 | 1.55 | 2 |  | 9.3
331.8913
| FLAT 7,8 & 9 LOBBY |  | 1 | 1 | 5.09 | 1.5 |  | 7.635
|  |  | 1 | 1 | 3.14 | 0.955 |  | 2.9987
| LIFT LOBBY |  | 1 | 1 | 3.95 | 1.61 |  | 6.3595
|  |  | 1 | 1 | 5.635 | 2.44 |  | 13.7494
| FLAT 10,11,12 LOBBY |  | 1 | 1 | 4.79 | 3.19 |  | 15.2801
|  |  | 1 | 1 | 1.4 | 0.655 |  | 0.917
Main s/case (2 No)
| Half landing |  | 1 | 2 | 1.5 | 1.5 |  | 4.5
| freight |  | 1 | 2 | 2.409 | 1.5 |  | 7.227
| mid freight |  | 1 | 1 | 1.484 | 1.5 |  | 2.226
| top landing |  | 1 | 1 | 3.96 | 0.26 |  | 1.0296
| landing beam 230x450 |  | 1 | 1 | 3.53 | 0.23 |  | 0.8119
| SIDE |  | 1 | 1 | 3.53 | 0.275 |  | 0.97075
| SIDE |  | 1 | 1 | 3.53 | 0.45 |  | 1.5885
Fire s/case (4 No)
| mid & full landing |  | 1 | 2 | 3.2 | 1.5 |  | 9.6
| freight |  | 1 | 2 | 3.343 | 1.5 |  | 10.029
| landing beam 230x450 |  | 1 | 1 | 3.2 | 0.23 |  | 0.736
| SIDE |  | 1 | 1 | 3.2 | 0.275 |  | 0.88
| SIDE |  | 1 | 1 | 3.2 | 0.45 |  | 1.44
87.9784
COLUMN (22-43/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 31 | 1 | 0.3 | 0.6 | 0.45 | 25.11
2 | C4, C5 (300X750) | CUM | 15 | 1 | 0.3 | 0.7 | 0.45 | 13.5
3 | C6, C11 (300X715) | CUM | 7 | 1 | 0.3 | 0.715 | 0.45 | 6.3945
4 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 0.45 | 1.98
5 | SW 1 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.792
6 |  | CUM | 1 | 1 | 0.23 | 1.42 | 0.45 | 1.485
7 | SW 2 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.792
8 |  | CUM | 1 | 1 | 0.23 | 1.62 | 0.45 | 1.665
9 | SW 3 (230x1000) | CUM | 1 | 1 | 0.23 | 1 | 0.45 | 1.107
10 | SW 4 (230x1150) | CUM | 1 | 1 | 0.23 | 1.15 | 0.45 | 1.242
11 | SW 5 (230x1700) | CUM | 2 | 1 | 0.23 | 1.7 | 0.45 | 3.474
12 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 0.45 | 2.547
13 | SW 7 (230x1855) | CUM | 1 | 1 | 0.23 | 1.855 | 0.45 | 1.8765
14 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 0.45 | 3.447
15 | SW 9 (L-SHAPE) | CUM | 3 | 1 | 0.23 | 0.65 | 0.45 | 2.376
16 |  | CUM | 3 | 1 | 0.23 | 1.62 | 0.45 | 4.995
17 | SW 10 (230x3445) | CUM | 1 | 1 | 0.23 | 3.445 | 0.45 | 3.3075
18 | SW 11 (230x4065) | CUM | 1 | 1 | 0.23 | 4.065 | 0.45 | 3.8655
19 | SW 12 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.792
20 |  | CUM | 1 | 1 | 0.23 | 1.305 | 0.45 | 1.3815
21 | SW 13 (200x3445) | CUM | 1 | 1 | 0.2 | 3.445 | 0.45 | 3.2805
85.41
1195.8149
2ND FLOOR LVL SLAB SHUTTERING WORK (1-22)
| B1 200X500 | SQM | 1 | 1 | 3.025 |  | 0.2 | 0.605
| SIDE | SQM | 1 | 1 | 3.025 |  | 0.3 | 0.9075
| SIDE | SQM | 1 | 1 | 3.025 |  | 0.365 | 1.1041
| B1 200X500 | SQM | 1 | 1 | 2.8 | 0.5 | 0.2 | 0.28
| SIDE | SQM | 1 | 1 | 2.8 |  | 0.3 | 0.84
| SIDE | SQM | 1 | 1 | 2.8 |  | 0.365 | 1.022
| B2 200X500 | SQM | 1 | 1 | 3.3 |  | 0.2 | 0.66
| SIDE | SQM | 1 | 1 | 3.3 |  | 0.3 | 0.99
| SIDE | SQM | 1 | 1 | 3.3 |  | 0.35 | 1.155
| B3 AT GRID B-C/27-28 | SQM | 1 | 1 | 1.395 |  | 0.1 | 0.1395
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.35 | 0.9765
| B3 AT GRID L-M/27-28 | SQM | 1 | 1 | 1.395 |  | 0.115 | 0.16043
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.35 | 0.9765
| B3 AT GRID E/32-33 | SQM | 1 | 1 | 1.185 |  | 0.1 | 0.1185
| SIDE | SQM | 1 | 2 | 1.185 |  | 0.35 | 0.8295
| B3 AT GRID F/43 | SQM | 3 | 1 | 2.055 |  | 0.1 | 0.6165
| SIDE | SQM | 3 | 2 | 2.055 |  | 0.35 | 4.3155
| B3 AT GRID F/39-40 | SQM | 3 | 1 | 1.485 |  | 0.1 | 0.4455
| SIDE | SQM | 3 | 2 | 1.485 |  | 0.35 | 3.1185
| B3 AT GRID M & O/39-40 | SQM | 3 | 1 | 2.315 |  | 0.1 | 0.6945
| SIDE | SQM | 3 | 2 | 2.315 |  | 0.35 | 4.8615
| B3 AT GRID C,K/25 | SQM | 2 | 1 | 2.315 |  | 0.1 | 0.463
| SIDE | SQM | 2 | 2 | 2.315 |  | 0.35 | 3.241
| B4 200X350 | SQM | 1 | 2 | 1.395 |  | 0.2 | 0.558
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.35 | 0.9765
| SIDE | SQM | 1 | 2 | 1.395 |  | 0.225 | 0.62775
| B5 200X450 | SQM | 1 | 1 | 6.875 |  | 0.2 | 1.375
| SIDE | SQM | 1 | 1 | 6.875 |  | 0.315 | 2.1656
| SIDE | SQM | 1 | 1 | 6.875 |  | 0.325 | 2.2344
| B6 230X350 | SQM | 1 | 1 | 3.16 |  | 0.23 | 0.7268
| SIDE | SQM | 1 | 1 | 3.16 |  | 0.225 | 0.711
| SIDE | SQM | 1 | 1 | 2.145 |  | 0.225 | 0.48262
| SIDE | SQM | 1 | 1 | 1.015 |  | 0.35 | 0.35525
| B7 200X450 | SQM | 1 | 1 | 2.7 |  | 0.2 | 0.54
| SIDE | SQM | 1 | 1 | 2.7 |  | 0.325 | 0.8775
| SIDE | SQM | 1 | 1 | 2.7 |  | 0.325 | 0.8775
| B8 200X500 | SQM | 1 | 1 | 2.875 |  | 0.2 | 0.575
| SIDE | SQM | 1 | 1 | 2.875 |  | 0.365 | 1.0494
| SIDE | SQM | 1 | 1 | 1.55 |  | 0.3 | 0.465
| SIDE | SQM | 1 | 1 | 1.325 |  | 0.375 | 0.49687
| B8 200X350 | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 2.615 |  | 0.15 | 0.39225
| SIDE | SQM | 1 | 1 | 0.315 |  | 0.35 | 0.11025
| B9 200X500 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.3 | 1.407
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.365 | 1.7119
| B10 200X500 | SQM | 1 | 1 | 3.15 |  | 0.2 | 0.63
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.3 | 0.945
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.365 | 1.1498
| B11 200X450 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.315 | 1.4774
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.325 | 1.5243
| B12 200X450 | SQM | 1 | 1 | 5.76 |  | 0.2 | 1.152
| SIDE | SQM | 1 | 1 | 3.035 |  | 0.315 | 0.95603
| SIDE | SQM | 1 | 1 | 2.725 |  | 0.325 | 0.88563
| SIDE | SQM | 1 | 1 | 2.61 |  | 0.325 | 0.84825
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.45 | 1.4175
| B13 200X350 | SQM | 1 | 1 | 1.6 |  | 0.2 | 0.32
| SIDE | SQM | 1 | 1 | 1.6 |  | 0.225 | 0.36
| SIDE | SQM | 1 | 1 | 1.6 |  | 0.35 | 0.56
| B13 200X450 | SQM | 1 | 1 | 4.105 |  | 0.2 | 0.821
| SIDE | SQM | 1 | 1 | 4.105 |  | 0.3 | 1.2315
| SIDE | SQM | 1 | 1 | 4.105 |  | 0.325 | 1.3341
| SIDE | SQM | 1 | 1 | 4.105 |  | 0.315 | 1.2931
| B14 200X450 | SQM | 1 | 1 | 1.5 |  | 0.2 | 0.3
| SIDE | SQM | 1 | 1 | 1.5 |  | 0.325 | 0.4875
| SIDE | SQM | 1 | 1 | 1.5 |  | 0.325 | 0.4875
| B14 200X450 | SQM | 1 | 1 | 2.2 |  | 0.2 | 0.44
| SIDE | SQM | 1 | 1 | 2.2 |  | 0.315 | 0.693
| SIDE | SQM | 1 | 1 | 2.2 |  | 0.3 | 0.66
| B15 200X500 | SQM | 1 | 1 | 3.115 |  | 0.2 | 0.623
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.375 | 1.1681
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.5 | 1.5575
| B16 200X350 | SQM | 1 | 3 | 1.02 |  | 0.2 | 0.612
| SIDE | SQM | 1 | 3 | 1.02 |  | 0.225 | 0.6885
| SIDE | SQM | 1 | 3 | 1.02 |  | 0.35 | 1.071
| B16 200X500 | SQM | 1 | 3 | 3.35 |  | 0.2 | 2.01
| SIDE | SQM | 1 | 3 | 3.35 |  | 0.3 | 3.015
| SIDE | SQM | 1 | 3 | 3.35 |  | 0.365 | 3.6683
| B16 200X500 | SQM | 1 | 3 | 3.25 |  | 0.2 | 1.95
| SIDE | SQM | 1 | 3 | 3.25 |  | 0.365 | 3.5587
| SIDE | SQM | 1 | 3 | 2.28 |  | 0.3 | 2.052
| SIDE | SQM | 1 | 3 | 0.97 |  | 0.5 | 1.455
| B17 200X500 | SQM | 1 | 1 | 3.215 |  | 0.2 | 0.643
| SIDE | SQM | 1 | 1 | 3.215 |  | 0.35 | 1.1252
| SIDE | SQM | 1 | 1 | 3.215 |  | 0.3 | 0.9645
| B18 230X500 | SQM | 1 | 1 | 2.76 |  | 0.23 | 0.6348
| SIDE | SQM | 1 | 1 | 2.76 |  | 0.365 | 1.0074
| SIDE | SQM | 1 | 1 | 2.76 |  | 0.5 | 1.38
| B19 200X450 | SQM | 1 | 1 | 6.79 |  | 0.2 | 1.358
| SIDE | SQM | 1 | 1 | 6.79 |  | 0.3 | 2.037
| SIDE | SQM | 1 | 1 | 6.79 |  | 0.3 | 2.037
| B20 200X350 | SQM | 1 | 1 | 2.41 |  | 0.2 | 0.482
| SIDE | SQM | 1 | 1 | 2.41 |  | 0.35 | 0.8435
| SIDE | SQM | 1 | 1 | 2.41 |  | 0.35 | 0.8435
| B21 230X450 | SQM | 1 | 1 | 5.76 |  | 0.23 | 1.3248
| SIDE | SQM | 1 | 1 | 2.61 |  | 0.325 | 0.84825
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.45 | 1.4175
| SIDE | SQM | 1 | 1 | 3.035 |  | 0.45 | 1.3658
| SIDE | SQM | 1 | 1 | 2.725 |  | 0.325 | 0.88563
| B22 200x450 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.325 | 1.5243
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.315 | 1.4774
| B23 200X450 | SQM | 1 | 1 | 2.22 |  | 0.2 | 0.444
| SIDE | SQM | 1 | 1 | 2.22 |  | 0.325 | 0.7215
| SIDE | SQM | 1 | 1 | 2.22 |  | 0.3 | 0.666
| B24 200X450 | SQM | 1 | 1 | 5.63 |  | 0.2 | 1.126
| SIDE | SQM | 1 | 2 | 5.63 |  | 0.45 | 5.067
| B25 200X450 | SQM | 1 | 1 | 1.5 |  | 0.2 | 0.3
| SIDE | SQM | 1 | 2 | 1.5 |  | 0.325 | 0.975
| B25 200X500 | SQM | 1 | 1 | 2.085 |  | 0.2 | 0.417
| SIDE | SQM | 1 | 2 | 2.085 |  | 0.325 | 1.3553
| B25 200X450 BESIDE STAIRS | SQM | 1 | 1 | 5.63 |  | 0.2 | 1.126
| SIDE | SQM | 1 | 1 | 5.63 |  | 0.45 | 2.5335
| SIDE | SQM | 1 | 1 | 5.63 |  | 0.325 | 1.8297
| B26 200X450 | SQM | 1 | 3 | 3.235 |  | 0.2 | 1.941
| SIDE | SQM | 1 | 3 | 3.235 |  | 0.315 | 3.0571
| SIDE | SQM | 1 | 3 | 1.61 |  | 0.3 | 1.449
| SIDE | SQM | 1 | 3 | 1.625 |  | 0.325 | 1.5844
| B26 200X450 | SQM | 1 | 3 | 4.72 |  | 0.2 | 2.832
| SIDE | SQM | 1 | 3 | 3.15 |  | 0.315 | 2.9768
| SIDE | SQM | 1 | 3 | 1.57 |  | 0.325 | 1.5308
| SIDE | SQM | 1 | 3 | 4.72 |  | 0.325 | 4.602
| B27 200X350 | SQM | 1 | 3 | 2.575 |  | 0.2 | 1.545
| SIDE | SQM | 1 | 3 | 2.575 |  | 0.225 | 1.7381
| SIDE | SQM | 1 | 3 | 2.575 |  | 0.35 | 2.7037
| B27 200X500 | SQM | 1 | 3 | 3.165 |  | 0.2 | 1.899
| SIDE | SQM | 1 | 3 | 3.165 |  | 0.375 | 3.5606
| SIDE | SQM | 1 | 3 | 3.165 |  | 0.5 | 4.7475
| B28 200X450 | SQM | 1 | 1 | 5.125 |  | 0.2 | 1.025
| SIDE | SQM | 1 | 1 | 5.125 |  | 0.3 | 1.5375
| SIDE | SQM | 1 | 1 | 1.69 |  | 0.325 | 0.54925
| SIDE | SQM | 1 | 1 | 3.435 |  | 0.315 | 1.082
| B29 200X450 | SQM | 1 | 1 | 1.9 |  | 0.2 | 0.38
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.325 | 0.6175
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.45 | 0.855
| B29 200X450 | SQM | 1 | 1 | 1.9 |  | 0.2 | 0.38
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.325 | 0.6175
| SIDE | SQM | 1 | 1 | 1.9 |  | 0.45 | 0.855
| B29 200X450 | SQM | 1 | 1 | 1.4 |  | 0.2 | 0.28
| SIDE | SQM | 1 | 2 | 1.4 |  | 0.325 | 0.91
| B30 200X350 | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 2.93 |  | 0.2 | 0.586
| SIDE | SQM | 1 | 1 | 0.315 |  | 0.35 | 0.11025
| SIDE | SQM | 1 | 1 | 2.615 |  | 0.15 | 0.39225
| B30 200X500 | SQM | 1 | 1 | 2.875 |  | 0.2 | 0.575
| SIDE | SQM | 1 | 1 | 1.55 |  | 0.3 | 0.465
| SIDE | SQM | 1 | 1 | 1.325 |  | 0.375 | 0.49687
| SIDE | SQM | 1 | 1 | 2.875 |  | 0.375 | 1.0781
| B30 200X450 | SQM | 1 | 1 | 3.95 |  | 0.2 | 0.79
| SIDE | SQM | 1 | 1 | 3.95 |  | 0.325 | 1.2838
| SIDE | SQM | 1 | 1 | 3.95 |  | 0.325 | 1.2838
| B31 200X500 | SQM | 1 | 1 | 4.69 |  | 0.2 | 0.938
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.365 | 1.7119
| SIDE | SQM | 1 | 1 | 4.69 |  | 0.3 | 1.407
| B31 200X500 | SQM | 1 | 1 | 3.15 |  | 0.2 | 0.63
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.5 | 1.575
| SIDE | SQM | 1 | 1 | 3.15 |  | 0.5 | 1.575
| B32 230X450 | SQM | 1 | 2 | 1.9 |  | 0.23 | 0.874
| SIDE | SQM | 1 | 2 | 1.9 |  | 0.325 | 1.235
| SIDE | SQM | 1 | 2 | 1.9 |  | 0.45 | 1.71
| B33 200X350 | SQM | 1 | 1 | 5.235 |  | 0.2 | 1.047
| SIDE | SQM | 1 | 2 | 3.235 |  | 0.215 | 1.391
| SIDE | SQM | 1 | 2 | 2 |  | 0.168 | 0.672
| B34 230X450 | SQM | 1 | 1 | 5.1 |  | 0.23 | 1.173
| SIDE | SQM | 1 | 1 | 5.1 |  | 0.3 | 1.53
| SIDE | SQM | 1 | 1 | 3.475 |  | 0.315 | 1.0946
| SIDE | SQM | 1 | 1 | 1.625 |  | 0.325 | 0.52812
| B34 230X450 | SQM | 1 | 1 | 5.1 |  | 0.23 | 1.173
| SIDE | SQM | 1 | 1 | 5.1 |  | 0.3 | 1.53
| SIDE | SQM | 1 | 1 | 3.475 |  | 0.315 | 1.0946
| SIDE | SQM | 1 | 1 | 1.625 |  | 0.325 | 0.52812
| B35 200X500 | SQM | 1 | 2 | 3.19 |  | 0.2 | 1.276
| SIDE | SQM | 1 | 2 | 3.19 |  | 0.3 | 1.914
| SIDE | SQM | 1 | 2 | 3.19 |  | 0.35 | 2.233
| B36 200X500 | SQM | 1 | 3 | 1.81 |  | 0.2 | 1.086
| SIDE | SQM | 1 | 3 | 1.81 |  | 0.375 | 2.0362
| SIDE | SQM | 1 | 3 | 1.81 |  | 0.5 | 2.715
| B36 200X500 | SQM | 1 | 3 | 3.55 |  | 0.2 | 2.13
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.375 | 3.9937
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.5 | 5.325
| B36 230X500 | SQM | 1 | 3 | 0.515 |  | 0.23 | 0.35535
| SIDE | SQM | 1 | 3 | 0.515 |  | 0.5 | 0.7725
| SIDE | SQM | 1 | 3 | 0.515 |  | 0.5 | 0.7725
| B37 200X450 | SQM | 1 | 3 | 3.86 |  | 0.2 | 2.316
| SIDE | SQM | 1 | 3 | 3.86 |  | 0.315 | 3.6477
| SIDE | SQM | 1 | 3 | 3.86 |  | 0.325 | 3.7635
| B38 200X450 | SQM | 3 | 1 | 3.45 |  | 0.2 | 2.07
| SIDE | SQM | 3 | 2 | 3.45 |  | 0.325 | 6.7275
| B39 200X450 | SQM | 1 | 3 | 2.91 |  | 0.2 | 1.746
| SIDE | SQM | 1 | 3 | 2.91 |  | 0.315 | 2.75
| SIDE | SQM | 1 | 3 | 2.91 |  | 0.315 | 2.75
| B39 230X350 | SQM | 1 | 3 | 3.55 |  | 0.23 | 2.4495
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.225 | 2.3962
| SIDE | SQM | 1 | 3 | 3.55 |  | 0.225 | 2.3962
| B40 200X450 | SQM | 1 | 2 | 3 |  | 0.2 | 1.2
| SIDE | SQM | 1 | 2 | 3 |  | 0.3 | 1.8
| SIDE | SQM | 1 | 2 | 3 |  | 0.325 | 1.95
| B40 200X350 | SQM | 1 | 2 | 2.065 |  | 0.2 | 0.826
| SIDE | SQM | 1 | 2 | 2.065 |  | 0.215 | 0.88795
| SIDE | SQM | 1 | 2 | 2.065 |  | 0.15 | 0.6195
| B41 200X500 | SQM | 1 | 3 | 3.31 |  | 0.2 | 1.986
| SIDE | SQM | 1 | 3 | 3.31 |  | 0.35 | 3.4755
| SIDE | SQM | 1 | 3 | 3.31 |  | 0.365 | 3.6244
| B42 200X450 | SQM | 1 | 2 | 3 |  | 0.2 | 1.2
| SIDE | SQM | 1 | 2 | 3 |  | 0.325 | 1.95
| SIDE | SQM | 1 | 2 | 3 |  | 0.315 | 1.89
| B43 200X450 | SQM | 1 | 1 | 5.245 |  | 0.2 | 1.049
| SIDE | SQM | 1 | 2 | 5.245 |  | 0.3 | 3.147
| B44 200X450 | SQM | 1 | 1 | 3 |  | 0.2 | 0.6
| SIDE | SQM | 1 | 1 | 3 |  | 0.3 | 0.9
| SIDE | SQM | 1 | 1 | 3 |  | 0.325 | 0.975
| B44 200X350 | SQM | 1 | 1 | 1.95 |  | 0.2 | 0.39
| SIDE | SQM | 1 | 1 | 1.95 |  | 0.15 | 0.2925
| SIDE | SQM | 1 | 1 | 1.95 |  | 0.215 | 0.41925
| B45 200X450 | SQM | 1 | 1 | 2.23 |  | 0.2 | 0.446
| SIDE | SQM | 1 | 1 | 2.23 |  | 0.315 | 0.70245
| SIDE | SQM | 1 | 1 | 2.23 |  | 0.325 | 0.72475
| B46 200X500 | SQM | 1 | 1 | 5.145 |  | 0.2 | 1.029
| SIDE | SQM | 1 | 1 | 5.145 |  | 0.35 | 1.8007
| SIDE | SQM | 1 | 1 | 2.775 |  | 0.375 | 1.0406
| SIDE | SQM | 1 | 1 | 2.37 |  | 0.5 | 1.185
| B47 200X500 | SQM | 1 | 1 | 3.8 |  | 0.2 | 0.76
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.375 | 0.6375
| SIDE | SQM | 1 | 1 | 2.1 |  | 0.365 | 0.7665
| SIDE | SQM | 1 | 1 | 3.8 |  | 0.5 | 1.9
| B48 200X350 | SQM | 1 | 1 | 2.95 |  | 0.2 | 0.59
| SIDE | SQM | 1 | 1 | 2.95 |  | 0.225 | 0.66375
| SIDE | SQM | 1 | 1 | 2.95 |  | 0.35 | 1.0325
| B49 200X450 | SQM | 1 | 1 | 4.55 |  | 0.2 | 0.91
| SIDE | SQM | 1 | 2 | 3.15 |  | 0.315 | 1.9845
| SIDE | SQM | 1 | 2 | 1.4 |  | 0.325 | 0.91
| B50 200X500 | SQM | 1 | 1 | 3.05 |  | 0.2 | 0.61
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.365 | 1.1132
| SIDE | SQM | 1 | 1 | 1.85 |  | 0.35 | 0.6475
| SIDE | SQM | 1 | 1 | 1.2 |  | 0.3 | 0.36
| B51 200X450 | SQM | 1 | 1 | 2.5 |  | 0.2 | 0.5
| SIDE | SQM | 1 | 2 | 2.5 |  | 0.325 | 1.625
| B52 230X500 | SQM | 1 | 1 | 3.115 |  | 0.23 | 0.71645
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.35 | 1.0902
| SIDE | SQM | 1 | 1 | 3.115 |  | 0.375 | 1.1681
| B53 200X350 | SQM | 1 | 1 | 2.335 |  | 0.2 | 0.467
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.15 | 0.35025
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.215 | 0.50202
| B54 230X500 | SQM | 1 | 1 | 3.2 |  | 0.23 | 0.736
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.325 | 1.04
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.5 | 1.6
| B55 230X450 | SQM | 1 | 1 | 0.35 |  | 0.23 | 0.0805
| SIDE | SQM | 1 | 2 | 0.35 |  | 0.45 | 0.315
| B56 200X450 | SQM | 1 | 1 | 1.96 |  | 0.2 | 0.392
| SIDE | SQM | 1 | 2 | 1.96 |  | 0.325 | 1.274
| B57 230X450 | SQM | 1 | 1 | 3.2 |  | 0.23 | 0.736
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.325 | 1.04
| SIDE | SQM | 1 | 1 | 3.2 |  | 0.45 | 1.44
| B57 200X450 | SQM | 1 | 1 | 2.335 |  | 0.2 | 0.467
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.315 | 0.73552
| SIDE | SQM | 1 | 1 | 2.335 |  | 0.325 | 0.75887
| B58 230X500 | SQM | 1 | 1 | 2.54 |  | 0.23 | 0.5842
| SIDE | SQM | 1 | 1 | 2.54 |  | 0.375 | 0.9525
| SIDE | SQM | 1 | 1 | 2.54 |  | 0.5 | 1.27
| B58 230X450 | SQM | 1 | 1 | 3.43 |  | 0.23 | 0.7889
| SIDE | SQM | 1 | 2 | 3.43 |  | 0.325 | 2.2295
| B59 200X500 | SQM | 1 | 1 | 2.225 |  | 0.2 | 0.445
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.318 | 0.70755
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.375 | 0.83438
| B60 200X450 | SQM | 1 | 1 | 3.14 |  | 0.2 | 0.628
| SIDE | SQM | 1 | 1 | 3.14 |  | 0.3 | 0.942
| SIDE | SQM | 1 | 1 | 3.14 |  | 0.325 | 1.0205
| B61 200X450 | SQM | 1 | 1 | 3.43 |  | 0.2 | 0.686
| SIDE | SQM | 1 | 1 | 3.43 |  | 0.315 | 1.0805
| SIDE | SQM | 1 | 1 | 1.205 |  | 0.325 | 0.39163
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.3 | 0.6675
| B61 230X450 | SQM | 1 | 1 | 1.99 |  | 0.23 | 0.4577
| SIDE | SQM | 1 | 1 | 1.99 |  | 0.325 | 0.64675
| SIDE | SQM | 1 | 1 | 1.99 |  | 0.3 | 0.597
| B62 200X500 | SQM | 1 | 1 | 2.225 |  | 0.2 | 0.445
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.318 | 0.70755
| SIDE | SQM | 1 | 1 | 2.225 |  | 0.375 | 0.83438
| B63 200X450 | SQM | 1 | 1 | 3.06 |  | 0.2 | 0.612
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.3 | 0.918
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.315 | 0.9639
| B63 200X450 | SQM | 1 | 1 | 3.06 |  | 0.2 | 0.612
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.3 | 0.918
| SIDE | SQM | 1 | 1 | 3.06 |  | 0.325 | 0.9945
| B64 200X350 | SQM | 1 | 2 | 3.05 |  | 0.2 | 1.22
| SIDE | SQM | 1 | 2 | 3.05 |  | 0.215 | 1.3115
| SIDE | SQM | 1 | 2 | 1.32 |  | 0.35 | 0.924
| SIDE | SQM | 1 | 2 | 1.73 |  | 0.2 | 0.692
| B64 200X350 | SQM | 1 | 2 | 0.38 |  | 0.2 | 0.152
| SIDE | SQM | 1 | 2 | 0.38 |  | 0.35 | 0.266
| B65 200X450 | SQM | 1 | 2 | 3.385 |  | 0.2 | 1.354
| SIDE | SQM | 1 | 2 | 3.385 |  | 0.325 | 2.2003
| SIDE | SQM | 1 | 2 | 3.385 |  | 0.3 | 2.031
| B66 200X450 | SQM | 2 | 1 | 3.25 |  | 0.2 | 1.3
| SIDE | SQM | 2 | 2 | 3.25 |  | 0.315 | 4.095
| B66 200X450 | SQM | 2 | 1 | 1.7 |  | 0.2 | 0.68
| SIDE | SQM | 2 | 2 | 1.7 |  | 0.325 | 2.21
| B66 200X350 | SQM | 1 | 2 | 1.385 |  | 0.2 | 0.554
| SIDE | SQM | 1 | 2 | 1.385 |  | 0.225 | 0.62325
| SIDE | SQM | 1 | 2 | 1.385 |  | 0.35 | 0.9695
| B67 200X450 | SQM | 1 | 1 | 3.05 |  | 0.2 | 0.61
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.315 | 0.96075
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.45 | 1.3725
| B67 200X450 | SQM | 1 | 1 | 1.7 |  | 0.2 | 0.34
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.325 | 0.5525
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.45 | 0.765
| B67 200X450 | SQM | 1 | 1 | 3.05 |  | 0.2 | 0.61
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.315 | 0.96075
| SIDE | SQM | 1 | 1 | 3.05 |  | 0.315 | 0.96075
| B67 200X450 | SQM | 1 | 1 | 1.7 |  | 0.2 | 0.34
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.325 | 0.5525
| SIDE | SQM | 1 | 1 | 1.7 |  | 0.325 | 0.5525
| B68 200X350 | SQM | 1 | 1 | 3.17 |  | 0.2 | 0.634
| SIDE | SQM | 1 | 1 | 3.17 |  | 0.225 | 0.71325
| SIDE | SQM | 1 | 1 | 3.17 |  | 0.35 | 1.1095
| B69 200X450 | SQM | 1 | 0.5 | 5.78 |  | 0.2 | 0.578
| SIDE | SQM | 1 | 0.5 | 3.78 |  | 0.315 | 0.59535
| SIDE | SQM | 1 | 0.5 | 3.78 |  | 0.315 | 0.59535
| SIDE | SQM | 1 | 0.5 | 2 |  | 0.268 | 0.268
| SIDE | SQM | 1 | 0.5 | 2 |  | 0.268 | 0.268
| B66 200X450 | SQM | 1 | 1 | 5.78 |  | 0.2 | 1.156
| SIDE | SQM | 1 | 2 | 5.78 |  | 0.315 | 3.6414
| B10 200X450 | SQM | 1 | 1 | 5.78 |  | 0.2 | 1.156
| SIDE | SQM | 1 | 2 | 6.3 |  | 0.315 | 3.969
399.1359
FLAT NO 4
| Bed room 1 | SQM | 1 | 1 | 3.575 | 3.55 |  | 12.6913
| Bed Room 2 | SQM | 1 | 1 | 3.55 | 3.2 |  | 11.36
| Bed Room 3 | SQM | 1 | 1 | 3.145 | 3.05 |  | 9.5922
|  | SQM | 1 | 1 | 0.9 | 0.4 |  | 0.36
| Service slab | SQM | 1 | 1 | 1.165 | 0.515 |  | 0.59998
| TOILET 1 | SQM | 1 | 1 | 3.575 | 1.57 |  | 5.6128
| TOILET 2 | SQM | 1 | 1 | 2.5 | 1.6 |  | 4
| PASSAGE | SQM | 1 | 1 | 2.785 | 1.2 |  | 3.342
| Living | SQM | 1 | 1 | 6.365 | 3.72 |  | 23.6778
|  | SQM | 1 | 1 | 4.115 | 0.385 |  | 1.5843
| Entry/ Porch | SQM | 1 | 1 | 1.5 | 1.035 |  | 1.5525
| Kitchen | SQM | 1 | 1 | 2.85 | 2.335 |  | 6.6547
| Balcony 1 | SQM | 1 | 1 | 6.3 | 2 |  | 12.6
| Balcony 2 | SQM | 1 | 1 | 4.065 | 2 |  | 8.13
| Kitchen Balcony | SQM | 1 | 1 | 1.4 | 2 |  | 2.8
|  | SQM | 1 | 1 | 1.185 | 0.435 |  | 0.51548
105.073
| FLAT NO 5 | [6 empty] | 0
| B. ROOM 1 | SQM | 1 | 1 | 3.56 | 3.275 |  | 11.659
| B. ROOM 2 | SQM | 1 | 1 | 3.25 | 2.925 |  | 9.5062
| B. ROOM 3 | SQM | 1 | 1 | 3.58 | 3.05 |  | 10.919
| PASSAGE | SQM | 1 | 1 | 2.925 | 1.7 |  | 4.9725
| KITCHEN | SQM | 1 | 1 | 3.25 | 2.365 |  | 7.6863
| LIVING | SQM | 1 | 1 | 5.23 | 3.33 |  | 17.4159
|  | SQM | 1 | 1 | 3.4 | 0.94 |  | 3.196
|  | SQM | 1 | 1 | 2.55 | 1.47 |  | 3.7485
| DRESSING AREA | SQM | 1 | 1 | 2.41 | 1.43 |  | 3.4463
| TOILET 1 | SQM | 1 | 1 | 2.225 | 1.495 |  | 3.3264
| TOILET 2 | SQM | 1 | 1 | 3.385 | 1.425 |  | 4.8236
| TOILET 3 | SQM | 1 | 1 | 2.41 | 1.54 |  | 3.7114
| BALCONY 1 | SQM | 1 | 1 | 4.665 | 2 |  | 9.33
| BALCONY 2 | SQM | 1 | 1 | 5.105 | 2 |  | 10.21
| BALCONY 3 | SQM | 1 | 1 | 3.265 | 2 |  | 6.53
110.4811
| FLAT NO 6 | [6 empty] | 0
| B. ROOM 1 | SQM | 1 | 1 | 3.56 | 3.245 |  | 11.5522
| B. ROOM 2 | SQM | 1 | 1 | 3.25 | 2.925 |  | 9.5062
| PASSAGE | SQM | 1 | 1 | 2.925 | 1.7 |  | 4.9725
| KITCHEN | SQM | 1 | 1 | 3.25 | 2.365 |  | 7.6863
| LIVING | SQM | 1 | 1 | 5.23 | 3.33 |  | 17.4159
|  | SQM | 1 | 1 | 3.4 | 0.94 |  | 3.196
|  | SQM | 1 | 1 | 2.55 | 1.47 |  | 3.7485
| TOILET 1 | SQM | 1 | 1 | 2.225 | 1.495 |  | 3.3264
| TOILET 2 | SQM | 1 | 1 | 3.385 | 1.425 |  | 4.8236
| BALCONY 1 | SQM | 1 | 1 | 4.665 | 2 |  | 9.33
| BALCONY 2 | SQM | 1 | 1 | 5.105 | 2 |  | 10.21
| BALCONY 3 AT 2950 MM HT | SQM | 1 | 2 | 3.05 | 2 |  | 12.2
| BEDROOM AT 2950 MM HT | SQM | 1 | 2 | 3.58 | 3.05 |  | 21.838
BEDROOM & BALCONY PLAIN AREA
| AT 4500 MM HT. | SQM | 1 | 1 | 6.3 | 5.78 |  | 36.414
| AT 5500 MM HT. | SQM | 1 | 1 | 6.3 | 5.78 |  | 36.414
| AT 5900 MM HT. | SQM | 1 | 1 | 6.3 | 5.78 |  | 36.414
229.0476
FLAT NO 1,2,3
| B. ROOM 1 |  | 3 | 1 | 3.86 | 3.25 |  | 37.635
| B. ROOM 2 |  | 3 | 1 | 3.86 | 3.335 |  | 38.6193
| B. ROOM 3 |  | 3 | 1 | 3.55 | 3.265 |  | 34.7722
| Living |  | 3 | 1 | 6.245 | 3.315 |  | 62.1065
|  |  | 3 | 1 | 3.17 | 1.91 |  | 18.1641
| KITCHEN |  | 3 | 1 | 3.435 | 2.345 |  | 24.1652
| TOILET 1 |  | 3 | 1 | 3.86 | 1.44 |  | 16.6752
| TOILET 2 |  | 3 | 1 | 3.55 | 1.425 |  | 15.1762
| TOILET 3 |  | 3 | 1 | 3.55 | 1.425 |  | 15.1762
| Service slab |  | 3 | 1 | 1.245 | 0.515 |  | 1.9235
| Service slab |  | 3 | 1 | 0.97 | 0.415 |  | 1.2076
| BALCONY 1 |  | 3 | 1 | 5.93 | 2 |  | 35.58
| BALCONY 2 |  | 3 | 1 | 3.565 | 2 |  | 21.39
| BALCONY 3 |  | 3 | 1 | 1.55 | 2 |  | 9.3
331.8913
| FLAT 6,5 & 4 LOBBY |  | 1 | 1 | 5.09 | 1.5 |  | 7.635
|  |  | 1 | 1 | 3.14 | 0.955 |  | 2.9987
| LIFT LOBBY |  | 1 | 1 | 3.95 | 1.61 |  | 6.3595
|  |  | 1 | 1 | 5.635 | 2.44 |  | 13.7494
| FLAT 1,2,3 LOBBY |  | 1 | 1 | 4.79 | 3.19 |  | 15.2801
|  |  | 1 | 1 | 1.4 | 0.655 |  | 0.917
Main s/case (2 No)
| Half landing |  | 1 | 2 | 1.5 | 1.5 |  | 4.5
| freight |  | 1 | 2 | 2.409 | 1.5 |  | 7.227
| mid freight |  | 1 | 1 | 1.484 | 1.5 |  | 2.226
| top landing |  | 1 | 1 | 3.96 | 0.26 |  | 1.0296
| landing beam 230x450 |  | 1 | 1 | 3.53 | 0.23 |  | 0.8119
| SIDE |  | 1 | 1 | 3.53 | 0.275 |  | 0.97075
| SIDE |  | 1 | 1 | 3.53 | 0.45 |  | 1.5885
Fire s/case (1 No)
| mid & full landing |  | 1 | 2 | 3.2 | 1.5 |  | 9.6
| freight |  | 1 | 2 | 3.343 | 1.5 |  | 10.029
| landing beam 230x450 |  | 1 | 1 | 3.2 | 0.23 |  | 0.736
| SIDE |  | 1 | 1 | 3.2 | 0.275 |  | 0.88
| SIDE |  | 1 | 1 | 3.2 | 0.45 |  | 1.44
87.9784
COLUMN (1-22/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 31 | 1 | 0.3 | 0.6 | 0.45 | 25.11
2 | C4, C5 (300X750) | CUM | 15 | 1 | 0.3 | 0.7 | 0.45 | 13.5
3 | C6, C11 (300X715) | CUM | 7 | 1 | 0.3 | 0.715 | 0.45 | 6.3945
4 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 0.45 | 1.98
5 | SW 1 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.792
6 |  | CUM | 1 | 1 | 0.23 | 1.42 | 0.45 | 1.485
7 | SW 2 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.792
8 |  | CUM | 1 | 1 | 0.23 | 1.62 | 0.45 | 1.665
9 | SW 3 (230x1000) | CUM | 1 | 1 | 0.23 | 1 | 0.45 | 1.107
10 | SW 4 (230x1150) | CUM | 1 | 1 | 0.23 | 1.15 | 0.45 | 1.242
11 | SW 5 (230x1700) | CUM | 2 | 1 | 0.23 | 1.7 | 0.45 | 3.474
12 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 0.45 | 2.547
13 | SW 7 (230x1855) | CUM | 1 | 1 | 0.23 | 1.855 | 0.45 | 1.8765
14 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 0.45 | 3.447
15 | SW 9 (L-SHAPE) | CUM | 3 | 1 | 0.23 | 0.65 | 0.45 | 2.376
16 |  | CUM | 3 | 1 | 0.23 | 1.62 | 0.45 | 4.995
17 | SW 10 (230x3445) | CUM | 1 | 1 | 0.23 | 3.445 | 0.45 | 3.3075
18 | SW 11 (230x4065) | CUM | 1 | 1 | 0.23 | 4.065 | 0.45 | 3.8655
19 | SW 12 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 0.45 | 0.792
20 |  | CUM | 1 | 1 | 0.23 | 1.305 | 0.45 | 1.3815
21 | SW 13 (200x3445) | CUM | 1 | 1 | 0.2 | 3.445 | 0.45 | 3.2805
85.41
1349.0173

## BRICK WORK SUMMARY
TOWER-E BRICK WORK SUMMARY
|  |  | QTY | [5 empty] | TOTAL
5 | MASONARY WORK |  | 3rd RA | 4th RA | 5th RA | 6th RA | 7th RA | 8th RA
(Quoted Rates are for all heights, all depths, all levels, including basement to roof (mumty) & all leads and lifts, including curved or circular including elevation masonary work) (Basic Rate of Brick @ Rs. 7/No. FOR at site without GST)
5.1. | Brick work in Sub Structure (Up to Stilt Floor level):
| Providing and laying 230mm thick brick masonry using 1st quality burnt clay FPS bricks in Sub-Structure laid in cement mortar 1:6 (1 cement : 6 coarse sand) mix, joints finished, flush/ raked to 6mm depth including scaffolding, curing complete as per specification and drawing or as directed by Project Manager. | CUM | [6 empty] | 0
5.2. | Brick work in Sub Structure (Up to Stilt Floor level):
| Providing and laying of 115 mm thick brick work with 1st quality burnt clay FPS bricks in sub-superstructure laid in cement mortar 1:4 (1 cement : 4 coarse sand) mix, joints finished, including placing hoop iron as per specification at every third course, scaffolding, curing complete in all respect as per direction of EIC. (Hoop iron shall be provided by client free of cost) (Items of RCC bands like shuttering, concrete and reinforcement to be paid in respective items). | SQM | 36.867 | 51.2765 |  |  |  |  | 88.1435
5.3. | Brick work in Super Structure (Above Stilt FLoor level)
5.3.1 | Providing and laying 230mm thick brick masonry using 1st quality burnt clay FPS bricks in Super-Structure laid in cement mortar 1:6 (1 cement : 6 coarse sand) mix, joints finished, flush/ raked to 6mm depth including scaffolding, curing complete as per specification and drawing or as directed by Project Manager.
(a) | Stilt Floor level to 7th Floor level | CUM | [6 empty] | 0
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | CUM | [6 empty] | 0
5.4. | Brick work in Super Structure (Above Stilt FLoor level)
5.4.1 | Providing and laying of 115 mm thick brick work with 1st quality burnt clay FPS bricks in Super-Superstructure laid in cement mortar 1:4 (1 cement : 4 coarse sand) mix, joints finished, including placing hoop iron as per specification at every third course, scaffolding, curing complete in all respect as per direction of EIC. (Hoop iron shall be provided by client free of cost) (Items of RCC bands like shuttering, concrete and reinforcement to be paid in respective items).
(a) | Stilt Floor level to 7th Floor level | SQM | [6 empty] | 0
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | [6 empty] | 0
5.8. | Brick work in staircase steps:
| Providing and laying and constructing brickwork in staircase steps using 1st quality burnt clay FPS bricks in cement mortar 1:3 (1 cement : 3 coarse sand) at all heights and levels including cutting, chamfering scaffolding, curing, complete as per specification. | CUM | [6 empty] | 0
[8 empty] | TOTAL | 88.1435

## BRICK WORK MB
COMPANY- OMAXE PANCHAM REALCON PVT LTD
PROJECT- TOWER-E
LOCATION- NAINI, PRAYAGRAJ
MB SHEET- BRICK WORK BELOW PLINTH BEAM
S.NO. | DESCRIPTION | UNIT | NOS | NOS | MEASUREMENT |  |  | QTY. | REMARKS
[5 empty] | L | B | H/T
RAFT OUTTER 115MM BRICK WORK
1 | GRID (22'-26'/M') | SQM | 1 | 1 | 11.005 |  | 0.3 | 3.3015 |  | 3rd RA
2 | GRID (26/M'-Q) | SQM | 1 | 1 | 12.415 |  | 0.3 | 3.7245
3 | GRID (26'-43'/Q') | SQM | 1 | 1 | 26.92 |  | 0.3 | 8.076
4 | GRID (43'/E'-Q') | SQM | 1 | 1 | 21.65 |  | 0.3 | 6.495
5 | GRID (38'-43'/E') | SQM | 1 | 1 | 11.09 |  | 0.3 | 3.327
6 | GRID (38'/A-E') | SQM | 1 | 1 | 10.285 |  | 0.3 | 3.0855
7 | GRID (30-38'/A) | SQM | 1 | 1 | 8.875 |  | 0.3 | 2.6625
8 | GRID (30/A-A') | SQM | 1 | 1 | 1.5 |  | 0.3 | 0.45
9 | GRID (27'-30/A') | SQM | 1 | 1 | 3.95 |  | 0.3 | 1.185
10 | GRID (27'/A'-B) | SQM | 1 | 1 | 0.815 |  | 0.3 | 0.2445
11 | GRID (26'-27'/B) | SQM | 1 | 1 | 1.695 |  | 0.3 | 0.5085
12 | GRID (26'/B-B') | SQM | 1 | 1 | 1.405 |  | 0.3 | 0.4215
13 | GRID (22'-26'/B') | SQM | 1 | 1 | 11.285 |  | 0.3 | 3.3855
[7 empty] | TOTAL | 36.867
RAFT OUTTER 115MM BRICK WORK
1 | GRID (17'-22'/M') | SQM | 1 | 1 | 15.175 |  | 0.3 | 4.5525 |  | 4th RA
2 | GRID (17'/M'-Q) | SQM | 1 | 1 | 12.415 |  | 0.3 | 3.7245
3 | GRID (1-17'/Q') | SQM | 1 | 1 | 26.92 |  | 0.3 | 8.076
4 | GRID (1/E'-Q') | SQM | 1 | 1 | 21.65 |  | 0.85 | 18.4025
5 | GRID (1-5'/E') | SQM | 1 | 1 | 11.09 |  | 0.3 | 3.327
6 | GRID (5'/A-E') | SQM | 1 | 1 | 10.285 |  | 0.3 | 3.0855
7 | GRID (5'-14'/A) | SQM | 1 | 1 | 8.875 |  | 0.3 | 2.6625
8 | GRID (14'/A-A') | SQM | 1 | 1 | 1.5 |  | 0.3 | 0.45
9 | GRID (14'-16'/A') | SQM | 1 | 1 | 3.95 |  | 0.3 | 1.185
10 | GRID (16'/A'-B) | SQM | 1 | 1 | 0.815 |  | 0.3 | 0.2445
11 | GRID (16'-17'/B) | SQM | 1 | 1 | 1.695 |  | 0.3 | 0.5085
12 | GRID (17'/B-B') | SQM | 1 | 1 | 1.405 |  | 0.3 | 0.4215
13 | GRID (17'-22'/B') | SQM | 1 | 1 | 15.455 |  | 0.3 | 4.6365
[7 empty] | TOTAL | 51.2765

## TMT STEEL RECO.
MARCO ENTERPRISES
TOWER-E
Reconcialation of TMT Steel
S.NO. | Description | Unit | Dia wise | [6 empty] | Total
|  |  | 6mm | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm
A | Total Steel Received upto date | Kg | 0 | 96633.74 | 47619.81 | 29402.88 | 115030.11 | 68874.19 | 31080 | 388640.73
B | Consumption Detail
4.1.1 | Up To Stilt Floor Lvl. | Kg | 0 | 5122.9778 | 9320.9855 | 6024.5952 | 63525.7549 | 35541.2635 | 17449.8883 | 136985.4651
4.1.2 | Stilt Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet) | Kg | 0 | 46398.8409 | 25468.8993 | 18174.3085 | 27731.2515 | 9545.2842 | 2864.169 | 130182.7534
4.1.3 | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | Kg | 0 | 36.1504 | 0 | 0 | 0 | 0 | 0 | 36.1504
C | Total consumption |  | 0 | 51557.9691 | 34789.8848 | 24198.9037 | 91257.0064 | 45086.5477 | 20314.0573 | 267204.3689
D | Theoretical Balance | Kg | 0 | 45075.7709 | 12829.9252 | 5203.9763 | 23773.1036 | 23787.6423 | 10765.9427 | 121436.3611
E | Steel available at yard | Kg | 0 | 34911 | 15499 | 3330 | 16740 | 21000 | 12190 | 103670
G | Column Dowels | Kg |  | 2166.891 | 2758.388 | 1936.242 | 2406.7429 | 1462.5684 | 272.58 | 11003.4123
I | For Rings | Kg |  | 3500 | [5 empty] | 3500
0
J | Total In Progress | Kg | 0 | 5666.891 | 2758.388 | 1936.242 | 2406.7429 | 1462.5684 | 272.58 | 14503.4123
K | Wastage (D-E-G) | Kg | 0 | 4497.8799 | -5427.4627 | -62.2657 | 4626.3607 | 1325.0739 | -1696.6373 | 3262.9488 | 1.221%
| SCRAP SALE | [8 empty] | 0
| Allowed Wastage 2.5% | Kg | [7 empty] | 6680.1092 |  | 3417.1604

## TMT STEEL REC.
(OMAXE TOWER-E, PRAYAGRAJ )
TMT STEEL BAR ISSUE BY OMAXE
S.NO. | DATE | Unit | 6mm Dia. | 8mm Dia. | 10mm Dia. | 12mm Dia. | 16mm Dia. | 20mm Dia. | 25mm Dia. | TOTAL | COMULAT.
1 | RECEIVED FROM OMAXE AT 19/4/25 | KG |  |  |  | 7700 | 37621 | 9370 | 5474 | 60165 | 60165
2 | RECEIVED FROM OMAXE AT 13/5/25 | KG |  | 9070 | 6840 |  |  | 20010 |  | 35920 | 96085
3 | RECEIVED FROM OMAXE AT 17/5/25 | KG |  |  |  |  | 29850 |  | 9850 | 39700 | 135785
4 | RECEIVED FROM OMAXE AT 03/6/25 | KG |  |  |  | 3766 |  | 6282 | 3148 | 13196 | 148981
5 | RECEIVED FROM OMAXE AT 03/6/25 | KG | [5 empty] | 4800 |  | 4800 | 153781
6 | RECEIVED FROM OMAXE AT 29/6/25 | KG |  |  | 6101 |  | 10573 | 2344 |  | 19018 | 172799
7 | TRANSFER FROM LIG AT 5/8/25 | KG |  |  |  | 1505 | 1758 | 892 |  | 4155 | 176954
8 | TRANSFER TO LIG AT 7/8/25 | KG |  |  | -1419 |  |  |  |  | -1419 | 175535
9 | RECEIVED FROM OMAXE AT 7/8/25 | KG |  | 2874 | 2860 |  |  |  |  | 5734 | 181269
10 | RECEIVED FROM OMAXE AT 22/8/25 | KG |  | 26488 | 12498 | 3334 |  |  |  | 42320 | 223589
11 | GIVE TO OMAXE AT 21/9/25 | KG |  | -2730 | -3520 |  |  |  |  | -6250 | 217339
12 | GIVE TO OMAXE AT 08/10/25 | KG |  | -5620 | [5 empty] | -5620 | 211719
13 | RECEIVED FROM OMAXE AT 17/10/25 | KG |  |  |  |  | 14269 | 11506 | 3502 | 29277 | 240996
14 | RECEIVED FROM OMAXE AT 10/12/25 | KG |  | 5472 |  |  | 12742 |  |  | 18214 | 259210
15 | RECEIVED FROM OMAXE AT 13/12/25 | KG |  |  |  | 8880 |  | 11167 |  | 20047 | 279257
16 | RECEIVED FROM OMAXE AT 22/12/25 | KG |  |  | 13058 |  |  |  |  | 13058 | 292315
17 | RECEIVED FROM OMAXE AT 30/12/25 | KG |  |  |  |  | 3237 |  | 3078 | 6315 | 298630
18 | TRANSFER FROM SHIVA-3 AT 03/01/26 | KG |  | 3011 | [5 empty] | 3011 | 301641
19 | TRANSFER FROM MLP AT 03/01/26 | KG |  | 3175 | [5 empty] | 3175 | 304816
20 | RECEIVED FROM OMAXE AT 11/01/26 | KG |  | 1422 | [5 empty] | 1422 | 306238
21 | RECEIVED FROM OMAXE AT 21/01/26 | KG |  | 12124 | 8657 | 8936 | 6810 | 5492 |  | 42019 | 348257
22 | TRANSFER TO EWS T-29/1/2026 |  |  | -8188 | -793 | -2794 | -3696.59 | -740.55 |  | -16212.14 | 332044.86
23 | TRANSFER TO LIG T-130/1/2026 |  |  | -1001.26 | -854.19 | -1929.12 | -615.3 | -2248.26 | -412 | -7060.13 | 324984.73
24 | TRANSFER TO Shiva-3 5/2/2026 | [5 empty] | -758 |  |  | -758 | 324226.73
25 | RECEIVED FROM OMAXE AT 8/02/26 | KG |  | 12204 | [5 empty] | 12204 | 336430.73
26 | TRANSFER TO Shiva-3 | KG |  |  | -3307 | -3325 |  |  |  | -6632 | 329798.73
25 | RECEIVED FROM OMAXE AT 24/02/26 | KG |  | 3422 | [5 empty] | 3422 | 333220.73
25 | RECEIVED FROM OMAXE AT 28/02/26 | KG |  | 29244 | [5 empty] | 29244 | 362464.73
26 | RECEIVED FROM OMAXE AT 01/03/26 | KG |  | 5667 | 7499 | 3330 | 3240 |  | 6440 | 26176 | 388640.73
| TOTAL QTY. |  | 0 | 96633.74 | 47619.81 | 29402.88 | 115030.11 | 68874.19 | 31080 | 388640.73 | KG

## TMT SUMMARY
(OMAXE TOWER-E, PRAYAGRAJ )
STEEL CONSUMPTION SUMMARY
S.NO. | DESCRIPTION | LOCATION | Unit | NOS | 6mm Dia. | 8mm Dia. | 10mm Dia. | 12mm Dia. | 16mm Dia. | 20mm Dia. | 25mm Dia. | TOTAL
4.1 TMT REINFORCEMENT
4.1.1. | UPTO STILT FLOOR LVL
1 | TOWER-E COLUMN GRID (22-23/A-Q) | UPTO RAFT | KG | 1 |  | 0 | 797.1553 | 381.856 | 971.207 | 698.3468 | 76.6199 | 2925.1849
2 | TOWER-E RAFT GRID (22-23/A-Q) | AS SUB-STRUCTURE | KG | 1 |  | 0 | 574.2481 | 1140.1236 | 26109.1413 | 15376.0061 | 8483.9735 | 51683.4926
3 | TOWER-E COLUMN GRID (1-22/A-Q) | UPTO RAFT | KG | 1 |  | 0 | 797.1553 | 381.856 | 971.207 | 698.3468 | 76.6199 | 2925.1849
4 | TOWER-E RAFT GRID (1-22/A-Q) | AS SUB-STRUCTURE | KG | 1 |  | 0 | 574.2481 | 1153.8272 | 26698.1337 | 15753.7631 | 8483.9735 | 52663.9457
5 | TOWER-E PADESTIAL GRID (1-43/A-Q) | AS SUB-STRUCTURE | KG | 1 |  | 1630.8341 | 6446.4863 | 1491.2362 | 3874.9184 | 2867.2991 | 328.7016 | 16639.4757
6 | COMPENSATORY STRIP GRID (22-23/B'-L') | AS SUB-STRUCTURE | KG | 1 |  | 0 | 0 | 0 | 139.849 | 0 | 0 | 139.849
7 | PLINTH BEAM GRID (1-43/A-Q) | AS SUB-STRUCTURE | KG | 1 |  | 3492.1437 | 131.6925 | 1475.6962 | 4761.2984 | 147.5016 | 0 | 10008.3323
[5 empty] | 0 | 5122.9778 | 9320.9855 | 6024.5952 | 63525.7549 | 35541.2635 | 17449.8883 | 136985.4651
4.1.2. | Stilt Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet)
1 | COLUMN PLINTH TO 1ST FLOOR LVL (1-43/A-Q) | AS SUPER-STRUCTURE | KG | 1 |  | 4818.3996 | 6767.1141 | 2814.1651 | 5637.993 | 4369.6488 | 1422.96 | 25830.2805
2 | 1ST FLOOR LVL SLAB (22-43/A-Q) | AS SUPER-STRUCTURE | KG | 1 |  | 8854.9441 | 2524.6776 | 2329.9078 | 3476.4898 | 225.4863 | 104.566 | 17516.0716 | 17516
3 | 1ST FLOOR LVL SLAB (1-22/A-Q) | AS SUPER-STRUCTURE | KG | 1 |  | 8854.9441 | 2524.6776 | 2329.9078 | 3476.4898 | 225.4863 | 104.566 | 17516.0716 | 17516
4 | COLUMN 1ST FLOOR LVL to 2nd floor LVL (1-43/A-Q) | AS SUPER-STRUCTURE | KG | 1 |  | 4333.782 | 5516.7759 | 3872.484 | 4813.4858 | 2925.1368 | 545.16 | 22006.8245
5 | 2nd FLOOR LVL SLAB (22-43/A-Q) | AS SUPER-STRUCTURE | KG | 1 |  | 8747.2197 | 2643.1725 | 2490.9022 | 3843.034 | 484.4658 | 284.1685 | 18492.9626 | 17516
6 | 2nd FLOOR LVL SLAB (1-43/A-Q) | AS SUPER-STRUCTURE | KG | 1 |  | 8747.2197 | 2643.1725 | 2490.9022 | 3843.034 | 484.4658 | 284.1685 | 18492.9626 | 17516
7 | COLUMN 2ND TO 3RD floor LVL (1-43/A-Q) | AS SUPER-STRUCTURE | KG | 1 |  | 2042.3317 | 2849.3091 | 1846.0396 | 2640.7251 | 830.5944 | 118.58 | 10327.5799
[5 empty] | 0 | 46398.8409 | 25468.8993 | 18174.3085 | 27731.2515 | 9545.2842 | 2864.169 | 130182.7534
4.1.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level
1 | COLUMN CLIT FIXING WORK (RAFT COL., G.F.) |  | KG | 2 |  | 36.1504 | 0 | 0 | 0 | 0 | 0 | 36.1504
2 | [11 empty] | 0
[5 empty] | 0 | 36.1504 | 0 | 0 | 0 | 0 | 0 | 36.1504
267204.3689

## RAFT BBS
TOWER-E RAFT BBS
TOWER-E RAFT BBS GRID (22'-43/A-Q)
S.No. | Description | Shape of Bar in mm |  |  |  | Spacing c/c | Dia of Bar | No's of Set | No's of Bar | Actual Length | Lap | No. Of Bend | Deduction In mm | Cut Length | Total Length | TMT BAR Fe-500D or EQR | [5 empty] | Remarks
A | RAFT | [14 empty] | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm
BOTTOM MAIN BAR
1 | GRID (39'-43/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 18 | 21.55 | 1.568 | 2 | 0.064 | 22.486 | 432.972 |  |  |  | 432.972
1 | GRID (39'-43/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 17 | 21.55 | 0.784 | 2 | 0.064 | 22.486 | 395.59 |  |  |  | 395.59
2 | GRID (38'-39'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 6 | 22.065 | 1.568 | 2 | 0.064 | 23.001 | 147.414 |  |  |  | 147.414
2 | GRID (38'-39'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 5 | 22.065 | 0.784 | 2 | 0.064 | 23.001 | 118.925 |  |  |  | 118.925
3 | GRID (32'-38'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 13 | 32.35 | 2.352 | 2 | 0.064 | 33.286 | 463.294 |  |  |  | 463.294
3 | GRID (32'-38'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 12 | 32.35 | 1.568 | 2 | 0.064 | 33.286 | 418.248 |  |  |  | 418.248
4 | GRID (30'-32'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 6 | 31.835 | 2.352 | 2 | 0.064 | 32.771 | 210.738 |  |  |  | 210.738
4 | GRID (30'-32'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 5 | 31.835 | 1.568 | 2 | 0.064 | 32.771 | 171.695 |  |  |  | 171.695
5 | GRID (27'-30/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 9 | 30.35 | 2.352 | 2 | 0.064 | 31.286 | 302.742 |  |  |  | 302.742
5 | GRID (27'-30/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 8 | 30.35 | 1.568 | 2 | 0.064 | 31.286 | 262.832 |  |  |  | 262.832
6 | GRID (26'-27'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 4 | 29.535 | 2.352 | 2 | 0.064 | 30.471 | 131.292 |  |  |  | 131.292
6 | GRID (26'-27'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 3 | 29.535 | 1.568 | 2 | 0.064 | 30.471 | 96.117 |  |  |  | 96.117
7 | GRID (22'-26'/B-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 15.7 |  | 0.5 | 0.25 | 16 | 1 | 46 | 15.7 | 0.784 | 2 | 0.064 | 16.636 | 801.32 |  |  |  | 801.32
BOTTOM DISTRIBUTION BAR
1 | GRID (30-38'/A)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.775 |  | 0.5 | 0.25 | 16 | 1 | 7 | 8.775 | 0 | 2 | 0.064 | 9.711 | 67.977 |  |  |  | 67.977
2 | GRID (27'-38'/A-B)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 12.725 |  | 0.5 | 0.25 | 16 | 1 | 4 | 12.725 | 0.784 | 2 | 0.064 | 13.661 | 57.78 |  |  |  | 57.78
3 | GRID (26'-38'/B-B')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 14.42 |  | 0.5 | 0.25 | 16 | 1 | 7 | 14.42 | 0.784 | 2 | 0.064 | 15.356 | 112.98 |  |  |  | 112.98
4 | GRID (22'-38'/B'-E')
| DIST. BAR BOTTOM (ALTH.) |  | 25.755 |  | 0.5 | 0.25 | 16 | 1 | 27 | 25.755 | 1.568 | 1 | 0.016 | 26.239 | 750.789 |  |  |  | 750.789
5 | GRID (22'-43'/E'-K)
| DIST. BAR BOTTOM (ALTH.) |  | 36.84 |  | 0.5 | 0.25 | 16 | 1 | 30 | 36.84 | 2.352 | 1 | 0.016 | 37.324 | 1190.28 |  |  |  | 1190.28
6 | GRID (26'-43'/M-Q)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 25.79 |  | 0.5 | 0.25 | 16 | 1 | 51 | 25.79 | 1.568 | 2 | 0.064 | 26.726 | 1442.994 |  |  |  | 1442.994
7 | GRID (33-39/Q')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.68 |  | 0.5 | 0.25 | 16 | 1 | 3 | 8.68 | 0 | 2 | 0.064 | 9.616 | 28.848 |  |  |  | 28.848
TOP MAIN BAR
1 | GRID (39'-43/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 19 | 21.55 | 1.568 | 2 | 0.064 | 22.486 | 457.026 |  |  |  | 457.026
1 | GRID (39'-43/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 18 | 21.55 | 0.784 | 2 | 0.064 | 22.486 | 418.86 |  |  |  | 418.86
2 | GRID (38'-39'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 6 | 22.065 | 1.568 | 2 | 0.064 | 23.001 | 147.414 |  |  |  | 147.414
2 | GRID (38'-39'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 5 | 22.065 | 0.784 | 2 | 0.064 | 23.001 | 118.925 |  |  |  | 118.925
3 | GRID (32'-38'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 13 | 32.35 | 2.352 | 2 | 0.064 | 33.286 | 463.294 |  |  |  | 463.294
3 | GRID (32'-38'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 12 | 32.35 | 1.568 | 2 | 0.064 | 33.286 | 418.248 |  |  |  | 418.248
4 | GRID (30'-32'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 6 | 31.835 | 2.352 | 2 | 0.064 | 32.771 | 210.738 |  |  |  | 210.738
4 | GRID (30'-32'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 5 | 31.835 | 1.568 | 2 | 0.064 | 32.771 | 171.695 |  |  |  | 171.695
5 | GRID (27'-30/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 9 | 30.35 | 2.352 | 2 | 0.064 | 31.286 | 302.742 |  |  |  | 302.742
5 | GRID (27'-30/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 8 | 30.35 | 1.568 | 2 | 0.064 | 31.286 | 262.832 |  |  |  | 262.832
6 | GRID (26'-27'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 4 | 29.535 | 2.352 | 2 | 0.064 | 30.471 | 131.292 |  |  |  | 131.292
6 | GRID (26'-27'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 3 | 29.535 | 1.568 | 2 | 0.064 | 30.471 | 96.117 |  |  |  | 96.117
7 | GRID (22'-26'/B-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 15.7 |  | 0.5 | 0.25 | 16 | 1 | 46 | 15.7 | 0.784 | 2 | 0.064 | 16.636 | 801.32 |  |  |  | 801.32
TOP DISTRIBUTION BAR
1 | GRID (30-38'/A)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.775 |  | 0.5 | 0.25 | 16 | 1 | 7 | 8.775 | 0 | 2 | 0.064 | 9.711 | 67.977 |  |  |  | 67.977
2 | GRID (27'-38'/A-B)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 12.725 |  | 0.5 | 0.25 | 16 | 1 | 4 | 12.725 | 0.784 | 2 | 0.064 | 13.661 | 57.78 |  |  |  | 57.78
3 | GRID (26'-38'/B-B')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 14.42 |  | 0.5 | 0.25 | 16 | 1 | 7 | 14.42 | 0.784 | 2 | 0.064 | 15.356 | 112.98 |  |  |  | 112.98
4 | GRID (22'-38'/B'-E')
| DIST. BAR BOTTOM (ALTH.) |  | 25.755 |  | 0.5 | 0.25 | 16 | 1 | 27 | 25.755 | 1.568 | 1 | 0.016 | 26.239 | 750.789 |  |  |  | 750.789
5 | GRID (22'-43'/E'-K)
| DIST. BAR BOTTOM (ALTH.) |  | 36.84 |  | 0.5 | 0.25 | 16 | 1 | 30 | 36.84 | 2.352 | 1 | 0.016 | 37.324 | 1190.28 |  |  |  | 1190.28
6 | GRID (26'-43'/M-Q)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 25.79 |  | 0.5 | 0.25 | 16 | 1 | 51 | 25.79 | 1.568 | 2 | 0.064 | 26.726 | 1442.994 |  |  |  | 1442.994
7 | GRID (33-39/Q')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.68 |  | 0.5 | 0.25 | 16 | 1 | 3 | 8.68 | 0 | 2 | 0.064 | 9.616 | 28.848 |  |  |  | 28.848
BINDER
1 | GRID (38'/A-E') |  | 10.285 |  |  | 0.25 | 12 | 1 | 2 | 10.285 | 0 |  | 0 | 10.285 | 20.57 |  |  | 20.57
2 | GRID (38'-43/E') |  | 11.09 |  |  | 0.25 | 12 | 1 | 2 | 11.09 | 0 |  | 0 | 11.09 | 22.18 |  |  | 22.18
3 | GRID (43/E'-Q') |  | 21.55 |  |  | 0.25 | 12 | 1 | 2 | 21.55 | 0.588 |  | 0 | 21.55 | 44.276 |  |  | 44.276
5 | GRID (30-38'/A) |  | 8.775 |  |  | 0.25 | 12 | 1 | 2 | 8.775 | 0 |  | 0 | 8.775 | 17.55 |  |  | 17.55
6 | GRID (30/A-B) |  | 1.5 |  |  | 0.25 | 12 | 1 | 2 | 1.5 | 0 |  | 0 | 1.5 | 3 |  |  | 3
7 | GRID (27'-30/A-B) |  | 3.95 |  |  | 0.25 | 12 | 1 | 2 | 3.95 | 0 |  | 0 | 3.95 | 7.9 |  |  | 7.9
8 | GRID (27'/A-B) |  | 0.815 |  |  | 0.25 | 12 | 1 | 2 | 0.815 | 0 |  | 0 | 0.815 | 1.63 |  |  | 1.63
9 | GRID (26'-27'/B) |  | 1.695 |  |  | 0.25 | 12 | 1 | 2 | 1.695 | 0 |  | 0 | 1.695 | 3.39 |  |  | 3.39
10 | GRID (26'/B-C) |  | 1.405 |  |  | 0.25 | 12 | 1 | 2 | 1.405 | 0 |  | 0 | 1.405 | 2.81 |  |  | 2.81
11 | GRID ( 22'-26'/B') |  | 11.285 |  |  | 0.25 | 12 | 1 | 2 | 11.285 | 0 |  | 0 | 11.285 | 22.57 |  |  | 22.57
12 | GRID ( 22'-26'/M') |  | 11.005 |  |  | 0.25 | 12 | 1 | 2 | 11.005 | 0 |  | 0 | 11.005 | 22.01 |  |  | 22.01
13 | GRID (26/M'-Q') |  | 12.415 |  |  | 0.25 | 12 | 1 | 2 | 12.415 | 0.588 |  | 0 | 12.415 | 26.006 |  |  | 26.006
14 | GRID (26-43'/Q') |  | 25.79 |  |  | 0.25 | 12 | 1 | 2 | 25.79 | 0.588 |  | 0 | 25.79 | 52.756 |  |  | 52.756
| CHAIR |  |  | 0.95
1 | [6 empty] | 20 | 1 | 785 | 3 | 0 |  | 0 | 3 | 2355 |  |  |  |  | 2355
0.675
0.35
BOTTOM EXTRA BAR
1 | MAIN BOTTOM EXTRA BAR |  | 3.35 |  |  | 0.25 | 20 | 1 | 9 | 3.35 | 0 | 0 | 0 | 3.35 | 30.15 |  |  |  |  | 30.15
SW1 GRID (38/A-B)
2 | DIST. BOTTOM EXTRA BAR |  | 1.95 |  |  | 0.25 | 12 | 1 | 14 | 1.95 | 0 | 0 | 0 | 1.95 | 27.3 |  |  | 27.3
SW1 GRID (38/A-B)
3 | MAIN BOTTOM EXTRA BAR |  | 2.55 |  |  | 0.25 | 25 | 1 | 10 | 2.55 | 0 | 0 | 0 | 2.55 | 25.5 | [5 empty] | 25.5
C1 GRID (34-35/A)
4 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 11 | 2.3 | 0 | 0 | 0 | 2.3 | 25.3 |  |  |  |  | 25.3
C1 GRID (34-35/A)
5 | MAIN BOTTOM EXTRA BAR |  | 2 |  |  | 0.25 | 20 | 1 | 10 | 2 | 0 | 0 | 0 | 2 | 20 |  |  |  |  | 20
C1 GRID (32/A)
6 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 9 | 2.3 | 0 | 0 | 0 | 2.3 | 20.7 |  |  |  |  | 20.7
C1 GRID (32/A)
7 | MAIN BOTTOM EXTRA BAR |  | 3.55 |  |  | 0.25 | 20 | 1 | 11 | 3.55 | 0 | 0 | 0 | 3.55 | 39.05 |  |  |  |  | 39.05
SW2, C7 GRID (27,28/B-C)
7 | MAIN BOTTOM EXTRA BAR |  | 2.5 |  |  | 0.25 | 25 | 1 | 8 | 2.5 | 0 | 0 | 0 | 2.5 | 20 | [5 empty] | 20
SW2, C7 GRID (27,28/B-C)
8 | DIST. BOTTOM EXTRA BAR |  | 2.35 |  |  | 0.25 | 25 | 1 | 4 | 2.35 | 0 | 0 | 0 | 2.35 | 9.4 | [5 empty] | 9.4
SW2, C7 GRID (27,28/B-C)
9 | DIST. BOTTOM EXTRA BAR |  | 4.095 |  |  | 0.25 | 25 | 1 | 12 | 4.095 | 0 | 0 | 0 | 4.095 | 49.14 | [5 empty] | 49.14
SW2, C7 GRID (27,28/B-C)
10 | MAIN BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C1 GRID (32/C)
11 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (32/C)
12 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 11 | 2.25 | 0 | 0 | 0 | 2.25 | 24.75 | [5 empty] | 24.75
C2 GRID ( 25/C)
13 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C2 GRID (25/C)
14 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 13 | 2.25 | 0 | 0 | 0 | 2.25 | 29.25 | [5 empty] | 29.25
C3 GRID (23/C)
15 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C3 GRID (23/C)
16 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 9 | 2.3 | 0 | 0 | 0 | 2.3 | 20.7 |  |  |  |  | 20.7
C1 GRID (38/D)
17 | DIST. BOTTOM EXTRA BAR |  | 1.9 |  |  | 0.25 | 12 | 1 | 10 | 1.9 | 0 | 0 | 0 | 1.9 | 19 |  |  | 19
C1 GRID (38/D)
18 | MAIN BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C2 GRID (35/D)
19 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 11 | 2.3 | 0 | 0 | 0 | 2.3 | 25.3 |  |  |  |  | 25.3
C2 GRID (35/D)
20 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (28/D)
21 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C1 GRID (28/D)
22 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (26/D)
23 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C1 GRID (26/D)
24 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C6 GRID (37/E)
25 | DIST. BOTTOM EXTRA BAR |  | 2.715 |  |  | 0.25 | 20 | 1 | 10 | 2.715 | 0 | 0 | 0 | 2.715 | 27.15 |  |  |  |  | 27.15
C6 GRID (37/E)
26 | MAIN BOTTOM EXTRA BAR |  | 3.935 |  |  | 0.25 | 20 | 1 | 17 | 3.935 | 0 | 0 | 0 | 3.935 | 66.895 |  |  |  |  | 66.895
SW4, SW3 GRID (32,33/E)
27 | DIST. BOTTOM EXTRA BAR |  | 4.06 |  |  | 0.25 | 20 | 1 | 17 | 4.06 | 0 | 0 | 0 | 4.06 | 69.02 |  |  |  |  | 69.02
SW4, SW3 GRID (32,33/E)
28 | MAIN BOTTOM EXTRA BAR |  | 1.83 |  |  | 0.25 | 16 | 1 | 14 | 1.83 | 0 | 0 | 0 | 1.83 | 25.62 |  |  |  | 25.62
SW6 GRID (28/E)
29 | DIST. BOTTOM EXTRA BAR |  | 3.185 |  |  | 0.25 | 20 | 1 | 8 | 3.185 | 0 | 0 | 0 | 3.185 | 25.48 |  |  |  |  | 25.48
SW6 GRID ( 28/E)
30 | MAIN BOTTOM EXTRA BAR |  | 2.2 |  |  | 0.25 | 20 | 1 | 12 | 2.2 | 0 | 0 | 0 | 2.2 | 26.4 |  |  |  |  | 26.4
C2 GRID (26/E)
31 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (26/E)
32 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 11 | 2.8 | 0 | 0 | 0 | 2.8 | 30.8 | [5 empty] | 30.8
C2 GRID (25/D-E)
33 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 12 | 2.6 | 0 | 0 | 0 | 2.6 | 31.2 |  |  |  |  | 31.2
C2 GRID (25/D-E)
34 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C8 GRID (23/D-E)
35 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C8 GRID (23/D-E)
36 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/F, J)
37 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/F, J)
38 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 25 | 2.6 | 0 | 0 | 0 | 2.6 | 65 |  |  |  |  | 65
SW9, C1 GRID (43/F, J)
39 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C2 GRID (41/F)
40 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (41/F)
41 | MAIN BOTTOM EXTRA BAR |  | 1.835 |  |  | 0.25 | 20 | 1 | 10 | 1.835 | 0 | 0 | 0 | 1.835 | 18.35 |  |  |  |  | 18.35
C6 GRID (39/F)
42 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 8 | 2.3 | 0 | 0 | 0 | 2.3 | 18.4 |  |  |  |  | 18.4
C6 GRID (39/F)
43 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C5 GRID (37/H)
44 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 14 | 2.8 | 0 | 0 | 0 | 2.8 | 39.2 | [5 empty] | 39.2
C5 GRID (37/H)
45 | MAIN BOTTOM EXTRA BAR |  | 2.73 |  |  | 0.25 | 25 | 1 | 16 | 2.73 | 0 | 0 | 0 | 2.73 | 43.68 | [5 empty] | 43.68
SW5 GRID (34/F)
46 | DIST. BOTTOM EXTRA BAR |  | 3.7 |  |  | 0.25 | 20 | 1 | 12 | 3.7 | 0 | 0 | 0 | 3.7 | 44.4 |  |  |  |  | 44.4
SW5 GRID (34/F)
47 | MAIN BOTTOM EXTRA BAR |  | 2.23 |  |  | 0.25 | 20 | 1 | 16 | 2.23 | 0 | 0 | 0 | 2.23 | 35.68 |  |  |  |  | 35.68
SW5 GRID (29/F)
48 | DIST. BOTTOM EXTRA BAR |  | 3.7 |  |  | 0.25 | 20 | 1 | 10 | 3.7 | 0 | 0 | 0 | 3.7 | 37 |  |  |  |  | 37
SW5 GRID (29/F)
49 | MAIN BOTTOM EXTRA BAR |  | 5.6 |  |  | 0.25 | 20 | 1 | 20 | 5.6 | 0 | 0 | 0 | 5.6 | 112 |  |  |  |  | 112
C1, SW7 GRID (24/E,G,H)
50 | DIST. BOTTOM EXTRA BAR |  | 4.725 |  |  | 0.25 | 25 | 1 | 23 | 4.725 | 0 | 0 | 0 | 4.725 | 108.675 | [5 empty] | 108.675
C1, SW7 GRID (24/E,G,H)
51 | MAIN BOTTOM EXTRA BAR |  | 6.1 |  |  | 0.25 | 25 | 1 | 12 | 6.1 | 0 | 0 | 0 | 6.1 | 73.2 | [5 empty] | 73.2
SW8 GRID (22/G)
52 | DIST. BOTTOM EXTRA BAR |  | 2.73 |  |  | 0.25 | 25 | 1 | 25 | 2.73 | 0 | 0 | 0 | 2.73 | 68.25 | [5 empty] | 68.25
SW8 GRID (22/G)
53 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 25 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 | [5 empty] | 33
C4 GRID (41/J)
54 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (41/J)
55 | DIST. BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 25 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 | [5 empty] | 33
C4 GRID (41/J)
56 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (41/J)
57 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C5 GRID (39/J)
58 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (39/J)
59 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (35/J)
60 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (35/J)
61 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (35/J)
62 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (29/J)
63 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (29/J)
64 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (29/J)
65 | MAIN BOTTOM EXTRA BAR |  | 1.83 |  |  | 0.25 | 16 | 1 | 14 | 1.83 | 0 | 0 | 0 | 1.83 | 25.62 |  |  |  | 25.62
SW6 GRID (28/I)
66 | DIST. BOTTOM EXTRA BAR |  | 3.185 |  |  | 0.25 | 20 | 1 | 8 | 3.185 | 0 | 0 | 0 | 3.185 | 25.48 |  |  |  |  | 25.48
SW6 GRID (28/I)
67 | MAIN BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 12 | 2.6 | 0 | 0 | 0 | 2.6 | 31.2 |  |  |  |  | 31.2
C2 GRID (26/I)
68 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 11 | 2.8 | 0 | 0 | 0 | 2.8 | 30.8 | [5 empty] | 30.8
C2 GRID (26/I)
69 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 11 | 2.8 | 0 | 0 | 0 | 2.8 | 30.8 |  |  |  |  | 30.8
C2 GRID (25/J)
70 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 25 | 1 | 12 | 2.6 | 0 | 0 | 0 | 2.6 | 31.2 | [5 empty] | 31.2
C2 GRID (25/J)
71 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C8 GRID (23/J)
72 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C8 GRID (23/J)
73 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 11 | 2.3 | 0 | 0 | 0 | 2.3 | 25.3 |  |  |  |  | 25.3
C1 GRID (28/J-K)
74 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C1 GRID (28/J-K)
75 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C1 GRID (26/D)
76 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C1 GRID ( 26/D)
77 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 11 | 2.25 | 0 | 0 | 0 | 2.25 | 24.75 | [5 empty] | 24.75
C2 GRID (25/L)
78 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C2 GRID (25/L)
79 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 13 | 2.25 | 0 | 0 | 0 | 2.25 | 29.25 | [5 empty] | 29.25
C3 GRID (23/L)
80 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C3 GRID (23/L)
81 | MAIN BOTTOM EXTRA BAR |  | 3.65 |  |  | 0.25 | 20 | 1 | 17 | 3.65 | 0 | 0 | 0 | 3.65 | 62.05 |  |  |  |  | 62.05
SW12, C7 GRID (27,28/M-N)
82 | DIST. BOTTOM EXTRA BAR |  | 4.345 |  |  | 0.25 | 20 | 1 | 15 | 4.345 | 0 | 0 | 0 | 4.345 | 65.175 |  |  |  |  | 65.175
SW12, C7 GRID (27,28/M-N)
83 | MAIN BOTTOM EXTRA BAR |  | 1.915 |  |  | 0.25 | 12 | 1 | 7 | 1.915 | 0 | 0 | 0 | 1.915 | 13.405 |  |  | 13.405
C6 GRID (43/M)
84 | DIST. BOTTOM EXTRA BAR |  | 1.6 |  |  | 0.25 | 12 | 1 | 9 | 1.6 | 0 | 0 | 0 | 1.6 | 14.4 |  |  | 14.4
C6 GRID (43/M)
85 | MAIN BOTTOM EXTRA BAR |  | 1.915 |  |  | 0.25 | 12 | 1 | 7 | 1.915 | 0 | 0 | 0 | 1.915 | 13.405 |  |  | 13.405
C6 GRID (43/O)
86 | DIST. BOTTOM EXTRA BAR |  | 1.6 |  |  | 0.25 | 12 | 1 | 9 | 1.6 | 0 | 0 | 0 | 1.6 | 14.4 |  |  | 14.4
C6 GRID (43/O)
87 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 25 | 1 | 10 | 2.3 | 0 | 0 | 0 | 2.3 | 23 | [5 empty] | 23
C1 GRID (42/M)
88 | DIST. BOTTOM EXTRA BAR |  | 2.2 |  |  | 0.25 | 16 | 1 | 10 | 2.2 | 0 | 0 | 0 | 2.2 | 22 |  |  |  | 22
C1 GRID (42/M)
89 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 25 | 1 | 10 | 2.3 | 0 | 0 | 0 | 2.3 | 23 | [5 empty] | 23
C1 GRID (42/O)
90 | DIST. BOTTOM EXTRA BAR |  | 2.2 |  |  | 0.25 | 16 | 1 | 10 | 2.2 | 0 | 0 | 0 | 2.2 | 22 |  |  |  | 22
C1 GRID (42/O)
91 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C4 GRID (39/M)
92 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 14 | 2.8 | 0 | 0 | 0 | 2.8 | 39.2 | [5 empty] | 39.2
C4 GRID (39/M)
91 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C4 GRID (39/O)
92 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 14 | 2.8 | 0 | 0 | 0 | 2.8 | 39.2 |  |  |  |  | 39.2
C4 GRID (39/O)
93 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (39/O)
94 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C2 GRID (38/N)
95 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C2 GRID (38/N)
96 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 8 | 2.75 | 0 | 0 | 0 | 2.75 | 22 |  |  |  |  | 22
C5 GRID (37/L)
97 | DIST. BOTTOM EXTRA BAR |  | 1.85 |  |  | 0.25 | 20 | 1 | 12 | 1.85 | 0 | 0 | 0 | 1.85 | 22.2 |  |  |  |  | 22.2
C5 GRID (37/L)
98 | DIST. BOTTOM EXTRA BAR |  | 1.85 |  |  | 0.25 | 20 | 1 | 8 | 1.85 | 0 | 0 | 0 | 1.85 | 14.8 |  |  |  |  | 14.8
C5 GRID (37/L)
99 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C4 GRID (37/O)
100 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C4 GRID (37/O)
101 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 10 | 2.75 | 0 | 0 | 0 | 2.75 | 27.5 |  |  |  |  | 27.5
C5 GRID (32/O)
102 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C5 GRID (32/O)
103 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C5 GRID (32/O)
104 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (29/O)
105 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 20 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 |  |  |  |  | 31
C1 GRID (29/O)
106 | MAIN BOTTOM EXTRA BAR |  | 1.915 |  |  | 0.25 | 12 | 1 | 9 | 1.915 | 0 | 0 | 0 | 1.915 | 17.235 |  |  | 17.235
C6 GRID (27/O)
107 | DIST. BOTTOM EXTRA BAR |  | 2 |  |  | 0.25 | 20 | 1 | 9 | 2 | 0 | 0 | 0 | 2 | 18 |  |  |  |  | 18
C6 GRID (27/O)
108 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/P, Q)
109 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/P, Q)
110 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 25 | 2.6 | 0 | 0 | 0 | 2.6 | 65 |  |  |  |  | 65
SW9, C1 GRID (43/P, Q)
111 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 20 | 1 | 10 | 5.96 | 0 | 0 | 0 | 5.96 | 59.6 |  |  |  |  | 59.6
SW9, C1 GRID (27/P, Q)
112 | DIST. BOTTOM EXTRA BAR |  | 2.35 |  |  | 0.25 | 20 | 1 | 25 | 2.35 | 0 | 0 | 0 | 2.35 | 58.75 |  |  |  |  | 58.75
SW9, C1 GRID (27/P, Q)
113 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C2 GRID (41/Q)
114 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (41/Q)
115 | MAIN BOTTOM EXTRA BAR |  | 2.415 |  |  | 0.25 | 20 | 1 | 10 | 2.415 | 0 | 0 | 0 | 2.415 | 24.15 |  |  |  |  | 24.15
C6 GRID (39/Q)
116 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 8 | 2.3 | 0 | 0 | 0 | 2.3 | 18.4 |  |  |  |  | 18.4
C6 GRID (39/Q)
117 | MAIN BOTTOM EXTRA BAR |  | 2.415 |  |  | 0.25 | 20 | 1 | 10 | 2.415 | 0 | 0 | 0 | 2.415 | 24.15 |  |  |  |  | 24.15
C6 GRID (34/Q)
118 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 8 | 2.3 | 0 | 0 | 0 | 2.3 | 18.4 |  |  |  |  | 18.4
C6 GRID (34/Q)
119 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C2 GRID (30/Q)
120 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (30/Q)
121 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C5 GRID (37/P-Q)
122 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (37/P-Q)
123 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 25 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 | [5 empty] | 33
C4 GRID (41/P)
124 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (41/P)
125 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (41/P)
126 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (41/P)
127 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C5 GRID (39/P)
128 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (39/P)
129 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (30/P)
130 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (30/P)
131 | DIST. BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (30/P)
132 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C5 GRID (34/P)
133 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (34/P)
134 | MAIN BOTTOM EXTRA BAR |  | 5.145 |  |  | 0.25 | 20 | 1 | 26 | 5.145 | 0 | 0 | 0 | 5.145 | 133.77 |  |  |  |  | 133.77
SW10, SW11, SW13 GRID (31-36/K-N)
135 | DIST. BOTTOM EXTRA BAR |  | 6.165 |  |  | 0.25 | 20 | 1 | 22 | 6.165 | 0 | 0 | 0 | 6.165 | 135.63 |  |  |  |  | 135.63
SW10, SW11, SW13 GRID (31-36/K-N)
136 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (29/J)
137 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (25/J)
138 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (41/J)
139 | SPACER B/W EXTRA BAR |  | 2.8 |  |  |  | 20 | 1 | 3 | 2.8 | 0 | 0 | 0 | 2.8 | 8.4 |  |  |  |  | 8.4
C4 GRID (41/J)
140 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C5 GRID (37/L)
141 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C5 GRID (32/O)
142 | SPACER B/W EXTRA BAR |  | 3.25 |  |  |  | 20 | 1 | 3 | 3.25 | 0 | 0 | 0 | 3.25 | 9.75 |  |  |  |  | 9.75
C4 GRID (40/O)
143 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (29/P)
144 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (41/P)
145 | SPACER B/W EXTRA BAR |  | 2.8 |  |  |  | 20 | 1 | 3 | 2.8 | 0 | 0 | 0 | 2.8 | 8.4 |  |  |  |  | 8.4
C4 GRID (41/P)
146 | SPACER B/W EXTRA BAR |  | 6.165 |  |  |  | 20 | 1 | 4 | 6.165 | 0 | 0 | 0 | 6.165 | 24.66 |  |  |  |  | 24.66
SW10, SW11, SW13 GRID (31-36/K-N)
TOP EXTRA BAR
1 | MAIN TOP EXTRA BAR |  | 2.425 |  |  | 0.25 | 20 | 1 | 23 | 2.425 | 0 | 0 | 0 | 2.425 | 55.775 |  |  |  |  | 55.775
GRID (35-37/A-D)
2 | DIST. TOP EXTRA BAR |  | 3.95 |  |  | 0.25 | 16 | 1 | 11 | 3.95 | 0 | 0 | 0 | 3.95 | 43.45 |  |  |  | 43.45
GRID (35-37/A-D)
3 | MAIN TOP EXTRA BAR |  | 2.2 |  |  | 0.25 | 10 | 1 | 31 | 2.2 | 0 | 0 | 0 | 2.2 | 68.2 |  | 68.2
GRID (32-35/A-D)
4 | DIST. TOP EXTRA BAR |  | 6.165 |  |  | 0.25 | 16 | 1 | 10 | 6.165 | 0 | 0 | 0 | 6.165 | 61.65 |  |  |  | 61.65
GRID (32-35/A-D)
5 | MAIN TOP EXTRA BAR |  | 4.52 |  |  | 0.25 | 12 | 1 | 13 | 4.52 | 0 | 0 | 0 | 4.52 | 58.76 |  |  | 58.76
GRID (28-31/B-E)
6 | MAIN TOP EXTRA BAR |  | 2.275 |  |  | 0.25 | 10 | 1 | 22 | 2.275 | 0 | 0 | 0 | 2.275 | 50.05 |  | 50.05
GRID (26-28/B-E)
7 | DIST. TOP EXTRA BAR |  | 5.355 |  |  | 0.25 | 12 | 1 | 10 | 5.355 | 0 | 0 | 0 | 5.355 | 53.55 |  |  | 53.55
GRID (26-28/B-E)
8 | MAIN TOP EXTRA BAR |  | 2.45 |  |  | 0.25 | 12 | 1 | 10 | 2.45 | 0 | 0 | 0 | 2.45 | 24.5 |  |  | 24.5
GRID (25-26/B-E)
9 | MAIN TOP EXTRA BAR |  | 4.09 |  |  | 0.25 | 12 | 1 | 24 | 4.09 | 0 | 0 | 0 | 4.09 | 98.16 |  |  | 98.16
GRID (24-26/B-E)
10 | DIST. TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 10 | 1 | 17 | 3.8 | 0 | 0 | 0 | 3.8 | 64.6 |  | 64.6
GRID (24-26/B-E)
11 | MAIN TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 10 | 1 | 24 | 3.8 | 0 | 0 | 0 | 3.8 | 91.2 |  | 91.2
GRID (21-23 /B-E)
12 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 20 | 1 | 24 | 5.7 | 0 | 0 | 0 | 5.7 | 136.8 |  |  |  |  | 136.8
GRID (21-23 /B-E)
13 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 16 | 1 | 10 | 5.7 | 0 | 0 | 0 | 5.7 | 57 |  |  |  | 57
GRID (21-23 /B-E)
14 | MAIN TOP EXTRA BAR |  | 2.515 |  |  | 0.25 | 12 | 1 | 17 | 2.515 | 0 | 0 | 0 | 2.515 | 42.755 |  |  | 42.755
GRID (34-36 /D-F)
15 | MAIN TOP EXTRA BAR |  | 4.19 |  |  | 0.25 | 12 | 1 | 11 | 4.19 | 0 | 0 | 0 | 4.19 | 46.09 |  |  | 46.09
GRID (41-43 /E-I)
16 | MAIN TOP EXTRA BAR |  | 7.71 |  |  | 0.25 | 12 | 1 | 12 | 7.71 | 0 | 0 | 0 | 7.71 | 92.52 |  |  | 92.52
GRID (40-42 /E-K)
17 | MAIN TOP EXTRA BAR |  | 2.785 |  |  | 0.25 | 12 | 1 | 11 | 2.785 | 0 | 0 | 0 | 2.785 | 30.635 |  |  | 30.635
GRID (41-42 /E-I)
18 | DIST. TOP EXTRA BAR |  | 2.615 |  |  | 0.25 | 20 | 1 | 12 | 2.615 | 0 | 0 | 0 | 2.615 | 31.38 |  |  |  |  | 31.38
GRID (41-42 /E-I)
19 | MAIN TOP EXTRA BAR |  | 4.12 |  |  | 0.25 | 20 | 1 | 34 | 4.12 | 0 | 0 | 0 | 4.12 | 140.08 |  |  |  |  | 140.08
GRID (41-42 /E-L)
20 | DIST. TOP EXTRA BAR |  | 3.12 |  |  | 0.25 | 20 | 1 | 14 | 3.12 | 0 | 0 | 0 | 3.12 | 43.68 |  |  |  |  | 43.68
GRID (40-42 /J-L)
21 | DIST. TOP EXTRA BAR |  | 2.92 |  |  | 0.25 | 16 | 1 | 23 | 2.92 | 0 | 0 | 0 | 2.92 | 67.16 |  |  |  | 67.16
GRID (40-42 /J-L)
22 | MAIN TOP EXTRA BAR |  | 4.545 |  |  | 0.25 | 16 | 1 | 21 | 4.545 | 0 | 0 | 0 | 4.545 | 95.445 |  |  |  | 95.445
GRID (34-38 /H-K)
23 | DIST. TOP EXTRA BAR |  | 5 |  |  | 0.25 | 16 | 1 | 19 | 5 | 0 | 0 | 0 | 5 | 95 |  |  |  | 95
GRID (34-38 /H-K)
24 | MAIN TOP EXTRA BAR |  | 5.24 |  |  | 0.25 | 16 | 1 | 21 | 5.24 | 0 | 0 | 0 | 5.24 | 110.04 |  |  |  | 110.04
GRID (28-33 /H-K)
25 | DIST. TOP EXTRA BAR |  | 2.54 |  |  | 0.25 | 12 | 1 | 18 | 2.54 | 0 | 0 | 0 | 2.54 | 45.72 |  |  | 45.72
GRID (25-28 /E-I)
26 | DIST. TOP EXTRA BAR |  | 4.375 |  |  | 0.25 | 10 | 1 | 12 | 4.375 | 0 | 0 | 0 | 4.375 | 52.5 |  | 52.5
GRID (25-28 /I-K)
27 | DIST. TOP EXTRA BAR |  | 3.64 |  |  | 0.25 | 10 | 1 | 64 | 3.64 | 0 | 0 | 0 | 3.64 | 232.96 |  | 232.96
GRID (24-25 /B-M)
28 | DIST. TOP EXTRA BAR |  | 2.45 |  |  | 0.25 | 10 | 1 | 10 | 2.45 | 0 | 0 | 0 | 2.45 | 24.5 |  | 24.5
GRID (24-25 /J-K)
29 | DIST. TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 10 | 1 | 17 | 3.8 | 0 | 0 | 0 | 3.8 | 64.6 |  | 64.6
GRID (22-24 /J-M)
30 | MAIN TOP EXTRA BAR |  | 6.4 |  |  | 0.25 | 10 | 1 | 23 | 6.4 | 0 | 0 | 0 | 6.4 | 147.2 |  | 147.2
GRID (22-24 /E-J)
31 | DIST. TOP EXTRA BAR |  | 5.53 |  |  | 0.25 | 16 | 1 | 27 | 5.53 | 0 | 0 | 0 | 5.53 | 149.31 |  |  |  | 149.31
GRID (22-24 /E-J)
32 | MAIN TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 12 | 1 | 24 | 3.8 | 0 | 0 | 0 | 3.8 | 91.2 |  |  | 91.2
GRID (21-23 /I-M)
33 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 20 | 1 | 24 | 5.7 | 0 | 0 | 0 | 5.7 | 136.8 |  |  |  |  | 136.8
GRID (21-23 /I-M)
34 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 16 | 1 | 10 | 5.7 | 0 | 0 | 0 | 5.7 | 57 |  |  |  | 57
GRID (21-23 /I-M)
35 | MAIN TOP EXTRA BAR |  | 5.745 |  |  | 0.25 | 16 | 1 | 15 | 5.745 | 0 | 0 | 0 | 5.745 | 86.175 |  |  |  | 86.175
GRID (40-43/M-O)
36 | DIST. TOP EXTRA BAR |  | 2.5 |  |  | 0.25 | 20 | 1 | 14 | 2.5 | 0 | 0 | 0 | 2.5 | 35 |  |  |  |  | 35
GRID (40-43 /M-O)
37 | DIST. TOP EXTRA BAR |  | 3.46 |  |  | 0.25 | 20 | 1 | 24 | 3.46 | 0 | 0 | 0 | 3.46 | 83.04 |  |  |  |  | 83.04
GRID (40-43 /M-O)
38 | MAIN TOP EXTRA BAR |  | 3.045 |  |  | 0.25 | 20 | 1 | 19 | 3.045 | 0 | 0 | 0 | 3.045 | 57.855 |  |  |  |  | 57.855
GRID (37-40 /K-N)
39 | DIST. TOP EXTRA BAR |  | 4.525 |  |  | 0.25 | 16 | 1 | 13 | 4.525 | 0 | 0 | 0 | 4.525 | 58.825 |  |  |  | 58.825
GRID (37-40 /K-N)
40 | MAIN TOP EXTRA BAR |  | 3.12 |  |  | 0.25 | 20 | 1 | 14 | 3.12 | 0 | 0 | 0 | 3.12 | 43.68 |  |  |  |  | 43.68
GRID (40-43 /O-Q)
41 | MAIN TOP EXTRA BAR |  | 2.85 |  |  | 0.25 | 16 | 1 | 23 | 2.85 | 0 | 0 | 0 | 2.85 | 65.55 |  |  |  | 65.55
GRID (40-43 /O-Q)
42 | DIST. TOP EXTRA BAR |  | 4.12 |  |  | 0.25 | 20 | 1 | 34 | 4.12 | 0 | 0 | 0 | 4.12 | 140.08 |  |  |  |  | 140.08
GRID (40-43 /O-Q)
43 | DIST. TOP EXTRA BAR |  | 4.19 |  |  | 0.25 | 12 | 1 | 11 | 4.19 | 0 | 0 | 0 | 4.19 | 46.09 |  |  | 46.09
GRID (40-43 /O-Q)
44 | DIST. TOP EXTRA BAR |  | 7.68 |  |  | 0.25 | 12 | 1 | 12 | 7.68 | 0 | 0 | 0 | 7.68 | 92.16 |  |  | 92.16
GRID (40-43 /O-Q)
45 | DIST. TOP EXTRA BAR |  | 3.915 |  |  | 0.25 | 20 | 1 | 19 | 3.915 | 0 | 0 | 0 | 3.915 | 74.385 |  |  |  |  | 74.385
GRID (36-39 /N-P)
46 | DIST. TOP EXTRA BAR |  | 4.5 |  |  | 0.25 | 16 | 1 | 17 | 4.5 | 0 | 0 | 0 | 4.5 | 76.5 |  |  |  | 76.5
GRID (36-39 /N-P)
47 | DIST. TOP EXTRA BAR |  | 4.55 |  |  | 0.25 | 10 | 1 | 19 | 4.55 | 0 | 0 | 0 | 4.55 | 86.45 |  | 86.45
GRID (31-36 /O-P)
48 | MAIN TOP EXTRA BAR |  | 3.975 |  |  | 0.25 | 25 | 1 | 25 | 3.975 | 0 | 0 | 0 | 3.975 | 99.375 | [5 empty] | 99.375
GRID (33-38 /O'-P')
49 | DIST. TOP EXTRA BAR |  | 6.08 |  |  | 0.25 | 16 | 1 | 17 | 6.08 | 0 | 0 | 0 | 6.08 | 103.36 |  |  |  | 103.36
GRID (33-38 /O'-P')
50 | MAIN TOP EXTRA BAR |  | 1.95 |  |  | 0.25 | 12 | 1 | 25 | 1.95 | 0 | 0 | 0 | 1.95 | 48.75 |  |  | 48.75
GRID (33-38 /P'-Q)
51 | DIST. TOP EXTRA BAR |  | 6.08 |  |  | 0.25 | 12 | 1 | 9 | 6.08 | 0 | 0 | 0 | 6.08 | 54.72 |  |  | 54.72
GRID (33-38 /P'-Q)
52 | DIST. TOP EXTRA BAR |  | 7.71 |  |  | 0.25 | 12 | 1 | 12 | 7.71 | 0 | 0 | 0 | 7.71 | 92.52 |  |  | 92.52
GRID (29-32 /O-Q)
53 | MAIN TOP EXTRA BAR |  | 2.85 |  |  | 0.25 | 10 | 1 | 17 | 2.85 | 0 | 0 | 0 | 2.85 | 48.45 |  | 48.45
GRID (26-29 /O-Q)
54 | DIST. TOP EXTRA BAR |  | 5.47 |  |  | 0.25 | 20 | 1 | 34 | 5.47 | 0 | 0 | 0 | 5.47 | 185.98 |  |  |  |  | 185.98
GRID (26-29 /O-Q)
55 | DIST. TOP EXTRA BAR |  | 4.19 |  |  | 0.25 | 16 | 1 | 11 | 4.19 | 0 | 0 | 0 | 4.19 | 46.09 |  |  |  | 46.09
GRID (26-29 /O-Q)
| TOTAL LENGTH IN METRE | [14 empty] | 0 | 930.71 | 1283.923 | 16524.773 | 6227.625 | 2199.06
| UNIT WEIGHT (IN KG) | [14 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.469 | 3.858
| TOTAL WEIGHT (IN KG) | [14 empty] | 0 | 574.2481 | 1140.1236 | 26109.1413 | 15376.0061 | 8483.9735 | 51683.4926 | KG
TOWER-E RAFT BBS GRID (1-22'/A-Q)
S.No. | Description | Shape of Bar in mm |  |  |  | Spacing c/c | Dia of Bar | No's of Set | No's of Bar | Actual Length | Lap | No. Of Bend | Deduction In mm | Cut Length | Total Length | TMT BAR Fe-500D or EQR | [5 empty] | Remarks
A | RAFT | [14 empty] | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm
BOTTOM MAIN BAR
1 | GRID (1-4'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 18 | 21.55 | 1.568 | 2 | 0.064 | 22.486 | 432.972 |  |  |  | 432.972
1 | GRID (1-4'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 17 | 21.55 | 0.784 | 2 | 0.064 | 22.486 | 395.59 |  |  |  | 395.59
2 | GRID (4'-5'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 6 | 22.065 | 1.568 | 2 | 0.064 | 23.001 | 147.414 |  |  |  | 147.414
2 | GRID (4'-5'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 5 | 22.065 | 0.784 | 2 | 0.064 | 23.001 | 118.925 |  |  |  | 118.925
3 | GRID (5'-11'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 13 | 32.35 | 2.352 | 2 | 0.064 | 33.286 | 463.294 |  |  |  | 463.294
3 | GRID (5'-11'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 12 | 32.35 | 1.568 | 2 | 0.064 | 33.286 | 418.248 |  |  |  | 418.248
4 | GRID (11'-14'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 6 | 31.835 | 2.352 | 2 | 0.064 | 32.771 | 210.738 |  |  |  | 210.738
4 | GRID (11'-14'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 5 | 31.835 | 1.568 | 2 | 0.064 | 32.771 | 171.695 |  |  |  | 171.695
5 | GRID (14-16'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 9 | 30.35 | 2.352 | 2 | 0.064 | 31.286 | 302.742 |  |  |  | 302.742
5 | GRID (14-16'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 8 | 30.35 | 1.568 | 2 | 0.064 | 31.286 | 262.832 |  |  |  | 262.832
6 | GRID (16'-17'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 4 | 29.535 | 2.352 | 2 | 0.064 | 30.471 | 131.292 |  |  |  | 131.292
6 | GRID (16'-17'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 3 | 29.535 | 1.568 | 2 | 0.064 | 30.471 | 96.117 |  |  |  | 96.117
7 | GRID (1-22'/B-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 15.7 |  | 0.5 | 0.25 | 16 | 1 | 46 | 15.7 | 0.784 | 2 | 0.064 | 16.636 | 801.32 |  |  |  | 801.32
BOTTOM DISTRIBUTION BAR
1 | GRID (5'-14/A)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.775 |  | 0.5 | 0.25 | 16 | 1 | 7 | 8.775 | 0 | 2 | 0.064 | 9.711 | 67.977 |  |  |  | 67.977
2 | GRID (5'-16'/A-B)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 12.725 |  | 0.5 | 0.25 | 16 | 1 | 4 | 12.725 | 0.784 | 2 | 0.064 | 13.661 | 57.78 |  |  |  | 57.78
3 | GRID (5'-17'/B-B')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 14.42 |  | 0.5 | 0.25 | 16 | 1 | 7 | 14.42 | 0.784 | 2 | 0.064 | 15.356 | 112.98 |  |  |  | 112.98
4 | GRID (5'-22'/B'-E')
| DIST. BAR BOTTOM (ALTH.) |  | 29.025 |  | 0.5 | 0.25 | 16 | 1 | 27 | 29.025 | 1.568 | 1 | 0.016 | 29.509 | 839.079 |  |  |  | 839.079
5 | GRID (1-22'/E'-K)
| DIST. BAR BOTTOM (ALTH.) |  | 40.11 |  | 0.5 | 0.25 | 16 | 1 | 30 | 40.11 | 2.352 | 1 | 0.016 | 40.594 | 1288.38 |  |  |  | 1288.38
6 | GRID (1-17'/M-Q)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 25.79 |  | 0.5 | 0.25 | 16 | 1 | 51 | 25.79 | 1.568 | 2 | 0.064 | 26.726 | 1442.994 |  |  |  | 1442.994
7 | GRID (4'-11'/Q')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.68 |  | 0.5 | 0.25 | 16 | 1 | 3 | 8.68 | 0 | 2 | 0.064 | 9.616 | 28.848 |  |  |  | 28.848
TOP MAIN BAR
1 | GRID (1-4'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 19 | 21.55 | 1.568 | 2 | 0.064 | 22.486 | 457.026 |  |  |  | 457.026
1 | GRID (1-4'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 18 | 21.55 | 0.784 | 2 | 0.064 | 22.486 | 418.86 |  |  |  | 418.86
2 | GRID (4'-5'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 6 | 22.065 | 1.568 | 2 | 0.064 | 23.001 | 147.414 |  |  |  | 147.414
2 | GRID (4'-5'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 5 | 22.065 | 0.784 | 2 | 0.064 | 23.001 | 118.925 |  |  |  | 118.925
3 | GRID (5'-11'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 13 | 32.35 | 2.352 | 2 | 0.064 | 33.286 | 463.294 |  |  |  | 463.294
3 | GRID (5'-11'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 12 | 32.35 | 1.568 | 2 | 0.064 | 33.286 | 418.248 |  |  |  | 418.248
4 | GRID (11'-14'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 6 | 31.835 | 2.352 | 2 | 0.064 | 32.771 | 210.738 |  |  |  | 210.738
4 | GRID (11'-14'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 5 | 31.835 | 1.568 | 2 | 0.064 | 32.771 | 171.695 |  |  |  | 171.695
5 | GRID (14-16'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 9 | 30.35 | 2.352 | 2 | 0.064 | 31.286 | 302.742 |  |  |  | 302.742
5 | GRID (14-16'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 8 | 30.35 | 1.568 | 2 | 0.064 | 31.286 | 262.832 |  |  |  | 262.832
6 | GRID (16'-17'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 4 | 29.535 | 2.352 | 2 | 0.064 | 30.471 | 131.292 |  |  |  | 131.292
6 | GRID (16'-17'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 3 | 29.535 | 1.568 | 2 | 0.064 | 30.471 | 96.117 |  |  |  | 96.117
7 | GRID (1-22'/B-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 15.7 |  | 0.5 | 0.25 | 16 | 1 | 46 | 15.7 | 0.784 | 2 | 0.064 | 16.636 | 801.32 |  |  |  | 801.32
TOP DISTRIBUTION BAR
1 | GRID (5'-14/A)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.775 |  | 0.5 | 0.25 | 16 | 1 | 7 | 8.775 | 0 | 2 | 0.064 | 9.711 | 67.977 |  |  |  | 67.977
2 | GRID (5'-16'/A-B)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 12.725 |  | 0.5 | 0.25 | 16 | 1 | 4 | 12.725 | 0.784 | 2 | 0.064 | 13.661 | 57.78 |  |  |  | 57.78
3 | GRID (5'-17'/B-B')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 14.42 |  | 0.5 | 0.25 | 16 | 1 | 7 | 14.42 | 0.784 | 2 | 0.064 | 15.356 | 112.98 |  |  |  | 112.98
4 | GRID (5'-22'/B'-E')
| DIST. BAR BOTTOM (ALTH.) |  | 29.025 |  | 0.5 | 0.25 | 16 | 1 | 27 | 29.025 | 1.568 | 1 | 0.016 | 29.509 | 839.079 |  |  |  | 839.079
5 | GRID (1-22'/E'-K)
| DIST. BAR BOTTOM (ALTH.) |  | 40.11 |  | 0.5 | 0.25 | 16 | 1 | 30 | 40.11 | 2.352 | 1 | 0.016 | 40.594 | 1288.38 |  |  |  | 1288.38
6 | GRID (1-17'/M-Q)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 25.79 |  | 0.5 | 0.25 | 16 | 1 | 51 | 25.79 | 1.568 | 2 | 0.064 | 26.726 | 1442.994 |  |  |  | 1442.994
7 | GRID (4'-11'/Q')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.68 |  | 0.5 | 0.25 | 16 | 1 | 3 | 8.68 | 0 | 2 | 0.064 | 9.616 | 28.848 |  |  |  | 28.848
BINDER
1 | GRID (5'/A-E') |  | 10.285 |  |  | 0.25 | 12 | 1 | 2 | 10.285 | 0 |  | 0 | 10.285 | 20.57 |  |  | 20.57
2 | GRID (5'-1/E') |  | 11.09 |  |  | 0.25 | 12 | 1 | 2 | 11.09 | 0 |  | 0 | 11.09 | 22.18 |  |  | 22.18
3 | GRID (1/E'-Q') |  | 21.55 |  |  | 0.25 | 12 | 1 | 2 | 21.55 | 0.588 |  | 0 | 21.55 | 44.276 |  |  | 44.276
5 | GRID (5'-14/A) |  | 8.775 |  |  | 0.25 | 12 | 1 | 2 | 8.775 | 0 |  | 0 | 8.775 | 17.55 |  |  | 17.55
6 | GRID (14/A-B) |  | 1.5 |  |  | 0.25 | 12 | 1 | 2 | 1.5 | 0 |  | 0 | 1.5 | 3 |  |  | 3
7 | GRID (14-16'/A-B) |  | 3.95 |  |  | 0.25 | 12 | 1 | 2 | 3.95 | 0 |  | 0 | 3.95 | 7.9 |  |  | 7.9
8 | GRID (16'/A-B) |  | 0.815 |  |  | 0.25 | 12 | 1 | 2 | 0.815 | 0 |  | 0 | 0.815 | 1.63 |  |  | 1.63
9 | GRID (16'-17'/B) |  | 1.695 |  |  | 0.25 | 12 | 1 | 2 | 1.695 | 0 |  | 0 | 1.695 | 3.39 |  |  | 3.39
10 | GRID (17'/B-C) |  | 1.405 |  |  | 0.25 | 12 | 1 | 2 | 1.405 | 0 |  | 0 | 1.405 | 2.81 |  |  | 2.81
11 | GRID ( 17'-22'/B') |  | 14.555 |  |  | 0.25 | 12 | 1 | 2 | 14.555 | 0.588 |  | 0 | 14.555 | 30.286 |  |  | 30.286
12 | GRID ( 17'-22'/M') |  | 14.275 |  |  | 0.25 | 12 | 1 | 2 | 14.275 | 0.588 |  | 0 | 14.275 | 29.726 |  |  | 29.726
13 | GRID (18/M'-Q') |  | 12.415 |  |  | 0.25 | 12 | 1 | 2 | 12.415 | 0.588 |  | 0 | 12.415 | 26.006 |  |  | 26.006
14 | GRID (1-17'/Q') |  | 25.79 |  |  | 0.25 | 12 | 1 | 2 | 25.79 | 0.588 |  | 0 | 25.79 | 52.756 |  |  | 52.756
| CHAIR |  |  | 0.95
1 | [6 empty] | 20 | 1 | 836 | 3 | 0 |  | 0 | 3 | 2508 |  |  |  |  | 2508
0.675
0.35
BOTTOM EXTRA BAR
1 | MAIN BOTTOM EXTRA BAR |  | 3.35 |  |  | 0.25 | 20 | 1 | 9 | 3.35 | 0 | 0 | 0 | 3.35 | 30.15 |  |  |  |  | 30.15
SW1 GRID (38/A-B)
2 | DIST. BOTTOM EXTRA BAR |  | 1.95 |  |  | 0.25 | 12 | 1 | 14 | 1.95 | 0 | 0 | 0 | 1.95 | 27.3 |  |  | 27.3
SW1 GRID (38/A-B)
3 | MAIN BOTTOM EXTRA BAR |  | 2.55 |  |  | 0.25 | 25 | 1 | 10 | 2.55 | 0 | 0 | 0 | 2.55 | 25.5 | [5 empty] | 25.5
C1 GRID (34-35/A)
4 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 11 | 2.3 | 0 | 0 | 0 | 2.3 | 25.3 |  |  |  |  | 25.3
C1 GRID (34-35/A)
5 | MAIN BOTTOM EXTRA BAR |  | 2 |  |  | 0.25 | 20 | 1 | 10 | 2 | 0 | 0 | 0 | 2 | 20 |  |  |  |  | 20
C1 GRID (32/A)
6 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 9 | 2.3 | 0 | 0 | 0 | 2.3 | 20.7 |  |  |  |  | 20.7
C1 GRID (32/A)
7 | MAIN BOTTOM EXTRA BAR |  | 3.55 |  |  | 0.25 | 20 | 1 | 11 | 3.55 | 0 | 0 | 0 | 3.55 | 39.05 |  |  |  |  | 39.05
SW2, C7 GRID (27,28/B-C)
7 | MAIN BOTTOM EXTRA BAR |  | 2.5 |  |  | 0.25 | 25 | 1 | 8 | 2.5 | 0 | 0 | 0 | 2.5 | 20 | [5 empty] | 20
SW2, C7 GRID (27,28/B-C)
8 | DIST. BOTTOM EXTRA BAR |  | 2.35 |  |  | 0.25 | 25 | 1 | 4 | 2.35 | 0 | 0 | 0 | 2.35 | 9.4 | [5 empty] | 9.4
SW2, C7 GRID (27,28/B-C)
9 | DIST. BOTTOM EXTRA BAR |  | 4.095 |  |  | 0.25 | 25 | 1 | 12 | 4.095 | 0 | 0 | 0 | 4.095 | 49.14 | [5 empty] | 49.14
SW2, C7 GRID (27,28/B-C)
10 | MAIN BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C1 GRID (32/C)
11 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (32/C)
12 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 11 | 2.25 | 0 | 0 | 0 | 2.25 | 24.75 | [5 empty] | 24.75
C2 GRID ( 25/C)
13 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C2 GRID (25/C)
14 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 13 | 2.25 | 0 | 0 | 0 | 2.25 | 29.25 | [5 empty] | 29.25
C3 GRID (23/C)
15 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C3 GRID (23/C)
16 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 9 | 2.3 | 0 | 0 | 0 | 2.3 | 20.7 |  |  |  |  | 20.7
C1 GRID (38/D)
17 | DIST. BOTTOM EXTRA BAR |  | 1.9 |  |  | 0.25 | 12 | 1 | 10 | 1.9 | 0 | 0 | 0 | 1.9 | 19 |  |  | 19
C1 GRID (38/D)
18 | MAIN BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C2 GRID (35/D)
19 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 11 | 2.3 | 0 | 0 | 0 | 2.3 | 25.3 |  |  |  |  | 25.3
C2 GRID (35/D)
20 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (28/D)
21 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C1 GRID (28/D)
22 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (26/D)
23 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C1 GRID (26/D)
24 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C6 GRID (37/E)
25 | DIST. BOTTOM EXTRA BAR |  | 2.715 |  |  | 0.25 | 20 | 1 | 10 | 2.715 | 0 | 0 | 0 | 2.715 | 27.15 |  |  |  |  | 27.15
C6 GRID (37/E)
26 | MAIN BOTTOM EXTRA BAR |  | 3.935 |  |  | 0.25 | 20 | 1 | 17 | 3.935 | 0 | 0 | 0 | 3.935 | 66.895 |  |  |  |  | 66.895
SW4, SW3 GRID (32,33/E)
27 | DIST. BOTTOM EXTRA BAR |  | 4.06 |  |  | 0.25 | 20 | 1 | 17 | 4.06 | 0 | 0 | 0 | 4.06 | 69.02 |  |  |  |  | 69.02
SW4, SW3 GRID (32,33/E)
28 | MAIN BOTTOM EXTRA BAR |  | 1.83 |  |  | 0.25 | 16 | 1 | 14 | 1.83 | 0 | 0 | 0 | 1.83 | 25.62 |  |  |  | 25.62
SW6 GRID (28/E)
29 | DIST. BOTTOM EXTRA BAR |  | 3.185 |  |  | 0.25 | 20 | 1 | 8 | 3.185 | 0 | 0 | 0 | 3.185 | 25.48 |  |  |  |  | 25.48
SW6 GRID ( 28/E)
30 | MAIN BOTTOM EXTRA BAR |  | 2.2 |  |  | 0.25 | 20 | 1 | 12 | 2.2 | 0 | 0 | 0 | 2.2 | 26.4 |  |  |  |  | 26.4
C2 GRID (26/E)
31 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (26/E)
32 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 11 | 2.8 | 0 | 0 | 0 | 2.8 | 30.8 | [5 empty] | 30.8
C2 GRID (25/D-E)
33 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 12 | 2.6 | 0 | 0 | 0 | 2.6 | 31.2 |  |  |  |  | 31.2
C2 GRID (25/D-E)
34 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C8 GRID (23/D-E)
35 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C8 GRID (23/D-E)
36 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/F, J)
37 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/F, J)
38 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 25 | 2.6 | 0 | 0 | 0 | 2.6 | 65 |  |  |  |  | 65
SW9, C1 GRID (43/F, J)
39 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C2 GRID (41/F)
40 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (41/F)
41 | MAIN BOTTOM EXTRA BAR |  | 1.835 |  |  | 0.25 | 20 | 1 | 10 | 1.835 | 0 | 0 | 0 | 1.835 | 18.35 |  |  |  |  | 18.35
C6 GRID (39/F)
42 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 8 | 2.3 | 0 | 0 | 0 | 2.3 | 18.4 |  |  |  |  | 18.4
C6 GRID (39/F)
43 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C5 GRID (37/H)
44 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 14 | 2.8 | 0 | 0 | 0 | 2.8 | 39.2 | [5 empty] | 39.2
C5 GRID (37/H)
45 | MAIN BOTTOM EXTRA BAR |  | 2.73 |  |  | 0.25 | 25 | 1 | 16 | 2.73 | 0 | 0 | 0 | 2.73 | 43.68 | [5 empty] | 43.68
SW5 GRID (34/F)
46 | DIST. BOTTOM EXTRA BAR |  | 3.7 |  |  | 0.25 | 20 | 1 | 12 | 3.7 | 0 | 0 | 0 | 3.7 | 44.4 |  |  |  |  | 44.4
SW5 GRID (34/F)
47 | MAIN BOTTOM EXTRA BAR |  | 2.23 |  |  | 0.25 | 20 | 1 | 16 | 2.23 | 0 | 0 | 0 | 2.23 | 35.68 |  |  |  |  | 35.68
SW5 GRID (29/F)
48 | DIST. BOTTOM EXTRA BAR |  | 3.7 |  |  | 0.25 | 20 | 1 | 10 | 3.7 | 0 | 0 | 0 | 3.7 | 37 |  |  |  |  | 37
SW5 GRID (29/F)
49 | MAIN BOTTOM EXTRA BAR |  | 5.6 |  |  | 0.25 | 20 | 1 | 20 | 5.6 | 0 | 0 | 0 | 5.6 | 112 |  |  |  |  | 112
C1, SW7 GRID (24/E,G,H)
50 | DIST. BOTTOM EXTRA BAR |  | 4.725 |  |  | 0.25 | 25 | 1 | 23 | 4.725 | 0 | 0 | 0 | 4.725 | 108.675 | [5 empty] | 108.675
C1, SW7 GRID (24/E,G,H)
51 | MAIN BOTTOM EXTRA BAR |  | 6.1 |  |  | 0.25 | 25 | 1 | 12 | 6.1 | 0 | 0 | 0 | 6.1 | 73.2 | [5 empty] | 73.2
SW8 GRID (22/G)
52 | DIST. BOTTOM EXTRA BAR |  | 2.73 |  |  | 0.25 | 25 | 1 | 25 | 2.73 | 0 | 0 | 0 | 2.73 | 68.25 | [5 empty] | 68.25
SW8 GRID (22/G)
53 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 25 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 | [5 empty] | 33
C4 GRID (41/J)
54 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (41/J)
55 | DIST. BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 25 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 | [5 empty] | 33
C4 GRID (41/J)
56 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (41/J)
57 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C5 GRID (39/J)
58 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (39/J)
59 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (35/J)
60 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (35/J)
61 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (35/J)
62 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (29/J)
63 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (29/J)
64 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (29/J)
65 | MAIN BOTTOM EXTRA BAR |  | 1.83 |  |  | 0.25 | 16 | 1 | 14 | 1.83 | 0 | 0 | 0 | 1.83 | 25.62 |  |  |  | 25.62
SW6 GRID (28/I)
66 | DIST. BOTTOM EXTRA BAR |  | 3.185 |  |  | 0.25 | 20 | 1 | 8 | 3.185 | 0 | 0 | 0 | 3.185 | 25.48 |  |  |  |  | 25.48
SW6 GRID (28/I)
67 | MAIN BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 12 | 2.6 | 0 | 0 | 0 | 2.6 | 31.2 |  |  |  |  | 31.2
C2 GRID (26/I)
68 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 11 | 2.8 | 0 | 0 | 0 | 2.8 | 30.8 | [5 empty] | 30.8
C2 GRID (26/I)
69 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 11 | 2.8 | 0 | 0 | 0 | 2.8 | 30.8 |  |  |  |  | 30.8
C2 GRID (25/J)
70 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 25 | 1 | 12 | 2.6 | 0 | 0 | 0 | 2.6 | 31.2 | [5 empty] | 31.2
C2 GRID (25/J)
71 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C8 GRID (23/J)
72 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C8 GRID (23/J)
73 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 11 | 2.3 | 0 | 0 | 0 | 2.3 | 25.3 |  |  |  |  | 25.3
C1 GRID (28/J-K)
74 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C1 GRID (28/J-K)
75 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C1 GRID (26/D)
76 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C1 GRID ( 26/D)
77 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 11 | 2.25 | 0 | 0 | 0 | 2.25 | 24.75 | [5 empty] | 24.75
C2 GRID (25/L)
78 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C2 GRID (25/L)
79 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 13 | 2.25 | 0 | 0 | 0 | 2.25 | 29.25 | [5 empty] | 29.25
C3 GRID (23/L)
80 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C3 GRID (23/L)
81 | MAIN BOTTOM EXTRA BAR |  | 3.65 |  |  | 0.25 | 20 | 1 | 17 | 3.65 | 0 | 0 | 0 | 3.65 | 62.05 |  |  |  |  | 62.05
SW12, C7 GRID (27,28/M-N)
82 | DIST. BOTTOM EXTRA BAR |  | 4.345 |  |  | 0.25 | 20 | 1 | 15 | 4.345 | 0 | 0 | 0 | 4.345 | 65.175 |  |  |  |  | 65.175
SW12, C7 GRID (27,28/M-N)
83 | MAIN BOTTOM EXTRA BAR |  | 1.915 |  |  | 0.25 | 12 | 1 | 7 | 1.915 | 0 | 0 | 0 | 1.915 | 13.405 |  |  | 13.405
C6 GRID (43/M)
84 | DIST. BOTTOM EXTRA BAR |  | 1.6 |  |  | 0.25 | 12 | 1 | 9 | 1.6 | 0 | 0 | 0 | 1.6 | 14.4 |  |  | 14.4
C6 GRID (43/M)
85 | MAIN BOTTOM EXTRA BAR |  | 1.915 |  |  | 0.25 | 12 | 1 | 7 | 1.915 | 0 | 0 | 0 | 1.915 | 13.405 |  |  | 13.405
C6 GRID (43/O)
86 | DIST. BOTTOM EXTRA BAR |  | 1.6 |  |  | 0.25 | 12 | 1 | 9 | 1.6 | 0 | 0 | 0 | 1.6 | 14.4 |  |  | 14.4
C6 GRID (43/O)
87 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 25 | 1 | 10 | 2.3 | 0 | 0 | 0 | 2.3 | 23 | [5 empty] | 23
C1 GRID (42/M)
88 | DIST. BOTTOM EXTRA BAR |  | 2.2 |  |  | 0.25 | 16 | 1 | 10 | 2.2 | 0 | 0 | 0 | 2.2 | 22 |  |  |  | 22
C1 GRID (42/M)
89 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 25 | 1 | 10 | 2.3 | 0 | 0 | 0 | 2.3 | 23 | [5 empty] | 23
C1 GRID (42/O)
90 | DIST. BOTTOM EXTRA BAR |  | 2.2 |  |  | 0.25 | 16 | 1 | 10 | 2.2 | 0 | 0 | 0 | 2.2 | 22 |  |  |  | 22
C1 GRID (42/O)
91 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C4 GRID (39/M)
92 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 14 | 2.8 | 0 | 0 | 0 | 2.8 | 39.2 | [5 empty] | 39.2
C4 GRID (39/M)
91 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C4 GRID (39/O)
92 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 14 | 2.8 | 0 | 0 | 0 | 2.8 | 39.2 |  |  |  |  | 39.2
C4 GRID (39/O)
93 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (39/O)
94 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C2 GRID (38/N)
95 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C2 GRID (38/N)
96 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 8 | 2.75 | 0 | 0 | 0 | 2.75 | 22 |  |  |  |  | 22
C5 GRID (37/L)
97 | DIST. BOTTOM EXTRA BAR |  | 1.85 |  |  | 0.25 | 20 | 1 | 12 | 1.85 | 0 | 0 | 0 | 1.85 | 22.2 |  |  |  |  | 22.2
C5 GRID (37/L)
98 | DIST. BOTTOM EXTRA BAR |  | 1.85 |  |  | 0.25 | 20 | 1 | 8 | 1.85 | 0 | 0 | 0 | 1.85 | 14.8 |  |  |  |  | 14.8
C5 GRID (37/L)
99 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C4 GRID (37/O)
100 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C4 GRID (37/O)
101 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 10 | 2.75 | 0 | 0 | 0 | 2.75 | 27.5 |  |  |  |  | 27.5
C5 GRID (32/O)
102 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C5 GRID (32/O)
103 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C5 GRID (32/O)
104 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (29/O)
105 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 20 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 |  |  |  |  | 31
C1 GRID (29/O)
106 | MAIN BOTTOM EXTRA BAR |  | 1.915 |  |  | 0.25 | 12 | 1 | 9 | 1.915 | 0 | 0 | 0 | 1.915 | 17.235 |  |  | 17.235
C6 GRID (27/O)
107 | DIST. BOTTOM EXTRA BAR |  | 2 |  |  | 0.25 | 20 | 1 | 9 | 2 | 0 | 0 | 0 | 2 | 18 |  |  |  |  | 18
C6 GRID (27/O)
108 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/P, Q)
109 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/P, Q)
110 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 25 | 2.6 | 0 | 0 | 0 | 2.6 | 65 |  |  |  |  | 65
SW9, C1 GRID (43/P, Q)
111 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 20 | 1 | 10 | 5.96 | 0 | 0 | 0 | 5.96 | 59.6 |  |  |  |  | 59.6
SW9, C1 GRID (27/P, Q)
112 | DIST. BOTTOM EXTRA BAR |  | 2.35 |  |  | 0.25 | 20 | 1 | 25 | 2.35 | 0 | 0 | 0 | 2.35 | 58.75 |  |  |  |  | 58.75
SW9, C1 GRID (27/P, Q)
113 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C2 GRID (41/Q)
114 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (41/Q)
115 | MAIN BOTTOM EXTRA BAR |  | 2.415 |  |  | 0.25 | 20 | 1 | 10 | 2.415 | 0 | 0 | 0 | 2.415 | 24.15 |  |  |  |  | 24.15
C6 GRID (39/Q)
116 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 8 | 2.3 | 0 | 0 | 0 | 2.3 | 18.4 |  |  |  |  | 18.4
C6 GRID (39/Q)
117 | MAIN BOTTOM EXTRA BAR |  | 2.415 |  |  | 0.25 | 20 | 1 | 10 | 2.415 | 0 | 0 | 0 | 2.415 | 24.15 |  |  |  |  | 24.15
C6 GRID (34/Q)
118 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 8 | 2.3 | 0 | 0 | 0 | 2.3 | 18.4 |  |  |  |  | 18.4
C6 GRID (34/Q)
119 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C2 GRID (30/Q)
120 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (30/Q)
121 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C5 GRID (37/P-Q)
122 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (37/P-Q)
123 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 25 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 | [5 empty] | 33
C4 GRID (41/P)
124 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (41/P)
125 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (41/P)
126 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (41/P)
127 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C5 GRID (39/P)
128 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (39/P)
129 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (30/P)
130 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (30/P)
131 | DIST. BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (30/P)
132 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C5 GRID (34/P)
133 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (34/P)
134 | MAIN BOTTOM EXTRA BAR |  | 5.145 |  |  | 0.25 | 20 | 1 | 26 | 5.145 | 0 | 0 | 0 | 5.145 | 133.77 |  |  |  |  | 133.77
SW10, SW11, SW13 GRID (31-36/K-N)
135 | DIST. BOTTOM EXTRA BAR |  | 6.165 |  |  | 0.25 | 20 | 1 | 22 | 6.165 | 0 | 0 | 0 | 6.165 | 135.63 |  |  |  |  | 135.63
SW10, SW11, SW13 GRID (31-36/K-N)
136 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (29/J)
137 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (25/J)
138 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (41/J)
139 | SPACER B/W EXTRA BAR |  | 2.8 |  |  |  | 20 | 1 | 3 | 2.8 | 0 | 0 | 0 | 2.8 | 8.4 |  |  |  |  | 8.4
C4 GRID (41/J)
140 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C5 GRID (37/L)
141 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C5 GRID (32/O)
142 | SPACER B/W EXTRA BAR |  | 3.25 |  |  |  | 20 | 1 | 3 | 3.25 | 0 | 0 | 0 | 3.25 | 9.75 |  |  |  |  | 9.75
C4 GRID (40/O)
143 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (29/P)
144 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (41/P)
145 | SPACER B/W EXTRA BAR |  | 2.8 |  |  |  | 20 | 1 | 3 | 2.8 | 0 | 0 | 0 | 2.8 | 8.4 |  |  |  |  | 8.4
C4 GRID (41/P)
146 | SPACER B/W EXTRA BAR |  | 6.165 |  |  |  | 20 | 1 | 4 | 6.165 | 0 | 0 | 0 | 6.165 | 24.66 |  |  |  |  | 24.66
SW10, SW11, SW13 GRID (31-36/K-N)
TOP EXTRA BAR
1 | MAIN TOP EXTRA BAR |  | 2.425 |  |  | 0.25 | 20 | 1 | 23 | 2.425 | 0 | 0 | 0 | 2.425 | 55.775 |  |  |  |  | 55.775
GRID (35-37/A-D)
2 | DIST. TOP EXTRA BAR |  | 3.95 |  |  | 0.25 | 16 | 1 | 11 | 3.95 | 0 | 0 | 0 | 3.95 | 43.45 |  |  |  | 43.45
GRID (35-37/A-D)
3 | MAIN TOP EXTRA BAR |  | 2.2 |  |  | 0.25 | 10 | 1 | 31 | 2.2 | 0 | 0 | 0 | 2.2 | 68.2 |  | 68.2
GRID (32-35/A-D)
4 | DIST. TOP EXTRA BAR |  | 6.165 |  |  | 0.25 | 16 | 1 | 10 | 6.165 | 0 | 0 | 0 | 6.165 | 61.65 |  |  |  | 61.65
GRID (32-35/A-D)
5 | MAIN TOP EXTRA BAR |  | 4.52 |  |  | 0.25 | 12 | 1 | 13 | 4.52 | 0 | 0 | 0 | 4.52 | 58.76 |  |  | 58.76
GRID (28-31/B-E)
6 | MAIN TOP EXTRA BAR |  | 2.275 |  |  | 0.25 | 10 | 1 | 22 | 2.275 | 0 | 0 | 0 | 2.275 | 50.05 |  | 50.05
GRID (26-28/B-E)
7 | DIST. TOP EXTRA BAR |  | 5.355 |  |  | 0.25 | 12 | 1 | 10 | 5.355 | 0 | 0 | 0 | 5.355 | 53.55 |  |  | 53.55
GRID (26-28/B-E)
8 | MAIN TOP EXTRA BAR |  | 2.45 |  |  | 0.25 | 12 | 1 | 10 | 2.45 | 0 | 0 | 0 | 2.45 | 24.5 |  |  | 24.5
GRID (25-26/B-E)
9 | MAIN TOP EXTRA BAR |  | 4.09 |  |  | 0.25 | 12 | 1 | 24 | 4.09 | 0 | 0 | 0 | 4.09 | 98.16 |  |  | 98.16
GRID (24-26/B-E)
10 | DIST. TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 10 | 1 | 17 | 3.8 | 0 | 0 | 0 | 3.8 | 64.6 |  | 64.6
GRID (24-26/B-E)
11 | MAIN TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 10 | 1 | 24 | 3.8 | 0 | 0 | 0 | 3.8 | 91.2 |  | 91.2
GRID (21-23 /B-E)
12 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 20 | 1 | 24 | 5.7 | 0 | 0 | 0 | 5.7 | 136.8 |  |  |  |  | 136.8
GRID (21-23 /B-E)
13 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 16 | 1 | 10 | 5.7 | 0 | 0 | 0 | 5.7 | 57 |  |  |  | 57
GRID (21-23 /B-E)
14 | MAIN TOP EXTRA BAR |  | 2.515 |  |  | 0.25 | 12 | 1 | 17 | 2.515 | 0 | 0 | 0 | 2.515 | 42.755 |  |  | 42.755
GRID (34-36 /D-F)
15 | MAIN TOP EXTRA BAR |  | 4.19 |  |  | 0.25 | 12 | 1 | 11 | 4.19 | 0 | 0 | 0 | 4.19 | 46.09 |  |  | 46.09
GRID (41-43 /E-I)
16 | MAIN TOP EXTRA BAR |  | 7.71 |  |  | 0.25 | 12 | 1 | 12 | 7.71 | 0 | 0 | 0 | 7.71 | 92.52 |  |  | 92.52
GRID (40-42 /E-K)
17 | MAIN TOP EXTRA BAR |  | 2.785 |  |  | 0.25 | 12 | 1 | 11 | 2.785 | 0 | 0 | 0 | 2.785 | 30.635 |  |  | 30.635
GRID (41-42 /E-I)
18 | DIST. TOP EXTRA BAR |  | 2.615 |  |  | 0.25 | 20 | 1 | 12 | 2.615 | 0 | 0 | 0 | 2.615 | 31.38 |  |  |  |  | 31.38
GRID (41-42 /E-I)
19 | MAIN TOP EXTRA BAR |  | 4.12 |  |  | 0.25 | 20 | 1 | 34 | 4.12 | 0 | 0 | 0 | 4.12 | 140.08 |  |  |  |  | 140.08
GRID (41-42 /E-L)
20 | DIST. TOP EXTRA BAR |  | 3.12 |  |  | 0.25 | 20 | 1 | 14 | 3.12 | 0 | 0 | 0 | 3.12 | 43.68 |  |  |  |  | 43.68
GRID (40-42 /J-L)
21 | DIST. TOP EXTRA BAR |  | 2.92 |  |  | 0.25 | 16 | 1 | 23 | 2.92 | 0 | 0 | 0 | 2.92 | 67.16 |  |  |  | 67.16
GRID (40-42 /J-L)
22 | MAIN TOP EXTRA BAR |  | 4.545 |  |  | 0.25 | 16 | 1 | 21 | 4.545 | 0 | 0 | 0 | 4.545 | 95.445 |  |  |  | 95.445
GRID (34-38 /H-K)
23 | DIST. TOP EXTRA BAR |  | 5 |  |  | 0.25 | 16 | 1 | 19 | 5 | 0 | 0 | 0 | 5 | 95 |  |  |  | 95
GRID (34-38 /H-K)
24 | MAIN TOP EXTRA BAR |  | 5.24 |  |  | 0.25 | 16 | 1 | 21 | 5.24 | 0 | 0 | 0 | 5.24 | 110.04 |  |  |  | 110.04
GRID (28-33 /H-K)
25 | DIST. TOP EXTRA BAR |  | 2.54 |  |  | 0.25 | 12 | 1 | 18 | 2.54 | 0 | 0 | 0 | 2.54 | 45.72 |  |  | 45.72
GRID (25-28 /E-I)
26 | DIST. TOP EXTRA BAR |  | 4.375 |  |  | 0.25 | 10 | 1 | 12 | 4.375 | 0 | 0 | 0 | 4.375 | 52.5 |  | 52.5
GRID (25-28 /I-K)
27 | DIST. TOP EXTRA BAR |  | 3.64 |  |  | 0.25 | 10 | 1 | 64 | 3.64 | 0 | 0 | 0 | 3.64 | 232.96 |  | 232.96
GRID (24-25 /B-M)
28 | DIST. TOP EXTRA BAR |  | 2.45 |  |  | 0.25 | 10 | 1 | 10 | 2.45 | 0 | 0 | 0 | 2.45 | 24.5 |  | 24.5
GRID (24-25 /J-K)
29 | DIST. TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 10 | 1 | 17 | 3.8 | 0 | 0 | 0 | 3.8 | 64.6 |  | 64.6
GRID (22-24 /J-M)
30 | MAIN TOP EXTRA BAR |  | 6.4 |  |  | 0.25 | 10 | 1 | 23 | 6.4 | 0 | 0 | 0 | 6.4 | 147.2 |  | 147.2
GRID (22-24 /E-J)
31 | DIST. TOP EXTRA BAR |  | 5.53 |  |  | 0.25 | 16 | 1 | 27 | 5.53 | 0 | 0 | 0 | 5.53 | 149.31 |  |  |  | 149.31
GRID (22-24 /E-J)
32 | MAIN TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 12 | 1 | 24 | 3.8 | 0 | 0 | 0 | 3.8 | 91.2 |  |  | 91.2
GRID (21-23 /I-M)
33 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 20 | 1 | 24 | 5.7 | 0 | 0 | 0 | 5.7 | 136.8 |  |  |  |  | 136.8
GRID (21-23 /I-M)
34 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 16 | 1 | 10 | 5.7 | 0 | 0 | 0 | 5.7 | 57 |  |  |  | 57
GRID (21-23 /I-M)
35 | MAIN TOP EXTRA BAR |  | 5.745 |  |  | 0.25 | 16 | 1 | 15 | 5.745 | 0 | 0 | 0 | 5.745 | 86.175 |  |  |  | 86.175
GRID (40-43/M-O)
36 | DIST. TOP EXTRA BAR |  | 2.5 |  |  | 0.25 | 20 | 1 | 14 | 2.5 | 0 | 0 | 0 | 2.5 | 35 |  |  |  |  | 35
GRID (40-43 /M-O)
37 | DIST. TOP EXTRA BAR |  | 3.46 |  |  | 0.25 | 20 | 1 | 24 | 3.46 | 0 | 0 | 0 | 3.46 | 83.04 |  |  |  |  | 83.04
GRID (40-43 /M-O)
38 | MAIN TOP EXTRA BAR |  | 3.045 |  |  | 0.25 | 20 | 1 | 19 | 3.045 | 0 | 0 | 0 | 3.045 | 57.855 |  |  |  |  | 57.855
GRID (37-40 /K-N)
39 | DIST. TOP EXTRA BAR |  | 4.525 |  |  | 0.25 | 16 | 1 | 13 | 4.525 | 0 | 0 | 0 | 4.525 | 58.825 |  |  |  | 58.825
GRID (37-40 /K-N)
40 | MAIN TOP EXTRA BAR |  | 3.12 |  |  | 0.25 | 20 | 1 | 14 | 3.12 | 0 | 0 | 0 | 3.12 | 43.68 |  |  |  |  | 43.68
GRID (40-43 /O-Q)
41 | MAIN TOP EXTRA BAR |  | 2.85 |  |  | 0.25 | 16 | 1 | 23 | 2.85 | 0 | 0 | 0 | 2.85 | 65.55 |  |  |  | 65.55
GRID (40-43 /O-Q)
42 | DIST. TOP EXTRA BAR |  | 4.12 |  |  | 0.25 | 20 | 1 | 34 | 4.12 | 0 | 0 | 0 | 4.12 | 140.08 |  |  |  |  | 140.08
GRID (40-43 /O-Q)
43 | DIST. TOP EXTRA BAR |  | 4.19 |  |  | 0.25 | 12 | 1 | 11 | 4.19 | 0 | 0 | 0 | 4.19 | 46.09 |  |  | 46.09
GRID (40-43 /O-Q)
44 | DIST. TOP EXTRA BAR |  | 7.68 |  |  | 0.25 | 12 | 1 | 12 | 7.68 | 0 | 0 | 0 | 7.68 | 92.16 |  |  | 92.16
GRID (40-43 /O-Q)
45 | DIST. TOP EXTRA BAR |  | 3.915 |  |  | 0.25 | 20 | 1 | 19 | 3.915 | 0 | 0 | 0 | 3.915 | 74.385 |  |  |  |  | 74.385
GRID (36-39 /N-P)
46 | DIST. TOP EXTRA BAR |  | 4.5 |  |  | 0.25 | 16 | 1 | 17 | 4.5 | 0 | 0 | 0 | 4.5 | 76.5 |  |  |  | 76.5
GRID (36-39 /N-P)
47 | DIST. TOP EXTRA BAR |  | 4.55 |  |  | 0.25 | 10 | 1 | 19 | 4.55 | 0 | 0 | 0 | 4.55 | 86.45 |  | 86.45
GRID (31-36 /O-P)
48 | MAIN TOP EXTRA BAR |  | 3.975 |  |  | 0.25 | 25 | 1 | 25 | 3.975 | 0 | 0 | 0 | 3.975 | 99.375 | [5 empty] | 99.375
GRID (33-38 /O'-P')
49 | DIST. TOP EXTRA BAR |  | 6.08 |  |  | 0.25 | 16 | 1 | 17 | 6.08 | 0 | 0 | 0 | 6.08 | 103.36 |  |  |  | 103.36
GRID (33-38 /O'-P')
50 | MAIN TOP EXTRA BAR |  | 1.95 |  |  | 0.25 | 12 | 1 | 25 | 1.95 | 0 | 0 | 0 | 1.95 | 48.75 |  |  | 48.75
GRID (33-38 /P'-Q)
51 | DIST. TOP EXTRA BAR |  | 6.08 |  |  | 0.25 | 12 | 1 | 9 | 6.08 | 0 | 0 | 0 | 6.08 | 54.72 |  |  | 54.72
GRID (33-38 /P'-Q)
52 | DIST. TOP EXTRA BAR |  | 7.71 |  |  | 0.25 | 12 | 1 | 12 | 7.71 | 0 | 0 | 0 | 7.71 | 92.52 |  |  | 92.52
GRID (29-32 /O-Q)
53 | MAIN TOP EXTRA BAR |  | 2.85 |  |  | 0.25 | 10 | 1 | 17 | 2.85 | 0 | 0 | 0 | 2.85 | 48.45 |  | 48.45
GRID (26-29 /O-Q)
54 | DIST. TOP EXTRA BAR |  | 5.47 |  |  | 0.25 | 20 | 1 | 34 | 5.47 | 0 | 0 | 0 | 5.47 | 185.98 |  |  |  |  | 185.98
GRID (26-29 /O-Q)
55 | DIST. TOP EXTRA BAR |  | 4.19 |  |  | 0.25 | 16 | 1 | 11 | 4.19 | 0 | 0 | 0 | 4.19 | 46.09 |  |  |  | 46.09
GRID (26-29 /O-Q)
| TOTAL LENGTH IN METRE | [14 empty] | 0 | 930.71 | 1299.355 | 16897.553 | 6380.625 | 2199.06
| UNIT WEIGHT (IN KG) | [14 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.469 | 3.858
| TOTAL WEIGHT (IN KG) | [14 empty] | 0 | 574.2481 | 1153.8272 | 26698.1337 | 15753.7631 | 8483.9735 | 52663.9457 | KG
COMPENSATORY STRIP (22-23/B'-L')
A | RAFT | [14 empty] | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm
1 | GRID (22-23/B'-L')
| MAIN BAR BOTTOM (ALTH.) |  | 0.9 |  |  | 0.25 | 16 | 1 | 26 | 0.9 | 0 | 2 | 0.064 | 0.836 | 21.736 |  |  |  | 21.736
2 | GRID (22-23/B'-L')
| MAIN BAR BOTTOM (ALTH.) |  | 0.9 |  |  | 0.25 | 16 | 1 | 26 | 0.9 | 0.784 | 2 | 0.064 | 0.836 | 22.52 |  |  |  | 22.52
1 | GRID (22-23/B'-L')
| MAIN BAR TOP (ALTH.) |  | 0.9 |  |  | 0.25 | 16 | 1 | 26 | 0.9 | 0 | 2 | 0.064 | 0.836 | 21.736 |  |  |  | 21.736
2 | GRID (22-23/B'-L')
| MAIN BAR TOP (ALTH.) |  | 0.9 |  |  | 0.25 | 16 | 1 | 26 | 0.9 | 0.784 | 2 | 0.064 | 0.836 | 22.52 |  |  |  | 22.52
| TOTAL LENGTH IN METRE | [14 empty] | 0 | 0 | 0 | 88.512 | 0 | 0
| UNIT WEIGHT (IN KG) | [14 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.469 | 3.858
| TOTAL WEIGHT (IN KG) | [14 empty] | 0 | 0 | 0 | 139.849 | 0 | 0 | 139.849 | KG
COLUMN CLIT FIXING (22-23/B'-L')
A | COLUMN CLIT FIXING | [14 empty] | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm
1 | GRID (22-23/B'-L')
| MAIN BAR BOTTOM (ALTH.) |  | 0.04 |  |  |  | 8 | 143 | 8 | 0.04 | 0 |  | 0 | 0.04 | 45.76 | 45.76
| TOTAL LENGTH IN METRE | [14 empty] | 45.76 | 0 | 0 | 0 | 0 | 0
| UNIT WEIGHT (IN KG) | [14 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.469 | 3.858
| TOTAL WEIGHT (IN KG) | [14 empty] | 18.0752 | 0 | 0 | 0 | 0 | 0 | 18.0752 | KG

## COL BBS
TOWER-E COLUMN FOUNDATION BBS (BELOW PLINTH BEAM)
S.No. | Description | Shape of Bar in mm |  |  | Spacing c/c | Dia of Bar | Nos of Columns | Nos of Bar | Actual Length | Lap | No. Of Bend | Deduction | Cut Length | Total Length | TMT BAR Fe-500D or EQR | [5 empty] | Remarks
[15 empty] | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm
1 | Column C1 (300x600)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 16 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 64.704 |  |  |  | 64.704
| VERTICAL BARS B |  |  |  |  | 12 | 16 | 2 | 0.743 | 0 | 1 | 0.024 | 1.019 | 32.608 |  |  | 32.608
| VERTICAL BARS C |  |  | 0.3 |  | 16 | 16 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 64.704 |  |  |  | 64.704
| VERTICAL BARS D |  |  |  |  | 12 | 16 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 65.216 |  |  | 65.216
0.08
| Stirupps a |  |  | 0.52 |  | 10 | 16 | 4 | 1.64 |  | 5 | 0.1 | 1.56 | 99.84 |  | 99.84
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 16 | 1 | 0.8656 |  | 5 | 0.1 | 0.7856 | 12.5696 |  | 12.5696
0.22
| Stirupps c |  |  |  |  | 10 | 16 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 10.4 |  | 10.4
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 16 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 10.4 |  | 10.4
|  | 0.175 |  | 0.175
0.22
2 | Column C2 (300x600)
| VERTICAL BARS A |  | 0.743 |  |  | 20 | 11 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 44.132 |  |  |  |  | 44.132
| VERTICAL BARS B |  |  |  |  | 20 | 11 | 2 | 0.743 | 0 | 1 | 0.04 | 1.003 | 22.066 |  |  |  |  | 22.066
| VERTICAL BARS C |  |  | 0.3 |  | 16 | 11 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 44.484 |  |  |  | 44.484
| VERTICAL BARS D |  |  |  |  | 16 | 11 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 44.484 |  |  |  | 44.484
0.08
| Stirupps a |  |  | 0.52 |  | 10 | 11 | 4 | 1.64 |  | 5 | 0.1 | 1.54 | 67.76 |  | 67.76
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 11 | 1 | 0.8656 |  | 5 | 0.1 | 0.7656 | 8.4216 |  | 8.4216
0.22
| Stirupps c |  |  |  |  | 10 | 11 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 7.15 |  | 7.15
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 11 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 7.15 |  | 7.15
|  | 0.175 |  | 0.175
0.22
3 | Column C3 (300x600)
| VERTICAL BARS A |  | 0.743 |  |  | 25 | 2 | 4 | 0.743 | 0 | 1 | 0.05 | 0.993 | 7.944 | [5 empty] | 7.944
| VERTICAL BARS B |  |  |  |  | 25 | 2 | 2 | 0.743 | 0 | 1 | 0.05 | 0.993 | 3.972 | [5 empty] | 3.972
| VERTICAL BARS C |  |  | 0.3 |  | 25 | 2 | 4 | 0.743 | 0 | 1 | 0.05 | 0.993 | 7.944 | [5 empty] | 7.944
| VERTICAL BARS D |  |  |  |  | 20 | 2 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 8.024 |  |  |  |  | 8.024
0.08
| Stirupps a |  |  | 0.52 |  | 10 | 2 | 4 | 1.64 |  | 5 | 0.1 | 1.54 | 12.32 |  | 12.32
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 2 | 1 | 0.8656 |  | 5 | 0.1 | 0.7656 | 1.5312 |  | 1.5312
0.22
| Stirupps c |  |  |  |  | 10 | 2 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 1.3 |  | 1.3
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 2 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 1.3 |  | 1.3
|  | 0.175 |  | 0.175
0.22
4 | Column C4 (300x750)
| VERTICAL BARS A |  | 0.743 |  |  | 20 | 8 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 32.096 |  |  |  |  | 32.096
| VERTICAL BARS B |  |  |  |  | 20 | 8 | 2 | 0.743 | 0 | 1 | 0.04 | 1.003 | 16.048 |  |  |  |  | 16.048
| VERTICAL BARS C |  |  | 0.3 |  | 20 | 8 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 32.096 |  |  |  |  | 32.096
| VERTICAL BARS D |  |  |  |  | 20 | 8 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 32.096 |  |  |  |  | 32.096
| VERTICAL BARS E |  |  |  |  | 20 | 8 | 2 | 0.743 | 0 | 1 | 0.04 | 1.003 | 16.048 |  |  |  |  | 16.048
0.08
| Stirupps a |  |  | 0.67 |  | 10 | 8 | 4 | 1.94 |  | 5 | 0.1 | 1.84 | 58.88 |  | 58.88
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 10 | 8 | 1 | 1.1 |  | 5 | 0.1 | 1 | 8 |  | 8
0.22
| Stirupps c |  |  |  |  | 10 | 8 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 5.2 |  | 5.2
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 8 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 5.2 |  | 5.2
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 8 | 1 | 0.38 |  | 2 | 0.04 | 0.34 | 2.72 |  | 2.72
0.08
5 | Column C5 (300x750)
| VERTICAL BARS A |  | 0.743 |  |  | 20 | 7 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 28.084 |  |  |  |  | 28.084
| VERTICAL BARS B |  |  |  |  | 16 | 7 | 2 | 0.743 | 0 | 1 | 0.032 | 1.011 | 14.154 |  |  |  | 14.154
| VERTICAL BARS C |  |  | 0.3 |  | 16 | 7 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 28.308 |  |  |  | 28.308
| VERTICAL BARS D |  |  |  |  | 16 | 7 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 28.308 |  |  |  | 28.308
| VERTICAL BARS E |  |  |  |  | 16 | 7 | 2 | 0.743 | 0 | 1 | 0.032 | 1.011 | 14.154 |  |  |  | 14.154
0.08
| Stirupps a |  |  | 0.67 |  | 10 | 7 | 4 | 1.94 |  | 5 | 0.1 | 1.84 | 51.52 |  | 51.52
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 10 | 7 | 1 | 1.1 |  | 5 | 0.1 | 1 | 7 |  | 7
0.22
| Stirupps c |  |  |  |  | 10 | 7 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 4.55 |  | 4.55
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 7 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 4.55 |  | 4.55
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 7 | 1 | 0.38 |  | 2 | 0.04 | 0.34 | 2.38 |  | 2.38
0.08
6 | Column C6 (300x715)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 7 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 28.308 |  |  |  | 28.308
| VERTICAL BARS B |  |  |  |  | 12 | 7 | 2 | 0.743 | 0 | 1 | 0.024 | 1.019 | 14.266 |  |  | 14.266
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 7 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 28.532 |  |  | 28.532
| VERTICAL BARS D |  |  |  |  | 12 | 7 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 28.532 |  |  | 28.532
| VERTICAL BARS E |  |  |  |  | 12 | 7 | 2 | 0.743 | 0 | 1 | 0.024 | 1.019 | 14.266 |  |  | 14.266
0.08
| Stirupps a |  |  | 0.635 |  | 10 | 7 | 4 | 1.87 |  | 5 | 0.1 | 1.77 | 49.56 |  | 49.56
0.22
0.08
| Stirupps b |  |  | 0.23833 |  | 10 | 7 | 1 | 1.0767 |  | 5 | 0.1 | 0.97667 | 6.8367 |  | 6.8367
0.22
| Stirupps c |  |  |  |  | 10 | 7 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 4.55 |  | 4.55
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 7 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 4.55 |  | 4.55
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 7 | 1 | 0.38 |  | 2 | 0.04 | 0.34 | 2.38 |  | 2.38
0.08
7 | Column C7 (300x800)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 2 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 2 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 2 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
0.08
| Stirupps a |  |  | 0.72 |  | 10 | 2 | 4 | 2.04 |  | 5 | 0.1 | 1.94 | 15.52 |  | 15.52
0.22
0.08
| Stirupps b |  |  | 0.13257 |  | 10 | 2 | 1 | 0.86514 |  | 5 | 0.1 | 0.76514 | 1.5303 |  | 1.5303
0.22
0.08
| Stirupps c |  |  | 0.13257 |  | 10 | 2 | 1 | 0.86514 |  | 5 | 0.1 | 0.76514 | 1.5303 |  | 1.5303
0.22
| Stirupps d |  |  |  |  | 10 | 2 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 1.3 |  | 1.3
|  | 0.175 |  | 0.175
0.22
| Stirupps e |  |  |  |  | 10 | 2 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 1.3 |  | 1.3
|  | 0.175 |  | 0.175
0.22
8 | Column C8 (300x600)
| VERTICAL BARS A |  | 0.743 |  |  | 20 | 2 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 8.024 |  |  |  |  | 8.024
| VERTICAL BARS B |  |  |  |  | 20 | 2 | 2 | 0.743 | 0 | 1 | 0.04 | 1.003 | 4.012 |  |  |  |  | 4.012
| VERTICAL BARS C |  |  | 0.3 |  | 20 | 2 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 8.024 |  |  |  |  | 8.024
| VERTICAL BARS D |  |  |  |  | 20 | 2 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 8.024 |  |  |  |  | 8.024
0.08
| Stirupps a |  |  | 0.52 |  | 10 | 2 | 4 | 1.64 |  | 5 | 0.1 | 1.54 | 12.32 |  | 12.32
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 2 | 1 | 0.8656 |  | 5 | 0.1 | 0.7656 | 1.5312 |  | 1.5312
0.22
| Stirupps c |  |  |  |  | 10 | 2 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 1.3 |  | 1.3
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 2 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 1.3 |  | 1.3
|  | 0.175 |  | 0.175
0.22
9 | SW1 (230x650/1650)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 12 | 1 | 16 | 0.743 | 0 | 1 | 0.024 | 1.019 | 16.304 |  |  | 16.304
| VERTICAL BARS C |  |  | 0.3 |  | 10 | 1 | 8 | 0.743 | 0 | 1 | 0.02 | 1.023 | 8.184 |  | 8.184
0.08
| Stirupps a |  |  | 0.6 |  | 10 | 1 | 4 | 1.72 |  | 5 | 0.1 | 1.62 | 6.48 |  | 6.48
0.18
0.08
| Stirupps b |  |  | 1.6 |  | 10 | 1 | 4 | 3.72 |  | 5 | 0.1 | 3.62 | 14.48 |  | 14.48
0.18
0.08
| Stirupps c |  |  | 0.2656 |  | 10 | 1 | 1 | 1.0512 |  | 5 | 0.1 | 0.9512 | 0.9512 |  | 0.9512
0.18
0.08
| Stirupps d |  |  | 0.46655 |  | 10 | 1 | 1 | 1.4531 |  | 5 | 0.1 | 1.3531 | 1.3531 |  | 1.3531
0.18
0.08
| Stirupps e |  |  | 0.75091 |  | 10 | 1 | 1 | 2.0218 |  | 5 | 0.1 | 1.9218 | 1.9218 |  | 1.9218
0.18
0.08
| Stirupps f |  |  | 0.17618 |  | 10 | 1 | 1 | 0.87236 |  | 5 | 0.1 | 0.77236 | 0.77236 |  | 0.77236
0.18
0.08
| Stirupps g |  | 0.18 |  |  | 10 | 1 | 4 | 0.34 |  | 2 | 0.04 | 0.3 | 1.2 |  | 1.2
0.08
10 | SW2 (230x650/1850)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 12 | 1 | 16 | 0.743 | 0 | 1 | 0.024 | 1.019 | 16.304 |  |  | 16.304
| VERTICAL BARS C |  |  | 0.3 |  | 10 | 1 | 10 | 0.743 | 0 | 1 | 0.02 | 1.023 | 10.23 |  | 10.23
0.08
| Stirupps a |  |  | 0.6 |  | 10 | 1 | 4 | 1.72 |  | 5 | 0.1 | 1.62 | 6.48 |  | 6.48
0.18
0.08
| Stirupps b |  |  | 1.8 |  | 10 | 1 | 4 | 4.12 |  | 5 | 0.1 | 4.02 | 16.08 |  | 16.08
0.18
0.08
| Stirupps c |  |  | 0.2656 |  | 10 | 1 | 1 | 1.0512 |  | 5 | 0.1 | 0.9512 | 0.9512 |  | 0.9512
0.18
0.08
| Stirupps d |  |  | 0.468 |  | 10 | 1 | 1 | 1.456 |  | 5 | 0.1 | 1.356 | 1.356 |  | 1.356
0.18
0.08
| Stirupps e |  |  | 0.75333 |  | 10 | 1 | 1 | 2.0267 |  | 5 | 0.1 | 1.9267 | 1.9267 |  | 1.9267
0.18
0.08
| Stirupps f |  |  | 0.17667 |  | 10 | 1 | 1 | 0.87333 |  | 5 | 0.1 | 0.77333 | 0.77333 |  | 0.77333
0.18
0.08
| Stirupps g |  | 0.18 |  |  | 10 | 1 | 4 | 0.34 |  | 2 | 0.04 | 0.3 | 1.2 |  | 1.2
0.08
11 | SW3 (230x1000)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS B |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS D |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS E |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
0.08
| Stirupps a |  |  | 0.95 |  | 10 | 1 | 4 | 2.42 |  | 5 | 0.1 | 2.32 | 9.28 |  | 9.28
0.18
0.08
| Stirupps b |  |  | 0.13578 |  | 10 | 1 | 4 | 0.79156 |  | 5 | 0.1 | 0.69156 | 2.7662 |  | 2.7662
0.18
12 | SW4 (230x1150)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS B |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS D |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS E |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS F |  |  |  |  | 12 | 1 | 2 | 0.743 | 0 | 1 | 0.024 | 1.019 | 2.038 |  |  | 2.038
0.08
| Stirupps a |  |  | 1.1 |  | 10 | 1 | 4 | 2.72 |  | 5 | 0.1 | 2.62 | 10.48 |  | 10.48
0.18
0.08
| Stirupps b |  |  | 0.1404 |  | 10 | 1 | 4 | 0.8008 |  | 5 | 0.1 | 0.7008 | 2.8032 |  | 2.8032
0.18
0.08
| Stirupps c |  | 0.18 |  |  | 10 | 1 | 1 | 0.34 |  | 2 | 0.04 | 0.3 | 0.3 |  | 0.3
0.08
13 | SW5 (230x1700)
| VERTICAL BARS A |  | 0.743 |  |  | 20 | 2 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 8.024 |  |  |  |  | 8.024
| VERTICAL BARS B |  |  |  |  | 20 | 2 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 8.024 |  |  |  |  | 8.024
| VERTICAL BARS C |  |  | 0.3 |  | 20 | 2 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 8.024 |  |  |  |  | 8.024
| VERTICAL BARS D |  |  |  |  | 16 | 2 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS E |  |  |  |  | 16 | 2 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS F |  |  |  |  | 16 | 2 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 16.176 |  |  |  | 16.176
| VERTICAL BARS G |  |  |  |  | 16 | 2 | 6 | 0.743 | 0 | 1 | 0.032 | 1.011 | 12.132 |  |  |  | 12.132
0.08
| Stirupps a |  |  | 1.65 |  | 10 | 2 | 4 | 3.82 |  | 5 | 0.1 | 3.72 | 29.76 |  | 29.76
0.18
0.08
| Stirupps b |  |  | 0.13787 |  | 10 | 2 | 6 | 0.79575 |  | 5 | 0.1 | 0.69575 | 8.349 |  | 8.349
0.18
0.08
| Stirupps c |  |  | 0.23975 |  | 10 | 2 | 6 | 0.9995 |  | 5 | 0.1 | 0.8995 | 10.794 |  | 10.794
0.18
0.08
| Stirupps d |  | 0.18 |  |  | 10 | 2 | 1 | 0.34 |  | 2 | 0.04 | 0.3 | 0.6 |  | 0.6
0.08
14 | SW6 (230x1185)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 2 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 16 | 2 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS C |  |  | 0.3 |  | 16 | 2 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS F |  |  |  |  | 12 | 2 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
0.08
| Stirupps a |  |  | 1.135 |  | 10 | 2 | 4 | 2.79 |  | 5 | 0.1 | 2.69 | 21.52 |  | 21.52
0.18
0.08
| Stirupps b |  |  | 0.13773 |  | 10 | 2 | 5 | 0.79545 |  | 5 | 0.1 | 0.69545 | 6.9545 |  | 6.9545
0.18
15 | SW7 (230x1855)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS B |  |  |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS C |  |  | 0.3 |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS D |  |  |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS E |  |  |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS F |  |  |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS G |  |  |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS H |  |  |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
0.08
| Stirupps a |  |  | 1.805 |  | 10 | 1 | 4 | 4.13 |  | 5 | 0.1 | 4.03 | 16.12 |  | 16.12
0.18
0.08
| Stirupps b |  |  | 0.14124 |  | 10 | 1 | 8 | 0.80247 |  | 5 | 0.1 | 0.70247 | 5.6198 |  | 5.6198
0.18
16 | SW9 (230x650/1850)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 3 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 24.264 |  |  |  | 24.264
| VERTICAL BARS B |  |  |  |  | 16 | 3 | 16 | 0.743 | 0 | 1 | 0.032 | 1.011 | 48.528 |  |  |  | 48.528
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 3 | 10 | 0.743 | 0 | 1 | 0.024 | 1.019 | 30.57 |  |  | 30.57
0.08
| Stirupps a |  |  | 0.6 |  | 10 | 3 | 4 | 1.72 |  | 5 | 0.1 | 1.62 | 19.44 |  | 19.44
0.18
0.08
| Stirupps b |  |  | 1.8 |  | 10 | 3 | 4 | 4.12 |  | 5 | 0.1 | 4.02 | 48.24 |  | 48.24
0.18
0.08
| Stirupps c |  |  | 0.2456 |  | 10 | 3 | 1 | 1.0112 |  | 5 | 0.1 | 0.9112 | 2.7336 |  | 2.7336
0.18
0.08
| Stirupps d |  |  | 0.468 |  | 10 | 3 | 1 | 1.456 |  | 5 | 0.1 | 1.356 | 4.068 |  | 4.068
0.18
0.08
| Stirupps e |  |  | 0.75333 |  | 10 | 3 | 1 | 2.0267 |  | 5 | 0.1 | 1.9267 | 5.78 |  | 5.78
0.18
0.08
| Stirupps f |  |  | 0.17667 |  | 10 | 3 | 1 | 0.87333 |  | 5 | 0.1 | 0.77333 | 2.32 |  | 2.32
0.18
0.08
| Stirupps g |  | 0.18 |  |  | 10 | 3 | 4 | 0.34 |  | 2 | 0.04 | 0.3 | 3.6 |  | 3.6
0.08
17 | SW10 (230x3445)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 1 | 8 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS D |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS E |  |  |  |  | 12 | 1 | 20 | 0.743 | 0 | 1 | 0.024 | 1.019 | 20.38 |  |  | 20.38
0.08
| Stirupps a |  |  | 0.91748 |  | 10 | 1 | 8 | 2.355 |  | 5 | 0.1 | 2.255 | 18.0397 |  | 18.0397
0.18
0.08
| Stirupps b |  |  | 1.652 |  | 10 | 1 | 4 | 3.8241 |  | 5 | 0.1 | 3.7241 | 14.8963 |  | 14.8963
0.18
0.08
| Stirupps c |  |  | 0.18291 |  | 10 | 1 | 4 | 0.88583 |  | 5 | 0.1 | 0.78583 | 3.1433 |  | 3.1433
0.18
0.08
| Stirupps d |  | 0.18 |  |  | 10 | 1 | 7 | 0.34 |  | 2 | 0.04 | 0.3 | 2.1 |  | 2.1
0.08
18 | SW11 (230x4065)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 1 | 8 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS D |  |  |  |  | 12 | 1 | 8 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS E |  |  |  |  | 12 | 1 | 8 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS F |  |  |  |  | 10 | 1 | 20 | 0.743 | 0 | 1 | 0.02 | 1.023 | 20.46 |  | 20.46
0.08
| Stirupps a |  |  | 1.2771 |  | 10 | 1 | 8 | 3.0741 |  | 5 | 0.1 | 2.9741 | 23.7931 |  | 23.7931
0.18
0.08
| Stirupps b |  |  | 1.5529 |  | 10 | 1 | 4 | 3.6257 |  | 5 | 0.1 | 3.5257 | 14.1029 |  | 14.1029
0.18
0.08
| Stirupps c |  |  | 0.1739 |  | 10 | 1 | 8 | 0.86779 |  | 5 | 0.1 | 0.76779 | 6.1423 |  | 6.1423
0.18
0.08
| Stirupps d |  | 0.18 |  |  | 10 | 1 | 5 | 0.34 |  | 2 | 0.04 | 0.3 | 1.5 |  | 1.5
0.08
19 | SW12 (230x650/1535)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 12 | 1 | 16 | 0.743 | 0 | 1 | 0.024 | 1.019 | 16.304 |  |  | 16.304
| VERTICAL BARS C |  |  | 0.3 |  | 10 | 1 | 8 | 0.743 | 0 | 1 | 0.02 | 1.023 | 8.184 |  | 8.184
0.08
| Stirupps a |  |  | 0.6 |  | 10 | 1 | 4 | 1.72 |  | 5 | 0.1 | 1.62 | 6.48 |  | 6.48
0.18
0.08
| Stirupps b |  |  | 1.485 |  | 10 | 1 | 4 | 3.49 |  | 5 | 0.1 | 3.39 | 13.56 |  | 13.56
0.18
0.08
| Stirupps c |  |  | 0.2656 |  | 10 | 1 | 1 | 1.0512 |  | 5 | 0.1 | 0.9512 | 0.9512 |  | 0.9512
0.18
0.08
| Stirupps d |  |  | 0.43518 |  | 10 | 1 | 1 | 1.3904 |  | 5 | 0.1 | 1.2904 | 1.2904 |  | 1.2904
0.18
0.08
| Stirupps e |  |  | 0.69864 |  | 10 | 1 | 1 | 1.9173 |  | 5 | 0.1 | 1.8173 | 1.8173 |  | 1.8173
0.18
0.08
| Stirupps f |  |  | 0.16573 |  | 10 | 1 | 1 | 0.85145 |  | 5 | 0.1 | 0.75145 | 0.75145 |  | 0.75145
0.18
0.08
| Stirupps g |  | 0.18 |  |  | 10 | 1 | 4 | 0.34 |  | 2 | 0.04 | 0.3 | 1.2 |  | 1.2
0.08
20 | SW13 (230x3445)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 12 | 1 | 8 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 1 | 8 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS D |  |  |  |  | 10 | 1 | 22 | 0.743 | 0 | 1 | 0.02 | 1.023 | 22.506 |  | 22.506
0.08
| Stirupps a |  |  | 0.80395 |  | 10 | 1 | 8 | 2.1279 |  | 5 | 0.1 | 2.0279 | 16.2233 |  | 16.2233
0.18
0.08
| Stirupps b |  |  | 1.8791 |  | 10 | 1 | 4 | 4.2782 |  | 5 | 0.1 | 4.1782 | 16.7127 |  | 16.7127
0.18
0.08
| Stirupps c |  |  | 0.18959 |  | 10 | 1 | 4 | 0.89918 |  | 5 | 0.1 | 0.79918 | 3.1967 |  | 3.1967
0.18
0.08
| Stirupps d |  | 0.18 |  |  | 10 | 1 | 5 | 0.34 |  | 2 | 0.04 | 0.3 | 1.5 |  | 1.5
0.08
21 | LIFT WALL |  | 0.1
| VERTICAL BARS |  | 2.7 |  |  | 10 | 4 | 26.3333 | 2.7 | 0 | 1 | 0.02 | 2.78 | 292.8267 |  | 292.8267
22 | SW8 (230x3600)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 0.5 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS B |  |  |  |  | 16 | 0.5 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS C |  |  | 0.3 |  | 16 | 0.5 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS D |  |  |  |  | 16 | 0.5 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS E |  |  |  |  | 16 | 0.5 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS F |  |  |  |  | 16 | 0.5 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS G |  |  |  |  | 12 | 0.5 | 12 | 0.743 | 0 | 1 | 0.024 | 1.019 | 6.114 |  |  | 6.114
0.08
| Stirupps a |  |  | 0.91748 |  | 10 | 0.5 | 8 | 2.355 |  | 5 | 0.1 | 2.255 | 9.0198 |  | 9.0198
0.18
0.08
| Stirupps b |  |  | 1.652 |  | 10 | 0.5 | 4 | 3.8241 |  | 5 | 0.1 | 3.7241 | 7.4482 |  | 7.4482
0.18
0.08
| Stirupps c |  |  | 0.18291 |  | 10 | 0.5 | 4 | 0.88583 |  | 5 | 0.1 | 0.78583 | 1.5717 |  | 1.5717
0.18
0.08
| Stirupps d |  | 0.18 |  |  | 10 | 0.5 | 7 | 0.34 |  | 2 | 0.04 | 0.3 | 1.05 |  | 1.05
0.08
TOTAL
| TOTAL LENGTH IN METRE | [13 empty] | 0 | 1291.9858 | 430.018 | 614.688 | 282.846 | 19.86
| UNIT WEIGHT (IN KG) | [13 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.469 | 3.858
| TOTAL WEIGHT (IN KG) | [13 empty] | 0 | 797.1553 | 381.856 | 971.207 | 698.3468 | 76.6199 | 2925.1849
FROM FOUNDATION TOP TO PLINTH BEAM TOP
1 | Column C1 (300x600)
| VERTICAL BARS A |  | 1.93 |  |  | 16 | 20 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 154.4 |  |  |  | 154.4
| VERTICAL BARS B |  |  |  |  | 12 | 20 | 2 | 1.93 | 0 | 0 | 0 | 1.93 | 77.2 |  |  | 77.2
| VERTICAL BARS C |  |  |  |  | 16 | 20 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 154.4 |  |  |  | 154.4
| VERTICAL BARS D |  |  |  |  | 12 | 20 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 154.4 |  |  | 154.4
| ZONE A | 0.08
| Stirupps a |  |  | 0.52 |  | 10 | 20 | 18 | 1.64 |  | 5 | 0.1 | 1.56 | 561.6 |  | 561.6
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 20 | 18 | 0.8656 |  | 5 | 0.1 | 0.7856 | 282.816 |  | 282.816
0.22
| Stirupps c |  |  |  |  | 10 | 20 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 234 |  | 234
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 20 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 234 |  | 234
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.52 |  | 8 | 20 | 2.8667 | 1.608 |  | 5 | 0.08 | 1.548 | 88.752 | 88.752
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 8 | 20 | 2.8667 | 0.8336 |  | 5 | 0.08 | 0.7736 | 44.3531 | 44.3531
0.22
| Stirupps c |  |  |  |  | 8 | 20 | 2.8667 | 0.698 |  | 4 | 0.064 | 0.634 | 36.3493 | 36.3493
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 20 | 2.8667 | 0.698 |  | 4 | 0.064 | 0.634 | 36.3493 | 36.3493
|  | 0.175 |  | 0.175
0.22
1 | Column C1 (300x600)
| VERTICAL BARS A |  | 2.13 |  |  | 16 | 12 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 102.24 |  |  |  | 102.24
| VERTICAL BARS B |  |  |  |  | 12 | 12 | 2 | 2.13 | 0 | 0 | 0 | 2.13 | 51.12 |  |  | 51.12
| VERTICAL BARS C |  |  |  |  | 16 | 12 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 102.24 |  |  |  | 102.24
| VERTICAL BARS D |  |  |  |  | 12 | 12 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 102.24 |  |  | 102.24
| ZONE A | 0.08
| Stirupps a |  |  | 0.52 |  | 10 | 12 | 18 | 1.64 |  | 5 | 0.1 | 1.56 | 336.96 |  | 336.96
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 12 | 18 | 0.8656 |  | 5 | 0.1 | 0.7856 | 169.6896 |  | 169.6896
0.22
| Stirupps c |  |  |  |  | 10 | 12 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 140.4 |  | 140.4
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 12 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 140.4 |  | 140.4
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.52 |  | 8 | 12 | 4.2 | 1.608 |  | 5 | 0.08 | 1.548 | 78.0192 | 78.0192
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 8 | 12 | 4.2 | 0.8336 |  | 5 | 0.08 | 0.7736 | 38.9894 | 38.9894
0.22
| Stirupps c |  |  |  |  | 8 | 12 | 4.2 | 0.698 |  | 4 | 0.064 | 0.634 | 31.9536 | 31.9536
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 12 | 4.2 | 0.698 |  | 4 | 0.064 | 0.634 | 31.9536 | 31.9536
|  | 0.175 |  | 0.175
0.22
2 | Column C2 (300x600)
| VERTICAL BARS A |  | 1.93 |  |  | 20 | 12 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 92.64 |  |  |  |  | 92.64
| VERTICAL BARS B |  |  |  |  | 20 | 12 | 2 | 1.93 | 0 | 0 | 0 | 1.93 | 46.32 |  |  |  |  | 46.32
| VERTICAL BARS C |  |  |  |  | 16 | 12 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 92.64 |  |  |  | 92.64
| VERTICAL BARS D |  |  |  |  | 16 | 12 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 92.64 |  |  |  | 92.64
| ZONE A | 0.08
| Stirupps a |  |  | 0.52 |  | 10 | 12 | 18 | 1.64 |  | 5 | 0.1 | 1.54 | 332.64 |  | 332.64
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 12 | 18 | 0.8656 |  | 5 | 0.1 | 0.7656 | 165.3696 |  | 165.3696
0.22
| Stirupps c |  |  |  |  | 10 | 12 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 140.4 |  | 140.4
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 12 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 140.4 |  | 140.4
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.52 |  | 8 | 12 | 2.8667 | 1.608 |  | 5 | 0.08 | 1.528 | 52.5632 | 52.5632
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 8 | 12 | 2.8667 | 0.8336 |  | 5 | 0.08 | 0.7536 | 25.9238 | 25.9238
0.22
| Stirupps c |  |  |  |  | 8 | 12 | 2.8667 | 0.698 |  | 4 | 0.064 | 0.634 | 21.8096 | 21.8096
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 12 | 2.8667 | 0.698 |  | 4 | 0.064 | 0.634 | 21.8096 | 21.8096
|  | 0.175 |  | 0.175
0.22
2 | Column C2 (300x600)
| VERTICAL BARS A |  | 2.13 |  |  | 20 | 10 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 85.2 |  |  |  |  | 85.2
| VERTICAL BARS B |  |  |  |  | 20 | 10 | 2 | 2.13 | 0 | 0 | 0 | 2.13 | 42.6 |  |  |  |  | 42.6
| VERTICAL BARS C |  |  |  |  | 16 | 10 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 85.2 |  |  |  | 85.2
| VERTICAL BARS D |  |  |  |  | 16 | 10 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 85.2 |  |  |  | 85.2
| ZONE A | 0.08
| Stirupps a |  |  | 0.52 |  | 10 | 10 | 18 | 1.64 |  | 5 | 0.1 | 1.54 | 277.2 |  | 277.2
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 10 | 18 | 0.8656 |  | 5 | 0.1 | 0.7656 | 137.808 |  | 137.808
0.22
| Stirupps c |  |  |  |  | 10 | 10 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 117 |  | 117
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 10 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 117 |  | 117
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.52 |  | 8 | 10 | 4.2 | 1.608 |  | 5 | 0.08 | 1.528 | 64.176 | 64.176
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 8 | 10 | 4.2 | 0.8336 |  | 5 | 0.08 | 0.7536 | 31.6512 | 31.6512
0.22
| Stirupps c |  |  |  |  | 8 | 10 | 4.2 | 0.698 |  | 4 | 0.064 | 0.634 | 26.628 | 26.628
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 10 | 4.2 | 0.698 |  | 4 | 0.064 | 0.634 | 26.628 | 26.628
|  | 0.175 |  | 0.175
0.22
3 | Column C3 (300x600)
| VERTICAL BARS A |  | 2.13 |  |  | 25 | 4 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 | [5 empty] | 34.08
| VERTICAL BARS B |  |  |  |  | 25 | 4 | 2 | 2.13 | 0 | 0 | 0 | 2.13 | 17.04 | [5 empty] | 17.04
| VERTICAL BARS C |  |  |  |  | 25 | 4 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 | [5 empty] | 34.08
| VERTICAL BARS D |  |  |  |  | 20 | 4 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  |  | 34.08
| ZONE A | 0.08
| Stirupps a |  |  | 0.52 |  | 10 | 4 | 18 | 1.64 |  | 5 | 0.1 | 1.54 | 110.88 |  | 110.88
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 4 | 18 | 0.8656 |  | 5 | 0.1 | 0.7656 | 55.1232 |  | 55.1232
0.22
| Stirupps c |  |  |  |  | 10 | 4 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 46.8 |  | 46.8
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 4 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 46.8 |  | 46.8
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.52 |  | 8 | 4 | 4.2 | 1.608 |  | 5 | 0.08 | 1.528 | 25.6704 | 25.6704
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 8 | 4 | 4.2 | 0.8336 |  | 5 | 0.08 | 0.7536 | 12.6605 | 12.6605
0.22
| Stirupps c |  |  |  |  | 8 | 4 | 4.2 | 0.698 |  | 4 | 0.064 | 0.634 | 10.6512 | 10.6512
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 4 | 4.2 | 0.698 |  | 4 | 0.064 | 0.634 | 10.6512 | 10.6512
|  | 0.175 |  | 0.175
0.22
4 | Column C4 (300x750)
| VERTICAL BARS A |  | 1.93 |  |  | 20 | 8 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 61.76 |  |  |  |  | 61.76
| VERTICAL BARS B |  |  |  |  | 20 | 8 | 2 | 1.93 | 0 | 0 | 0 | 1.93 | 30.88 |  |  |  |  | 30.88
| VERTICAL BARS C |  |  |  |  | 20 | 8 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 61.76 |  |  |  |  | 61.76
| VERTICAL BARS D |  |  |  |  | 20 | 8 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 61.76 |  |  |  |  | 61.76
| VERTICAL BARS E |  |  |  |  | 20 | 8 | 2 | 1.93 | 0 | 0 | 0 | 1.93 | 30.88 |  |  |  |  | 30.88
| ZONE A | 0.08
| Stirupps a |  |  | 0.67 |  | 10 | 8 | 22 | 1.94 |  | 5 | 0.1 | 1.84 | 323.84 |  | 323.84
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 10 | 8 | 22 | 1.1 |  | 5 | 0.1 | 1 | 176 |  | 176
0.22
| Stirupps c |  |  |  |  | 10 | 8 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 114.4 |  | 114.4
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 8 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 114.4 |  | 114.4
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 8 | 22 | 0.38 |  | 2 | 0.04 | 0.34 | 59.84 |  | 59.84
0.08
| ZONE B | 0.08
| Stirupps a |  |  | 0.67 |  | 8 | 8 | 0.86667 | 1.908 |  | 5 | 0.08 | 1.828 | 12.6741 | 12.6741
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 8 | 8 | 0.86667 | 1.068 |  | 5 | 0.08 | 0.988 | 6.8501 | 6.8501
0.22
| Stirupps c |  |  |  |  | 8 | 8 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 4.3957 | 4.3957
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 8 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 4.3957 | 4.3957
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 8 | 8 | 0.86667 | 0.38 |  | 2 | 0.032 | 0.348 | 2.4128 | 2.4128
0.08
4 | Column C4 (300x750)
| VERTICAL BARS A |  | 2.13 |  |  | 20 | 8 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 68.16 |  |  |  |  | 68.16
| VERTICAL BARS B |  |  |  |  | 20 | 8 | 2 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  |  | 34.08
| VERTICAL BARS C |  |  |  |  | 20 | 8 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 68.16 |  |  |  |  | 68.16
| VERTICAL BARS D |  |  |  |  | 20 | 8 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 68.16 |  |  |  |  | 68.16
| VERTICAL BARS E |  |  |  |  | 20 | 8 | 2 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  |  | 34.08
| ZONE A | 0.08
| Stirupps a |  |  | 0.67 |  | 10 | 8 | 22 | 1.94 |  | 5 | 0.1 | 1.84 | 323.84 |  | 323.84
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 10 | 8 | 22 | 1.1 |  | 5 | 0.1 | 1 | 176 |  | 176
0.22
| Stirupps c |  |  |  |  | 10 | 8 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 114.4 |  | 114.4
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 8 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 114.4 |  | 114.4
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 8 | 22 | 0.38 |  | 2 | 0.04 | 0.34 | 59.84 |  | 59.84
0.08
| ZONE B | 0.08
| Stirupps a |  |  | 0.67 |  | 8 | 8 | 2.2 | 1.908 |  | 5 | 0.08 | 1.828 | 32.1728 | 32.1728
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 8 | 8 | 2.2 | 1.068 |  | 5 | 0.08 | 0.988 | 17.3888 | 17.3888
0.22
| Stirupps c |  |  |  |  | 8 | 8 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 11.1584 | 11.1584
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 8 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 11.1584 | 11.1584
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 8 | 8 | 2.2 | 0.38 |  | 2 | 0.032 | 0.348 | 6.1248 | 6.1248
0.08
5 | Column C5 (300x750)
| VERTICAL BARS A |  | 2.13 |  |  | 20 | 10 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 85.2 |  |  |  |  | 85.2
| VERTICAL BARS B |  |  |  |  | 16 | 10 | 2 | 2.13 | 0 | 0 | 0 | 2.13 | 42.6 |  |  |  | 42.6
| VERTICAL BARS C |  |  |  |  | 16 | 10 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 85.2 |  |  |  | 85.2
| VERTICAL BARS D |  |  |  |  | 16 | 10 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 85.2 |  |  |  | 85.2
| VERTICAL BARS E |  |  |  |  | 16 | 10 | 2 | 2.13 | 0 | 0 | 0 | 2.13 | 42.6 |  |  |  | 42.6
| ZONE A | 0.08
| Stirupps a |  |  | 0.67 |  | 10 | 10 | 22 | 1.94 |  | 5 | 0.1 | 1.84 | 404.8 |  | 404.8
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 10 | 10 | 22 | 1.1 |  | 5 | 0.1 | 1 | 220 |  | 220
0.22
| Stirupps c |  |  |  |  | 10 | 10 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 143 |  | 143
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 10 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 143 |  | 143
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 10 | 22 | 0.38 |  | 2 | 0.04 | 0.34 | 74.8 |  | 74.8
0.08
| ZONE B | 0.08
| Stirupps a |  |  | 0.67 |  | 8 | 10 | 0.86667 | 1.908 |  | 5 | 0.08 | 1.828 | 15.8427 | 15.8427
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 8 | 10 | 0.86667 | 1.068 |  | 5 | 0.08 | 0.988 | 8.5627 | 8.5627
0.22
| Stirupps c |  |  |  |  | 8 | 10 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 5.4947 | 5.4947
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 10 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 5.4947 | 5.4947
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 8 | 10 | 0.86667 | 0.38 |  | 2 | 0.032 | 0.348 | 3.016 | 3.016
0.08
5 | Column C5 (300x750)
| VERTICAL BARS A |  | 2.13 |  |  | 20 | 4 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  |  | 34.08
| VERTICAL BARS B |  |  |  |  | 16 | 4 | 2 | 2.13 | 0 | 0 | 0 | 2.13 | 17.04 |  |  |  | 17.04
| VERTICAL BARS C |  |  |  |  | 16 | 4 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  | 34.08
| VERTICAL BARS D |  |  |  |  | 16 | 4 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  | 34.08
| VERTICAL BARS E |  |  |  |  | 16 | 4 | 2 | 2.13 | 0 | 0 | 0 | 2.13 | 17.04 |  |  |  | 17.04
| ZONE A | 0.08
| Stirupps a |  |  | 0.67 |  | 10 | 4 | 22 | 1.94 |  | 5 | 0.1 | 1.84 | 161.92 |  | 161.92
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 10 | 4 | 22 | 1.1 |  | 5 | 0.1 | 1 | 88 |  | 88
0.22
| Stirupps c |  |  |  |  | 10 | 4 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 57.2 |  | 57.2
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 4 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 57.2 |  | 57.2
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 4 | 22 | 0.38 |  | 2 | 0.04 | 0.34 | 29.92 |  | 29.92
0.08
| ZONE B | 0.08
| Stirupps a |  |  | 0.67 |  | 8 | 4 | 2.2 | 1.908 |  | 5 | 0.08 | 1.828 | 16.0864 | 16.0864
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 8 | 4 | 2.2 | 1.068 |  | 5 | 0.08 | 0.988 | 8.6944 | 8.6944
0.22
| Stirupps c |  |  |  |  | 8 | 4 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 5.5792 | 5.5792
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 4 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 5.5792 | 5.5792
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 8 | 4 | 2.2 | 0.38 |  | 2 | 0.032 | 0.348 | 3.0624 | 3.0624
0.08
6 | Column C6 (300x715)
| VERTICAL BARS A |  | 1.93 |  |  | 16 | 14 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 108.08 |  |  |  | 108.08
| VERTICAL BARS B |  |  |  |  | 12 | 14 | 2 | 1.93 | 0 | 0 | 0 | 1.93 | 54.04 |  |  | 54.04
| VERTICAL BARS C |  |  |  |  | 12 | 14 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 108.08 |  |  | 108.08
| VERTICAL BARS D |  |  |  |  | 12 | 14 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 108.08 |  |  | 108.08
| VERTICAL BARS E |  |  |  |  | 12 | 14 | 2 | 1.93 | 0 | 0 | 0 | 1.93 | 54.04 |  |  | 54.04
| ZONE A | 0.08
| Stirupps a |  |  | 0.635 |  | 10 | 14 | 21.0667 | 1.87 |  | 5 | 0.1 | 1.77 | 522.032 |  | 522.032
0.22
0.08
| Stirupps b |  |  | 0.23833 |  | 10 | 14 | 21.0667 | 1.0767 |  | 5 | 0.1 | 0.97667 | 288.0516 |  | 288.0516
0.22
| Stirupps c |  |  |  |  | 10 | 14 | 21.0667 | 0.73 |  | 4 | 0.08 | 0.65 | 191.7067 |  | 191.7067
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 14 | 21.0667 | 0.73 |  | 4 | 0.08 | 0.65 | 191.7067 |  | 191.7067
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 14 | 21.0667 | 0.38 |  | 2 | 0.04 | 0.34 | 100.2773 |  | 100.2773
0.08
| ZONE B | 0.08
| Stirupps a |  |  | 0.635 |  | 8 | 14 | 0.86667 | 1.838 |  | 5 | 0.08 | 1.758 | 21.3304 | 21.3304
0.22
0.08
| Stirupps b |  |  | 0.23833 |  | 8 | 14 | 0.86667 | 1.0447 |  | 5 | 0.08 | 0.96467 | 11.7046 | 11.7046
0.22
| Stirupps c |  |  |  |  | 8 | 14 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 7.6925 | 7.6925
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 14 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 7.6925 | 7.6925
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 8 | 14 | 0.86667 | 0.38 |  | 2 | 0.032 | 0.348 | 4.2224 | 4.2224
0.08
7 | Column C7 (300x800)
| VERTICAL BARS A |  | 1.93 |  |  | 16 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 2 | 1.93 | 0 | 0 | 0 | 1.93 | 7.72 |  |  | 7.72
| VERTICAL BARS C |  |  |  |  | 12 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  | 15.44
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  | 15.44
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  | 15.44
| ZONE A | 0.08
| Stirupps a |  |  | 0.72 |  | 10 | 2 | 23.3333 | 2.04 |  | 5 | 0.1 | 1.94 | 90.5333 |  | 90.5333
0.22
0.08
| Stirupps b |  |  | 0.13257 |  | 10 | 2 | 23.3333 | 0.86514 |  | 5 | 0.1 | 0.76514 | 35.7067 |  | 35.7067
0.22
0.08
| Stirupps c |  |  | 0.13257 |  | 10 | 2 | 23.3333 | 0.86514 |  | 5 | 0.1 | 0.76514 | 35.7067 |  | 35.7067
0.22
| Stirupps d |  |  |  |  | 10 | 2 | 23.3333 | 0.73 |  | 4 | 0.08 | 0.65 | 30.3333 |  | 30.3333
|  | 0.175 |  | 0.175
0.22
| Stirupps e |  |  |  |  | 10 | 2 | 23.3333 | 0.73 |  | 4 | 0.08 | 0.65 | 30.3333 |  | 30.3333
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.72 |  | 8 | 2 | 0.86667 | 2.008 |  | 5 | 0.08 | 1.928 | 3.3419 | 3.3419
0.22
0.08
| Stirupps b |  |  | 0.13257 |  | 8 | 2 | 0.86667 | 0.83314 |  | 5 | 0.08 | 0.75314 | 1.3054 | 1.3054
0.22
0.08
| Stirupps c |  |  | 0.13257 |  | 8 | 2 | 0.86667 | 0.83314 |  | 5 | 0.08 | 0.75314 | 1.3054 | 1.3054
0.22
| Stirupps d |  |  |  |  | 8 | 2 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 1.0989 | 1.0989
|  | 0.175 |  | 0.175
0.22
| Stirupps e |  |  |  |  | 8 | 2 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 1.0989 | 1.0989
|  | 0.175 |  | 0.175
0.22
7 | Column C7 (300x800)
| VERTICAL BARS A |  | 2.13 |  |  | 16 | 2 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 17.04 |  |  |  | 17.04
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 2 | 2.13 | 0 | 0 | 0 | 2.13 | 8.52 |  |  | 8.52
| VERTICAL BARS C |  |  |  |  | 12 | 2 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 17.04 |  |  | 17.04
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 17.04 |  |  | 17.04
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 17.04 |  |  | 17.04
| ZONE A | 0.08
| Stirupps a |  |  | 0.72 |  | 10 | 2 | 23.3333 | 2.04 |  | 5 | 0.1 | 1.94 | 90.5333 |  | 90.5333
0.22
0.08
| Stirupps b |  |  | 0.13257 |  | 10 | 2 | 23.3333 | 0.86514 |  | 5 | 0.1 | 0.76514 | 35.7067 |  | 35.7067
0.22
0.08
| Stirupps c |  |  | 0.13257 |  | 10 | 2 | 23.3333 | 0.86514 |  | 5 | 0.1 | 0.76514 | 35.7067 |  | 35.7067
0.22
| Stirupps d |  |  |  |  | 10 | 2 | 23.3333 | 0.73 |  | 4 | 0.08 | 0.65 | 30.3333 |  | 30.3333
|  | 0.175 |  | 0.175
0.22
| Stirupps e |  |  |  |  | 10 | 2 | 23.3333 | 0.73 |  | 4 | 0.08 | 0.65 | 30.3333 |  | 30.3333
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.72 |  | 8 | 2 | 2.2 | 2.008 |  | 5 | 0.08 | 1.928 | 8.4832 | 8.4832
0.22
0.08
| Stirupps b |  |  | 0.13257 |  | 8 | 2 | 2.2 | 0.83314 |  | 5 | 0.08 | 0.75314 | 3.3138 | 3.3138
0.22
0.08
| Stirupps c |  |  | 0.13257 |  | 8 | 2 | 2.2 | 0.83314 |  | 5 | 0.08 | 0.75314 | 3.3138 | 3.3138
0.22
| Stirupps d |  |  |  |  | 8 | 2 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 2.7896 | 2.7896
|  | 0.175 |  | 0.175
0.22
| Stirupps e |  |  |  |  | 8 | 2 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 2.7896 | 2.7896
|  | 0.175 |  | 0.175
0.22
8 | Column C8 (300x600)
| VERTICAL BARS A |  | 2.13 |  |  | 20 | 4 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  |  | 34.08
| VERTICAL BARS B |  |  |  |  | 20 | 4 | 2 | 2.13 | 0 | 0 | 0 | 2.13 | 17.04 |  |  |  |  | 17.04
| VERTICAL BARS C |  |  |  |  | 20 | 4 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  |  | 34.08
| VERTICAL BARS D |  |  |  |  | 20 | 4 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  |  | 34.08
| ZONE A | 0.08
| Stirupps a |  |  | 0.52 |  | 10 | 4 | 18 | 1.64 |  | 5 | 0.1 | 1.54 | 110.88 |  | 110.88
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 4 | 18 | 0.8656 |  | 5 | 0.1 | 0.7656 | 55.1232 |  | 55.1232
0.22
| Stirupps c |  |  |  |  | 10 | 4 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 46.8 |  | 46.8
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 4 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 46.8 |  | 46.8
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.52 |  | 8 | 4 | 2.2 | 1.608 |  | 5 | 0.08 | 1.528 | 13.4464 | 13.4464
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 8 | 4 | 2.2 | 0.8336 |  | 5 | 0.08 | 0.7536 | 6.6317 | 6.6317
0.22
| Stirupps c |  |  |  |  | 8 | 4 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 5.5792 | 5.5792
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 4 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 5.5792 | 5.5792
|  | 0.175 |  | 0.175
0.22
9 | SW1 (230x650/1650)
| VERTICAL BARS A |  | 1.93 |  |  | 16 | 2 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 30.88 |  |  |  | 30.88
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 16 | 1.93 | 0 | 0 | 0 | 1.93 | 61.76 |  |  | 61.76
| VERTICAL BARS C |  |  |  |  | 10 | 2 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 30.88 |  | 30.88
0.08
| BE MAIN |  |  | 0.6 |  | 8 | 2 | 15.8 | 1.688 |  | 5 | 0.08 | 1.608 | 50.8128 | 50.8128
0.18
0.08
| BE OTHERS |  |  | 0.2656 |  | 8 | 2 | 15.8 | 1.0192 |  | 5 | 0.08 | 0.9392 | 29.6787 | 29.6787
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 2 | 15.8 | 0.34 |  | 2 | 0.032 | 0.308 | 9.7328 | 9.7328
0.08
0.08
| BE MAIN |  |  | 0.391 |  | 8 | 2 | 31.6 | 1.27 |  | 5 | 0.08 | 1.19 | 75.208 | 75.208
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 2 | 31.6 | 0.34 |  | 2 | 0.032 | 0.308 | 19.4656 | 19.4656
0.08
0.08
| MID MAIN |  |  | 0.882 |  | 8 | 2 | 8.4 | 2.252 |  | 5 | 0.08 | 2.172 | 36.4896 | 36.4896
0.18
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 2 | 9.4 | 0.34 |  | 2 | 0.032 | 0.308 | 5.7904 | 5.7904
0.08
10 | SW2 (230x650/1850)
| VERTICAL BARS A |  | 1.93 |  |  | 16 | 2 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 30.88 |  |  |  | 30.88
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 16 | 1.93 | 0 | 0 | 0 | 1.93 | 61.76 |  |  | 61.76
| VERTICAL BARS C |  |  |  |  | 10 | 2 | 10 | 1.93 | 0 | 0 | 0 | 1.93 | 38.6 |  | 38.6
0.08
| BE MAIN |  |  | 0.6 |  | 8 | 2 | 15.8 | 1.688 |  | 5 | 0.08 | 1.608 | 50.8128 | 50.8128
0.18
0.08
| BE OTHERS |  |  | 0.2656 |  | 8 | 2 | 15.8 | 1.0192 |  | 5 | 0.08 | 0.9392 | 29.6787 | 29.6787
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 2 | 15.8 | 0.34 |  | 2 | 0.032 | 0.308 | 9.7328 | 9.7328
0.08
0.08
| BE MAIN |  |  | 0.391 |  | 8 | 2 | 31.6 | 1.27 |  | 5 | 0.08 | 1.19 | 75.208 | 75.208
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 2 | 31.6 | 0.34 |  | 2 | 0.032 | 0.308 | 19.4656 | 19.4656
0.08
0.08
| MID MAIN |  |  | 1.082 |  | 8 | 2 | 8.4 | 2.652 |  | 5 | 0.08 | 2.572 | 43.2096 | 43.2096
0.18
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 2 | 9.4 | 0.34 |  | 2 | 0.032 | 0.308 | 5.7904 | 5.7904
0.08
11 | SW3 (230x1000)
| VERTICAL BARS A |  | 1.93 |  |  | 16 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  | 15.44
| VERTICAL BARS C |  |  |  |  | 12 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  | 15.44
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  | 15.44
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  | 15.44
0.08
| Stirupps a |  |  | 0.95 |  | 10 | 2 | 15.8 | 2.42 |  | 5 | 0.1 | 2.32 | 73.312 |  | 73.312
0.18
0.08
| Stirupps b |  |  | 0.13578 |  | 10 | 2 | 15.8 | 0.79156 |  | 5 | 0.1 | 0.69156 | 21.8532 |  | 21.8532
0.18
12 | SW4 (230x1150)
| VERTICAL BARS A |  | 1.93 |  |  | 16 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  | 15.44
| VERTICAL BARS C |  |  |  |  | 12 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  | 15.44
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  | 15.44
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  | 15.44
| VERTICAL BARS F |  |  |  |  | 12 | 2 | 2 | 1.93 | 0 | 0 | 0 | 1.93 | 7.72 |  |  | 7.72
0.08
| Stirupps a |  |  | 1.1 |  | 10 | 2 | 15.8 | 2.72 |  | 5 | 0.1 | 2.62 | 82.792 |  | 82.792
0.18
0.08
| Stirupps b |  |  | 0.1404 |  | 10 | 2 | 15.8 | 0.8008 |  | 5 | 0.1 | 0.7008 | 22.1453 |  | 22.1453
0.18
0.08
| Stirupps c |  | 0.18 |  |  | 10 | 2 | 15.8 | 0.34 |  | 2 | 0.04 | 0.3 | 9.48 |  | 9.48
0.08
13 | SW5 (230x1700)
| VERTICAL BARS A |  | 2.13 |  |  | 20 | 4 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  |  | 34.08
| VERTICAL BARS B |  |  |  |  | 20 | 4 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  |  | 34.08
| VERTICAL BARS C |  |  |  |  | 20 | 4 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  |  | 34.08
| VERTICAL BARS D |  |  |  |  | 16 | 4 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  | 34.08
| VERTICAL BARS E |  |  |  |  | 16 | 4 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  | 34.08
| VERTICAL BARS F |  |  |  |  | 16 | 4 | 8 | 2.13 | 0 | 0 | 0 | 2.13 | 68.16 |  |  |  | 68.16
| VERTICAL BARS G |  |  |  |  | 16 | 4 | 6 | 2.13 | 0 | 0 | 0 | 2.13 | 51.12 |  |  |  | 51.12
0.08
| Stirupps a |  |  | 1.65 |  | 10 | 4 | 17.8 | 3.82 |  | 5 | 0.1 | 3.72 | 264.864 |  | 264.864
0.18
0.08
| Stirupps b |  |  | 0.13787 |  | 10 | 4 | 17.8 | 0.79575 |  | 5 | 0.1 | 0.69575 | 49.5374 |  | 49.5374
0.18
0.08
| Stirupps c |  |  | 0.23975 |  | 10 | 4 | 17.8 | 0.9995 |  | 5 | 0.1 | 0.8995 | 64.0444 |  | 64.0444
0.18
0.08
| Stirupps d |  | 0.18 |  |  | 10 | 4 | 17.8 | 0.34 |  | 2 | 0.04 | 0.3 | 21.36 |  | 21.36
0.08
14 | SW6 (230x1185)
| VERTICAL BARS A |  | 1.93 |  |  | 16 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS B |  |  |  |  | 16 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS C |  |  |  |  | 16 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  | 15.44
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  | 15.44
| VERTICAL BARS F |  |  |  |  | 12 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  | 15.44
0.08
| Stirupps a |  |  | 1.135 |  | 10 | 2 | 15.8 | 2.79 |  | 5 | 0.1 | 2.69 | 85.004 |  | 85.004
0.18
0.08
| Stirupps b |  |  | 0.13773 |  | 10 | 2 | 15.8 | 0.79545 |  | 5 | 0.1 | 0.69545 | 21.9764 |  | 21.9764
0.18
14 | SW6 (230x1185)
| VERTICAL BARS A |  | 2.13 |  |  | 16 | 2 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 17.04 |  |  |  | 17.04
| VERTICAL BARS B |  |  |  |  | 16 | 2 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 17.04 |  |  |  | 17.04
| VERTICAL BARS C |  |  |  |  | 16 | 2 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 17.04 |  |  |  | 17.04
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 17.04 |  |  | 17.04
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 17.04 |  |  | 17.04
| VERTICAL BARS F |  |  |  |  | 12 | 2 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 17.04 |  |  | 17.04
0.08
| Stirupps a |  |  | 1.135 |  | 10 | 2 | 17.8 | 2.79 |  | 5 | 0.1 | 2.69 | 95.764 |  | 95.764
0.18
0.08
| Stirupps b |  |  | 0.13773 |  | 10 | 2 | 17.8 | 0.79545 |  | 5 | 0.1 | 0.69545 | 24.7582 |  | 24.7582
0.18
15 | SW7 (230x1855)
| VERTICAL BARS A |  | 1.93 |  |  | 16 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS B |  |  |  |  | 16 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS C |  |  |  |  | 16 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS D |  |  |  |  | 16 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS E |  |  |  |  | 16 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS F |  |  |  |  | 16 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS G |  |  |  |  | 16 | 2 | 4 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS H |  |  |  |  | 16 | 2 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 30.88 |  |  |  | 30.88
0.08
| Stirupps a |  |  | 1.805 |  | 10 | 2 | 15.8 | 4.13 |  | 5 | 0.1 | 4.03 | 127.348 |  | 127.348
0.18
0.08
| Stirupps b |  |  | 0.14124 |  | 10 | 2 | 15.8 | 0.80247 |  | 5 | 0.1 | 0.70247 | 22.1981 |  | 22.1981
0.18
16 | SW9 (230x650/1850)
| VERTICAL BARS A |  | 1.93 |  |  | 16 | 6 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 92.64 |  |  |  | 92.64
| VERTICAL BARS B |  |  |  |  | 16 | 6 | 16 | 1.93 | 0 | 0 | 0 | 1.93 | 185.28 |  |  |  | 185.28
| VERTICAL BARS C |  |  |  |  | 12 | 6 | 10 | 1.93 | 0 | 0 | 0 | 1.93 | 115.8 |  |  | 115.8
0.08
| BE MAIN |  |  | 0.6 |  | 8 | 6 | 15.8 | 1.688 |  | 5 | 0.08 | 1.608 | 152.4384 | 152.4384
0.18
0.08
| BE OTHERS |  |  | 0.2656 |  | 8 | 6 | 15.8 | 1.0192 |  | 5 | 0.08 | 0.9392 | 89.0362 | 89.0362
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 6 | 15.8 | 0.34 |  | 2 | 0.032 | 0.308 | 29.1984 | 29.1984
0.08
0.08
| BE MAIN |  |  | 0.391 |  | 8 | 6 | 31.6 | 1.27 |  | 5 | 0.08 | 1.19 | 225.624 | 225.624
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 6 | 31.6 | 0.34 |  | 2 | 0.032 | 0.308 | 58.3968 | 58.3968
0.08
0.08
| MID MAIN |  |  | 1.082 |  | 8 | 6 | 8.4 | 2.652 |  | 5 | 0.08 | 2.572 | 129.6288 | 129.6288
0.18
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 6 | 9.4 | 0.34 |  | 2 | 0.032 | 0.308 | 17.3712 | 17.3712
0.08
17 | SW10 (230x3445)
| VERTICAL BARS A |  | 2.13 |  |  | 16 | 2 | 8 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  | 34.08
| VERTICAL BARS B |  |  |  |  | 16 | 2 | 8 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  | 34.08
| VERTICAL BARS C |  |  |  |  | 12 | 2 | 8 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  | 34.08
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 2.13 | 0 | 0 | 0 | 2.13 | 17.04 |  |  | 17.04
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 20 | 2.13 | 0 | 0 | 0 | 2.13 | 85.2 |  |  | 85.2
0.08
| BE MAIN |  |  | 0.691 |  | 8 | 2 | 35.6 | 1.87 |  | 5 | 0.08 | 1.79 | 127.448 | 127.448
0.18
0.08
| MID MAIN |  |  | 2.052 |  | 8 | 2 | 9.4 | 4.592 |  | 5 | 0.08 | 4.512 | 84.8256 | 84.8256
0.18
0.08
| BE OTHERS |  |  | 0.11517 |  | 8 | 2 | 71.2 | 0.71833 |  | 5 | 0.08 | 0.63833 | 90.8987 | 90.8987
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 2 | 35.6 | 0.34 |  | 2 | 0.032 | 0.308 | 21.9296 | 21.9296
0.08
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 2 | 26 | 0.34 |  | 2 | 0.032 | 0.308 | 16.016 | 16.016
0.08
18 | SW11 (230x4065)
| VERTICAL BARS A |  | 1.93 |  |  | 16 | 2 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 30.88 |  |  |  | 30.88
| VERTICAL BARS B |  |  |  |  | 16 | 2 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 30.88 |  |  |  | 30.88
| VERTICAL BARS C |  |  |  |  | 12 | 2 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 30.88 |  |  | 30.88
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 30.88 |  |  | 30.88
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 30.88 |  |  | 30.88
| VERTICAL BARS F |  |  |  |  | 10 | 2 | 20 | 1.93 | 0 | 0 | 0 | 1.93 | 77.2 |  | 77.2
0.08
| BE MAIN |  |  | 0.991 |  | 8 | 2 | 35.6 | 2.47 |  | 5 | 0.08 | 2.39 | 170.168 | 170.168
0.18
0.08
| MID MAIN |  |  | 2.072 |  | 8 | 2 | 9.4 | 4.632 |  | 5 | 0.08 | 4.552 | 85.5776 | 85.5776
0.18
0.08
| BE OTHERS |  |  | 0.11011 |  | 8 | 2 | 142.4 | 0.70822 |  | 5 | 0.08 | 0.62822 | 178.9177 | 178.9177
0.18
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 2 | 26 | 0.34 |  | 2 | 0.032 | 0.308 | 16.016 | 16.016
0.08
19 | SW12 (230x650/1535)
| VERTICAL BARS A |  | 2.13 |  |  | 16 | 2 | 8 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  | 34.08
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 16 | 2.13 | 0 | 0 | 0 | 2.13 | 68.16 |  |  | 68.16
| VERTICAL BARS C |  |  |  |  | 10 | 2 | 8 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  | 34.08
0.08
| BE MAIN |  |  | 0.6 |  | 8 | 2 | 17.8 | 1.688 |  | 5 | 0.08 | 1.608 | 57.2448 | 57.2448
0.18
0.08
| BE OTHERS |  |  | 0.2656 |  | 8 | 2 | 17.8 | 1.0192 |  | 5 | 0.08 | 0.9392 | 33.4355 | 33.4355
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 2 | 17.8 | 0.34 |  | 2 | 0.032 | 0.308 | 10.9648 | 10.9648
0.08
0.08
| BE MAIN |  |  | 0.391 |  | 8 | 2 | 35.6 | 1.27 |  | 5 | 0.08 | 1.19 | 84.728 | 84.728
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 2 | 35.6 | 0.34 |  | 2 | 0.032 | 0.308 | 21.9296 | 21.9296
0.08
0.08
| MID MAIN |  |  | 0.767 |  | 8 | 2 | 9.4 | 2.022 |  | 5 | 0.08 | 1.942 | 36.5096 | 36.5096
0.18
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 2 | 10.4 | 0.34 |  | 2 | 0.032 | 0.308 | 6.4064 | 6.4064
0.08
20 | SW13 (230x3445)
| VERTICAL BARS A |  | 2.13 |  |  | 16 | 2 | 8 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  |  | 34.08
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 8 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  | 34.08
| VERTICAL BARS C |  |  |  |  | 12 | 2 | 8 | 2.13 | 0 | 0 | 0 | 2.13 | 34.08 |  |  | 34.08
| VERTICAL BARS D |  |  |  |  | 10 | 2 | 22 | 2.13 | 0 | 0 | 0 | 2.13 | 93.72 |  | 93.72
0.08
| BE MAIN |  |  | 0.591 |  | 8 | 2 | 35.6 | 1.67 |  | 5 | 0.08 | 1.59 | 113.208 | 113.208
0.18
0.08
| MID MAIN |  |  | 2.252 |  | 8 | 2 | 9.4 | 4.992 |  | 5 | 0.08 | 4.912 | 92.3456 | 92.3456
0.18
0.08
| BE OTHERS |  |  | 0.1182 |  | 8 | 2 | 71.2 | 0.7244 |  | 5 | 0.08 | 0.6444 | 91.7626 | 91.7626
0.18
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 2 | 26 | 0.34 |  | 2 | 0.032 | 0.308 | 16.016 | 16.016
0.08
21 | LIFT WALL
| VERTICAL BARS |  | 2.13 |  |  | 10 | 8 | 26.3333 | 2.13 | 0 | 1 | 0.02 | 2.11 | 444.5067 |  | 444.5067
| BINDER |  | 1.9 |  | 0.2 | 8 | 8 | 17.8 | 1.9 | 0 | 1 | 0.016 | 1.884 | 268.2816 | 268.2816
| KENDA |  | 0.23 |  |  | 8 | 8 | 40 | 0.23 | 0 | 1 | 0.016 | 0.214 | 68.48 | 68.48
22 | SW8 (230x3600)
| VERTICAL BARS A |  | 1.93 |  |  | 16 | 1 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS B |  |  |  |  | 16 | 1 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS C |  |  |  |  | 16 | 1 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS D |  |  |  |  | 16 | 1 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS E |  |  |  |  | 16 | 1 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS F |  |  |  |  | 16 | 1 | 8 | 1.93 | 0 | 0 | 0 | 1.93 | 15.44 |  |  |  | 15.44
| VERTICAL BARS G |  |  |  |  | 12 | 1 | 12 | 1.93 | 0 | 0 | 0 | 1.93 | 23.16 |  |  | 23.16
0.08
| BE MAIN |  |  | 1.191 |  | 8 | 1 | 31.6 | 2.87 |  | 5 | 0.08 | 2.79 | 88.164 | 88.164
0.18
0.08
| MID MAIN |  |  | 1.207 |  | 8 | 1 | 8.4 | 2.902 |  | 5 | 0.08 | 2.822 | 23.7048 | 23.7048
0.18
0.08
| BE OTHERS |  |  | 0.2382 |  | 8 | 1 | 158 | 0.9644 |  | 5 | 0.08 | 0.8844 | 139.7352 | 139.7352
0.18
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 1 | 15.6 | 0.34 |  | 2 | 0.032 | 0.308 | 4.8048 | 4.8048
0.08
TOTAL
| TOTAL LENGTH IN METRE | [13 empty] | 4128.694 | 10448.114 | 1679.32 | 2452.48 | 1161.32 | 85.2
| UNIT WEIGHT (IN KG) | [13 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.469 | 3.858
| TOTAL WEIGHT (IN KG) | [13 empty] | 1630.8341 | 6446.4863 | 1491.2362 | 3874.9184 | 2867.2991 | 328.7016 | 16639.4757

## PLINTH BEAM BBS
Reinforcement
Sr. No. | Designation | Dia | C/C (mm) | No | No | No of Bars | Bar Length (mtr) |  |  | Lap Length | One Bar Length (MTR) | Dia Wise Weight (Kg)
[7 empty] | a | b | c |  |  | 8mm | 10mm | 12mm | 16mm | 20MM | 25mm
Typical Beam
200X450 | PB1 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 7.315 | 0.3 |  | 7.915 | 0 | 0 | 0 | 31.66 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 7.315 | 0.3 |  | 7.915 | 0 | 0 | 0 | 31.66 | 0 | 0
| TOP EXTRA | 0 |  | 2 | 1 | 2 | 0.3 | 1.52 |  |  | 1.82 | 0 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 9 |  | 1.188 |  |  | 1.188 | 21.38 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 8 |  | 1.188 |  |  | 1.188 | 19.01 | 0 | 0 | 0 | 0 | 0
200X450 | PB2 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 4.09 | 0.3 |  | 4.69 | 0 | 0 | 0 | 18.76 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 4.09 | 0.3 |  | 4.69 | 0 | 0 | 0 | 18.76 | 0 | 0
| TOP EXTRA | 0 |  | 2 | 1 | 2 | 0.3 | 1.52 |  |  | 1.82 | 0 | 0 | 0 | 0 | 0 | 0
3.3 | STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 11 |  | 1.188 |  |  | 1.188 | 26.14 | 0 | 0 | 0 | 0 | 0
100X450 | PB3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 10 |  | 4 | 1 | 2 | 0.3 | 1.865 | 0.3 |  | 2.465 | 0 | 19.72 | 0 | 0 | 0 | 0
| TOP | 10 |  | 4 | 1 | 2 | 0.3 | 1.865 | 0.3 |  | 2.465 | 0 | 19.72 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 4 | 1 | 10 |  | 1.008 |  |  | 1.008 | 40.32 | 0 | 0 | 0 | 0 | 0
100X450 | PB3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 10 |  | 2 | 1 | 2 | 0.3 | 1.47 | 0.3 |  | 2.07 | 0 | 8.28 | 0 | 0 | 0 | 0
| TOP | 10 |  | 2 | 1 | 2 | 0.3 | 1.47 | 0.3 |  | 2.07 | 0 | 8.28 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 2 | 1 | 9 |  | 1.008 |  |  | 1.008 | 18.14 | 0 | 0 | 0 | 0 | 0
100X450 | PB3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 10 |  | 6 | 1 | 2 | 0.3 | 1.64 | 0.3 |  | 2.24 | 0 | 26.88 | 0 | 0 | 0 | 0
| TOP | 10 |  | 6 | 1 | 2 | 0.3 | 1.64 | 0.3 |  | 2.24 | 0 | 26.88 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 6 | 1 | 10 |  | 1.008 |  |  | 1.008 | 60.48 | 0 | 0 | 0 | 0 | 0
100X450 | PB3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 10 |  | 6 | 1 | 2 | 0.3 | 1.81 | 0.3 |  | 2.41 | 0 | 28.92 | 0 | 0 | 0 | 0
| TOP | 10 |  | 6 | 1 | 2 | 0.3 | 1.81 | 0.3 |  | 2.41 | 0 | 28.92 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 6 | 1 | 11 |  | 1.008 |  |  | 1.008 | 66.53 | 0 | 0 | 0 | 0 | 0
100X450 | PB3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 10 |  | 6 | 1 | 2 | 0.3 | 1.31 | 0.3 |  | 1.91 | 0 | 22.92 | 0 | 0 | 0 | 0
| TOP | 10 |  | 6 | 1 | 2 | 0.3 | 1.31 | 0.3 |  | 1.91 | 0 | 22.92 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 6 | 1 | 7 |  | 1.008 |  |  | 1.008 | 42.34 | 0 | 0 | 0 | 0 | 0
200X450 | PB4 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 1.865 | 0.3 |  | 2.465 | 0 | 0 | 0 | 9.86 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 1.865 | 0.3 |  | 2.465 | 0 | 0 | 0 | 9.86 | 0 | 0
| STIRRUPS | 8 | 125 | 2 | 1 | 12 |  | 1.188 |  |  | 1.188 | 28.51 | 0 | 0 | 0 | 0 | 0
200X450 | PB5 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 3.54 | 0.3 |  | 4.14 | 0 | 0 | 16.56 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 3.54 | 0.3 |  | 4.14 | 0 | 0 | 16.56 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.188 |  |  | 1.188 | 23.76 | 0 | 0 | 0 | 0 | 0
200X450 | PB6 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 1 | 1 | 2 | 0.3 | 18.91 | 0.3 | 0.588 | 20.098 | 0 | 0 | 40.2 | 0 | 0 | 0
| TOP | 12 |  | 1 | 1 | 2 | 0.3 | 18.91 | 0.3 | 0.588 | 20.098 | 0 | 0 | 40.2 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 2 | 23 |  | 1.188 |  |  | 1.188 | 54.65 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 17 |  | 1.188 |  |  | 1.188 | 40.39 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 2 | 32 |  | 1.188 |  |  | 1.188 | 76.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 22 |  | 1.188 |  |  | 1.188 | 52.27 | 0 | 0 | 0 | 0 | 0
200X450 | PB7 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 7.145 | 0.3 |  | 7.745 | 0 | 0 | 0 | 30.98 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 7.145 | 0.3 |  | 7.745 | 0 | 0 | 0 | 30.98 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 8 |  | 1.188 |  |  | 1.188 | 19.01 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 9 |  | 1.188 |  |  | 1.188 | 21.38 | 0 | 0 | 0 | 0 | 0
200X450 | PB8 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 4.06 | 0.3 |  | 4.66 | 0 | 0 | 0 | 18.64 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 4.06 | 0.3 |  | 4.66 | 0 | 0 | 0 | 18.64 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.188 |  |  | 1.188 | 23.76 | 0 | 0 | 0 | 0 | 0
200X450 | PB9 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 6.305 | 0.3 |  | 6.905 | 0 | 0 | 0 | 27.62 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 6.305 | 0.3 |  | 6.905 | 0 | 0 | 0 | 27.62 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 21 |  | 1.188 |  |  | 1.188 | 49.9 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 15 |  | 1.188 |  |  | 1.188 | 35.64 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 16 |  | 1.188 |  |  | 1.188 | 38.02 | 0 | 0 | 0 | 0 | 0
200X450 | PB10 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 5.83 | 0.3 |  | 6.43 | 0 | 0 | 0 | 25.72 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 5.83 | 0.3 |  | 6.43 | 0 | 0 | 0 | 25.72 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 23 |  | 1.188 |  |  | 1.188 | 54.65 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 17 |  | 1.188 |  |  | 1.188 | 40.39 | 0 | 0 | 0 | 0 | 0
200X450 | PB11 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.3 | 12.89 | 0.3 | 0.784 | 14.274 | 0 | 0 | 0 | 28.55 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.3 | 12.89 | 0.3 | 0.784 | 14.274 | 0 | 0 | 0 | 28.55 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 2 | 2 |  | 1.46 |  |  | 1.46 | 0 | 0 | 5.84 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 |  | 3.83 |  |  | 3.83 | 0 | 0 | 7.66 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 2 | 2 | 0.3 | 2.37 |  |  | 2.67 | 0 | 0 | 10.68 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 2 | 29 |  | 1.188 |  |  | 1.188 | 68.9 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 20 |  | 1.188 |  |  | 1.188 | 47.52 | 0 | 0 | 0 | 0 | 0
200X450 | PB12 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 3.645 | 0.3 |  | 4.245 | 0 | 0 | 0 | 16.98 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 3.645 | 0.3 |  | 4.245 | 0 | 0 | 0 | 16.98 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 23 |  | 1.188 |  |  | 1.188 | 54.65 | 0 | 0 | 0 | 0 | 0
200X450 | PB13 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 4 | 0.3 |  | 4.6 | 0 | 0 | 0 | 18.4 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 4 | 0.3 |  | 4.6 | 0 | 0 | 0 | 18.4 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 31 |  | 1.188 |  |  | 1.188 | 73.66 | 0 | 0 | 0 | 0 | 0
200X450 | PB14 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 6 | 1 | 2 | 0.3 | 8.795 | 0.3 |  | 9.395 | 0 | 0 | 0 | 112.74 | 0 | 0
| TOP | 16 |  | 6 | 1 | 2 | 0.3 | 8.795 | 0.3 |  | 9.395 | 0 | 0 | 0 | 112.74 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 22 |  | 1.188 |  |  | 1.188 | 156.82 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 1 | 16 |  | 1.188 |  |  | 1.188 | 114.05 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 18 |  | 1.188 |  |  | 1.188 | 128.3 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 1 | 11 |  | 1.188 |  |  | 1.188 | 78.41 | 0 | 0 | 0 | 0 | 0
200X450 | PB15 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 3.655 | 0.3 |  | 4.255 | 0 | 0 | 17.02 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 3.655 | 0.3 |  | 4.255 | 0 | 0 | 17.02 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.188 |  |  | 1.188 | 23.76 | 0 | 0 | 0 | 0 | 0
230X450 | PB16 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 6.1 | 0.3 |  | 6.7 | 0 | 0 | 0 | 26.8 | 0 | 0
| TOP | 20 |  | 2 | 1 | 3 | 0.3 | 6.1 | 0.3 |  | 6.7 | 0 | 0 | 0 | 0 | 40.2 | 0
| STIRRUPS 230X450 | 8 | 100 | 2 | 1 | 18 |  | 1.248 |  |  | 1.248 | 44.93 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 7 |  | 1.248 |  |  | 1.248 | 17.47 | 0 | 0 | 0 | 0 | 0
230X450 | PB17 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.3 | 35.49 | 0.3 | 1.568 | 37.658 | 0 | 0 | 0 | 75.32 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.3 | 35.49 | 0.3 | 1.568 | 37.658 | 0 | 0 | 0 | 75.32 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 2 | 2 |  | 4.165 |  |  | 4.165 | 0 | 0 | 16.66 | 0 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 2 | 2 |  | 4.06 |  |  | 4.06 | 0 | 0 | 16.24 | 0 | 0 | 0
| TOP EXTRA | 16 |  | 1 | 1 | 2 |  | 3.63 | 0.3 |  | 3.93 | 0 | 0 | 0 | 7.86 | 0 | 0
| TOP EXTRA | 16 |  | 1 | 2 | 2 |  | 4 | 0.3 |  | 4.3 | 0 | 0 | 0 | 17.2 | 0 | 0
| TOP EXTRA | 16 |  | 1 | 2 | 2 |  | 2.7 | 0.3 |  | 3 | 0 | 0 | 0 | 12 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 2 | 39 |  | 1.248 |  |  | 1.248 | 97.34 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 2 | 29 |  | 1.248 |  |  | 1.248 | 72.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 21 |  | 1.248 |  |  | 1.248 | 52.42 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 2 | 29 |  | 1.248 |  |  | 1.248 | 72.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 20 |  | 1.248 |  |  | 1.248 | 49.92 | 0 | 0 | 0 | 0 | 0
200X450 | PB18 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 9.36 | 0.3 |  | 9.96 | 0 | 0 | 0 | 39.84 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 9.36 | 0.3 |  | 9.96 | 0 | 0 | 0 | 39.84 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 3.54 |  |  | 3.54 | 0 | 0 | 14.16 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 1 | 2 |  | 2.9 |  |  | 2.9 | 0 | 0 | 11.6 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 1 | 2 |  | 1.97 | 0.3 |  | 2.27 | 0 | 0 | 9.08 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 11 |  | 1.188 |  |  | 1.188 | 26.14 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 23 |  | 1.188 |  |  | 1.188 | 54.65 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 17 |  | 1.188 |  |  | 1.188 | 40.39 | 0 | 0 | 0 | 0 | 0
200X450 | PB19 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 6.17 | 0.3 |  | 6.77 | 0 | 0 | 0 | 27.08 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 6.17 | 0.3 |  | 6.77 | 0 | 0 | 0 | 27.08 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 4.53 |  |  | 4.53 | 0 | 0 | 18.12 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 2 | 2 |  | 1.87 | 0.3 |  | 2.17 | 0 | 0 | 17.36 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 28 |  | 1.188 |  |  | 1.188 | 66.53 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 20 |  | 1.188 |  |  | 1.188 | 47.52 | 0 | 0 | 0 | 0 | 0
200X450 | PB20 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 8.54 | 0.3 |  | 9.14 | 0 | 0 | 0 | 36.56 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 8.54 | 0.3 |  | 9.14 | 0 | 0 | 0 | 36.56 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 4.28 |  |  | 4.28 | 0 | 0 | 17.12 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 1 | 2 |  | 1.97 | 0.3 |  | 2.27 | 0 | 0 | 9.08 | 0 | 0 | 0
|  | 12 |  | 2 | 1 | 2 |  | 2.5 |  |  | 2.5 | 0 | 0 | 10 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 22 |  | 1.188 |  |  | 1.188 | 52.27 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 28 |  | 1.188 |  |  | 1.188 | 66.53 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 20 |  | 1.188 |  |  | 1.188 | 47.52 | 0 | 0 | 0 | 0 | 0
200X450 | PB21 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 6 | 1 | 2 | 0.3 | 8.795 | 0.3 |  | 9.395 | 0 | 0 | 0 | 112.74 | 0 | 0
| TOP | 16 |  | 6 | 1 | 2 | 0.3 | 8.795 | 0.3 |  | 9.395 | 0 | 0 | 0 | 112.74 | 0 | 0
| BOTTOM EXTRA | 12 |  | 6 | 1 | 2 |  | 3.57 |  |  | 3.57 | 0 | 0 | 42.84 | 0 | 0 | 0
| TOP EXTRA | 16 |  | 6 | 1 | 2 |  | 2.6 |  |  | 2.6 | 0 | 0 | 0 | 31.2 | 0 | 0
|  | 16 |  | 6 | 1 | 2 | 0.3 | 1.67 |  |  | 1.97 | 0 | 0 | 0 | 23.64 | 0 | 0
|  | 12 |  | 6 | 1 | 2 |  | 1.17 | 0.3 |  | 1.47 | 0 | 0 | 17.64 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 24 |  | 1.188 |  |  | 1.188 | 171.07 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 1 | 17 |  | 1.188 |  |  | 1.188 | 121.18 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 18 |  | 1.188 |  |  | 1.188 | 128.3 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 6 | 1 | 11 |  | 1.188 |  |  | 1.188 | 78.41 | 0 | 0 | 0 | 0 | 0
200X450 | PB22 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 6 | 1 | 2 | 0.3 | 6.885 | 0.3 |  | 7.485 | 0 | 0 | 0 | 89.82 | 0 | 0
| TOP | 16 |  | 6 | 1 | 2 | 0.3 | 6.885 | 0.3 |  | 7.485 | 0 | 0 | 0 | 89.82 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 18 |  | 1.188 |  |  | 1.188 | 128.3 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 1 | 10 |  | 1.188 |  |  | 1.188 | 71.28 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 18 |  | 1.188 |  |  | 1.188 | 128.3 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 6 | 1 | 6 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
200X450 | PB23 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 5.665 | 0.3 |  | 6.265 | 0 | 0 | 0 | 25.06 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 5.665 | 0.3 |  | 6.265 | 0 | 0 | 0 | 25.06 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 4.14 |  |  | 4.14 | 0 | 0 | 16.56 | 0 | 0 | 0
| TOP EXTRA | 16 |  | 2 | 2 | 2 | 0.3 | 1.77 |  |  | 2.07 | 0 | 0 | 0 | 16.56 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 23 |  | 1.188 |  |  | 1.188 | 54.65 | 0 | 0 | 0 | 0 | 0
200X450 | PB24 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 20 |  | 2 | 1 | 2 | 0.3 | 1.87 | 0.3 |  | 2.47 | 0 | 0 | 0 | 0 | 9.88 | 0
| TOP | 20 |  | 2 | 1 | 2 | 0.3 | 1.87 | 0.3 |  | 2.47 | 0 | 0 | 0 | 0 | 9.88 | 0
| STIRRUPS 200X450 | 8 | 125 | 2 | 1 | 12 |  | 1.188 |  |  | 1.188 | 28.51 | 0 | 0 | 0 | 0 | 0
200X450 | PB25 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 11.295 | 0.3 |  | 11.895 | 0 | 0 | 0 | 47.58 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 11.295 | 0.3 |  | 11.895 | 0 | 0 | 0 | 47.58 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 41 |  | 1.188 |  |  | 1.188 | 97.42 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 30 |  | 1.188 |  |  | 1.188 | 71.28 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 2 | 1 | 18 |  | 1.312 |  |  | 1.312 | 47.23 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 150 | 2 | 1 | 9 |  | 1.312 |  |  | 1.312 | 23.62 | 0 | 0 | 0 | 0 | 0
230X450 | PB26 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.3 | 18.85 | 0.3 | 0.784 | 20.234 | 0 | 0 | 0 | 40.47 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.3 | 18.85 | 0.3 | 0.784 | 20.234 | 0 | 0 | 0 | 40.47 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 2 | 4 |  | 1.248 |  |  | 1.248 | 9.98 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 2 | 23 |  | 1.248 |  |  | 1.248 | 57.41 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 150 | 1 | 2 | 17 |  | 1.248 |  |  | 1.248 | 42.43 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 1 | 32 |  | 1.248 |  |  | 1.248 | 39.94 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 150 | 1 | 1 | 22 |  | 1.248 |  |  | 1.248 | 27.46 | 0 | 0 | 0 | 0 | 0
230X450 | PB27 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 4.35 | 0.3 |  | 4.95 | 0 | 0 | 0 | 19.8 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 4.35 | 0.3 |  | 4.95 | 0 | 0 | 0 | 19.8 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 2 | 1 | 18 |  | 1.248 |  |  | 1.248 | 44.93 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 13 |  | 1.248 |  |  | 1.248 | 32.45 | 0 | 0 | 0 | 0 | 0
200X450 | PB28 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 3.775 | 0.3 |  | 4.375 | 0 | 0 | 17.5 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 3.775 | 0.3 |  | 4.375 | 0 | 0 | 17.5 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 9 |  | 1.188 |  |  | 1.188 | 21.38 | 0 | 0 | 0 | 0 | 0
200X450 | PB29 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 11.04 | 0.3 |  | 11.64 | 0 | 0 | 0 | 46.56 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 11.04 | 0.3 |  | 11.64 | 0 | 0 | 0 | 46.56 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 3.85 |  |  | 3.85 | 0 | 0 | 15.4 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 1 | 2 |  | 3.3 |  |  | 3.3 | 0 | 0 | 13.2 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 2 | 2 | 0.3 | 1.77 |  |  | 2.07 | 0 | 0 | 16.56 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 2 | 26 |  | 1.188 |  |  | 1.188 | 123.55 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 2 | 18 |  | 1.188 |  |  | 1.188 | 85.54 | 0 | 0 | 0 | 0 | 0
200X450 | PB30 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 7.02 | 0.3 |  | 7.62 | 0 | 0 | 0 | 30.48 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 7.02 | 0.3 |  | 7.62 | 0 | 0 | 0 | 30.48 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 2 | 18 |  | 1.188 |  |  | 1.188 | 85.54 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 2 | 10 |  | 1.188 |  |  | 1.188 | 47.52 | 0 | 0 | 0 | 0 | 0
200X450 | PB31 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 6 | 1 | 2 | 0.3 | 8.98 | 0.3 |  | 9.58 | 0 | 0 | 114.96 | 0 | 0 | 0
| TOP | 12 |  | 6 | 1 | 2 | 0.3 | 8.98 | 0.3 |  | 9.58 | 0 | 0 | 114.96 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 18 |  | 1.188 |  |  | 1.188 | 128.3 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 1 | 13 |  | 1.188 |  |  | 1.188 | 92.66 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 19 |  | 1.188 |  |  | 1.188 | 135.43 | 0 | 0 | 0 | 0 | 0
100X450 | PB32 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 18 | 1 | 2 | 0.3 | 0.655 | 0.3 |  | 1.255 | 0 | 0 | 45.18 | 0 | 0 | 0
| TOP | 12 |  | 18 | 1 | 2 | 0.3 | 0.655 | 0.3 |  | 1.255 | 0 | 0 | 45.18 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 18 | 1 | 5 |  | 1.008 |  |  | 1.008 | 90.72 | 0 | 0 | 0 | 0 | 0
200X450 | PB33 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 6 | 1 | 2 | 0.3 | 3.89 | 0.3 |  | 4.49 | 0 | 0 | 53.88 | 0 | 0 | 0
| TOP | 12 |  | 6 | 1 | 2 | 0.3 | 3.89 | 0.3 |  | 4.49 | 0 | 0 | 53.88 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 2 | 18 |  | 1.188 |  |  | 1.188 | 256.61 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 2 | 12 |  | 1.188 |  |  | 1.188 | 171.07 | 0 | 0 | 0 | 0 | 0
200X450 | PB34 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 6 | 1 | 2 | 0.3 | 4.2 | 0.3 |  | 4.8 | 0 | 0 | 0 | 57.6 | 0 | 0
| TOP | 16 |  | 6 | 1 | 2 | 0.3 | 4.2 | 0.3 |  | 4.8 | 0 | 0 | 0 | 57.6 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 18 |  | 1.188 |  |  | 1.188 | 128.3 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 1 | 9 |  | 1.188 |  |  | 1.188 | 64.15 | 0 | 0 | 0 | 0 | 0
200X450 | PB35 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 11.97 | 0.3 | 0.784 | 13.354 | 0 | 0 | 0 | 53.42 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 11.97 | 0.3 | 0.784 | 13.354 | 0 | 0 | 0 | 53.42 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 2.93 |  |  | 2.93 | 0 | 0 | 11.72 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 2 | 2 |  | 2.85 |  |  | 2.85 | 0 | 0 | 22.8 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 31 |  | 1.188 |  |  | 1.188 | 73.66 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 21 |  | 1.188 |  |  | 1.188 | 49.9 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 15 |  | 1.188 |  |  | 1.188 | 35.64 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 9 |  | 1.188 |  |  | 1.188 | 21.38 | 0 | 0 | 0 | 0 | 0
200X450 | PB36 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 6 | 1 | 2 | 0.3 | 4.715 | 0.3 |  | 5.315 | 0 | 0 | 0 | 63.78 | 0 | 0
| TOP | 16 |  | 6 | 1 | 2 | 0.3 | 4.715 | 0.3 |  | 5.315 | 0 | 0 | 0 | 63.78 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 20 |  | 1.188 |  |  | 1.188 | 142.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 1 | 10 |  | 1.188 |  |  | 1.188 | 71.28 | 0 | 0 | 0 | 0 | 0
200X450 | PB37 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 6 | 1 | 2 | 0.3 | 5.13 | 0.3 |  | 5.73 | 0 | 0 | 68.76 | 0 | 0 | 0
| TOP | 12 |  | 6 | 1 | 2 | 0.3 | 5.13 | 0.3 |  | 5.73 | 0 | 0 | 68.76 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 47 |  | 1.188 |  |  | 1.188 | 335.02 | 0 | 0 | 0 | 0 | 0
200X450 | PB38 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 6.685 | 0.3 |  | 7.285 | 0 | 0 | 29.14 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 6.685 | 0.3 |  | 7.285 | 0 | 0 | 29.14 | 0 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 4.245 |  |  | 4.245 | 0 | 0 | 16.98 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 2 | 2 |  | 2.22 | 0.3 |  | 2.52 | 0 | 0 | 20.16 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 26 |  | 1.188 |  |  | 1.188 | 61.78 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
200X450 | PB39 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 2.4 | 0.944 |  | 3.644 | 0 | 0 | 14.58 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 2.4 | 0.944 |  | 3.644 | 0 | 0 | 14.58 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 23 |  | 1.188 |  |  | 1.188 | 54.65 | 0 | 0 | 0 | 0 | 0
200X450 | PB40 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 6.07 | 0.3 |  | 6.67 | 0 | 0 | 0 | 26.68 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 6.07 | 0.3 |  | 6.67 | 0 | 0 | 0 | 26.68 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 51 |  | 1.188 |  |  | 1.188 | 121.18 | 0 | 0 | 0 | 0 | 0
200X450 | PB41 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 6.585 | 0.3 |  | 7.185 | 0 | 0 | 0 | 28.74 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 6.585 | 0.3 |  | 7.185 | 0 | 0 | 0 | 28.74 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 4.245 |  |  | 4.245 | 0 | 0 | 16.98 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 2 | 2 |  | 2.22 | 0.3 |  | 2.52 | 0 | 0 | 20.16 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 26 |  | 1.188 |  |  | 1.188 | 61.78 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
230X450 | PB42 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 4.12 | 0.3 |  | 4.72 | 0 | 0 | 0 | 18.88 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 4.12 | 0.3 |  | 4.72 | 0 | 0 | 0 | 18.88 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 2 | 1 | 18 |  | 1.248 |  |  | 1.248 | 44.93 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.248 |  |  | 1.248 | 24.96 | 0 | 0 | 0 | 0 | 0
200X450 | PB43 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 3.39 | 0.3 |  | 3.99 | 0 | 0 | 15.96 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 3.39 | 0.3 |  | 3.99 | 0 | 0 | 15.96 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 9 |  | 1.188 |  |  | 1.188 | 21.38 | 0 | 0 | 0 | 0 | 0
200X450 | PB44 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 5.69 | 0.3 |  | 6.29 | 0 | 0 | 0 | 25.16 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 5.69 | 0.3 |  | 6.29 | 0 | 0 | 0 | 25.16 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 19 |  | 1.188 |  |  | 1.188 | 45.14 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 14 |  | 1.188 |  |  | 1.188 | 33.26 | 0 | 0 | 0 | 0 | 0
200X450 | PB45 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 5.69 | 0.3 |  | 6.29 | 0 | 0 | 0 | 25.16 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 5.69 | 0.3 |  | 6.29 | 0 | 0 | 0 | 25.16 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 23 |  | 1.188 |  |  | 1.188 | 54.65 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 16 |  | 1.188 |  |  | 1.188 | 38.02 | 0 | 0 | 0 | 0 | 0
200X450 | PB46 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 3.89 | 0.3 |  | 4.49 | 0 | 0 | 0 | 17.96 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 3.89 | 0.3 |  | 4.49 | 0 | 0 | 0 | 17.96 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 9 |  | 1.188 |  |  | 1.188 | 21.38 | 0 | 0 | 0 | 0 | 0
200X450 | PB47 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 4.255 | 0.3 |  | 4.855 | 0 | 0 | 19.42 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 4.255 | 0.3 |  | 4.855 | 0 | 0 | 19.42 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.188 |  |  | 1.188 | 23.76 | 0 | 0 | 0 | 0 | 0
200X450 | PB48 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.2 | 2.715 | 0.2 |  | 3.115 | 0 | 0 | 12.46 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.2 | 2.715 | 0.2 |  | 3.115 | 0 | 0 | 12.46 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 15 |  | 1.188 |  |  | 1.188 | 35.64 | 0 | 0 | 0 | 0 | 0
230X450 | PB49 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 0.69 | 0.3 |  | 1.29 | 0 | 0 | 5.16 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 0.69 | 0.3 |  | 1.29 | 0 | 0 | 5.16 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 8 |  | 1.248 |  |  | 1.248 | 19.97 | 0 | 0 | 0 | 0 | 0
230X450 | PB50 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.944 | 2.33 | 0.3 |  | 3.574 | 0 | 0 | 14.3 | 0 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.944 | 2.33 | 0.3 |  | 3.574 | 0 | 0 | 0 | 14.3 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 23 |  | 1.248 |  |  | 1.248 | 57.41 | 0 | 0 | 0 | 0 | 0
230X450 | PB51 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 4.12 | 0.3 |  | 4.72 | 0 | 0 | 0 | 18.88 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 4.12 | 0.3 |  | 4.72 | 0 | 0 | 0 | 18.88 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 2 | 1 | 18 |  | 1.248 |  |  | 1.248 | 44.93 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.248 |  |  | 1.248 | 24.96 | 0 | 0 | 0 | 0 | 0
230X450 | PB 52 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 18.915 | 0.3 | 0.784 | 20.299 | 0 | 0 | 0 | 81.2 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 18.915 | 0.3 | 0.784 | 20.299 | 0 | 0 | 0 | 81.2 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 2 | 1 | 18 |  | 1.248 |  |  | 1.248 | 44.93 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 6 |  | 1.248 |  |  | 1.248 | 14.98 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 2 | 18 |  | 1.188 |  |  | 1.188 | 85.54 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 2 | 12 |  | 1.188 |  |  | 1.188 | 57.02 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.188 |  |  | 1.188 | 23.76 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 20 |  | 1.188 |  |  | 1.188 | 47.52 | 0 | 0 | 0 | 0 | 0
200X450 | PB53 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 4 | 1 | 2 | 0.3 | 3.165 | 0.3 |  | 3.765 | 0 | 0 | 30.12 | 0 | 0 | 0
| TOP | 12 |  | 4 | 1 | 2 | 0.3 | 3.165 | 0.3 |  | 3.765 | 0 | 0 | 30.12 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 4 | 1 | 23 |  | 1.188 |  |  | 1.188 | 109.3 | 0 | 0 | 0 | 0 | 0
200X450 | PB54 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 3.9 | 0.3 |  | 4.5 | 0 | 0 | 18 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 3.9 | 0.3 |  | 4.5 | 0 | 0 | 18 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 8 |  | 1.188 |  |  | 1.188 | 19.01 | 0 | 0 | 0 | 0 | 0
200X450 | PB55 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 3.9 | 0.3 |  | 4.5 | 0 | 0 | 0 | 18 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 3.9 | 0.3 |  | 4.5 | 0 | 0 | 0 | 18 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 8 |  | 1.188 |  |  | 1.188 | 19.01 | 0 | 0 | 0 | 0 | 0
200X450 | PB56 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 2.03 | 0.3 |  | 2.63 | 0 | 0 | 10.52 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 2.03 | 0.3 |  | 2.63 | 0 | 0 | 10.52 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 19 |  | 1.188 |  |  | 1.188 | 45.14 | 0 | 0 | 0 | 0 | 0
200X450 | PB57 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 4 | 1 | 2 | 0.3 | 3.59 | 0.3 |  | 4.19 | 0 | 0 | 0 | 33.52 | 0 | 0
| TOP | 16 |  | 4 | 1 | 2 | 0.3 | 3.59 | 0.3 |  | 4.19 | 0 | 0 | 0 | 33.52 | 0 | 0
| STIRRUPS | 8 | 100 | 4 | 1 | 18 |  | 1.188 |  |  | 1.188 | 85.54 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
200X450 | PB58 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 7.34 | 0.3 |  | 7.94 | 0 | 0 | 0 | 31.76 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 7.34 | 0.3 |  | 7.94 | 0 | 0 | 0 | 31.76 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 34 |  | 1.188 |  |  | 1.188 | 80.78 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 12 |  | 1.188 |  |  | 1.188 | 28.51 | 0 | 0 | 0 | 0 | 0
200X450 | PB59 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 7.34 | 0.3 |  | 7.94 | 0 | 0 | 31.76 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 7.34 | 0.3 |  | 7.94 | 0 | 0 | 31.76 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 65 |  | 1.188 |  |  | 1.188 | 154.44 | 0 | 0 | 0 | 0 | 0
200X450 | PB60 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 4 | 1 | 2 | 0.3 | 5.49 | 0.3 |  | 6.09 | 0 | 0 | 48.72 | 0 | 0 | 0
| TOP | 12 |  | 4 | 1 | 2 | 0.3 | 5.49 | 0.3 |  | 6.09 | 0 | 0 | 48.72 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 4 | 1 | 18 |  | 1.188 |  |  | 1.188 | 85.54 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 4 | 1 | 18 |  | 1.188 |  |  | 1.188 | 85.54 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
200X450 | PB61 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 3.54 | 0.3 |  | 4.14 | 0 | 0 | 16.56 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 3.54 | 0.3 |  | 4.14 | 0 | 0 | 16.56 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.188 |  |  | 1.188 | 23.76 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL UPTO PLINTH | [10 empty] | 3492.1437 | 131.6925 | 1475.6962 | 4761.2984 | 147.5016 | 0 | 10008.3323
[6 empty] | 178.6 | 6 | 1071.6
[6 empty] | 160 | 5 | 800
[6 empty] | 87 | 4.5 | 391.5
[6 empty] | 78.6 | 4.5 | 353.7
[6 empty] | 135 | 4.5 | 607.5
[6 empty] | 20 | 8.5 | 170
[6 empty] | 90 | 4.5 | 405
[6 empty] | 90 | 4.5 | 405
[6 empty] | 137.5 | 4.5 | 618.75
[6 empty] | 100 | 4.5 | 450
[6 empty] | 92 | 4.5 | 414
[6 empty] | 50 | 6 | 300
[6 empty] | 60 | 6 | 360
[6 empty] | 129 | 5 | 645
[6 empty] | 118 | 4.5 | 531
[6 empty] | 115 | 4.5 | 517.5
[6 empty] | 95 | 4.5 | 427.5
[6 empty] | 86 | 4.5 | 387
[6 empty] | 156 | 4.5 | 702
[6 empty] | 153 | 6 | 918
[6 empty] | 78 | 4.5 | 351
[6 empty] | 61 | 4.5 | 274.5
[8 empty] | 11100.55 | 119486.3202

## TYP COL BBS
Reinforcement
Sr. No. | Designation | Dia | C/C (mm) | No | No | No of Bars | Bar Length (mtr) |  |  | Lap Length | One Bar Length (MTR) | Dia Wise Weight (Kg)
[7 empty] | a | b | c |  |  | 8mm | 10mm | 12mm | 16mm | 20MM | 25mm
Column From Plinth Level to 1st Floor Lvl (103.25-100.15)
28 | C 1 (300X600) | 16 |  | 28 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 789.82 | 0 | 0 | 224 | 789.824
|  | 12 |  | 28 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 568.18 | 0 | 0 | 0 | 168
| Stirrups ZONE A | 10 | 75 | 28 | 2 | 12 |  | 1.64 |  |  | 1.64 | 0 | 1102.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 389.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 4 | 8 |  | 0.716 |  |  | 0.716 | 0 | 641.54 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 28 | 1 | 10 |  | 1.608 |  |  | 1.608 | 450.24 | 0 | 0 | 0 | 0 | 0 |  | 450.24
|  | 8 | 150 | 28 | 1 | 10 |  | 0.828 |  |  | 0.828 | 231.84 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 2 | 10 |  | 0.684 |  |  | 0.684 | 383.04 | 0 | 0 | 0 | 0 | 0
12 | C 2 (300X600) | 20 |  | 12 | 1 | 6 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 264.24 | 0 | 72
|  | 16 |  | 12 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 338.5 | 0 | 0 | 96
| Stirrups ZONE A | 10 | 75 | 12 | 2 | 12 |  | 1.64 |  |  | 1.64 | 0 | 472.32 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 167.04 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 4 | 8 |  | 0.716 |  |  | 0.716 | 0 | 274.94 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 12 | 1 | 10 |  | 1.608 |  |  | 1.608 | 192.96 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 1 | 10 |  | 0.828 |  |  | 0.828 | 99.36 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 2 | 10 |  | 0.684 |  |  | 0.684 | 164.16 | 0 | 0 | 0 | 0 | 0
4 | C 3 (300X600) | 25 |  | 4 | 1 | 14 |  | 2.95 |  | 0.9 | 3.85 | 0 | 0 | 0 | 0 | 0 | 215.6 | 56
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 12 |  | 1.64 |  |  | 1.64 | 0 | 157.44 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 55.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.716 |  |  | 0.716 | 0 | 91.65 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 10 |  | 1.608 |  |  | 1.608 | 64.32 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 10 |  | 0.838 |  |  | 0.838 | 33.52 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 10 |  | 0.684 |  |  | 0.684 | 54.72 | 0 | 0 | 0 | 0 | 0
16 | C 4 (300X750) | 20 |  | 16 | 1 | 16 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 939.52 | 0 | 256
| Stirrups ZONE A | 10 | 75 | 16 | 2 | 14 |  | 1.94 |  |  | 1.94 | 0 | 869.12 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 1.1 |  |  | 1.1 | 0 | 352 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 4 | 10 |  | 0.716 |  |  | 0.716 | 0 | 458.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 134.4 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 16 | 1 | 8 |  | 1.908 |  |  | 1.908 | 244.22 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 8 |  | 1.068 |  |  | 1.068 | 136.7 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 2 | 8 |  | 0.684 |  |  | 0.684 | 175.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 8 |  | 0.38 |  |  | 0.38 | 48.64 | 0 | 0 | 0 | 0 | 0
14 | C 5 (300X750) | 16 |  | 14 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 493.64 | 0 | 0 | 140
|  | 12 |  | 14 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 284.09 | 0 | 0 | 0 | 84
| Stirrups ZONE A | 10 | 75 | 14 | 2 | 14 |  | 1.94 |  |  | 1.94 | 0 | 760.48 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 1.1 |  |  | 1.1 | 0 | 308 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 4 | 10 |  | 0.716 |  |  | 0.716 | 0 | 400.96 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 117.6 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 14 | 1 | 8 |  | 1.908 |  |  | 1.908 | 213.7 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 8 |  | 1.068 |  |  | 1.068 | 119.62 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 2 | 8 |  | 0.684 |  |  | 0.684 | 153.22 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 8 |  | 0.38 |  |  | 0.38 | 42.56 | 0 | 0 | 0 | 0 | 0
10 | C 6 (300X715) | 16 |  | 10 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0 | 40
|  | 12 |  | 10 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 405.84 | 0 | 0 | 0 | 120
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 14 |  | 1.87 |  |  | 1.87 | 0 | 523.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 1.07 |  |  | 1.07 | 0 | 214 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 10 |  | 0.716 |  |  | 0.716 | 0 | 286.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 84 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 9 |  | 1.838 |  |  | 1.838 | 165.42 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 9 |  | 1.038 |  |  | 1.038 | 93.42 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 9 |  | 0.684 |  |  | 0.684 | 123.12 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 9 |  | 0.38 |  |  | 0.38 | 34.2 | 0 | 0 | 0 | 0 | 0
4 | C 7 (300X800) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 4 | 1 | 14 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 189.39 | 0 | 0 | 0 | 56
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 15 |  | 2.04 |  |  | 2.04 | 0 | 244.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.87 |  |  | 0.87 | 0 | 153.12 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.716 |  |  | 0.716 | 0 | 126.02 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 8 |  | 2.008 |  |  | 2.008 | 64.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 8 |  | 0.828 |  |  | 0.828 | 52.99 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 8 |  | 0.684 |  |  | 0.684 | 43.78 | 0 | 0 | 0 | 0 | 0
4 | C 8 (300X600) | 20 |  | 4 | 1 | 10 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 146.8 | 0 | 40
|  | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 12 |  | 1.64 |  |  | 1.64 | 0 | 157.44 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 55.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.716 |  |  | 0.716 | 0 | 91.65 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 10 |  | 1.608 |  |  | 1.608 | 64.32 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 10 |  | 0.828 |  |  | 0.828 | 33.12 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 10 |  | 0.684 |  |  | 0.684 | 54.72 | 0 | 0 | 0 | 0 | 0
4 | C 9 (300X600) | 20 |  | 4 | 1 | 4 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 58.72 | 0 | 16
|  | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0 | 32
|  | 12 |  | 4 | 1 | 2 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 27.06 | 0 | 0 | 0 | 8
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 12 |  | 1.64 |  |  | 1.64 | 0 | 157.44 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 55.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.716 |  |  | 0.716 | 0 | 91.65 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 10 |  | 1.608 |  |  | 1.608 | 64.32 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 10 |  | 0.828 |  |  | 0.828 | 33.12 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 10 |  | 0.684 |  |  | 0.684 | 54.72 | 0 | 0 | 0 | 0 | 0
10 | C 10 (300X600) | 25 |  | 10 | 1 | 4 |  | 2.95 |  | 0.9 | 3.85 | 0 | 0 | 0 | 0 | 0 | 154 | 40
|  | 20 |  | 10 | 1 | 10 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 367 | 0 | 100
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 12 |  | 1.64 |  |  | 1.64 | 0 | 393.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 139.2 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 8 |  | 0.716 |  |  | 0.716 | 0 | 229.12 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 10 |  | 1.608 |  |  | 1.608 | 160.8 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 10 |  | 0.828 |  |  | 0.828 | 82.8 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 10 |  | 0.684 |  |  | 0.684 | 136.8 | 0 | 0 | 0 | 0 | 0
4 | C 11 (300X715) | 16 |  | 4 | 1 | 14 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 197.46 | 0 | 0 | 56
|  | 12 |  | 4 | 1 | 2 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 27.06 | 0 | 0 | 0 | 8
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 14 |  | 1.87 |  |  | 1.87 | 0 | 209.44 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 1.07 |  |  | 1.07 | 0 | 85.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 10 |  | 0.716 |  |  | 0.716 | 0 | 114.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 33.6 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.838 |  |  | 1.838 | 66.17 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 1.102 |  |  | 1.102 | 39.67 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.684 |  |  | 0.684 | 49.25 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.38 |  |  | 0.38 | 13.68 | 0 | 0 | 0 | 0 | 0
| Shear wall from plinth level to 1st floor LVL | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | SW 1 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0 | 32
|  | 10 |  | 2 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 52.96 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 31 |  | 1.688 |  |  | 1.688 | 104.66 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X256) | 8 | 100 | 2 | 1 | 27 |  | 1 |  |  | 1 | 54 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 27 |  | 0.34 |  |  | 0.34 | 18.36 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 4 |  | 1.258 |  |  | 1.258 | 20.13 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 27 |  | 1.024 |  |  | 1.024 | 55.3 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 27 |  | 0.34 |  |  | 0.34 | 18.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X866) | 8 | 200 | 2 | 1 | 18 |  | 2.22 |  |  | 2.22 | 79.92 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
2 | SW 2 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0 | 32
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 31 |  | 1.688 |  |  | 1.688 | 104.66 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X256) | 8 | 100 | 2 | 1 | 27 |  | 1 |  |  | 1 | 54 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 27 |  | 0.34 |  |  | 0.34 | 18.36 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 31 |  | 1.258 |  |  | 1.258 | 155.99 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 27 |  | 1.024 |  |  | 1.024 | 55.3 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 27 |  | 0.34 |  |  | 0.34 | 18.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 2 | 1 | 18 |  | 2.62 |  |  | 2.62 | 94.32 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
2 | SW 3 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0 | 8
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0 | 32
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X950) | 8 | 100 | 2 | 1 | 31 |  | 2.388 |  |  | 2.388 | 148.06 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 2 | 4 | 27 |  | 0.728 |  |  | 0.728 | 157.25 | 0 | 0 | 0 | 0 | 0
2 | SW 4 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0 | 8
|  | 12 |  | 2 | 1 | 18 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 121.75 | 0 | 0 | 0 | 36
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1100) | 8 | 100 | 2 | 1 | 31 |  | 2.688 |  |  | 2.688 | 166.66 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X125) | 8 | 100 | 2 | 4 | 27 |  | 0.738 |  |  | 0.738 | 159.41 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 27 |  | 0.34 |  |  | 0.34 | 18.36 | 0 | 0 | 0 | 0 | 0
4 | SW 5A | 16 |  | 4 | 1 | 24 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 338.5 | 0 | 0 | 96
|  | 12 |  | 4 | 1 | 4 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0 | 16
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X583) | 8 | 100 | 4 | 2 | 31 |  | 1.654 |  |  | 1.654 | 410.19 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 4 | 4 | 27 |  | 0.728 |  |  | 0.728 | 314.5 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X516) | 8 | 200 | 4 | 1 | 18 |  | 1.52 |  |  | 1.52 | 109.44 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 4 | 2 | 7 |  | 0.34 |  |  | 0.34 | 19.04 | 0 | 0 | 0 | 0 | 0
4 | SW 6 | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0 | 32
|  | 12 |  | 4 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 216.45 | 0 | 0 | 0 | 64
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1135) | 8 | 100 | 4 | 1 | 31 |  | 2.758 |  |  | 2.758 | 341.99 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X118) | 8 | 100 | 4 | 5 | 27 |  | 0.724 |  |  | 0.724 | 390.96 | 0 | 0 | 0 | 0 | 0
2 | SW 7A | 16 |  | 2 | 1 | 24 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 169.25 | 0 | 0 | 48
|  | 12 |  | 2 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 40.58 | 0 | 0 | 0 | 12
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X583) | 8 | 100 | 2 | 2 | 31 |  | 1.654 |  |  | 1.654 | 205.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 2 | 4 | 27 |  | 0.732 |  |  | 0.732 | 158.11 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X671) | 8 | 200 | 2 | 1 | 18 |  | 1.83 |  |  | 1.83 | 65.88 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 1 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
1 | SW 8 | 16 |  | 1 | 1 | 40 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0 | 40
|  | 12 |  | 1 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 67.64 | 0 | 0 | 0 | 20
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1183) | 8 | 100 | 1 | 2 | 31 |  | 2.854 |  |  | 2.854 | 176.95 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 1 | 10 | 27 |  | 0.732 |  |  | 0.732 | 197.64 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1216) | 8 | 200 | 1 | 1 | 18 |  | 2.92 |  |  | 2.92 | 52.56 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 1 | 3 | 7 |  | 0.34 |  |  | 0.34 | 7.14 | 0 | 0 | 0 | 0 | 0
6 | SW 9 | 16 |  | 6 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 169.25 | 0 | 0 | 48
|  | 12 |  | 6 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0 | 96
|  | 10 |  | 6 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 198.6 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 6 | 1 | 31 |  | 1.688 |  |  | 1.688 | 313.97 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 6 | 1 | 27 |  | 0.984 |  |  | 0.984 | 159.41 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 27 |  | 0.34 |  |  | 0.34 | 55.08 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 6 | 2 | 31 |  | 1.258 |  |  | 1.258 | 467.98 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 6 | 1 | 27 |  | 1.024 |  |  | 1.024 | 165.89 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 27 |  | 0.34 |  |  | 0.34 | 55.08 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 6 | 1 | 18 |  | 2.62 |  |  | 2.62 | 282.96 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 6 | 2 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
2 | SW 10 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 2 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0 | 40
|  | 10 |  | 2 | 1 | 20 |  | 2.95 |  | 0.36 | 3.31 | 0 | 132.4 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X683) | 8 | 100 | 2 | 2 | 31 |  | 1.854 |  |  | 1.854 | 229.9 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X128) | 8 | 100 | 2 | 4 | 27 |  | 0.744 |  |  | 0.744 | 160.7 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 27 |  | 0.34 |  |  | 0.34 | 36.72 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2061) | 8 | 200 | 2 | 1 | 18 |  | 4.61 |  |  | 4.61 | 165.96 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 5 | 7 |  | 0.34 |  |  | 0.34 | 23.8 | 0 | 0 | 0 | 0 | 0
2 | SW 11 | 16 |  | 2 | 1 | 16 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0 | 32
|  | 12 |  | 2 | 1 | 24 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 162.34 | 0 | 0 | 0 | 48
|  | 10 |  | 2 | 1 | 20 |  | 2.95 |  | 0.36 | 3.31 | 0 | 132.4 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X983) | 8 | 100 | 2 | 2 | 31 |  | 2.454 |  |  | 2.454 | 304.3 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X124) | 8 | 100 | 2 | 8 | 27 |  | 0.736 |  |  | 0.736 | 317.95 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2081) | 8 | 200 | 2 | 1 | 18 |  | 4.65 |  |  | 4.65 | 167.4 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 5 | 7 |  | 0.34 |  |  | 0.34 | 23.8 | 0 | 0 | 0 | 0 | 0
2 | SW 12 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0 | 32
|  | 10 |  | 2 | 1 | 6 |  | 2.95 |  | 0.36 | 3.31 | 0 | 39.72 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 31 |  | 1.688 |  |  | 1.688 | 104.66 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 27 |  | 0.984 |  |  | 0.984 | 53.14 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 27 |  | 0.34 |  |  | 0.34 | 18.36 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 31 |  | 1.258 |  |  | 1.258 | 155.99 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 27 |  | 1.024 |  |  | 1.024 | 55.3 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 27 |  | 0.34 |  |  | 0.34 | 18.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X751) | 8 | 200 | 2 | 1 | 18 |  | 1.99 |  |  | 1.99 | 71.64 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 1 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
2 | SW 13 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0 | 32
|  | 10 |  | 2 | 1 | 22 |  | 2.95 |  | 0.36 | 3.31 | 0 | 145.64 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (140X583) | 8 | 100 | 2 | 2 | 31 |  | 1.608 |  |  | 1.608 | 199.39 | 0 | 0 | 0 | 0 | 0
| BE OTHER (140X133) | 8 | 100 | 2 | 4 | 27 |  | 0.674 |  |  | 0.674 | 145.58 | 0 | 0 | 0 | 0 | 0
| MID MAIN (140X2261) | 8 | 200 | 2 | 1 | 18 |  | 4.93 |  |  | 4.93 | 177.48 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 5 | 7 |  | 0.3 |  |  | 0.3 | 21 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL FROM PLINTH TO 1ST FLOOR LVL | [10 empty] | 4818.3996 | 6767.1141 | 2814.1651 | 5637.993 | 4369.6488 | 1422.96 | 25830.2805
Column From 1st Floor Lvl TO 2ND FLOOR LVL (103.25-106.2)
| C 1 (300X600) | 16 |  | 28 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 394.91 | 0 | 0
|  | 12 |  | 28 | 1 | 10 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 946.96 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 28 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 770.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 407.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 485.99 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 28 | 1 | 9 |  | 1.672 |  |  | 1.672 | 421.34 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 1 | 9 |  | 0.862 |  |  | 0.862 | 217.22 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 272.97 | 0 | 0 | 0 | 0 | 0
| C 2 (300X600) | 16 |  | 12 | 1 | 14 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 592.37 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 12 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 330.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 174.72 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 208.28 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 12 | 1 | 9 |  | 1.672 |  |  | 1.672 | 180.58 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 1 | 9 |  | 0.862 |  |  | 0.862 | 93.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 116.99 | 0 | 0 | 0 | 0 | 0
| C 3 (300X600) | 25 |  | 4 | 1 | 12 |  | 2.95 |  |  | 2.95 | 0 | 0 | 0 | 0 | 0 | 141.6
|  | 20 |  | 4 | 1 | 2 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 29.36 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  | 0.36 | 2.08 | 0 | 133.12 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 4 (300X750) | 20 |  | 16 | 1 | 10 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 587.2 | 0
|  | 16 |  | 16 | 1 | 6 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 338.5 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 16 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 646.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 302.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 353.28 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 134.4 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 16 | 1 | 7 |  | 1.972 |  |  | 1.972 | 220.86 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.896 |  |  | 0.896 | 100.35 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 123.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.38 |  |  | 0.38 | 42.56 | 0 | 0 | 0 | 0 | 0
| C 5 (300X750) | 16 |  | 14 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 197.46 | 0 | 0
|  | 12 |  | 14 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 568.18 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 14 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 565.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 264.32 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 309.12 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 117.6 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 14 | 1 | 7 |  | 1.972 |  |  | 1.972 | 193.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.896 |  |  | 0.896 | 87.81 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 108.11 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.38 |  |  | 0.38 | 37.24 | 0 | 0 | 0 | 0 | 0
| C 6 (300X715) | 16 |  | 10 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
|  | 12 |  | 10 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 405.84 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 10 |  | 1.95 |  |  | 1.95 | 0 | 390 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 188.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 220.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 84 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 8 |  | 1.902 |  |  | 1.902 | 152.16 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.896 |  |  | 0.896 | 71.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 8 |  | 0.5516 |  |  | 0.5516 | 88.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.38 |  |  | 0.38 | 30.4 | 0 | 0 | 0 | 0 | 0
| C 7 (300X800) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 14 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 189.39 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 11 |  | 2.12 |  |  | 2.12 | 0 | 186.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.91 |  |  | 0.91 | 0 | 160.16 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.552 |  |  | 0.552 | 0 | 97.15 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 6 |  | 2.072 |  |  | 2.072 | 49.73 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.862 |  |  | 0.862 | 41.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.5516 |  |  | 0.5516 | 26.48 | 0 | 0 | 0 | 0 | 0
| C 8 (300X600) | 20 |  | 4 | 1 | 4 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 58.72 | 0
|  | 16 |  | 4 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 110.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 9 (300X600) | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0 | 32
|  | 12 |  | 4 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 81.17 | 0 | 0 | 0 | 24
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 104.96 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 55.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 94.21 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 10 |  | 1.608 |  |  | 1.608 | 64.32 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 10 |  | 0.83 |  |  | 0.83 | 33.2 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 10 |  | 0.7 |  |  | 0.7 | 56 | 0 | 0 | 0 | 0 | 0
| C 10 (300X600) | 20 |  | 10 | 1 | 14 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 513.8 | 0 | 140
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 262.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 139.2 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 235.52 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 10 |  | 1.608 |  |  | 1.608 | 160.8 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 10 |  | 0.83 |  |  | 0.83 | 83 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 10 |  | 0.7 |  |  | 0.7 | 140 | 0 | 0 | 0 | 0 | 0
| C 11 (300X715) | 16 |  | 4 | 1 | 12 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 169.25 | 0 | 0 | 48
|  | 12 |  | 4 | 1 | 4 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0 | 16
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 10 |  | 1.87 |  |  | 1.87 | 0 | 149.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 1.072 |  |  | 1.072 | 0 | 85.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 10 |  | 0.736 |  |  | 0.736 | 0 | 117.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 0.4 |  |  | 0.4 | 0 | 32 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.886 |  |  | 1.886 | 67.9 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 1.082 |  |  | 1.082 | 38.95 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.74 |  |  | 0.74 | 53.28 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.404 |  |  | 0.404 | 14.54 | 0 | 0 | 0 | 0 | 0
| Shear wall from 1st floor LVL to 2nd floor lvl | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SW 1 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 52.96 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X866) | 8 | 200 | 2 | 1 | 13 |  | 2.284 |  |  | 2.284 | 59.38 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 2 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 2 | 1 | 13 |  | 2.684 |  |  | 2.684 | 69.78 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 3 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X950) | 8 | 100 | 2 | 1 | 26 |  | 2.452 |  |  | 2.452 | 127.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 2 | 4 | 26 |  | 0.792 |  |  | 0.792 | 164.74 | 0 | 0 | 0 | 0 | 0
| SW 4 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 18 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 121.75 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1100) | 8 | 100 | 2 | 1 | 26 |  | 2.752 |  |  | 2.752 | 143.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X125) | 8 | 100 | 2 | 4 | 26 |  | 0.802 |  |  | 0.802 | 166.82 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| SW 5A | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0
|  | 12 |  | 4 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 270.56 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X583) | 8 | 100 | 4 | 2 | 26 |  | 1.718 |  |  | 1.718 | 357.34 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 4 | 4 | 26 |  | 0.792 |  |  | 0.792 | 329.47 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X516) | 8 | 200 | 4 | 1 | 13 |  | 1.584 |  |  | 1.584 | 82.37 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 4 | 2 | 7 |  | 0.34 |  |  | 0.34 | 19.04 | 0 | 0 | 0 | 0 | 0
| SW 6 | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 270.56 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1135) | 8 | 100 | 4 | 1 | 26 |  | 2.822 |  |  | 2.822 | 293.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X118) | 8 | 100 | 4 | 5 | 26 |  | 0.788 |  |  | 0.788 | 409.76 | 0 | 0 | 0 | 0 | 0
| SW 7A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 22 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 148.81 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X583) | 8 | 100 | 2 | 2 | 26 |  | 1.718 |  |  | 1.718 | 178.67 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 2 | 4 | 26 |  | 0.796 |  |  | 0.796 | 165.57 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X671) | 8 | 200 | 2 | 1 | 13 |  | 1.894 |  |  | 1.894 | 49.24 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 1 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
| SW 8A | 16 |  | 1 | 1 | 16 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 1 | 1 | 40 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X983) | 8 | 100 | 1 | 2 | 26 |  | 2.518 |  |  | 2.518 | 130.94 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 1 | 8 | 26 |  | 0.796 |  |  | 0.796 | 165.57 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1616) | 8 | 200 | 1 | 1 | 13 |  | 3.784 |  |  | 3.784 | 49.19 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 1 | 4 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 9 | 16 |  | 6 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 169.25 | 0 | 0
|  | 12 |  | 6 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
|  | 10 |  | 6 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 198.6 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 6 | 1 | 26 |  | 1.752 |  |  | 1.752 | 273.31 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 6 | 1 | 26 |  | 1.048 |  |  | 1.048 | 163.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 6 | 2 | 26 |  | 1.322 |  |  | 1.322 | 412.46 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 6 | 1 | 26 |  | 1.088 |  |  | 1.088 | 169.73 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 6 | 1 | 13 |  | 2.684 |  |  | 2.684 | 209.35 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 6 | 2 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 10 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 20 |  | 2.95 |  | 0.36 | 3.31 | 0 | 132.4 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X683) | 8 | 100 | 2 | 2 | 26 |  | 1.918 |  |  | 1.918 | 199.47 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X128) | 8 | 100 | 2 | 4 | 26 |  | 0.808 |  |  | 0.808 | 168.06 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 26 |  | 0.34 |  |  | 0.34 | 35.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2061) | 8 | 200 | 2 | 1 | 13 |  | 4.674 |  |  | 4.674 | 121.52 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 5 | 7 |  | 0.34 |  |  | 0.34 | 23.8 | 0 | 0 | 0 | 0 | 0
| SW 11 | 16 |  | 2 | 1 | 16 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0
|  | 12 |  | 2 | 1 | 24 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 162.34 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 20 |  | 2.95 |  | 0.36 | 3.31 | 0 | 132.4 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X983) | 8 | 100 | 2 | 2 | 26 |  | 2.518 |  |  | 2.518 | 261.87 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X124) | 8 | 100 | 2 | 8 | 26 |  | 0.8 |  |  | 0.8 | 332.8 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2081) | 8 | 200 | 2 | 1 | 13 |  | 4.714 |  |  | 4.714 | 122.56 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 5 | 7 |  | 0.34 |  |  | 0.34 | 23.8 | 0 | 0 | 0 | 0 | 0
| SW 12 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 6 |  | 2.95 |  | 0.36 | 3.31 | 0 | 39.72 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X751) | 8 | 200 | 2 | 1 | 13 |  | 2.054 |  |  | 2.054 | 53.4 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 1 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
| SW 13 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 22 |  | 2.95 |  | 0.36 | 3.31 | 0 | 145.64 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (140X583) | 8 | 100 | 2 | 2 | 26 |  | 1.638 |  |  | 1.638 | 170.35 | 0 | 0 | 0 | 0 | 0
| BE OTHER (140X133) | 8 | 100 | 2 | 4 | 26 |  | 0.738 |  |  | 0.738 | 153.5 | 0 | 0 | 0 | 0 | 0
| MID MAIN (140X2261) | 8 | 200 | 2 | 1 | 13 |  | 4.994 |  |  | 4.994 | 129.84 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 5 | 7 |  | 0.3 |  |  | 0.3 | 21 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FROM 1ST TO 2ND FLOOR LVL | [10 empty] | 4333.782 | 5516.7759 | 3872.484 | 4813.4858 | 2925.1368 | 545.16 | 22006.8245
Column From 2 Floor Lvl TO 3 FLOOR LVL (106.2-109.15))
| C 1 (300X600) | 16 |  | 28 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 394.91 | 0 | 0
|  | 12 |  | 28 | 1 | 10 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 946.96 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 28 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 770.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 407.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 485.99 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 28 | 1 | 9 |  | 1.672 |  |  | 1.672 | 421.34 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 1 | 9 |  | 0.862 |  |  | 0.862 | 217.22 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 272.97 | 0 | 0 | 0 | 0 | 0
| C 2 (300X600) | 16 |  | 12 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 423.12 | 0 | 0
|  | 12 |  | 12 | 1 | 4 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 162.34 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 12 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 330.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 174.72 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 208.28 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 12 | 1 | 9 |  | 1.672 |  |  | 1.672 | 180.58 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 1 | 9 |  | 0.862 |  |  | 0.862 | 93.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 116.99 | 0 | 0 | 0 | 0 | 0
| C 3 (300X600) | 25 |  | 4 | 1 | 4 |  | 2.95 |  | 0.9 | 3.85 | 0 | 0 | 0 | 0 | 0 | 61.6
|  | 20 |  | 4 | 1 | 10 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 146.8 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 110.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 4 (300X750) | 20 |  | 16 | 1 | 4 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 234.88 | 0
|  | 16 |  | 16 | 1 | 12 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 676.99 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 16 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 646.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 302.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 353.28 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 134.4 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 16 | 1 | 7 |  | 1.972 |  |  | 1.972 | 220.86 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.896 |  |  | 0.896 | 100.35 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 123.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.38 |  |  | 0.38 | 42.56 | 0 | 0 | 0 | 0 | 0
| C 5 (300X750) | 16 |  | 14 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 197.46 | 0 | 0
|  | 12 |  | 14 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 568.18 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 14 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 565.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 264.32 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 309.12 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 117.6 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 14 | 1 | 7 |  | 1.972 |  |  | 1.972 | 193.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.896 |  |  | 0.896 | 87.81 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 108.11 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.38 |  |  | 0.38 | 37.24 | 0 | 0 | 0 | 0 | 0
| C 6 (300X715) | 16 |  | 10 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
|  | 12 |  | 10 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 405.84 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 10 |  | 1.95 |  |  | 1.95 | 0 | 390 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 188.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 220.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 84 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 8 |  | 1.902 |  |  | 1.902 | 152.16 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.896 |  |  | 0.896 | 71.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 8 |  | 0.5516 |  |  | 0.5516 | 88.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.38 |  |  | 0.38 | 30.4 | 0 | 0 | 0 | 0 | 0
| C 7 (300X800) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 14 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 189.39 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 11 |  | 2.12 |  |  | 2.12 | 0 | 186.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.91 |  |  | 0.91 | 0 | 160.16 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.552 |  |  | 0.552 | 0 | 97.15 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 6 |  | 2.072 |  |  | 2.072 | 49.73 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.862 |  |  | 0.862 | 41.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.5516 |  |  | 0.5516 | 26.48 | 0 | 0 | 0 | 0 | 0
| C 8 (300X600) | 16 |  | 4 | 1 | 14 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 197.46 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 110.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 9 (300X600) | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0 | 32
|  | 12 |  | 4 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 81.17 | 0 | 0 | 0 | 24
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 104.96 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 55.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 94.21 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 10 |  | 1.608 |  |  | 1.608 | 64.32 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 10 |  | 0.83 |  |  | 0.83 | 33.2 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 10 |  | 0.7 |  |  | 0.7 | 56 | 0 | 0 | 0 | 0 | 0
| C 10 (300X600) | 20 |  | 10 | 1 | 8 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 293.6 | 0 | 80
|  | 16 |  | 10 | 1 | 6 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 211.56 | 0 | 0 | 60
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 262.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 139.2 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 235.52 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 10 |  | 1.608 |  |  | 1.608 | 160.8 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 10 |  | 0.83 |  |  | 0.83 | 83 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 10 |  | 0.7 |  |  | 0.7 | 140 | 0 | 0 | 0 | 0 | 0
| C 11 (300X715) | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0 | 32
|  | 12 |  | 4 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0 | 32
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 10 |  | 1.87 |  |  | 1.87 | 0 | 149.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 1.072 |  |  | 1.072 | 0 | 85.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 10 |  | 0.736 |  |  | 0.736 | 0 | 117.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 0.4 |  |  | 0.4 | 0 | 32 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.886 |  |  | 1.886 | 67.9 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 1.082 |  |  | 1.082 | 38.95 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.74 |  |  | 0.74 | 53.28 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.404 |  |  | 0.404 | 14.54 | 0 | 0 | 0 | 0 | 0
| Shear wall from 2nd floor lvl to 3rd floor lvl | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SW 1 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 52.96 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X866) | 8 | 200 | 2 | 1 | 13 |  | 2.284 |  |  | 2.284 | 59.38 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 2 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 2 | 1 | 13 |  | 2.684 |  |  | 2.684 | 69.78 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 3 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X950) | 8 | 100 | 2 | 1 | 26 |  | 2.452 |  |  | 2.452 | 127.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 2 | 4 | 26 |  | 0.792 |  |  | 0.792 | 164.74 | 0 | 0 | 0 | 0 | 0
| SW 4 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 18 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 121.75 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1100) | 8 | 100 | 2 | 1 | 26 |  | 2.752 |  |  | 2.752 | 143.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X125) | 8 | 100 | 2 | 4 | 26 |  | 0.802 |  |  | 0.802 | 166.82 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| SW 5B | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0
|  | 12 |  | 4 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 4 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 105.92 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X383) | 8 | 100 | 4 | 2 | 26 |  | 1.318 |  |  | 1.318 | 274.14 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 4 | 2 | 26 |  | 0.792 |  |  | 0.792 | 164.74 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X916) | 8 | 200 | 4 | 1 | 13 |  | 2.384 |  |  | 2.384 | 123.97 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 4 | 2 | 7 |  | 0.34 |  |  | 0.34 | 19.04 | 0 | 0 | 0 | 0 | 0
| SW 6 | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 270.56 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1135) | 8 | 100 | 4 | 1 | 26 |  | 2.822 |  |  | 2.822 | 293.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X118) | 8 | 100 | 4 | 5 | 26 |  | 0.788 |  |  | 0.788 | 409.76 | 0 | 0 | 0 | 0 | 0
| SW 7B | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X383) | 8 | 100 | 2 | 2 | 26 |  | 1.318 |  |  | 1.318 | 137.07 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 2 | 2 | 26 |  | 0.796 |  |  | 0.796 | 82.78 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1071) | 8 | 200 | 2 | 1 | 13 |  | 2.694 |  |  | 2.694 | 70.04 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 8A | 16 |  | 1 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 1 | 1 | 32 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 1 | 1 | 16 |  | 2.95 |  | 0.36 | 3.31 | 0 | 52.96 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X983) | 8 | 100 | 1 | 2 | 26 |  | 2.518 |  |  | 2.518 | 130.94 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 1 | 8 | 26 |  | 0.796 |  |  | 0.796 | 165.57 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1616) | 8 | 200 | 1 | 1 | 13 |  | 3.784 |  |  | 3.784 | 49.19 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 1 | 4 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 9 | 16 |  | 6 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 169.25 | 0 | 0
|  | 12 |  | 6 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
|  | 10 |  | 6 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 198.6 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 6 | 1 | 26 |  | 1.752 |  |  | 1.752 | 273.31 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 6 | 1 | 26 |  | 1.048 |  |  | 1.048 | 163.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 6 | 2 | 26 |  | 1.322 |  |  | 1.322 | 412.46 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 6 | 1 | 26 |  | 1.088 |  |  | 1.088 | 169.73 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 6 | 1 | 13 |  | 2.684 |  |  | 2.684 | 209.35 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 6 | 2 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 10A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 81.17 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 24 |  | 2.95 |  | 0.36 | 3.31 | 0 | 158.88 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X483) | 8 | 100 | 2 | 2 | 26 |  | 1.518 |  |  | 1.518 | 157.87 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X250) | 8 | 100 | 2 | 2 | 26 |  | 1.052 |  |  | 1.052 | 109.41 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 26 |  | 0.34 |  |  | 0.34 | 35.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2461) | 8 | 200 | 2 | 1 | 13 |  | 5.474 |  |  | 5.474 | 142.32 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 11A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 26 |  | 2.95 |  | 0.36 | 3.31 | 0 | 172.12 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X683) | 8 | 100 | 2 | 2 | 26 |  | 1.918 |  |  | 1.918 | 199.47 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X124) | 8 | 100 | 2 | 4 | 26 |  | 0.8 |  |  | 0.8 | 166.4 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 26 |  | 0.34 |  |  | 0.34 | 35.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2681) | 8 | 200 | 2 | 1 | 13 |  | 5.914 |  |  | 5.914 | 153.76 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 12 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 6 |  | 2.95 |  | 0.36 | 3.31 | 0 | 39.72 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X751) | 8 | 200 | 2 | 1 | 13 |  | 2.054 |  |  | 2.054 | 53.4 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 1 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
| SW 13A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 26 |  | 2.95 |  | 0.36 | 3.31 | 0 | 172.12 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (140X383) | 8 | 100 | 2 | 2 | 26 |  | 1.238 |  |  | 1.238 | 128.75 | 0 | 0 | 0 | 0 | 0
| BE OTHER (140X133) | 8 | 100 | 2 | 2 | 26 |  | 0.738 |  |  | 0.738 | 76.75 | 0 | 0 | 0 | 0 | 0
| MID MAIN (140X2661) | 8 | 200 | 2 | 1 | 13 |  | 5.794 |  |  | 5.794 | 150.64 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.3 |  |  | 0.3 | 25.2 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FROM 2nd TO 3rd FLOOR LVL | [10 empty] | 4084.6634 | 5698.6182 | 3692.0792 | 5281.4502 | 1661.1888 | 237.16 | 20655.1598
Column From 3 Floor Lvl TO 4 FLOOR
| C 1 (300X600) | 16 |  | 28 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 394.91 | 0 | 0
|  | 12 |  | 28 | 1 | 10 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 946.96 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 28 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 770.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 407.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 485.99 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 28 | 1 | 9 |  | 1.672 |  |  | 1.672 | 421.34 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 1 | 9 |  | 0.862 |  |  | 0.862 | 217.22 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 272.97 | 0 | 0 | 0 | 0 | 0
| C 2 (300X600) | 16 |  | 12 | 1 | 6 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 253.87 | 0 | 0
|  | 12 |  | 12 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 12 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 330.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 174.72 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 208.28 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 12 | 1 | 9 |  | 1.672 |  |  | 1.672 | 180.58 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 1 | 9 |  | 0.862 |  |  | 0.862 | 93.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 116.99 | 0 | 0 | 0 | 0 | 0
| C 3 (300X600) | 20 |  | 4 | 1 | 8 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 117.44 | 0
|  | 16 |  | 4 | 1 | 6 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 84.62 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 110.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 4 (300X750) | 16 |  | 16 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 564.16 | 0 | 0
|  | 12 |  | 16 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 16 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 646.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 302.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 353.28 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 134.4 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 16 | 1 | 7 |  | 1.972 |  |  | 1.972 | 220.86 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.896 |  |  | 0.896 | 100.35 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 123.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.38 |  |  | 0.38 | 42.56 | 0 | 0 | 0 | 0 | 0
| C 5 (300X750) | 16 |  | 14 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 197.46 | 0 | 0
|  | 12 |  | 14 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 568.18 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 14 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 565.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 264.32 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 309.12 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 117.6 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 14 | 1 | 7 |  | 1.972 |  |  | 1.972 | 193.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.896 |  |  | 0.896 | 87.81 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 108.11 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.38 |  |  | 0.38 | 37.24 | 0 | 0 | 0 | 0 | 0
| C 6 (300X715) | 16 |  | 10 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
|  | 12 |  | 10 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 405.84 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 10 |  | 1.95 |  |  | 1.95 | 0 | 390 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 188.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 220.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 84 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 8 |  | 1.902 |  |  | 1.902 | 152.16 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.896 |  |  | 0.896 | 71.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 8 |  | 0.5516 |  |  | 0.5516 | 88.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.38 |  |  | 0.38 | 30.4 | 0 | 0 | 0 | 0 | 0
| C 7 (300X800) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 14 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 189.39 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 11 |  | 2.12 |  |  | 2.12 | 0 | 186.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.91 |  |  | 0.91 | 0 | 160.16 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.552 |  |  | 0.552 | 0 | 97.15 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 6 |  | 2.072 |  |  | 2.072 | 49.73 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.862 |  |  | 0.862 | 41.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.5516 |  |  | 0.5516 | 26.48 | 0 | 0 | 0 | 0 | 0
| C 8 (300X600) | 16 |  | 4 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
|  | 12 |  | 4 | 1 | 4 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 110.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 9 (300X600) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 4 | 1 | 10 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0 | 40
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 104.96 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 55.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 94.21 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 10 |  | 1.608 |  |  | 1.608 | 64.32 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 10 |  | 0.83 |  |  | 0.83 | 33.2 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 10 |  | 0.7 |  |  | 0.7 | 56 | 0 | 0 | 0 | 0 | 0
| C 10 (300X600) | 16 |  | 10 | 1 | 14 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 493.64 | 0 | 0 | 140
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 262.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 139.2 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 235.52 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 10 |  | 1.608 |  |  | 1.608 | 160.8 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 10 |  | 0.83 |  |  | 0.83 | 83 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 10 |  | 0.7 |  |  | 0.7 | 140 | 0 | 0 | 0 | 0 | 0
| C 11 (300X715) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 4 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 162.34 | 0 | 0 | 0 | 48
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 10 |  | 1.87 |  |  | 1.87 | 0 | 149.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 1.072 |  |  | 1.072 | 0 | 85.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 10 |  | 0.736 |  |  | 0.736 | 0 | 117.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 0.4 |  |  | 0.4 | 0 | 32 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.886 |  |  | 1.886 | 67.9 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 1.082 |  |  | 1.082 | 38.95 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.74 |  |  | 0.74 | 53.28 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.404 |  |  | 0.404 | 14.54 | 0 | 0 | 0 | 0 | 0
| Shear wall from 3 floor lvl to 4 floor lvl | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SW 1 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 52.96 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X866) | 8 | 200 | 2 | 1 | 13 |  | 2.284 |  |  | 2.284 | 59.38 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 2 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 2 | 1 | 13 |  | 2.684 |  |  | 2.684 | 69.78 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 3 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X950) | 8 | 100 | 2 | 1 | 26 |  | 2.452 |  |  | 2.452 | 127.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 2 | 4 | 26 |  | 0.792 |  |  | 0.792 | 164.74 | 0 | 0 | 0 | 0 | 0
| SW 4 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 18 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 121.75 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1100) | 8 | 100 | 2 | 1 | 26 |  | 2.752 |  |  | 2.752 | 143.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X125) | 8 | 100 | 2 | 4 | 26 |  | 0.802 |  |  | 0.802 | 166.82 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| SW 5B | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0
|  | 12 |  | 4 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 4 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 105.92 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X383) | 8 | 100 | 4 | 2 | 26 |  | 1.318 |  |  | 1.318 | 274.14 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 4 | 2 | 26 |  | 0.792 |  |  | 0.792 | 164.74 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X916) | 8 | 200 | 4 | 1 | 13 |  | 2.384 |  |  | 2.384 | 123.97 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 4 | 2 | 7 |  | 0.34 |  |  | 0.34 | 19.04 | 0 | 0 | 0 | 0 | 0
| SW 6 | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 162.34 | 0 | 0 | 0
|  | 10 |  | 4 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 105.92 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1135) | 8 | 100 | 4 | 1 | 26 |  | 2.822 |  |  | 2.822 | 293.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X118) | 8 | 100 | 4 | 5 | 26 |  | 0.788 |  |  | 0.788 | 409.76 | 0 | 0 | 0 | 0 | 0
| SW 7B | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X383) | 8 | 100 | 2 | 2 | 26 |  | 1.318 |  |  | 1.318 | 137.07 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 2 | 2 | 26 |  | 0.796 |  |  | 0.796 | 82.78 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1071) | 8 | 200 | 2 | 1 | 13 |  | 2.694 |  |  | 2.694 | 70.04 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 8B | 16 |  | 1 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 1 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 67.64 | 0 | 0 | 0
|  | 10 |  | 1 | 1 | 22 |  | 2.95 |  | 0.36 | 3.31 | 0 | 72.82 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X683) | 8 | 100 | 1 | 2 | 26 |  | 1.918 |  |  | 1.918 | 99.74 | 0 | 0 | 0 | 0 | 0 | 683
| BE OTHER (180X122) | 8 | 100 | 1 | 4 | 26 |  | 0.796 |  |  | 0.796 | 82.78 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 400 | 1 | 2 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2216) | 8 | 200 | 1 | 1 | 13 |  | 4.984 |  |  | 4.984 | 64.79 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 1 | 5 | 7 |  | 0.34 |  |  | 0.34 | 11.9 | 0 | 0 | 0 | 0 | 0
| SW 9 | 16 |  | 6 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 169.25 | 0 | 0
|  | 12 |  | 6 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
|  | 10 |  | 6 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 198.6 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 6 | 1 | 26 |  | 1.752 |  |  | 1.752 | 273.31 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 6 | 1 | 26 |  | 1.048 |  |  | 1.048 | 163.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 6 | 2 | 26 |  | 1.322 |  |  | 1.322 | 412.46 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 6 | 1 | 26 |  | 1.088 |  |  | 1.088 | 169.73 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 6 | 1 | 13 |  | 2.684 |  |  | 2.684 | 209.35 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 6 | 2 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 10A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 81.17 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 24 |  | 2.95 |  | 0.36 | 3.31 | 0 | 158.88 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X483) | 8 | 100 | 2 | 2 | 26 |  | 1.518 |  |  | 1.518 | 157.87 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X250) | 8 | 100 | 2 | 2 | 26 |  | 1.052 |  |  | 1.052 | 109.41 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 26 |  | 0.34 |  |  | 0.34 | 35.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2461) | 8 | 200 | 2 | 1 | 13 |  | 5.474 |  |  | 5.474 | 142.32 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 11A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 26 |  | 2.95 |  | 0.36 | 3.31 | 0 | 172.12 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X683) | 8 | 100 | 2 | 2 | 26 |  | 1.918 |  |  | 1.918 | 199.47 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X124) | 8 | 100 | 2 | 4 | 26 |  | 0.8 |  |  | 0.8 | 166.4 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 26 |  | 0.34 |  |  | 0.34 | 35.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2681) | 8 | 200 | 2 | 1 | 13 |  | 5.914 |  |  | 5.914 | 153.76 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 12 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 6 |  | 2.95 |  | 0.36 | 3.31 | 0 | 39.72 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X751) | 8 | 200 | 2 | 1 | 13 |  | 2.054 |  |  | 2.054 | 53.4 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 1 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
| SW 13A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 26 |  | 2.95 |  | 0.36 | 3.31 | 0 | 172.12 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (140X383) | 8 | 100 | 2 | 2 | 26 |  | 1.238 |  |  | 1.238 | 128.75 | 0 | 0 | 0 | 0 | 0
| BE OTHER (140X133) | 8 | 100 | 2 | 2 | 26 |  | 0.738 |  |  | 0.738 | 76.75 | 0 | 0 | 0 | 0 | 0
| MID MAIN (140X2661) | 8 | 200 | 2 | 1 | 13 |  | 5.794 |  |  | 5.794 | 150.64 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.3 |  |  | 0.3 | 25.2 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Column From 3 Floor Lvl TO 4 FLOOR | [10 empty] | 4048.6197 | 5776.2244 | 4137.0593 | 5147.7506 | 288.9024 | 0 | 19398.5564
Column From 4 Floor Lvl TO 5 FLOOR
| C 1 (300X600) | 16 |  | 28 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 394.91 | 0 | 0
|  | 12 |  | 28 | 1 | 10 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 946.96 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 28 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 770.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 407.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 485.99 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 28 | 1 | 9 |  | 1.672 |  |  | 1.672 | 421.34 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 1 | 9 |  | 0.862 |  |  | 0.862 | 217.22 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 272.97 | 0 | 0 | 0 | 0 | 0
| C 2 (300X600) | 16 |  | 12 | 1 | 6 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 253.87 | 0 | 0
|  | 12 |  | 12 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 12 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 330.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 174.72 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 208.28 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 12 | 1 | 9 |  | 1.672 |  |  | 1.672 | 180.58 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 1 | 9 |  | 0.862 |  |  | 0.862 | 93.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 116.99 | 0 | 0 | 0 | 0 | 0
| C 3 (300X600) | 16 |  | 4 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
|  | 20 |  | 4 | 1 | 4 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 58.72 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 110.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 4 (300X750) | 16 |  | 16 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 564.16 | 0 | 0
|  | 12 |  | 16 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 16 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 646.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 302.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 353.28 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 134.4 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 16 | 1 | 7 |  | 1.972 |  |  | 1.972 | 220.86 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.896 |  |  | 0.896 | 100.35 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 123.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.38 |  |  | 0.38 | 42.56 | 0 | 0 | 0 | 0 | 0
| C 5 (300X750) | 16 |  | 14 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 197.46 | 0 | 0
|  | 12 |  | 14 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 568.18 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 14 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 565.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 264.32 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 309.12 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 117.6 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 14 | 1 | 7 |  | 1.972 |  |  | 1.972 | 193.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.896 |  |  | 0.896 | 87.81 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 108.11 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.38 |  |  | 0.38 | 37.24 | 0 | 0 | 0 | 0 | 0
| C 6 (300X715) | 16 |  | 10 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
|  | 12 |  | 10 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 405.84 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 10 |  | 1.95 |  |  | 1.95 | 0 | 390 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 188.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 220.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 84 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 8 |  | 1.902 |  |  | 1.902 | 152.16 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.896 |  |  | 0.896 | 71.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 8 |  | 0.5516 |  |  | 0.5516 | 88.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.38 |  |  | 0.38 | 30.4 | 0 | 0 | 0 | 0 | 0
| C 7 (300X800) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 14 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 189.39 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 11 |  | 2.12 |  |  | 2.12 | 0 | 186.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.91 |  |  | 0.91 | 0 | 160.16 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.552 |  |  | 0.552 | 0 | 97.15 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 6 |  | 2.072 |  |  | 2.072 | 49.73 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.862 |  |  | 0.862 | 41.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.5516 |  |  | 0.5516 | 26.48 | 0 | 0 | 0 | 0 | 0
| C 8 (300X600) | 16 |  | 4 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
|  | 12 |  | 4 | 1 | 4 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 110.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 9 (300X600) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 4 | 1 | 10 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0 | 40
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 104.96 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 55.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 94.21 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 10 |  | 1.608 |  |  | 1.608 | 64.32 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 10 |  | 0.83 |  |  | 0.83 | 33.2 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 10 |  | 0.7 |  |  | 0.7 | 56 | 0 | 0 | 0 | 0 | 0
| C 10 (300X600) | 16 |  | 10 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 282.08 | 0 | 0 | 80
|  | 12 |  | 10 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 202.92 | 0 | 0 | 0 | 60
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 262.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 139.2 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 235.52 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 10 |  | 1.608 |  |  | 1.608 | 160.8 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 10 |  | 0.83 |  |  | 0.83 | 83 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 10 |  | 0.7 |  |  | 0.7 | 140 | 0 | 0 | 0 | 0 | 0
| C 11 (300X715) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 4 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 162.34 | 0 | 0 | 0 | 48
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 10 |  | 1.87 |  |  | 1.87 | 0 | 149.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 1.072 |  |  | 1.072 | 0 | 85.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 10 |  | 0.736 |  |  | 0.736 | 0 | 117.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 0.4 |  |  | 0.4 | 0 | 32 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.886 |  |  | 1.886 | 67.9 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 1.082 |  |  | 1.082 | 38.95 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.74 |  |  | 0.74 | 53.28 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.404 |  |  | 0.404 | 14.54 | 0 | 0 | 0 | 0 | 0
| Shear wall from 3 floor lvl to 4 floor lvl | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SW 1 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 52.96 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X866) | 8 | 200 | 2 | 1 | 13 |  | 2.284 |  |  | 2.284 | 59.38 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 2 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 2 | 1 | 13 |  | 2.684 |  |  | 2.684 | 69.78 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 3 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X950) | 8 | 100 | 2 | 1 | 26 |  | 2.452 |  |  | 2.452 | 127.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 2 | 4 | 26 |  | 0.792 |  |  | 0.792 | 164.74 | 0 | 0 | 0 | 0 | 0
| SW 4 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 18 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 121.75 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1100) | 8 | 100 | 2 | 1 | 26 |  | 2.752 |  |  | 2.752 | 143.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X125) | 8 | 100 | 2 | 4 | 26 |  | 0.802 |  |  | 0.802 | 166.82 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| SW 5B | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0
|  | 12 |  | 4 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 4 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 105.92 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X383) | 8 | 100 | 4 | 2 | 26 |  | 1.318 |  |  | 1.318 | 274.14 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 4 | 2 | 26 |  | 0.792 |  |  | 0.792 | 164.74 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X916) | 8 | 200 | 4 | 1 | 13 |  | 2.384 |  |  | 2.384 | 123.97 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 4 | 2 | 7 |  | 0.34 |  |  | 0.34 | 19.04 | 0 | 0 | 0 | 0 | 0
| SW 6 | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 162.34 | 0 | 0 | 0
|  | 10 |  | 4 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 105.92 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1135) | 8 | 100 | 4 | 1 | 26 |  | 2.822 |  |  | 2.822 | 293.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X118) | 8 | 100 | 4 | 5 | 26 |  | 0.788 |  |  | 0.788 | 409.76 | 0 | 0 | 0 | 0 | 0
| SW 7B | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X383) | 8 | 100 | 2 | 2 | 26 |  | 1.318 |  |  | 1.318 | 137.07 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 2 | 2 | 26 |  | 0.796 |  |  | 0.796 | 82.78 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1071) | 8 | 200 | 2 | 1 | 13 |  | 2.694 |  |  | 2.694 | 70.04 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 8B | 16 |  | 1 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 1 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 67.64 | 0 | 0 | 0
|  | 10 |  | 1 | 1 | 22 |  | 2.95 |  | 0.36 | 3.31 | 0 | 72.82 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X683) | 8 | 100 | 1 | 2 | 26 |  | 1.918 |  |  | 1.918 | 99.74 | 0 | 0 | 0 | 0 | 0 | 683
| BE OTHER (180X122) | 8 | 100 | 1 | 4 | 26 |  | 0.796 |  |  | 0.796 | 82.78 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 400 | 1 | 2 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2216) | 8 | 200 | 1 | 1 | 13 |  | 4.984 |  |  | 4.984 | 64.79 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 1 | 5 | 7 |  | 0.34 |  |  | 0.34 | 11.9 | 0 | 0 | 0 | 0 | 0
| SW 9 | 16 |  | 6 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 169.25 | 0 | 0
|  | 12 |  | 6 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
|  | 10 |  | 6 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 198.6 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 6 | 1 | 26 |  | 1.752 |  |  | 1.752 | 273.31 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 6 | 1 | 26 |  | 1.048 |  |  | 1.048 | 163.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 6 | 2 | 26 |  | 1.322 |  |  | 1.322 | 412.46 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 6 | 1 | 26 |  | 1.088 |  |  | 1.088 | 169.73 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 6 | 1 | 13 |  | 2.684 |  |  | 2.684 | 209.35 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 6 | 2 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 10A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 81.17 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 24 |  | 2.95 |  | 0.36 | 3.31 | 0 | 158.88 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X483) | 8 | 100 | 2 | 2 | 26 |  | 1.518 |  |  | 1.518 | 157.87 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X250) | 8 | 100 | 2 | 2 | 26 |  | 1.052 |  |  | 1.052 | 109.41 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 26 |  | 0.34 |  |  | 0.34 | 35.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2461) | 8 | 200 | 2 | 1 | 13 |  | 5.474 |  |  | 5.474 | 142.32 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 11A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 26 |  | 2.95 |  | 0.36 | 3.31 | 0 | 172.12 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X683) | 8 | 100 | 2 | 2 | 26 |  | 1.918 |  |  | 1.918 | 199.47 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X124) | 8 | 100 | 2 | 4 | 26 |  | 0.8 |  |  | 0.8 | 166.4 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 26 |  | 0.34 |  |  | 0.34 | 35.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2681) | 8 | 200 | 2 | 1 | 13 |  | 5.914 |  |  | 5.914 | 153.76 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 12 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 6 |  | 2.95 |  | 0.36 | 3.31 | 0 | 39.72 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X751) | 8 | 200 | 2 | 1 | 13 |  | 2.054 |  |  | 2.054 | 53.4 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 1 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
| SW 13A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 26 |  | 2.95 |  | 0.36 | 3.31 | 0 | 172.12 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (140X383) | 8 | 100 | 2 | 2 | 26 |  | 1.238 |  |  | 1.238 | 128.75 | 0 | 0 | 0 | 0 | 0
| BE OTHER (140X133) | 8 | 100 | 2 | 2 | 26 |  | 0.738 |  |  | 0.738 | 76.75 | 0 | 0 | 0 | 0 | 0
| MID MAIN (140X2661) | 8 | 200 | 2 | 1 | 13 |  | 5.794 |  |  | 5.794 | 150.64 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.3 |  |  | 0.3 | 25.2 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Column From 3 Floor Lvl TO 4 FLOOR | [10 empty] | 4048.6197 | 5776.2244 | 4317.4552 | 4902.6294 | 144.4512 | 0 | 19189.3799

## 1ST FLOOR LVL SLAB BBS
Reinforcement
Sr. No. | Designation | Dia | C/C (mm) | No | No | No of Bars | Bar Length (mtr) |  |  | Lap Length | One Bar Length (MTR) | Dia Wise Weight (Kg)
[7 empty] | a | b | c |  |  | 8mm | 10mm | 12mm | 16mm | 20MM | 25mm
Typical Beam
200X500 | B1 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 6.125 | 0.708 |  | 7.541 | 0 | 0 | 0 | 15.08 | 0 | 0
| TOP | 20 |  | 1 | 1 | 2 | 0.88 | 6.125 | 0.88 |  | 7.885 | 0 | 0 | 0 | 0 | 15.77 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 | 0.536 | 0.85 |  |  | 1.386 | 0 | 0 | 2.77 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 20 |  | 1.328 |  |  | 1.328 | 26.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 8 |  | 1.328 |  |  | 1.328 | 10.62 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 20 |  | 1.328 |  |  | 1.328 | 26.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 6 |  | 1.328 |  |  | 1.328 | 7.97 | 0 | 0 | 0 | 0 | 0
200X500 | B2 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 3.3 | 0.36333 |  | 4.3713 | 0 | 0 | 0 | 8.74 | 0 | 0
| TOP | 20 |  | 1 | 1 | 2 | 0.88 | 3.3 | 0.42667 |  | 4.6067 | 0 | 0 | 0 | 0 | 9.21 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 20 |  | 1.328 |  |  | 1.328 | 26.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 10 |  | 1.328 |  |  | 1.328 | 13.28 | 0 | 0 | 0 | 0 | 0
100X350 | B3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 1 | 1 | 2 | 0.456 | 1.395 | 0.456 |  | 2.307 | 0 | 0 | 4.61 | 0 | 0 | 0
| TOP | 12 |  | 1 | 1 | 2 | 0.456 | 1.395 | 0.456 |  | 2.307 | 0 | 0 | 4.61 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 1 | 1 | 10 |  | 0.828 |  |  | 0.828 | 8.28 | 0 | 0 | 0 | 0 | 0
200X350 | B4 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.708 | 1.395 | 0.708 |  | 2.811 | 0 | 0 | 0 | 11.24 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.708 | 1.395 | 0.708 |  | 2.811 | 0 | 0 | 0 | 11.24 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 15 |  | 1.028 |  |  | 1.028 | 30.84 | 0 | 0 | 0 | 0 | 0
200X450 | B5 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 6.875 | 0.36333 |  | 7.9463 | 0 | 0 | 0 | 15.89 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 6.875 | 0.36333 |  | 7.9463 | 0 | 0 | 0 | 15.89 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 18 |  | 1.228 |  |  | 1.228 | 22.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 13 |  | 1.228 |  |  | 1.228 | 15.96 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 18 |  | 1.228 |  |  | 1.228 | 22.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 10 |  | 1.228 |  |  | 1.228 | 12.28 | 0 | 0 | 0 | 0 | 0
230X350 | B6 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 3.16 | 0.708 |  | 4.576 | 0 | 0 | 0 | 9.15 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 3.16 | 0.708 |  | 4.576 | 0 | 0 | 0 | 9.15 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 | 0.536 | 3.16 |  |  | 3.696 | 0 | 0 | 7.39 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 16 |  | 1.088 |  |  | 1.088 | 17.41 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 12 |  | 1.088 |  |  | 1.088 | 13.06 | 0 | 0 | 0 | 0 | 0
200X450 | B7 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 2.7 | 0.708 |  | 3.7713 | 0 | 0 | 0 | 7.54 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 2.7 | 0.708 |  | 3.7713 | 0 | 0 | 0 | 7.54 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 18 |  | 1.228 |  |  | 1.228 | 22.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 7 |  | 1.228 |  |  | 1.228 | 8.6 | 0 | 0 | 0 | 0 | 0
200X500 | B8 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 2.875 | 0.708 |  | 4.291 | 0 | 0 | 0 | 8.58 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.58 | 2.93 | 0.36333 |  | 3.8733 | 0 | 0 | 0 | 7.75 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 6.405 | 0.36333 |  | 7.4763 | 0 | 0 | 0 | 14.95 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 20 |  | 1.328 |  |  | 1.328 | 26.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 7 |  | 1.328 |  |  | 1.328 | 9.3 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 1 | 20 |  | 1.328 |  |  | 1.328 | 26.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 7 |  | 1.328 |  |  | 1.328 | 9.3 | 0 | 0 | 0 | 0 | 0
200X500 | B9 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 4.69 | 0.708 |  | 6.106 | 0 | 0 | 0 | 12.21 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 4.69 | 0.708 |  | 6.106 | 0 | 0 | 0 | 12.21 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 3.29 |  |  | 3.29 | 0 | 0 | 6.58 | 0 | 0 | 0
| TOP EXTRA | 16 |  | 1 | 1 | 4 | 0.708 | 1.4 |  |  | 2.108 | 0 | 0 | 0 | 8.43 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 23 |  | 1.328 |  |  | 1.328 | 30.54 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 17 |  | 1.328 |  |  | 1.328 | 22.58 | 0 | 0 | 0 | 0 | 0
200X500 | B10 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 20 |  | 1 | 0.5 | 2 | 0.42667 | 6.3 | 0.42667 |  | 7.1533 | 0 | 0 | 0 | 0 | 7.15 | 0
| TOP | 25 |  | 1 | 0.5 | 2 | 0.50833 | 6.3 | 0.50833 |  | 7.3167 | 0 | 0 | 0 | 0 | 0 | 7.32
| BOTTOM EXTRA | 12 |  | 1 | 0.5 | 2 |  | 5.1 |  |  | 5.1 | 0 | 0 | 5.1 | 0 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 0.5 | 32 |  | 1.328 |  |  | 1.328 | 21.25 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 0.5 | 22 |  | 1.328 |  |  | 1.328 | 14.61 | 0 | 0 | 0 | 0 | 0
200X450 | B11, B22 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.708 | 4.69 | 0.708 |  | 6.106 | 0 | 0 | 0 | 24.42 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.708 | 4.69 | 0.708 |  | 6.106 | 0 | 0 | 0 | 24.42 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 3.79 |  |  | 3.79 | 0 | 0 | 15.16 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 1 | 4 | 0.536 | 1.4 |  |  | 1.936 | 0 | 0 | 15.49 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 23 |  | 1.328 |  |  | 1.328 | 61.09 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 17 |  | 1.328 |  |  | 1.328 | 45.15 | 0 | 0 | 0 | 0 | 0
200X450 | B12 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 0.5 | 2 | 0.708 | 11.75 | 0.708 | 0.79 | 13.956 | 0 | 0 | 0 | 13.96 | 0 | 0
| TOP | 16 |  | 1 | 0.5 | 2 | 0.708 | 11.75 | 0.708 | 0.79 | 13.956 | 0 | 0 | 0 | 13.96 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 0.5 | 4 |  | 4.36 |  |  | 4.36 | 0 | 0 | 8.72 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 0.5 | 2 |  | 3.83 |  |  | 3.83 | 0 | 0 | 3.83 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 0.5 | 4 | 0.536 | 1.8 |  |  | 2.336 | 0 | 0 | 4.67 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 0.5 | 58 |  | 1.228 |  |  | 1.228 | 35.61 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 0.5 | 40 |  | 1.228 |  |  | 1.228 | 24.56 | 0 | 0 | 0 | 0 | 0
200X450 | B13 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 4.105 | 0.708 |  | 5.1763 | 0 | 0 | 0 | 10.35 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.79 | 1.6 | 0.708 |  | 3.098 | 0 | 0 | 0 | 6.2 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 5.935 | 0.708 |  | 7.0063 | 0 | 0 | 0 | 14.01 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 21 |  | 1.228 |  |  | 1.228 | 25.79 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 15 |  | 1.228 |  |  | 1.228 | 18.42 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 1 | 17 |  | 1.092 |  |  | 1.092 | 18.56 | 0 | 0 | 0 | 0 | 0
200X450 | B14 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 20 |  | 1 | 1 | 2 | 0.88 | 4.905 | 0.42667 |  | 6.2117 | 0 | 0 | 0 | 0 | 12.42 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 4.905 | 0.36333 |  | 5.9763 | 0 | 0 | 0 | 11.95 | 0 | 0
| TOP EXTRA | 16 |  | 1 | 1 | 2 |  | 2.785 |  |  | 2.785 | 0 | 0 | 0 | 5.57 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 23 |  | 1.228 |  |  | 1.228 | 28.24 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 10 | 100 | 1 | 1 | 16 |  | 1.26 |  |  | 1.26 | 0 | 20.16 | 0 | 0 | 0 | 0
200X500 | B15 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 3.115 | 0.708 |  | 4.531 | 0 | 0 | 0 | 9.06 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 3.115 | 0.708 |  | 4.531 | 0 | 0 | 0 | 9.06 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 32 |  | 1.328 |  |  | 1.328 | 42.5 | 0 | 0 | 0 | 0 | 0
200X500 | B16 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.708 | 6.685 | 0.36333 |  | 7.7563 | 0 | 0 | 0 | 46.54 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.95 | 1.02 | 0.708 |  | 2.678 | 0 | 0 | 0 | 16.07 | 0 | 0
| TOP | 16 |  | 3 | 1 | 2 | 0.708 | 7.905 | 0.708 |  | 9.321 | 0 | 0 | 0 | 55.93 | 0 | 0
| BOTTOM EXTRA | 16 |  | 3 | 1 | 2 | 0.95 | 1.02 | 0.708 |  | 2.678 | 0 | 0 | 0 | 16.07 | 0 | 0
| BOTTOM EXTRA | 12 |  | 3 | 1 | 2 |  | 2.5 | 0.29667 |  | 2.7967 | 0 | 0 | 16.78 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 3 | 1 | 2 |  | 2.4 |  |  | 2.4 | 0 | 0 | 14.4 | 0 | 0 | 0
| TOP EXTRA | 16 |  | 3 | 1 | 2 | 0.708 | 1.3 |  |  | 2.008 | 0 | 0 | 0 | 12.05 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 3 | 1 | 34 |  | 1.392 |  |  | 1.392 | 141.98 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 23 |  | 1.392 |  |  | 1.392 | 96.05 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 3 | 1 | 11 |  | 1.028 |  |  | 1.028 | 33.92 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 3 | 1 | 20 |  | 1.328 |  |  | 1.328 | 79.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 9 |  | 1.328 |  |  | 1.328 | 35.86 | 0 | 0 | 0 | 0 | 0
200X500 | B17 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 3.215 | 0.36333 |  | 4.2863 | 0 | 0 | 0 | 8.57 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 3.215 | 0.36333 |  | 4.2863 | 0 | 0 | 0 | 8.57 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 |  | 0.9 | 0.536 |  | 1.436 | 0 | 0 | 2.87 | 0 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 20 |  | 1.328 |  |  | 1.328 | 26.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 9 |  | 1.328 |  |  | 1.328 | 11.95 | 0 | 0 | 0 | 0 | 0
230X500 | B18 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 25 |  | 1 | 1 | 2 | 1.1 | 2.76 | 1.1 |  | 4.96 | 0 | 0 | 0 | 0 | 0 | 9.92
| TOP | 25 |  | 1 | 1 | 2 | 1.1 | 2.76 | 1.1 |  | 4.96 | 0 | 0 | 0 | 0 | 0 | 9.92
| TOP EXTRA | 12 |  | 1 | 1 | 2 | 0.536 | 2.76 | 0.536 |  | 3.832 | 0 | 0 | 7.66 | 0 | 0 | 0
| STIRRUPS 200X500 | 10 | 100 | 1 | 1 | 20 |  | 1.42 |  |  | 1.42 | 0 | 28.4 | 0 | 0 | 0 | 0
|  | 10 | 150 | 1 | 1 | 6 |  | 1.42 |  |  | 1.42 | 0 | 8.52 | 0 | 0 | 0 | 0
200X450 | B19 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 6.79 | 0.36333 |  | 7.8613 | 0 | 0 | 0 | 15.72 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 6.79 | 0.36333 |  | 7.8613 | 0 | 0 | 0 | 15.72 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 5.59 |  |  | 5.59 | 0 | 0 | 11.18 | 0 | 0 | 0
| TOP EXTRA | 16 |  | 1 | 1 | 2 |  | 2 | 0.708 |  | 2.708 | 0 | 0 | 0 | 5.42 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 34 |  | 1.228 |  |  | 1.228 | 41.75 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 24 |  | 1.228 |  |  | 1.228 | 29.47 | 0 | 0 | 0 | 0 | 0
230X350 | B20 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 0.5 | 2 | 0.36333 | 5.05 | 0.36333 |  | 5.7767 | 0 | 0 | 0 | 5.78 | 0 | 0
| TOP | 20 |  | 1 | 0.5 | 2 | 0.42667 | 5.05 | 0.42667 |  | 5.9033 | 0 | 0 | 0 | 0 | 5.9 | 0
| STIRRUPS | 8 | 100 | 1 | 0.5 | 50 |  | 1.088 |  |  | 1.088 | 27.2 | 0 | 0 | 0 | 0 | 0
230X450 | B21 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 0.5 | 2 | 0.708 | 11.75 | 0.708 |  | 13.166 | 0 | 0 | 0 | 13.17 | 0 | 0
| TOP | 16 |  | 1 | 0.5 | 2 | 0.708 | 11.75 | 0.708 |  | 13.166 | 0 | 0 | 0 | 13.17 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 0.5 | 4 |  | 4.36 |  |  | 4.36 | 0 | 0 | 8.72 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 0.5 | 2 |  | 3.83 |  |  | 3.83 | 0 | 0 | 3.83 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 0.5 | 4 | 0.686 | 1.8 |  |  | 2.486 | 0 | 0 | 4.97 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 0.5 | 60 |  | 1.288 |  |  | 1.288 | 38.64 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 1 | 0.5 | 14 |  | 1.288 |  |  | 1.288 | 9.02 | 0 | 0 | 0 | 0 | 0
200X450 | B23 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 2.22 | 0.708 |  | 3.636 | 0 | 0 | 0 | 7.27 | 0 | 0
| TOP | 20 |  | 1 | 1 | 2 | 0.88 | 2.22 | 0.88 |  | 3.98 | 0 | 0 | 0 | 0 | 7.96 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 23 |  | 1.228 |  |  | 1.228 | 28.24 | 0 | 0 | 0 | 0 | 0
200X450 | B24 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 5.63 | 0.708 |  | 7.046 | 0 | 0 | 0 | 14.09 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 5.63 | 0.708 |  | 7.046 | 0 | 0 | 0 | 14.09 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 4.53 |  |  | 4.53 | 0 | 0 | 9.06 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 4 | 0.536 | 1.6 |  |  | 2.136 | 0 | 0 | 8.54 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 28 |  | 1.228 |  |  | 1.228 | 34.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 20 |  | 1.228 |  |  | 1.228 | 24.56 | 0 | 0 | 0 | 0 | 0
200X450 | B25 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 9.815 | 0.36333 |  | 10.5417 | 0 | 0 | 0 | 21.08 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 9.815 | 0.36333 |  | 10.5417 | 0 | 0 | 0 | 21.08 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 4.03 |  |  | 4.03 | 0 | 0 | 8.06 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 |  | 2.4 |  |  | 2.4 | 0 | 0 | 4.8 | 0 | 0 | 0
|  | 12 |  | 1 | 1 | 2 |  | 2.23 |  |  | 2.23 | 0 | 0 | 4.46 | 0 | 0 | 0
|  | 12 |  | 1 | 1 | 2 |  | 1.17 | 0.3 |  | 1.47 | 0 | 0 | 2.94 | 0 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 16 |  | 1.328 |  |  | 1.328 | 21.25 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 28 |  | 1.228 |  |  | 1.228 | 34.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 20 |  | 1.228 |  |  | 1.228 | 24.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 1 | 1 | 22 |  | 1.228 |  |  | 1.228 | 27.02 | 0 | 0 | 0 | 0 | 0
200x500 | B26 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.708 | 8.255 | 0.708 |  | 9.671 | 0 | 0 | 0 | 58.03 | 0 | 0
| TOP | 16 |  | 3 | 1 | 2 | 0.708 | 8.255 | 0.708 |  | 9.671 | 0 | 0 | 0 | 58.03 | 0 | 0
| BOTTOM EXTRA | 12 |  | 3 | 1 | 2 |  | 3.57 |  |  | 3.57 | 0 | 0 | 21.42 | 0 | 0 | 0
| TOP EXTRA | 16 |  | 3 | 1 | 2 |  | 2.5 |  |  | 2.5 | 0 | 0 | 0 | 15 | 0 | 0
| TOP EXTRA | 12 |  | 3 | 1 | 2 | 0.536 | 1.4 |  |  | 1.936 | 0 | 0 | 11.62 | 0 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 3 | 1 | 24 |  | 1.328 |  |  | 1.328 | 95.62 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 17 |  | 1.328 |  |  | 1.328 | 67.73 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 3 | 1 | 20 |  | 1.328 |  |  | 1.328 | 79.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 3 | 1 | 9 |  | 1.328 |  |  | 1.328 | 35.86 | 0 | 0 | 0 | 0 | 0
200X500 | B27 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.708 | 3.165 | 0.708 |  | 4.581 | 0 | 0 | 0 | 27.49 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.79 | 2.58 | 0.708 |  | 4.078 | 0 | 0 | 0 | 24.47 | 0 | 0
| TOP | 16 |  | 3 | 1 | 2 | 0.708 | 6.345 | 0.708 |  | 7.761 | 0 | 0 | 0 | 46.57 | 0 | 0
| TOP EXTRA | 12 |  | 3 | 1 | 2 |  | 2.3 |  |  | 2.3 | 0 | 0 | 13.8 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 3 | 1 | 2 | 0.536 | 0.9 |  |  | 1.436 | 0 | 0 | 8.62 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 3 | 1 | 2 | 0.536 | 0.8 |  |  | 1.336 | 0 | 0 | 8.02 | 0 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 3 | 1 | 20 |  | 1.328 |  |  | 1.328 | 79.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 9 |  | 1.328 |  |  | 1.328 | 35.86 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 3 | 1 | 20 |  | 1.028 |  |  | 1.028 | 61.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 5 |  | 1.028 |  |  | 1.028 | 15.42 | 0 | 0 | 0 | 0 | 0
200X450 | B28 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 5.125 | 0.708 |  | 6.541 | 0 | 0 | 0 | 13.08 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 5.125 | 0.708 |  | 6.541 | 0 | 0 | 0 | 13.08 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 4.125 |  |  | 4.125 | 0 | 0 | 8.25 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 4 | 0.676 | 1.5 |  |  | 2.176 | 0 | 0 | 8.7 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 27 |  | 1.228 |  |  | 1.228 | 33.16 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 18 |  | 1.228 |  |  | 1.228 | 22.1 | 0 | 0 | 0 | 0 | 0
230X450 | B29 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 5.635 | 0.708 |  | 7.051 | 0 | 0 | 0 | 14.1 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 5.635 | 0.708 |  | 7.051 | 0 | 0 | 0 | 14.1 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 20 |  | 1.288 |  |  | 1.288 | 25.76 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 1 | 1 | 20 |  | 1.288 |  |  | 1.288 | 25.76 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 1 | 1 | 15 |  | 1.288 |  |  | 1.288 | 19.32 | 0 | 0 | 0 | 0 | 0
230X450 | B30 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 7.425 | 0.708 |  | 8.841 | 0 | 0 | 0 | 17.68 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.58 | 2.93 | 0.708 |  | 4.218 | 0 | 0 | 0 | 8.44 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 10.955 | 0.708 |  | 12.371 | 0 | 0 | 0 | 24.74 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 41 |  | 1.228 |  |  | 1.228 | 50.35 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 30 |  | 1.328 |  |  | 1.328 | 39.84 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 1 | 30 |  | 1.028 |  |  | 1.028 | 30.84 | 0 | 0 | 0 | 0 | 0
200X500 | B31 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 0.5 | 2 | 0.708 | 16.88 | 0.708 |  | 18.296 | 0 | 0 | 0 | 18.3 | 0 | 0
| TOP | 16 |  | 1 | 0.5 | 2 | 0.708 | 16.88 | 0.708 |  | 18.296 | 0 | 0 | 0 | 18.3 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 0.5 | 4 |  | 3.44 |  |  | 3.44 | 0 | 0 | 6.88 | 0 | 0 | 0
| TOP EXTRA | 16 |  | 1 | 0.5 | 4 |  | 3.8 |  |  | 3.8 | 0 | 0 | 0 | 7.6 | 0 | 0
| TOP EXTRA | 16 |  | 1 | 0.5 | 4 | 0.708 | 1.4 |  |  | 2.108 | 0 | 0 | 0 | 4.22 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 0.5 | 48 |  | 1.328 |  |  | 1.328 | 31.87 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 0.5 | 34 |  | 1.328 |  |  | 1.328 | 22.58 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 0.5 | 33 |  | 1.328 |  |  | 1.328 | 21.91 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 0.5 | 22 |  | 1.328 |  |  | 1.328 | 14.61 | 0 | 0 | 0 | 0 | 0
230X450 | B32 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 4.005 | 0.708 |  | 5.421 | 0 | 0 | 0 | 10.84 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 4.005 | 0.708 |  | 5.421 | 0 | 0 | 0 | 10.84 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 2 | 19 |  | 1.288 |  |  | 1.288 | 48.94 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 19 |  | 1.288 |  |  | 1.288 | 48.94 | 0 | 0 | 0 | 0 | 0
200X350 | B33 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 5.035 | 0.36333 |  | 6.1063 | 0 | 0 | 0 | 12.21 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 5.035 | 0.36333 |  | 6.1063 | 0 | 0 | 0 | 12.21 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 2 | 21 |  | 1.028 |  |  | 1.028 | 43.18 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 1 | 2 | 21 |  | 1.028 |  |  | 1.028 | 43.18 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 8 |  | 1.028 |  |  | 1.028 | 16.45 | 0 | 0 | 0 | 0 | 0
200X450 | B34 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 10.5 | 0.708 |  | 11.916 | 0 | 0 | 0 | 23.83 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 10.5 | 0.708 |  | 11.916 | 0 | 0 | 0 | 23.83 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 4 |  | 3.85 |  |  | 3.85 | 0 | 0 | 15.4 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 |  | 3.3 |  |  | 3.3 | 0 | 0 | 6.6 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 4 |  | 1.5 | 0.536 |  | 2.036 | 0 | 0 | 8.14 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 2 | 26 |  | 1.2 |  |  | 1.2 | 62.4 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 18 |  | 1.2 |  |  | 1.2 | 43.2 | 0 | 0 | 0 | 0 | 0
200X500 | B35 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 6.68 | 0.36333 |  | 7.4067 | 0 | 0 | 0 | 14.81 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 6.68 | 0.36333 |  | 7.4067 | 0 | 0 | 0 | 14.81 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 |  | 2.1 |  |  | 2.1 | 0 | 0 | 4.2 | 0 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 2 | 20 |  | 1.328 |  |  | 1.328 | 53.12 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 9 |  | 1.328 |  |  | 1.328 | 23.9 | 0 | 0 | 0 | 0 | 0
200X450 | B36 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.708 | 8.225 | 0.36333 |  | 9.2963 | 0 | 0 | 0 | 55.78 | 0 | 0
| TOP | 16 |  | 3 | 1 | 2 | 0.708 | 8.225 | 0.36333 |  | 9.2963 | 0 | 0 | 0 | 55.78 | 0 | 0
| TOP EXTRA | 16 |  | 3 | 1 | 2 |  | 2.865 | 0.31333 |  | 3.1783 | 0 | 0 | 0 | 19.07 | 0 | 0
| STIRRUPS 230X500 | 8 | 100 | 3 | 2 | 5 |  | 1.388 |  |  | 1.388 | 41.64 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X500 | 8 | 100 | 3 | 2 | 19 |  | 1.388 |  |  | 1.388 | 158.23 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 3 | 2 | 20 |  | 1.392 |  |  | 1.392 | 167.04 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 2 | 11 |  | 1.392 |  |  | 1.392 | 91.87 | 0 | 0 | 0 | 0 | 0
200X450 | B37 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.36333 | 3.86 | 0.36333 |  | 4.5867 | 0 | 0 | 0 | 27.52 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.95 | 0.415 | 0.36333 |  | 1.7283 | 0 | 0 | 0 | 10.37 | 0 | 0
| TOP | 16 |  | 3 | 1 | 2 | 0.36333 | 4.475 | 0.36333 |  | 5.2017 | 0 | 0 | 0 | 31.21 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 3 | 1 | 19 |  | 1.228 |  |  | 1.228 | 70 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 14 |  | 1.228 |  |  | 1.228 | 51.58 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 100X350 | 8 | 100 | 3 | 1 | 5 |  | 0.828 |  |  | 0.828 | 12.42 | 0 | 0 | 0 | 0 | 0
200X450 | B38 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.708 | 3.52 | 0.36333 |  | 4.5913 | 0 | 0 | 0 | 27.55 | 0 | 0
| TOP | 16 |  | 3 | 1 | 2 | 0.708 | 3.52 | 0.36333 |  | 4.5913 | 0 | 0 | 0 | 27.55 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 3 | 1 | 18 |  | 1.228 |  |  | 1.228 | 66.31 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 12 |  | 1.228 |  |  | 1.228 | 44.21 | 0 | 0 | 0 | 0 | 0
200X450 | B39 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 2 | 2 | 0.36333 | 3.55 | 0.58 |  | 4.4933 | 0 | 0 | 0 | 17.97 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 2.955 | 0.708 |  | 4.371 | 0 | 0 | 0 | 8.74 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 7.21 | 0.708 | 0.784 | 9.0653 | 0 | 0 | 0 | 18.13 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 2 | 18 |  | 1.028 |  |  | 1.028 | 37.01 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 13 |  | 1.028 |  |  | 1.028 | 26.73 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 18 |  | 1.228 |  |  | 1.228 | 22.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 9 |  | 1.228 |  |  | 1.228 | 11.05 | 0 | 0 | 0 | 0 | 0
200X450 | B40 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 4 | 0.36333 | 3 | 0.708 |  | 4.0713 | 0 | 0 | 0 | 16.29 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.58 | 4.13 | 0.58 |  | 5.29 | 0 | 0 | 0 | 10.58 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 11.63 | 0.36333 |  | 12.3567 | 0 | 0 | 0 | 24.71 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 3.33 |  |  | 3.33 | 0 | 0 | 6.66 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 4 |  | 2.85 |  |  | 2.85 | 0 | 0 | 11.4 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 2 | 18 |  | 1.228 |  |  | 1.228 | 44.21 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 9 |  | 1.228 |  |  | 1.228 | 22.1 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 1 | 21 |  | 1.028 |  |  | 1.028 | 21.59 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 15 |  | 1.028 |  |  | 1.028 | 15.42 | 0 | 0 | 0 | 0 | 0
200X500 | B41 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.708 | 3.31 | 0.708 |  | 4.726 | 0 | 0 | 0 | 28.36 | 0 | 0
| TOP | 16 |  | 3 | 1 | 2 | 0.708 | 3.31 | 0.708 |  | 4.726 | 0 | 0 | 0 | 28.36 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 3 | 1 | 20 |  | 1.328 |  |  | 1.328 | 79.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 11 |  | 1.328 |  |  | 1.328 | 43.82 | 0 | 0 | 0 | 0 | 0
200X450 | B42 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 4.79 | 0.36333 |  | 5.5167 | 0 | 0 | 0 | 11.03 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 4.79 | 0.36333 |  | 5.5167 | 0 | 0 | 0 | 11.03 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 2 | 23 |  | 1.228 |  |  | 1.228 | 56.49 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
200X450 | B43 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 7.795 | 0.708 |  | 8.8663 | 0 | 0 | 0 | 17.73 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 7.795 | 0.708 |  | 8.8663 | 0 | 0 | 0 | 17.73 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 3.995 |  |  | 3.995 | 0 | 0 | 7.99 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 2 | 2 |  | 3.25 |  |  | 3.25 | 0 | 0 | 13 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 2 | 2 |  | 1.5 | 0.536 |  | 2.036 | 0 | 0 | 8.14 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 21 |  | 1.352 |  |  | 1.352 | 28.39 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 1 | 1 | 26 |  | 1.352 |  |  | 1.352 | 35.15 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 18 |  | 1.352 |  |  | 1.352 | 24.34 | 0 | 0 | 0 | 0 | 0
200X450 | B44 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 3 | 0.708 |  | 4.0713 | 0 | 0 | 0 | 8.14 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.58 | 1.95 | 0.36333 |  | 2.8933 | 0 | 0 | 0 | 5.79 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 5.7 | 0.36333 |  | 6.4267 | 0 | 0 | 0 | 12.85 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 31 |  | 1.328 |  |  | 1.328 | 41.17 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 1 | 21 |  | 1.028 |  |  | 1.028 | 21.59 | 0 | 0 | 0 | 0 | 0
200X450 | B45 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 2.23 | 0.74 |  | 3.3333 | 0 | 0 | 0 | 6.67 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 2.23 | 0.74 |  | 3.3333 | 0 | 0 | 0 | 6.67 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 23 |  | 1.228 |  |  | 1.228 | 28.24 | 0 | 0 | 0 | 0 | 0
200X500 | B46 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 5.145 | 0.708 |  | 6.561 | 0 | 0 | 0 | 13.12 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 5.145 | 0.708 |  | 6.561 | 0 | 0 | 0 | 13.12 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 4.145 |  |  | 4.145 | 0 | 0 | 8.29 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 4 | 0.536 | 1.5 |  |  | 2.036 | 0 | 0 | 8.14 | 0 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 26 |  | 1.328 |  |  | 1.328 | 34.53 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 18 |  | 1.328 |  |  | 1.328 | 23.9 | 0 | 0 | 0 | 0 | 0
200X500 | B47 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 3.8 | 0.708 |  | 5.216 | 0 | 0 | 0 | 10.43 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 3.8 | 0.708 |  | 5.216 | 0 | 0 | 0 | 10.43 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 20 |  | 1.328 |  |  | 1.328 | 26.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 13 |  | 1.328 |  |  | 1.328 | 17.26 | 0 | 0 | 0 | 0 | 0
200X350 | B48 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 2.95 | 0.36333 |  | 4.0213 | 0 | 0 | 0 | 8.04 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 2.95 | 0.36333 |  | 4.0213 | 0 | 0 | 0 | 8.04 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 1 | 15 |  | 1.028 |  |  | 1.028 | 15.42 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 11 |  | 1.028 |  |  | 1.028 | 11.31 | 0 | 0 | 0 | 0 | 0
200X450 | B49 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 4.55 | 0.708 |  | 5.966 | 0 | 0 | 0 | 11.93 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 4.55 | 0.708 |  | 5.966 | 0 | 0 | 0 | 11.93 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 23 |  | 1.228 |  |  | 1.228 | 28.24 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 16 |  | 1.228 |  |  | 1.228 | 19.65 | 0 | 0 | 0 | 0 | 0
200X500 | B50 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 3.05 | 0.708 |  | 4.466 | 0 | 0 | 0 | 8.93 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 3.05 | 0.708 |  | 4.466 | 0 | 0 | 0 | 8.93 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 20 |  | 1.328 |  |  | 1.328 | 26.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 8 |  | 1.328 |  |  | 1.328 | 10.62 | 0 | 0 | 0 | 0 | 0
200X450 | B51 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 2.515 | 0.36333 |  | 3.5863 | 0 | 0 | 0 | 7.17 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 2.515 | 0.36333 |  | 3.5863 | 0 | 0 | 0 | 7.17 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 25 |  | 1.228 |  |  | 1.228 | 30.7 | 0 | 0 | 0 | 0 | 0
230X450 | B52 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 3.115 | 0.36333 |  | 4.1863 | 0 | 0 | 0 | 8.37 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 3.115 | 0.36333 |  | 4.1863 | 0 | 0 | 0 | 8.37 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 1 | 19 |  | 1.288 |  |  | 1.288 | 24.47 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 10 |  | 1.288 |  |  | 1.288 | 12.88 | 0 | 0 | 0 | 0 | 0
200X350 | B53 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 1 | 1 | 2 | 0.29667 | 2.345 | 0.29667 |  | 2.9383 | 0 | 0 | 5.88 | 0 | 0 | 0
| TOP | 12 |  | 1 | 1 | 2 | 0.29667 | 2.345 | 0.29667 |  | 2.9383 | 0 | 0 | 5.88 | 0 | 0 | 0
| STIRRUPS 200X350 | 10 | 100 | 1 | 1 | 24 |  | 1.06 |  |  | 1.06 | 0 | 25.44 | 0 | 0 | 0 | 0
230X500 | B54 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 3.2 | 0.708 |  | 4.616 | 0 | 0 | 0 | 9.23 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 3.2 | 0.708 |  | 4.616 | 0 | 0 | 0 | 9.23 | 0 | 0
| STIRRUPS 230X500 | 10 | 100 | 1 | 1 | 18 |  | 1.42 |  |  | 1.42 | 0 | 25.56 | 0 | 0 | 0 | 0
|  | 10 | 150 | 1 | 1 | 9 |  | 1.42 |  |  | 1.42 | 0 | 12.78 | 0 | 0 | 0 | 0
230X450 | B55 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 1 | 1 | 2 | 0.29667 | 0.35 | 0.29667 |  | 0.94333 | 0 | 0 | 1.89 | 0 | 0 | 0
| TOP | 12 |  | 1 | 1 | 2 | 0.29667 | 0.35 | 0.29667 |  | 0.94333 | 0 | 0 | 1.89 | 0 | 0 | 0
| STIRRUPS 230X450 | 10 | 100 | 1 | 1 | 5 |  | 1.32 |  |  | 1.32 | 0 | 6.6 | 0 | 0 | 0 | 0
200X450 | B56 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.74 | 2.36 | 0.36333 |  | 3.4633 | 0 | 0 | 0 | 6.93 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.74 | 2.36 | 0.36333 |  | 3.4633 | 0 | 0 | 0 | 6.93 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 | 0.56 | 0.6 |  |  | 1.16 | 0 | 0 | 2.32 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 18 |  | 1.228 |  |  | 1.228 | 22.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 1 | 1 | 5 |  | 1.228 |  |  | 1.228 | 6.14 | 0 | 0 | 0 | 0 | 0
230X450 | B57 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 5.775 | 0.36333 |  | 6.8463 | 0 | 0 | 0 | 13.69 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 5.775 | 0.36333 |  | 6.8463 | 0 | 0 | 0 | 13.69 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 |  | 1.93 |  |  | 1.93 | 0 | 0 | 3.86 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 1 | 18 |  | 1.288 |  |  | 1.288 | 23.18 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 10 |  | 1.288 |  |  | 1.288 | 12.88 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 1 | 19 |  | 1.288 |  |  | 1.288 | 24.47 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 5 |  | 1.288 |  |  | 1.288 | 6.44 | 0 | 0 | 0 | 0 | 0
230X500/450 | B58 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 6.27 | 0.708 |  | 7.686 | 0 | 0 | 0 | 15.37 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 6.27 | 0.708 |  | 7.686 | 0 | 0 | 0 | 15.37 | 0 | 0
| STIRRUPS 230X500 | 8 | 100 | 1 | 1 | 21 |  | 1.388 |  |  | 1.388 | 29.15 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 5 |  | 1.388 |  |  | 1.388 | 6.94 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 1 | 21 |  | 1.288 |  |  | 1.288 | 27.05 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 11 |  | 1.288 |  |  | 1.288 | 14.17 | 0 | 0 | 0 | 0 | 0
200X500 | B59, B62 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.708 | 2.225 | 0.36333 |  | 3.2963 | 0 | 0 | 0 | 13.19 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.708 | 2.225 | 0.36333 |  | 3.2963 | 0 | 0 | 0 | 13.19 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 2 | 1 | 23 |  | 1.328 |  |  | 1.328 | 61.09 | 0 | 0 | 0 | 0 | 0
200X450 | B60 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 3.14 | 0.708 |  | 4.556 | 0 | 0 | 0 | 9.11 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 3.14 | 0.708 |  | 4.556 | 0 | 0 | 0 | 9.11 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 18 |  | 1.228 |  |  | 1.228 | 22.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 10 |  | 1.228 |  |  | 1.228 | 12.28 | 0 | 0 | 0 | 0 | 0
200/230X450 | B61 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 5.72 | 0.708 |  | 7.136 | 0 | 0 | 0 | 14.27 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 5.72 | 0.708 |  | 7.136 | 0 | 0 | 0 | 14.27 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 19 |  | 1.228 |  |  | 1.228 | 23.33 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 12 |  | 1.228 |  |  | 1.228 | 14.74 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 1 | 21 |  | 1.288 |  |  | 1.288 | 27.05 | 0 | 0 | 0 | 0 | 0
200X450 | B63 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.708 | 3.06 | 0.708 |  | 4.476 | 0 | 0 | 0 | 17.9 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.708 | 3.06 | 0.708 | 0.784 | 5.26 | 0 | 0 | 0 | 21.04 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 2 | 18 |  | 1.252 |  |  | 1.252 | 90.14 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 2 | 9 |  | 1.252 |  |  | 1.252 | 45.07 | 0 | 0 | 0 | 0 | 0
200X350 | B64 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.708 | 3.63 | 0.708 |  | 5.046 | 0 | 0 | 0 | 20.18 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.708 | 3.63 | 0.708 |  | 5.046 | 0 | 0 | 0 | 20.18 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 1 | 2 |  | 0.85 |  |  | 0.85 | 0 | 0 | 3.4 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 2 | 2 | 4 |  | 1.028 |  |  | 1.028 | 16.45 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 2 | 2 | 15 |  | 1.028 |  |  | 1.028 | 61.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 2 | 11 |  | 1.028 |  |  | 1.028 | 45.23 | 0 | 0 | 0 | 0 | 0
200X450 | B65 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 7 | 0.36333 |  | 7.7267 | 0 | 0 | 0 | 15.45 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 7 | 0.36333 |  | 7.7267 | 0 | 0 | 0 | 15.45 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 2 | 18 |  | 1.228 |  |  | 1.228 | 44.21 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 12 |  | 1.228 |  |  | 1.228 | 29.47 | 0 | 0 | 0 | 0 | 0
200X450 | B66 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 2 | 2 | 0.708 | 5.15 | 0.36333 |  | 6.2213 | 0 | 0 | 0 | 24.89 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.79 | 3 | 0.79 |  | 4.58 | 0 | 0 | 0 | 9.16 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 13.9 | 0.708 | 0.79 | 16.106 | 0 | 0 | 0 | 32.21 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 2 | 18 |  | 1.228 |  |  | 1.228 | 44.21 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 11 |  | 1.228 |  |  | 1.228 | 27.02 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 2 | 18 |  | 1.228 |  |  | 1.228 | 44.21 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 2 | 15 |  | 1.028 |  |  | 1.028 | 30.84 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 12 |  | 1.228 |  |  | 1.228 | 29.47 | 0 | 0 | 0 | 0 | 0
200X450 | B67 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.708 | 5.05 | 0.36333 |  | 6.1213 | 0 | 0 | 0 | 24.49 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.708 | 5.05 | 0.36333 | 0.79 | 6.9113 | 0 | 0 | 0 | 27.65 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.228 |  |  | 1.228 | 44.21 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 11 |  | 1.228 |  |  | 1.228 | 27.02 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.228 |  |  | 1.228 | 44.21 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 2 | 12 |  | 1.228 |  |  | 1.228 | 58.94 | 0 | 0 | 0 | 0 | 0
200X350 | B68 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 3.17 | 0.36333 |  | 3.8967 | 0 | 0 | 0 | 7.79 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 3.17 | 0.36333 | 0.79 | 4.6867 | 0 | 0 | 0 | 9.37 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 1 | 16 |  | 1.028 |  |  | 1.028 | 16.45 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 12 |  | 1.028 |  |  | 1.028 | 12.34 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 12 |  | 1.228 |  |  | 1.228 | 29.47 | 0 | 0 | 0 | 0 | 0
200X450 | B69 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 0.5 | 2 | 0.36333 | 5.58 | 0.58 |  | 6.5233 | 0 | 0 | 0 | 6.52 | 0 | 0
| TOP | 16 |  | 1 | 0.5 | 2 | 0.36333 | 5.58 | 0.58 | 0.79 | 7.3133 | 0 | 0 | 0 | 7.31 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 0.5 | 18 |  | 1.228 |  |  | 1.228 | 11.05 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 0.5 | 13 |  | 1.228 |  |  | 1.228 | 7.98 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 0.5 | 21 |  | 1.228 |  |  | 1.228 | 12.89 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 10 |  | 1.328 |  |  | 1.328 | 13.28 | 0 | 0 | 0 | 0 | 0
100X350 | B3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 3 | 1 | 2 | 0.456 | 1.525 | 0.456 |  | 2.437 | 0 | 0 | 14.62 | 0 | 0 | 0
| TOP | 12 |  | 3 | 1 | 2 | 0.456 | 1.525 | 0.456 |  | 2.437 | 0 | 0 | 14.62 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 3 | 1 | 11 |  | 0.828 |  |  | 0.828 | 27.32 | 0 | 0 | 0 | 0 | 0
100X350 | B3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 5 | 1 | 2 | 0.456 | 1.9 | 0.456 |  | 2.812 | 0 | 0 | 28.12 | 0 | 0 | 0
| TOP | 12 |  | 5 | 1 | 2 | 0.456 | 1.9 | 0.456 |  | 2.812 | 0 | 0 | 28.12 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 5 | 1 | 14 |  | 0.828 |  |  | 0.828 | 57.96 | 0 | 0 | 0 | 0 | 0
200X350 | B3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 3 | 1 | 2 | 0.456 | 0.315 | 0.456 |  | 1.227 | 0 | 0 | 7.36 | 0 | 0 | 0
| TOP | 12 |  | 3 | 1 | 2 | 0.456 | 0.315 | 0.456 |  | 1.227 | 0 | 0 | 7.36 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 3 | 1 | 3 |  | 0.928 |  |  | 0.928 | 8.35 | 0 | 0 | 0 | 0 | 0
115X350 | B3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 1 | 1 | 2 | 0.456 | 1.305 | 0.456 |  | 2.217 | 0 | 0 | 4.43 | 0 | 0 | 0
| TOP | 12 |  | 1 | 1 | 2 | 0.456 | 1.305 | 0.456 |  | 2.217 | 0 | 0 | 4.43 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 1 | 1 | 10 |  | 0.858 |  |  | 0.858 | 8.58 | 0 | 0 | 0 | 0 | 0
100X350 | B3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 3 | 1 | 2 | 0.456 | 1.385 | 0.456 |  | 2.297 | 0 | 0 | 13.78 | 0 | 0 | 0
| TOP | 12 |  | 3 | 1 | 2 | 0.456 | 1.385 | 0.456 |  | 2.297 | 0 | 0 | 13.78 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 3 | 1 | 10 |  | 0.828 |  |  | 0.828 | 24.84 | 0 | 0 | 0 | 0 | 0
100X350 | B3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 1 | 1 | 2 | 0.456 | 1.885 | 0.456 |  | 2.797 | 0 | 0 | 5.59 | 0 | 0 | 0
| TOP | 12 |  | 1 | 1 | 2 | 0.456 | 1.885 | 0.456 |  | 2.797 | 0 | 0 | 5.59 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 1 | 1 | 9 |  | 0.828 |  |  | 0.828 | 7.45 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | [10 empty] | 5502.24 | 127.46 | 545.39 | 2200.31 | 58.41 | 27.16
| UNIT WT. | [10 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.47 | 3.85 | A
| TOTAL WT. | [10 empty] | 2173.3848 | 78.6428 | 484.3063 | 3476.4898 | 144.2727 | 104.566 | 6461.6624
SLAB STEEL
FLAT NO- 4, 9
| S 02 Bed room (3200x3550) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 19 |  | 3.55 |  |  | 3.55 | 67.45 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 17 |  | 4.425 |  |  | 4.425 | 75.23 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 |  | 1.2 |  |  | 1.2 | 10.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 |  | 0.65 |  |  | 0.65 | 5.85 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 17 | 0.1 | 0.725 |  |  | 0.825 | 14.03 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 11 |  | 1.2 |  |  | 1.2 | 13.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 10 |  | 0.65 |  |  | 0.65 | 6.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 9.5 |  | 1.3 |  |  | 1.3 | 12.35 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 9.5 |  | 0.7 |  |  | 0.7 | 6.65 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.2 | 3.55 |  |  | 3.75 | 26.25 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.2 | 3.55 |  |  | 3.75 | 26.25 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 3.2 |  |  | 3.4 | 13.6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.2 | 3.2 |  |  | 3.4 | 23.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 7 | 0.1 | 0.725 |  |  | 0.825 | 5.78 | 0 | 0 | 0 | 0 | 0
| S 01 Bed room (3575x3550) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 18 |  | 3.925 |  |  | 3.925 | 70.65 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 18 |  | 4.425 |  |  | 4.425 | 79.65 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 19 | 0.1 | 0.775 |  |  | 0.875 | 16.63 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 18 | 0.1 | 0.775 |  |  | 0.875 | 15.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 11 | 0.1 | 0.775 |  |  | 0.875 | 9.63 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 3 |  | 1.3 |  |  | 1.3 | 3.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 3 |  | 0.7 |  |  | 0.7 | 2.1 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 |  | 1.3 |  |  | 1.3 | 11.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 |  | 0.7 |  |  | 0.7 | 6.3 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 2.9 |  |  | 3.1 | 12.4 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.2 | 2.9 |  |  | 3.1 | 21.7 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 2.6 |  |  | 2.8 | 11.2 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.2 | 2.6 |  |  | 2.8 | 19.6 | 0 | 0 | 0 | 0 | 0
| S 03 Passage (1200x2.785) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 15 |  | 1.55 |  |  | 1.55 | 23.25 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 7 |  | 3.135 |  |  | 3.135 | 21.95 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 6 |  | 1 |  |  | 1 | 6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 5 |  | 0.55 |  |  | 0.55 | 2.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 5 |  | 0.65 |  |  | 0.65 | 3.25 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 17 |  | 0.55 |  |  | 0.55 | 9.35 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 1.2 |  |  | 1.4 | 8.4 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.2 | 1.2 |  |  | 1.4 | 9.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 2.785 |  |  | 2.985 | 8.96 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 11 | 0.2 | 0.575 |  |  | 0.775 | 8.53 | 0 | 0 | 0 | 0 | 0
| S 03 Toilet (1570x3575) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 18 |  | 1.92 |  |  | 1.92 | 34.56 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 9 |  | 3.925 |  |  | 3.925 | 35.33 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 | 0.1 | 0.775 |  |  | 0.875 | 7.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.625 |  |  | 0.725 | 9.43 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.625 |  |  | 0.725 | 9.43 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 8 |  | 0.65 |  |  | 0.65 | 5.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 6 |  | 0.65 |  |  | 0.65 | 3.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 |  | 0.7 |  |  | 0.7 | 6.3 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 1.57 |  |  | 1.77 | 7.08 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 1.57 |  |  | 1.77 | 7.08 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 3.575 |  |  | 3.775 | 15.1 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 3.575 |  |  | 3.775 | 15.1 | 0 | 0 | 0 | 0 | 0
| S 04 Bed room (3050x3115) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 11 |  | 3.4 |  |  | 3.4 | 37.4 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 5 |  | 3.8 |  |  | 3.8 | 19 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 16 |  | 3.465 |  |  | 3.465 | 55.44 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 3 |  | 1.1 |  |  | 1.1 | 3.3 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 10 | 0.1 | 0.675 |  |  | 0.775 | 7.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 14 | 0.1 | 1.29 |  |  | 1.39 | 19.46 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 17 | 0.1 | 0.675 |  |  | 0.775 | 13.18 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 16 | 0.1 | 0.675 |  |  | 0.775 | 12.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 7 |  | 1.1 |  |  | 1.1 | 7.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 6 |  | 0.6 |  |  | 0.6 | 3.6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 3.05 |  |  | 3.25 | 13 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 3.45 |  |  | 3.65 | 14.6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 3.115 |  |  | 3.315 | 13.26 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 2.245 |  |  | 2.445 | 14.67 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 1.05 |  |  | 1.25 | 3.75 | 0 | 0 | 0 | 0 | 0
| S 05 Toilet (1600x2515) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 13 |  | 1.95 |  |  | 1.95 | 25.35 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 9 |  | 2.865 |  |  | 2.865 | 25.79 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.625 |  |  | 0.725 | 9.43 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.625 |  |  | 0.725 | 9.43 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.625 |  |  | 0.725 | 5.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.675 |  |  | 0.775 | 6.2 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 1.6 |  |  | 1.8 | 5.4 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 1.6 |  |  | 1.8 | 5.4 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 2.515 |  |  | 2.715 | 8.15 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 2.515 |  |  | 2.715 | 8.15 | 0 | 0 | 0 | 0 | 0
| S 06 Drawing Room (4105x6165) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR a | 8 | 100 | 1 | 1 | 31.5 |  | 4.455 |  |  | 4.455 | 140.33 | 0 | 0 | 0 | 0 | 0
| MAIN BAR a | 8 | 100 | 1 | 1 | 31 |  | 3.305 |  |  | 3.305 | 102.46 | 0 | 0 | 0 | 0 | 0
| DIST. BAR c | 8 | 150 | 1 | 1 | 14 |  | 7.165 |  |  | 7.165 | 100.31 | 0 | 0 | 0 | 0 | 0
| DIST. BAR c | 8 | 150 | 1 | 1 | 14 |  | 4.665 |  |  | 4.665 | 65.31 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 22 | 0.1 | 1.125 |  |  | 1.225 | 26.95 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 13 |  | 1.3 |  |  | 1.3 | 16.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 12 |  | 1.3 |  |  | 1.3 | 15.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 6 |  | 1.4 |  |  | 1.4 | 8.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 6.5 |  | 0.75 |  |  | 0.75 | 4.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 15 | 0.1 | 0.825 |  |  | 0.925 | 13.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 14 |  | 2 |  |  | 2 | 28 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 13 |  | 1.05 |  |  | 1.05 | 13.65 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 27 | 0.1 | 0.825 |  |  | 0.925 | 24.98 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 11.5 |  | 1.4 |  |  | 1.4 | 16.1 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 11.5 |  | 0.75 |  |  | 0.75 | 8.63 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 11 | 0.2 | 4.105 |  |  | 4.305 | 47.36 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 4.105 |  |  | 4.305 | 25.83 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.2 | 6.165 |  |  | 6.365 | 44.56 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 8 | 0.2 | 6.165 |  |  | 6.365 | 50.92 | 0 | 0 | 0 | 0 | 0
| S 07 Kitchen (2335x2850) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 1 | 1 | 15 |  | 2.685 |  |  | 2.685 | 40.28 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 13 |  | 3.2 |  |  | 3.2 | 41.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.1 | 0.625 |  |  | 0.725 | 8.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 15 | 0.1 | 0.625 |  |  | 0.725 | 10.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 9 |  | 0.9 |  |  | 0.9 | 8.1 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 9 |  | 0.5 |  |  | 0.5 | 4.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 4 |  | 1 |  |  | 1 | 4 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 1.5 | 0.2 | 2.335 |  |  | 2.535 | 3.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 2.335 |  |  | 2.535 | 7.61 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 1.5 | 0.2 | 2.85 |  |  | 3.05 | 4.58 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 2.5 | 0.2 | 2.85 |  |  | 3.05 | 7.63 | 0 | 0 | 0 | 0 | 0
| S 08 Foyer (1035x1500) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 1 | 1 | 9 |  | 1.385 |  |  | 1.385 | 12.47 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 6 |  | 1.85 |  |  | 1.85 | 11.1 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 10 |  | 1.23 |  |  | 1.23 | 12.3 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 8 |  | 1.72 |  |  | 1.72 | 13.76 | 0 | 0 | 0 | 0 | 0
| S 024 Balcony Bedroom (2000x6300) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 43 | 0.25 | 2.13 | 0.4 |  | 2.78 | 0 | 119.54 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 11 | 0.1 | 6.25 | 0.1 |  | 6.45 | 70.95 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 32 |  | 4.475 | 0.1 |  | 4.575 | 0 | 0 | 146.4 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 32 |  | 3.55 |  |  | 3.55 | 0 | 113.6 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 11 | 0.1 | 6.25 | 0.1 |  | 6.45 | 141.9 | 0 | 0 | 0 | 0 | 0
| S 024 Balcony Drawing Room (2000x4065) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 28 | 0.25 | 2.13 | 0.4 |  | 2.78 | 0 | 77.84 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 11 |  | 4.015 | 0.1 |  | 4.115 | 45.27 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 21 |  | 4.475 | 0.1 |  | 4.575 | 0 | 0 | 96.08 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 21 |  | 3.55 |  |  | 3.55 | 0 | 74.55 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 11 | 0.1 | 4.015 | 0.1 |  | 4.215 | 92.73 | 0 | 0 | 0 | 0 | 0
| L-SHAPE IN LEDGE WALL | 10 | 150 | 1 | 1 | 17 | 0.1 | 0.3 | 0.49 |  | 0.89 | 0 | 15.13 | 0 | 0 | 0 | 0
| S 024 Balcony Kitchen (2000x1845) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 3 |  | 1.5 |  |  | 1.5 | 0 | 4.5 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 9 | 0.05 | 2.1 | 0.4 |  | 2.55 | 0 | 22.95 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 6 |  | 1.795 | 0.1 |  | 1.895 | 11.37 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 7 |  | 4.675 | 0.1 |  | 4.775 | 0 | 0 | 33.43 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 9.5 |  | 3.55 |  |  | 3.55 | 0 | 33.73 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 6 |  | 1.795 |  |  | 1.795 | 21.54 | 0 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 4 |  | 1.7 |  |  | 1.7 | 13.6 | 0 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 4 |  | 1.7 |  |  | 1.7 | 13.6 | 0 | 0 | 0 | 0 | 0
| FLAT NO- 5, 8 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S 09 Bed room (3205x3560) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 19 |  | 3.555 |  |  | 3.555 | 67.55 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 17 |  | 4.435 |  |  | 4.435 | 75.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 17 | 0.1 | 0.725 |  |  | 0.825 | 14.03 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 18.5 |  | 1.2 |  |  | 1.2 | 22.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 18 |  | 0.65 |  |  | 0.65 | 11.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 12.5 |  | 1.2 |  |  | 1.2 | 15 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 12 |  | 0.65 |  |  | 0.65 | 7.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 11 |  | 1.2 |  |  | 1.2 | 13.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 11 |  | 0.65 |  |  | 0.65 | 7.15 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.2 | 3.205 |  |  | 3.405 | 23.84 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 3.205 |  |  | 3.405 | 13.62 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.2 | 3.56 |  |  | 3.76 | 26.32 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.2 | 3.56 |  |  | 3.76 | 26.32 | 0 | 0 | 0 | 0 | 0
| S 05 Bed room Toilet (1500x2225) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 12 |  | 1.85 |  |  | 1.85 | 22.2 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 9 |  | 2.575 |  |  | 2.575 | 23.18 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 11 | 0.1 | 0.625 |  |  | 0.725 | 7.98 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 11 | 0.1 | 0.625 |  |  | 0.725 | 7.98 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.625 |  |  | 0.725 | 5.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.675 |  |  | 0.775 | 6.2 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 1.5 |  |  | 1.7 | 5.1 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 1.5 |  |  | 1.7 | 5.1 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 2.225 |  |  | 2.425 | 7.28 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 2.225 |  |  | 2.425 | 7.28 | 0 | 0 | 0 | 0 | 0
| S 011 Drawing Room | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 6 |  | 3.68 |  |  | 3.68 | 22.08 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 6.5 |  | 1.93 |  |  | 1.93 | 12.55 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 7 |  | 4.62 |  |  | 4.62 | 32.34 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 6 |  | 2.87 |  |  | 2.87 | 17.22 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 5 |  | 7.15 |  |  | 7.15 | 35.75 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 5.5 |  | 5.1 |  |  | 5.1 | 28.05 | 0 | 0 | 0 | 0 | 0
| Dist. Bar d | 8 | 175 | 1 | 1 | 15 |  | 1.82 |  |  | 1.82 | 27.3 | 0 | 0 | 0 | 0 | 0
| Dist. Bar d | 8 | 175 | 1 | 1 | 19 |  | 6.09 |  |  | 6.09 | 115.71 | 0 | 0 | 0 | 0 | 0
| Dist. Bar d | 8 | 175 | 1 | 1 | 6 |  | 3.75 |  |  | 3.75 | 22.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 20 | 0.1 | 0.975 |  |  | 1.075 | 21.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 13 |  | 1.2 |  |  | 1.2 | 15.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 13 |  | 0.65 |  |  | 0.65 | 8.45 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 6.5 |  | 1.2 |  |  | 1.2 | 7.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 6.5 |  | 0.65 |  |  | 0.65 | 4.23 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 4.5 |  | 1.5 |  |  | 1.5 | 6.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 4 |  | 0.8 |  |  | 0.8 | 3.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.875 |  |  | 0.975 | 12.68 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 14.5 |  | 1.7 |  |  | 1.7 | 24.65 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 14.5 |  | 0.9 |  |  | 0.9 | 13.05 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 17 |  | 1.67 |  |  | 1.67 | 28.39 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.2 | 3.05 |  |  | 3.25 | 16.25 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.1 | 3.76 |  |  | 3.86 | 27.02 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 3.2 |  |  | 3.4 | 20.4 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 9 | 0.2 | 6.79 |  |  | 6.99 | 62.91 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 8 | 0.2 | 1.47 |  |  | 1.67 | 13.36 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 8 | 0.2 | 2.55 |  |  | 2.75 | 22 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.1 | 3.76 |  |  | 3.86 | 27.02 | 0 | 0 | 0 | 0 | 0
| S 012 Kitchen (2365x3250) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 17 |  | 2.715 |  |  | 2.715 | 46.16 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 13 |  | 4.12 |  |  | 4.12 | 53.56 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.1 | 0.725 |  |  | 0.825 | 9.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.625 |  |  | 0.725 | 5.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 5.5 |  | 0.9 |  |  | 0.9 | 4.95 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 5 |  | 0.5 |  |  | 0.5 | 2.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8.5 |  | 0.9 |  |  | 0.9 | 7.65 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.5 |  |  | 0.5 | 4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 6 |  | 0.65 |  |  | 0.65 | 3.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 5 |  | 1.1 |  |  | 1.1 | 5.5 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 2.365 |  |  | 2.565 | 10.26 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.2 | 3.25 |  |  | 3.45 | 17.25 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.2 | 3.25 |  |  | 3.45 | 17.25 | 0 | 0 | 0 | 0 | 0
| S 013 Bed room (2925x3250) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 17 |  | 3.275 |  |  | 3.275 | 55.68 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 16 |  | 4.12 |  |  | 4.12 | 65.92 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 16 | 0.1 | 0.725 |  |  | 0.825 | 13.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.675 |  |  | 0.775 | 6.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4.5 |  | 1.1 |  |  | 1.1 | 4.95 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 0.6 |  |  | 0.6 | 2.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 1.1 |  |  | 1.1 | 8.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.6 |  |  | 0.6 | 4.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 1.1 |  |  | 1.1 | 8.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.6 |  |  | 0.6 | 4.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 2.925 |  |  | 3.125 | 12.5 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 3.25 |  |  | 3.45 | 20.7 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 3.25 |  |  | 3.45 | 20.7 | 0 | 0 | 0 | 0 | 0
| S 14 Passege (1700x2925) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 1 | 1 | 16 |  | 2.05 |  |  | 2.05 | 32.8 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 9 |  | 3.275 |  |  | 3.275 | 29.48 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 16 |  | 0.7 |  |  | 0.7 | 11.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 15 | 0.1 | 0.675 |  |  | 0.775 | 11.63 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 5 |  | 1.1 |  |  | 1.1 | 5.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 0.6 |  |  | 0.6 | 2.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 3 |  | 1.1 |  |  | 1.1 | 3.3 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 3 |  | 0.6 |  |  | 0.6 | 1.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 2.925 |  |  | 3.125 | 12.5 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 2.925 |  |  | 3.125 | 12.5 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 1.7 |  |  | 1.9 | 11.4 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 1.7 |  |  | 1.9 | 11.4 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.1 | 0.725 |  |  | 0.825 | 2.48 | 0 | 0 | 0 | 0 | 0
| S 03 Bedroom Toilet (1425x3385) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 18 |  | 1.775 |  |  | 1.775 | 31.95 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 8 |  | 3.735 |  |  | 3.735 | 29.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.1 | 0.77 |  |  | 0.87 | 10.44 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.1 | 0.625 |  |  | 0.725 | 8.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.625 |  |  | 0.725 | 5.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 6 |  | 1.625 |  |  | 1.625 | 9.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.7 |  |  | 0.7 | 5.6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 1.42 |  |  | 1.62 | 6.48 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 1.42 |  |  | 1.62 | 6.48 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 3.575 |  |  | 3.775 | 15.1 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 3.575 |  |  | 3.775 | 15.1 | 0 | 0 | 0 | 0 | 0
| S 024 Balcony Drg. Room (2000x4665) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 32 | 0.25 | 2.13 | 0.4 |  | 2.78 | 0 | 88.96 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 10 |  | 4.615 |  |  | 4.615 | 46.15 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 24 |  | 4.475 | 0.1 |  | 4.575 | 0 | 0 | 109.8 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 24 |  | 3.55 |  |  | 3.55 | 0 | 85.2 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 10 |  | 4.615 |  |  | 4.615 | 92.3 | 0 | 0 | 0 | 0 | 0
| S 024 Balcony Bedroom & Kitchen (2000x5105) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 35 | 0.25 | 2.13 | 0.4 |  | 2.78 | 0 | 97.3 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 11 | 0.1 | 5.055 | 0.1 |  | 5.255 | 57.81 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 26 |  | 4.475 | 0.1 |  | 4.575 | 0 | 0 | 118.95 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 26 |  | 3.55 |  |  | 3.55 | 0 | 92.3 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 11 | 0.1 | 5.055 | 0.1 |  | 5.255 | 115.61 | 0 | 0 | 0 | 0 | 0
| L-SHAPE IN LEDGE WALL | 10 | 150 | 1 | 2 | 14 | 0.1 | 0.3 | 0.49 |  | 0.89 | 0 | 24.92 | 0 | 0 | 0 | 0
| S 15 Bedroom (3050x3580) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 1 | 1 | 18 |  | 3.4 |  |  | 3.4 | 61.2 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 16 |  | 3.93 |  |  | 3.93 | 62.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 16 | 0.1 | 0.775 |  |  | 0.875 | 14 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.7 |  |  | 0.7 | 5.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 7 |  | 1.3 |  |  | 1.3 | 9.1 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 2 | 9 |  | 0.6 |  |  | 0.6 | 10.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 2 | 9 |  | 1.1 |  |  | 1.1 | 19.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 3.05 |  |  | 3.25 | 13 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.2 | 3.05 |  |  | 3.25 | 22.75 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 3.58 |  |  | 3.78 | 22.68 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 3.58 |  |  | 3.78 | 22.68 | 0 | 0 | 0 | 0 | 0
| S 16 Dressing Area (1410x2430) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 1 | 1 | 13 |  | 1.78 |  |  | 1.78 | 23.14 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 8 |  | 0.75 |  |  | 0.75 | 6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 | 0.1 | 0.625 |  |  | 0.725 | 6.53 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.625 |  |  | 0.725 | 9.43 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 |  | 0.6 |  |  | 0.6 | 7.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.9 |  |  | 0.9 | 7.2 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 1.41 |  |  | 1.61 | 4.83 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.2 | 1.41 |  |  | 1.61 | 8.05 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 2.43 |  |  | 2.63 | 10.52 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 2.43 |  |  | 2.63 | 7.89 | 0 | 0 | 0 | 0 | 0
| S 05 Toilet (1540x2410) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 1 | 1 | 13 |  | 1.89 |  |  | 1.89 | 24.57 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 8 |  | 2.76 |  |  | 2.76 | 22.08 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 | 0.15 | 0.625 |  |  | 0.775 | 6.98 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 | 0.15 | 0.625 |  |  | 0.775 | 6.98 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.15 | 0.55 |  |  | 0.7 | 8.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.15 | 0.55 |  |  | 0.7 | 8.4 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 1.54 |  |  | 1.74 | 5.22 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 1.54 |  |  | 1.74 | 5.22 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 2.41 |  |  | 2.61 | 7.83 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 2.41 |  |  | 2.61 | 7.83 | 0 | 0 | 0 | 0 | 0
| S 024 Balcony Bedroom (2000x3265) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 21 | 0.25 | 2.13 | 0.4 |  | 2.78 | 0 | 58.38 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 11 |  | 3.215 |  |  | 3.215 | 35.37 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 16 |  | 4.475 | 0.1 |  | 4.575 | 0 | 0 | 73.2 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 16 |  | 3.55 |  |  | 3.55 | 0 | 56.8 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 12 |  | 3.215 |  |  | 3.215 | 77.16 | 0 | 0 | 0 | 0 | 0
| FLAT NO- 6, 7 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S 09 Bed room (3205x3560) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 19 |  | 3.555 |  |  | 3.555 | 67.55 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 17 |  | 4.435 |  |  | 4.435 | 75.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 17 | 0.1 | 0.725 |  |  | 0.825 | 14.03 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 18.5 |  | 1.2 |  |  | 1.2 | 22.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 18 |  | 0.65 |  |  | 0.65 | 11.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 12.5 |  | 1.2 |  |  | 1.2 | 15 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 12 |  | 0.65 |  |  | 0.65 | 7.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 11 |  | 1.2 |  |  | 1.2 | 13.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 11 |  | 0.65 |  |  | 0.65 | 7.15 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.2 | 3.205 |  |  | 3.405 | 23.84 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 3.205 |  |  | 3.405 | 13.62 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.2 | 3.56 |  |  | 3.76 | 26.32 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.2 | 3.56 |  |  | 3.76 | 26.32 | 0 | 0 | 0 | 0 | 0
| S 05 Bed room Toilet (1500x2225) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 12 |  | 1.85 |  |  | 1.85 | 22.2 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 9 |  | 2.575 |  |  | 2.575 | 23.18 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 11 | 0.1 | 0.625 |  |  | 0.725 | 7.98 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 11 | 0.1 | 0.625 |  |  | 0.725 | 7.98 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.625 |  |  | 0.725 | 5.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.675 |  |  | 0.775 | 6.2 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 1.5 |  |  | 1.7 | 5.1 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 1.5 |  |  | 1.7 | 5.1 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 2.225 |  |  | 2.425 | 7.28 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 2.225 |  |  | 2.425 | 7.28 | 0 | 0 | 0 | 0 | 0
| S 011 Drawing Room | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 6 |  | 3.68 |  |  | 3.68 | 22.08 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 6.5 |  | 1.93 |  |  | 1.93 | 12.55 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 7 |  | 4.62 |  |  | 4.62 | 32.34 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 6 |  | 2.87 |  |  | 2.87 | 17.22 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 5 |  | 7.15 |  |  | 7.15 | 35.75 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 5.5 |  | 5.1 |  |  | 5.1 | 28.05 | 0 | 0 | 0 | 0 | 0
| Dist. Bar d | 8 | 175 | 1 | 1 | 15 |  | 1.82 |  |  | 1.82 | 27.3 | 0 | 0 | 0 | 0 | 0
| Dist. Bar d | 8 | 175 | 1 | 1 | 19 |  | 6.09 |  |  | 6.09 | 115.71 | 0 | 0 | 0 | 0 | 0
| Dist. Bar d | 8 | 175 | 1 | 1 | 6 |  | 3.75 |  |  | 3.75 | 22.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 20 | 0.1 | 0.975 |  |  | 1.075 | 21.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 13 |  | 1.2 |  |  | 1.2 | 15.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 13 |  | 0.65 |  |  | 0.65 | 8.45 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 6.5 |  | 1.2 |  |  | 1.2 | 7.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 6.5 |  | 0.65 |  |  | 0.65 | 4.23 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 4.5 |  | 1.5 |  |  | 1.5 | 6.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 4 |  | 0.8 |  |  | 0.8 | 3.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.875 |  |  | 0.975 | 12.68 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 14.5 |  | 1.7 |  |  | 1.7 | 24.65 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 14.5 |  | 0.9 |  |  | 0.9 | 13.05 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 17 |  | 1.67 |  |  | 1.67 | 28.39 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.2 | 3.05 |  |  | 3.25 | 16.25 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.1 | 3.76 |  |  | 3.86 | 27.02 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 3.2 |  |  | 3.4 | 20.4 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 9 | 0.2 | 6.79 |  |  | 6.99 | 62.91 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 8 | 0.2 | 1.47 |  |  | 1.67 | 13.36 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 8 | 0.2 | 2.55 |  |  | 2.75 | 22 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.1 | 3.76 |  |  | 3.86 | 27.02 | 0 | 0 | 0 | 0 | 0
| S 012 Kitchen (2365x3250) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 17 |  | 2.715 |  |  | 2.715 | 46.16 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 13 |  | 3.6 |  |  | 3.6 | 46.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.725 |  |  | 0.825 | 10.73 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 | 0.1 | 0.625 |  |  | 0.725 | 6.53 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 5.5 |  | 0.9 |  |  | 0.9 | 4.95 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 5.5 |  | 0.5 |  |  | 0.5 | 2.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8.5 |  | 0.9 |  |  | 0.9 | 7.65 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8.5 |  | 0.5 |  |  | 0.5 | 4.25 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 2.365 |  |  | 2.565 | 10.26 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.2 | 3.25 |  |  | 3.45 | 17.25 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.2 | 3.25 |  |  | 3.45 | 17.25 | 0 | 0 | 0 | 0 | 0
| S 013 Bed room (2925x3250) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 16 |  | 3.275 |  |  | 3.275 | 52.4 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 15 |  | 3.6 |  |  | 3.6 | 54 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 16 | 0.1 | 0.725 |  |  | 0.825 | 13.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 15 | 0.1 | 0.675 |  |  | 0.775 | 11.63 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 1.1 |  |  | 1.1 | 8.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 7 |  | 0.6 |  |  | 0.6 | 4.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 |  | 1.1 |  |  | 1.1 | 9.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.6 |  |  | 0.6 | 4.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 2.925 |  |  | 3.125 | 12.5 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 3.25 |  |  | 3.45 | 20.7 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 3.25 |  |  | 3.45 | 20.7 | 0 | 0 | 0 | 0 | 0
| S 14 Passege (1700x2925) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 1 | 1 | 15 |  | 2.05 |  |  | 2.05 | 30.75 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 10 |  | 3.275 |  |  | 3.275 | 32.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 15 |  | 0.7 |  |  | 0.7 | 10.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 15 | 0.1 | 0.675 |  |  | 0.775 | 11.63 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 5 |  | 1.1 |  |  | 1.1 | 5.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 0.6 |  |  | 0.6 | 2.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 9 | 0.1 | 0.675 |  |  | 0.775 | 6.98 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 2.925 |  |  | 3.125 | 12.5 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 2.925 |  |  | 3.125 | 12.5 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 1.7 |  |  | 1.9 | 11.4 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 1.7 |  |  | 1.9 | 11.4 | 0 | 0 | 0 | 0 | 0
| S 03 Bedroom Toilet (1425x3385) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 18 |  | 1.775 |  |  | 1.775 | 31.95 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 8 |  | 3.735 |  |  | 3.735 | 29.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.1 | 0.775 |  |  | 0.875 | 10.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.1 | 0.625 |  |  | 0.725 | 8.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.625 |  |  | 0.725 | 5.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 8 |  | 1.625 |  |  | 1.625 | 13 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.7 |  |  | 0.7 | 5.6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 1.425 |  |  | 1.625 | 6.5 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 1.425 |  |  | 1.625 | 6.5 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 3.575 |  |  | 3.775 | 15.1 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 3.575 |  |  | 3.775 | 15.1 | 0 | 0 | 0 | 0 | 0
| S 024 Balcony Drg. Room (2000x4665) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 32 | 0.25 | 2.13 | 0.4 |  | 2.78 | 0 | 88.96 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 10 |  | 4.615 |  |  | 4.615 | 46.15 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 24 |  | 4.475 | 0.1 |  | 4.575 | 0 | 0 | 109.8 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 24 |  | 3.55 |  |  | 3.55 | 0 | 85.2 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 10 |  | 4.615 |  |  | 4.615 | 92.3 | 0 | 0 | 0 | 0 | 0
| S 024 Balcony Bedroom & Kitchen (2000x5105) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 35 | 0.25 | 1.975 | 0.4 |  | 2.625 | 0 | 91.88 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 11 | 0.1 | 5.055 | 0.1 |  | 5.255 | 57.81 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 26 |  | 4.475 | 0.1 |  | 4.575 | 0 | 0 | 118.95 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 26 |  | 3.55 |  |  | 3.55 | 0 | 92.3 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 11 | 0.1 | 5.055 | 0.1 |  | 5.255 | 115.61 | 0 | 0 | 0 | 0 | 0
| L-SHAPE IN LEDGE WALL | 10 | 150 | 1 | 2 | 14 | 0.1 | 0.3 | 0.49 |  | 0.89 | 0 | 24.92 | 0 | 0 | 0 | 0
| FLAT NO- 1,2,3, 10,11,12 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S 20 Bed room (3250x3860) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 3 | 1 | 20 |  | 3.6 |  |  | 3.6 | 216 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 1 | 17 |  | 4.21 |  |  | 4.21 | 214.71 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 17 | 0.1 | 0.725 |  |  | 0.825 | 42.08 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 12 | 0.1 | 0.775 |  |  | 0.875 | 31.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 8.5 |  | 1.3 |  |  | 1.3 | 33.15 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 8 |  | 0.7 |  |  | 0.7 | 16.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 10 |  | 1.2 |  |  | 1.2 | 36 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 9 |  | 0.6 |  |  | 0.6 | 16.2 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 12 | 0.2 | 3.25 |  |  | 3.45 | 124.2 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 7 | 0.2 | 3.25 |  |  | 3.45 | 72.45 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 4 | 0.2 | 3.86 |  |  | 4.06 | 48.72 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 6 | 0.2 | 3.86 |  |  | 4.06 | 73.08 | 0 | 0 | 0 | 0 | 0
| S 20, 2nd Bed room (3335X3860) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 3 | 1 | 20 |  | 3.685 |  |  | 3.685 | 221.1 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 1 | 18 |  | 4.21 |  |  | 4.21 | 227.34 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 18 | 0.1 | 0.775 |  |  | 0.875 | 47.25 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 40 |  | 1.2 |  |  | 1.2 | 144 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 40 |  | 0.65 |  |  | 0.65 | 78 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 10 |  | 1.3 |  |  | 1.3 | 39 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 9 |  | 0.7 |  |  | 0.7 | 18.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 9 |  | 1.2 |  |  | 1.2 | 32.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 9 |  | 0.6 |  |  | 0.6 | 16.2 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 12 | 0.2 | 3.335 |  |  | 3.535 | 127.26 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 7 | 0.2 | 3.335 |  |  | 3.535 | 74.24 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 4 | 0.2 | 3.86 |  |  | 4.06 | 48.72 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 7 | 0.2 | 3.86 |  |  | 4.06 | 85.26 | 0 | 0 | 0 | 0 | 0
| S 01, 3rd Bed room (3265x3550) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 3 | 1 | 19 |  | 3.615 |  |  | 3.615 | 206.06 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 1 | 17 |  | 4.425 |  |  | 4.425 | 225.68 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 19 | 0.1 | 0.775 |  |  | 0.875 | 49.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 17 | 0.1 | 0.775 |  |  | 0.875 | 44.63 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 12 | 0.1 | 0.775 |  |  | 0.875 | 31.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 3 | 1 | 3 |  | 1.3 |  |  | 1.3 | 11.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 3 | 1 | 3 |  | 0.65 |  |  | 0.65 | 5.85 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 8.5 |  | 1.2 |  |  | 1.2 | 30.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 8 |  | 0.65 |  |  | 0.65 | 15.6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 4 | 0.2 | 3.265 |  |  | 3.465 | 41.58 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 7 | 0.2 | 3.265 |  |  | 3.465 | 72.77 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 4 | 0.2 | 3.55 |  |  | 3.75 | 45 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 7 | 0.2 | 3.55 |  |  | 3.75 | 78.75 | 0 | 0 | 0 | 0 | 0
| S 03 Bedroom Toilet (1425X2275) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 3 | 2 | 12 |  | 1.775 |  |  | 1.775 | 127.8 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 2 | 8 |  | 3.195 |  |  | 3.195 | 153.36 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 2 | 12 | 0.1 | 0.75 |  |  | 0.85 | 61.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 2 | 12 | 0.1 | 0.625 |  |  | 0.725 | 52.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 2 | 12 | 0.1 | 0.625 |  |  | 0.725 | 52.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 3 | 2 | 7 |  | 0.65 |  |  | 0.65 | 27.3 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 2 | 7 |  | 0.65 |  |  | 0.65 | 27.3 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 2 | 8 |  | 0.7 |  |  | 0.7 | 33.6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 2 | 4 | 0.2 | 1.57 |  |  | 1.77 | 42.48 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 2 | 4 | 0.2 | 1.57 |  |  | 1.77 | 42.48 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 2 | 4 | 0.2 | 3.575 |  |  | 3.775 | 90.6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 2 | 4 | 0.2 | 3.575 |  |  | 3.775 | 90.6 | 0 | 0 | 0 | 0 | 0
| S 03 Living Room | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar a | 8 | 100 | 3 | 1 | 15 |  | 3.665 |  |  | 3.665 | 164.93 | 0 | 0 | 0 | 0 | 0
| Main Bar a | 8 | 100 | 3 | 1 | 16 |  | 2.465 |  |  | 2.465 | 118.32 | 0 | 0 | 0 | 0 | 0
| Main Bar a | 8 | 100 | 3 | 1 | 16.5 |  | 5.475 |  |  | 5.475 | 271.01 | 0 | 0 | 0 | 0 | 0
| Main Bar a | 8 | 100 | 3 | 1 | 16.5 |  | 3.825 |  |  | 3.825 | 189.34 | 0 | 0 | 0 | 0 | 0
| Dist. Bar c | 8 | 150 | 3 | 1 | 17 |  | 7.11 |  |  | 7.11 | 362.61 | 0 | 0 | 0 | 0 | 0
| Dist. Bar c | 8 | 150 | 3 | 1 | 17 |  | 4.86 |  |  | 4.86 | 247.86 | 0 | 0 | 0 | 0 | 0
| Dist. Bar c | 8 | 150 | 3 | 1 | 9 |  | 3.52 |  |  | 3.52 | 95.04 | 0 | 0 | 0 | 0 | 0
| Dist. Bar c | 8 | 150 | 3 | 1 | 8 |  | 1.62 |  |  | 1.62 | 38.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 3 | 1 | 23 | 0.1 | 1.175 |  |  | 1.275 | 87.98 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA b | 8 | 125 | 3 | 1 | 26 | 0.1 | 0.7 |  |  | 0.8 | 62.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 16 |  | 1.7 |  |  | 1.7 | 81.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 16 |  | 0.9 |  |  | 0.9 | 43.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 3 | 1 | 12 |  | 2.1 |  |  | 2.1 | 75.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 3 | 1 | 11 |  | 1.1 |  |  | 1.1 | 36.3 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 3 | 1 | 12 |  | 1.1 |  |  | 1.1 | 39.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 3 | 1 | 12 |  | 0.6 |  |  | 0.6 | 21.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA b | 8 | 125 | 3 | 1 | 16 | 0.1 | 0.975 |  |  | 1.075 | 51.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 6 |  | 1.7 |  |  | 1.7 | 30.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 6.5 |  | 0.9 |  |  | 0.9 | 17.55 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 16 |  | 1.2 |  |  | 1.2 | 57.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 16 |  | 0.65 |  |  | 0.65 | 31.2 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 6 | 0.2 | 3.215 |  |  | 3.415 | 61.47 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 9 | 0.2 | 6.245 |  |  | 6.445 | 174.02 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 11 | 0.2 | 5.125 |  |  | 5.325 | 175.73 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 9 | 0.2 | 3.17 |  |  | 3.37 | 90.99 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 7 | 0.2 | 3.075 |  |  | 3.275 | 68.78 | 0 | 0 | 0 | 0 | 0
| S 21 Kitchen (2345x3435) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 3 | 1 | 18 |  | 2.695 |  |  | 2.695 | 145.53 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 1 | 12 |  | 4.3 |  |  | 4.3 | 154.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 12 | 0.1 | 0.725 |  |  | 0.825 | 29.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 9 |  | 0.9 |  |  | 0.9 | 24.3 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 8 |  | 0.5 |  |  | 0.5 | 12 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 6 |  | 1.2 |  |  | 1.2 | 21.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 6 |  | 0.65 |  |  | 0.65 | 11.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 3 | 1 | 12 |  | 0.9 |  |  | 0.9 | 32.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 3 | 1 | 12 |  | 0.5 |  |  | 0.5 | 18 | 0 | 0 | 0 | 0 | 0
| S 024 Balcony Bedroom (2000x5845) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 3 | 1 | 40 | 0.25 | 2.175 | 0.4 |  | 2.825 | 0 | 339 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 1 | 11 | 0.1 | 5.795 | 0.1 |  | 5.995 | 197.84 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 3 | 1 | 31 |  | 4.475 | 0.1 |  | 4.575 | 0 | 0 | 425.48 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 3 | 1 | 29 |  | 3.55 |  |  | 3.55 | 0 | 308.85 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 3 | 2 | 11 | 0.1 | 5.795 | 0.1 |  | 5.995 | 395.67 | 0 | 0 | 0 | 0 | 0
| L-SHAPE IN LEDGE WALL | 10 | 150 | 1 | 2 | 14 | 0.1 | 0.3 | 0.49 |  | 0.89 | 0 | 24.92 | 0 | 0 | 0 | 0
| S 024 Balcony Drawing Room (2000x3630) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 3 | 1 | 25 | 0.25 | 1.975 | 0.4 |  | 2.625 | 0 | 196.88 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 1 | 11 |  | 3.58 | 0.1 |  | 3.68 | 121.44 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 3 | 1 | 18.5 |  | 4.475 |  |  | 4.475 | 0 | 0 | 248.36 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 3 | 1 | 18.5 |  | 3.55 |  |  | 3.55 | 0 | 197.03 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 3 | 2 | 11 | 0.1 | 3.58 | 0.1 |  | 3.78 | 249.48 | 0 | 0 | 0 | 0 | 0
| L-SHAPE IN LEDGE WALL | 10 | 150 | 1 | 1 | 14 | 0.1 | 0.3 | 0.49 |  | 0.89 | 0 | 12.46 | 0 | 0 | 0 | 0
| S 024 Balcony Kitchen (2000x1650) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 3 | 1 | 12 | 0.25 | 1.975 | 0.4 |  | 2.625 | 0 | 94.5 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 1 | 11 |  | 1.6 | 0.1 |  | 1.7 | 56.1 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 3 | 1 | 9 |  | 4.475 |  |  | 4.475 | 0 | 0 | 120.83 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 3 | 1 | 9 |  | 3.55 |  |  | 3.55 | 0 | 95.85 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 3 | 2 | 11 |  | 1.6 |  |  | 1.6 | 105.6 | 0 | 0 | 0 | 0 | 0
| Lobby S10 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 16 |  | 2.82 |  |  | 2.82 | 45.12 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 10 |  | 1.85 |  |  | 1.85 | 18.5 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 8 |  | 5.44 |  |  | 5.44 | 43.52 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 5 |  | 3.55 |  |  | 3.55 | 17.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 25 | 0.1 | 0.705 |  |  | 0.805 | 20.13 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 5.09 |  |  | 5.29 | 21.16 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 7 |  | 1.7 |  |  | 1.7 | 11.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 9 |  | 0.9 |  |  | 0.9 | 8.1 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 8 | 0.2 | 2 |  |  | 2.2 | 17.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 19 |  | 0.8 |  |  | 0.8 | 15.2 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.2 | 3.14 |  |  | 3.34 | 16.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 14 |  | 0.6 |  |  | 0.6 | 8.4 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.2 | 1.95 |  |  | 2.15 | 8.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 |  | 1.7 |  |  | 1.7 | 15.3 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 9 | 0.2 | 1.95 |  |  | 2.15 | 19.35 | 0 | 0 | 0 | 0 | 0
| Lobby S17 (1610x3950) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 21 |  | 1.96 |  |  | 1.96 | 41.16 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 9 |  | 4.3 |  |  | 4.3 | 38.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 14 | 0.1 | 0.725 |  |  | 0.825 | 11.55 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 23 |  | 0.65 |  |  | 0.65 | 14.95 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 3.95 |  |  | 4.15 | 24.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4.5 |  | 1.3 |  |  | 1.3 | 5.85 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 0.7 |  |  | 0.7 | 2.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.2 | 1.61 |  |  | 1.81 | 10.86 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 200 | 1 | 1 | 4.5 |  | 1.3 |  |  | 1.3 | 5.85 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 4 |  | 0.7 |  |  | 0.7 | 2.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 150 | 1 | 1 | 7 | 0.2 | 1.61 |  |  | 1.81 | 12.67 | 0 | 0 | 0 | 0 | 0
| Lobby S18 (2440x5665) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 29 |  | 2.79 |  |  | 2.79 | 80.91 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 13 |  | 6.015 |  |  | 6.015 | 78.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 29 | 0.1 | 0.625 |  |  | 0.725 | 21.03 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.2 | 5.665 |  |  | 5.865 | 17.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 12.5 |  | 1.9 |  |  | 1.9 | 23.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 12.5 |  | 1 |  |  | 1 | 12.5 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 10 | 0.2 | 2.44 |  |  | 2.64 | 26.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 22 | 0.1 | 0.625 |  |  | 0.725 | 15.95 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 0.9 |  |  | 0.9 | 3.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 0.5 |  |  | 0.5 | 2 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.2 | 1.4 |  |  | 1.6 | 8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 1.9 |  |  | 1.9 | 7.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 6 |  | 1 |  |  | 1 | 6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 10 | 0.2 | 2.6 |  |  | 2.8 | 28 | 0 | 0 | 0 | 0 | 0
| Lobby S22 (3190x4790) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 3 | 0.1 | 1.98 |  |  | 2.08 | 6.24 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 24 |  | 3.54 |  |  | 3.54 | 84.96 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 7 |  | 5.845 |  |  | 5.845 | 40.92 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 9 |  | 5.14 |  |  | 5.14 | 46.26 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 16 | 0.1 | 0.7 |  |  | 0.8 | 12.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 10 | 0.2 | 5.445 |  |  | 5.645 | 56.45 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 1.6 |  |  | 1.6 | 6.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 0.85 |  |  | 0.85 | 3.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 |  | 1.2 |  |  | 1.2 | 15.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 11 |  | 0.6 |  |  | 0.6 | 6.6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 9 | 0.2 | 1.9 |  |  | 2.1 | 18.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 6.5 |  | 1.6 |  |  | 1.6 | 10.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 6.5 |  | 0.85 |  |  | 0.85 | 5.53 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 9 | 0.2 | 1.95 |  |  | 2.15 | 19.35 | 0 | 0 | 0 | 0 | 0
| Chajja S23 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 4 | 1 | 8 | 0.07 | 1.13 |  |  | 1.2 | 38.4 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 4 | 1 | 6 | 0.2 | 1.48 |  |  | 1.68 | 40.32 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 4 | 1 | 8 | 0.2 | 0.5 |  |  | 0.7 | 22.4 | 0 | 0 | 0 | 0 | 0
FLAT NO.- 7
| Toilet Beam at Drop (1425x2160) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar | 10 |  | 1 | 1 | 4 |  | 1.835 |  |  | 1.835 | 0 | 7.34 | 0 | 0 | 0 | 0
| Main Bar | 8 | 200 | 1 | 1 | 6 |  | 1.07 |  |  | 1.07 | 6.42 | 0 | 0 | 0 | 0 | 0
| stirrups | 8 | 200 | 1 | 1 | 8 |  | 0.63 |  |  | 0.63 | 5.04 | 0 | 0 | 0 | 0 | 0
FLAT NO.- 8
| Toilet Beam at Drop (1425x2160) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar | 10 |  | 1 | 1 | 4 |  | 1.835 |  |  | 1.835 | 0 | 7.34 | 0 | 0 | 0 | 0
| Main Bar | 8 | 200 | 1 | 1 | 6 |  | 1.07 |  |  | 1.07 | 6.42 | 0 | 0 | 0 | 0 | 0
| stirrups | 8 | 200 | 1 | 1 | 8 |  | 0.63 |  |  | 0.63 | 5.04 | 0 | 0 | 0 | 0 | 0
| Toilet Beam at Drop (2410x1910) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar | 10 |  | 1 | 1 | 4 |  | 2.82 |  |  | 2.82 | 0 | 11.28 | 0 | 0 | 0 | 0
| Main Bar | 8 | 200 | 1 | 1 | 11 |  | 1.07 |  |  | 1.07 | 11.77 | 0 | 0 | 0 | 0 | 0
| stirrups | 8 | 200 | 1 | 1 | 13 |  | 0.63 |  |  | 0.63 | 8.19 | 0 | 0 | 0 | 0 | 0
FLAT NO.- 9
| Toilet Beam at Drop (1510x2370) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar | 10 |  | 1 | 1 | 4 |  | 1.92 |  |  | 1.92 | 0 | 7.68 | 0 | 0 | 0 | 0
| Main Bar | 8 | 200 | 1 | 1 | 7 |  | 1.07 |  |  | 1.07 | 7.49 | 0 | 0 | 0 | 0 | 0
| stirrups | 8 | 200 | 1 | 1 | 9 |  | 0.63 |  |  | 0.63 | 5.67 | 0 | 0 | 0 | 0 | 0
FLAT NO.- 10,11,12
| Toilet Beam at Drop (1420x2275) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar | 10 |  | 3 | 2 | 4 |  | 1.83 |  |  | 1.83 | 0 | 43.92 | 0 | 0 | 0 | 0
| Main Bar | 8 | 200 | 3 | 2 | 6 |  | 1.07 |  |  | 1.07 | 38.52 | 0 | 0 | 0 | 0 | 0
| stirrups | 8 | 200 | 3 | 2 | 8 |  | 0.63 |  |  | 0.63 | 30.24 | 0 | 0 | 0 | 0 | 0
| Toilet Beam at Drop (1440x2275) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar | 10 |  | 3 | 1 | 4 |  | 1.85 |  |  | 1.85 | 0 | 22.2 | 0 | 0 | 0 | 0
| Main Bar | 8 | 200 | 3 | 1 | 6 |  | 1.07 |  |  | 1.07 | 19.26 | 0 | 0 | 0 | 0 | 0
| stirrups | 8 | 200 | 3 | 1 | 8 |  | 0.63 |  |  | 0.63 | 15.12 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
MAIN Stairs case (03)
230X450 | LB1 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 20 |  | 1 | 1 | 2 | 0.2 | 3.2 | 0.2 |  | 3.6 | 0 | 0 | 0 | 0 | 7.2 | 0
| TOP | 20 |  | 1 | 1 | 2 | 0.2 | 3.2 | 0.2 |  | 3.6 | 0 | 0 | 0 | 0 | 7.2 | 0
| STIRRUPS | 10 | 100 | 1 | 1 | 33 |  | 1.32 |  |  | 1.32 | 0 | 43.56 | 0 | 0 | 0 | 0
| Main Bottom | 12 | 100 | 1 | 2 | 16 | 0.1 | 4.705 |  |  | 4.805 | 0 | 0 | 153.76 | 0 | 0 | 0
| Main Bottom | 12 | 100 | 1 | 2 | 16 | 0.1 | 2.325 |  |  | 2.425 | 0 | 0 | 77.6 | 0 | 0 | 0
| Main Top | 10 | 150 | 1 | 2 | 11 | 0.2 | 2.3 |  |  | 2.5 | 0 | 55 | 0 | 0 | 0 | 0
| Main Top | 10 | 150 | 1 | 2 | 11 |  | 1.625 |  |  | 1.625 | 0 | 35.75 | 0 | 0 | 0 | 0
| Main Top | 10 | 200 | 1 | 2 | 9 |  | 2.7 | 0.2 |  | 2.9 | 0 | 52.2 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 2 | 43 |  | 1.45 |  |  | 1.45 | 124.7 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 2 | 11 |  | 3.36 |  |  | 3.36 | 73.92 | 0 | 0 | 0 | 0 | 0
FIRE Stairs case (04)
230X450 | LB | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 20 |  | 1 | 1 | 2 | 0.1 | 4.12 | 0.3 |  | 4.52 | 0 | 0 | 0 | 0 | 9.04 | 0
| TOP | 20 |  | 1 | 1 | 2 | 0.3 | 4.12 | 0.3 |  | 4.72 | 0 | 0 | 0 | 0 | 9.44 | 0
| STIRRUPS | 10 | 100 | 1 | 1 | 33 |  | 1.32 |  |  | 1.32 | 0 | 43.56 | 0 | 0 | 0 | 0
| Main Bottom | 12 | 150 | 1 | 1 | 11 | 0.1 | 4.6 | 0.1 |  | 4.8 | 0 | 0 | 52.8 | 0 | 0 | 0
| Main Bottom | 10 | 150 | 1 | 1 | 8 | 0.1 | 4.1 |  |  | 4.2 | 0 | 33.6 | 0 | 0 | 0 | 0
| Main Top | 12 | 150 | 1 | 2 | 11 | 0.1 | 1.52 | 0.1 |  | 1.72 | 0 | 0 | 37.84 | 0 | 0 | 0
| Main Top | 12 | 150 | 1 | 2 | 11 |  | 1.4 | 0.45 |  | 1.85 | 0 | 0 | 40.7 | 0 | 0 | 0
| Main Top | 10 | 200 | 1 | 2 | 11 |  | 2.25 | 0.2 |  | 2.45 | 0 | 53.9 | 0 | 0 | 0 | 0
| Main Top | 12 | 200 | 1 | 2 | 11 |  | 2.1 | 0.1 |  | 2.2 | 0 | 0 | 48.4 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 |  | 1.5 |  |  | 1.5 | 6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 13 |  | 1.7 |  |  | 1.7 | 22.1 | 0 | 0 | 0 | 0 | 0
| Mid landing 2nd freight | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Main Bottom | 12 | 150 | 1 | 1 | 11 |  | 4.6 |  |  | 4.6 | 0 | 0 | 50.6 | 0 | 0 | 0
| Main Bottom | 10 | 200 | 1 | 1 | 8 |  | 2.63 |  |  | 2.63 | 0 | 21.04 | 0 | 0 | 0 | 0
| BINDER | 10 | 200 | 1 | 1 | 8 |  | 1.5 |  |  | 1.5 | 0 | 12 | 0 | 0 | 0 | 0
| 2ND FREIGHT MAIN TOP | 12 | 200 | 1 | 1 | 11 |  | 1.4 |  |  | 1.4 | 0 | 0 | 15.4 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Chair (in 125mm thk slab) | 10 |  | 1 | 1 | 196 | 0.3 | 0.6 | 0.3 |  | 1.2 | 0 | 235.2 | 0 | 0 | 0 | 0
| Chair (in 135mm thk slab) | 10 |  | 1 | 1 | 194 | 0.31 | 0.6 | 0.31 |  | 1.22 | 0 | 236.68 | 0 | 0 | 0 | 0
| Chair (in 150mm thk slab) | 10 |  | 1 | 1 | 122 | 0.325 | 0.6 | 0.325 |  | 1.25 | 0 | 152.5 | 0 | 0 | 0 | 0
| Chair (in 175mm thk slab) | 10 |  | 1 | 1 | 30 | 0.35 | 0.6 | 0.35 |  | 1.3 | 0 | 39 | 0 | 0 | 0 | 0
| Chair (in 200mm thk slab) | 10 |  | 1 | 1 | 172 | 0.375 | 0.6 | 0.375 |  | 1.35 | 0 | 232.2 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | [10 empty] | 16915.34 | 3964.4 | 2078.38 | 0 | 32.88 | 0
| UNIT WT. | [10 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.47 | 3.85 | B
| TOTAL WT. | [10 empty] | 6681.5593 | 2446.0348 | 1845.6014 | 0 | 81.2136 | 0 | 11054.4091
[17 empty] | A+B | 17516.0716

## 2nd Floor LVL Slab BBS
Reinforcement
Sr. No. | Designation | Dia | C/C (mm) | No | No | No of Bars | Bar Length (mtr) |  |  |  | Lap Length | One Bar Length (MTR) | Dia Wise Weight (Kg)
[7 empty] | a | b | c |  |  |  | 8mm | 10mm | 12mm | 16mm | 20MM | 25mm
Typical Beam
200X500 | B1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 6.125 | 0.768 |  |  | 7.661 | 0 | 0 | 0 | 15.32 | 0 | 0
| TOP | 20 |  | 1 | 1 | 2 | 0.96 | 6.125 | 0.96 |  |  | 8.045 | 0 | 0 | 0 | 0 | 16.09 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 | 0.576 | 0.85 |  |  |  | 1.426 | 0 | 0 | 2.85 | 0 | 0 | 0
| SPECHER | 25 |  | 1 | 1 | 2 | [5 empty] | 0.18 | [5 empty] | 0.36
| STIRRUPS | 8 | 100 | 1 | 1 | 20 |  | 1.328 |  |  |  | 1.328 | 26.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 8 |  | 1.328 |  |  |  | 1.328 | 10.62 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 20 |  | 1.328 |  |  |  | 1.328 | 26.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 6 |  | 1.328 |  |  |  | 1.328 | 7.97 | 0 | 0 | 0 | 0 | 0
200X500 | B2 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 3.3 | 0.36333 |  |  | 4.4313 | 0 | 0 | 0 | 8.86 | 0 | 0
| TOP | 20 |  | 1 | 1 | 2 | 0.96 | 3.3 | 0.42667 |  |  | 4.6867 | 0 | 0 | 0 | 0 | 9.37 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 20 |  | 1.328 |  |  |  | 1.328 | 26.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 10 |  | 1.328 |  |  |  | 1.328 | 13.28 | 0 | 0 | 0 | 0 | 0
100X350 | B3 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 1 | 1 | 2 | 0.576 | 1.395 | 0.576 |  |  | 2.547 | 0 | 0 | 5.09 | 0 | 0 | 0
| TOP | 12 |  | 1 | 1 | 2 | 0.576 | 1.395 | 0.576 |  |  | 2.547 | 0 | 0 | 5.09 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 1 | 1 | 10 |  | 0.828 |  |  |  | 0.828 | 8.28 | 0 | 0 | 0 | 0 | 0
200X350 | B4 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.768 | 1.395 | 0.708 |  |  | 2.871 | 0 | 0 | 0 | 11.48 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.768 | 1.395 | 0.708 |  |  | 2.871 | 0 | 0 | 0 | 11.48 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 15 |  | 1.028 |  |  |  | 1.028 | 30.84 | 0 | 0 | 0 | 0 | 0
200X450 | B5 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 6.875 | 0.36333 |  |  | 8.0063 | 0 | 0 | 0 | 16.01 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 6.875 | 0.36333 |  |  | 8.0063 | 0 | 0 | 0 | 16.01 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 18 |  | 1.228 |  |  |  | 1.228 | 22.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 13 |  | 1.228 |  |  |  | 1.228 | 15.96 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 18 |  | 1.228 |  |  |  | 1.228 | 22.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 10 |  | 1.228 |  |  |  | 1.228 | 12.28 | 0 | 0 | 0 | 0 | 0
230X350 | B6 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 3.16 | 0.708 |  |  | 4.636 | 0 | 0 | 0 | 9.27 | 0 | 0
| TOP | 20 |  | 1 | 1 | 2 | 0.96 | 3.16 | 0.74 |  |  | 4.86 | 0 | 0 | 0 | 0 | 9.72 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 16 |  | 1.088 |  |  |  | 1.088 | 17.41 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 12 |  | 1.088 |  |  |  | 1.088 | 13.06 | 0 | 0 | 0 | 0 | 0
200X450 | B7 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 2.7 | 0.768 |  |  | 3.8313 | 0 | 0 | 0 | 7.66 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 2.7 | 0.768 |  |  | 3.8313 | 0 | 0 | 0 | 7.66 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 18 |  | 1.228 |  |  |  | 1.228 | 22.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 7 |  | 1.228 |  |  |  | 1.228 | 8.6 | 0 | 0 | 0 | 0 | 0
200X500 | B8 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 2.875 | 0.708 |  |  | 4.351 | 0 | 0 | 0 | 8.7 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 2.93 | 0.36333 |  |  | 4.0613 | 0 | 0 | 0 | 8.12 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 6.405 | 0.36333 |  |  | 7.5363 | 0 | 0 | 0 | 15.07 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 20 |  | 1.328 |  |  |  | 1.328 | 26.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 7 |  | 1.328 |  |  |  | 1.328 | 9.3 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 1 | 19 |  | 1.328 |  |  |  | 1.328 | 25.23 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 7 |  | 1.328 |  |  |  | 1.328 | 9.3 | 0 | 0 | 0 | 0 | 0
200X500 | B9 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.768 | 4.69 | 0.768 |  |  | 6.226 | 0 | 0 | 0 | 24.9 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.768 | 4.69 | 0.768 |  |  | 6.226 | 0 | 0 | 0 | 24.9 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 3.29 |  |  |  | 3.29 | 0 | 0 | 13.16 | 0 | 0 | 0
| TOP EXTRA | 16 |  | 2 | 1 | 4 | 0.768 | 1.4 |  |  |  | 2.168 | 0 | 0 | 0 | 17.34 | 0 | 0
| SPACER | 25 | 1000 |  |  | 6 | [5 empty] | 0.18 | [5 empty] | 1.08
| STIRRUPS | 8 | 100 | 2 | 1 | 26 |  | 1.328 |  |  |  | 1.328 | 69.06 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 14 |  | 1.328 |  |  |  | 1.328 | 37.18 | 0 | 0 | 0 | 0 | 0
200X500 | B10 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 20 |  | 1 | 1 | 2 | 0.42667 | 6.3 | 0.42667 |  |  | 7.1533 | 0 | 0 | 0 | 0 | 14.31 | 0
| TOP | 25 |  | 1 | 1 | 2 | 0.50833 | 6.3 | 0.50833 |  |  | 7.3167 | 0 | 0 | 0 | 0 | 0 | 14.63
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 5.1 |  |  |  | 5.1 | 0 | 0 | 10.2 | 0 | 0 | 0
| SPACER | 25 | 1000 | 1 |  | 3 | [5 empty] | 0.18 | [5 empty] | 0.54
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 32 |  | 1.328 |  |  |  | 1.328 | 42.5 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 22 |  | 1.328 |  |  |  | 1.328 | 29.22 | 0 | 0 | 0 | 0 | 0
200X450 | B11 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 4 | 1 | 2 | 0.768 | 4.69 | 0.768 |  |  | 6.226 | 0 | 0 | 0 | 49.81 | 0 | 0
| TOP | 16 |  | 4 | 1 | 2 | 0.768 | 4.69 | 0.768 |  |  | 6.226 | 0 | 0 | 0 | 49.81 | 0 | 0
| BOTTOM EXTRA | 12 |  | 4 | 1 | 2 |  | 3.79 |  |  |  | 3.79 | 0 | 0 | 30.32 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 4 | 1 | 4 | 0.576 | 1.4 |  |  |  | 1.976 | 0 | 0 | 31.62 | 0 | 0 | 0
| SPACER | 25 | 1000 |  |  | 3 | [5 empty] | 0.18 | [5 empty] | 0.54
| STIRRUPS | 8 | 100 | 4 | 1 | 23 |  | 1.328 |  |  |  | 1.328 | 122.18 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 17 |  | 1.328 |  |  |  | 1.328 | 90.3 | 0 | 0 | 0 | 0 | 0
200X450 | B12 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 0.5 | 2 | 0.768 | 11.75 | 0.768 |  | 0.86 | 14.146 | 0 | 0 | 0 | 14.15 | 0 | 0
| TOP | 16 |  | 1 | 0.5 | 2 | 0.768 | 11.75 | 0.768 |  | 0.86 | 14.146 | 0 | 0 | 0 | 14.15 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 0.5 | 4 |  | 4.36 |  |  |  | 4.36 | 0 | 0 | 8.72 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 0.5 | 2 |  | 3.83 |  |  |  | 3.83 | 0 | 0 | 3.83 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 0.5 | 4 | 0.536 | 1.8 |  |  |  | 2.336 | 0 | 0 | 4.67 | 0 | 0 | 0
| SPACER | 25 | 1000 | 1 |  | 11 | [5 empty] | 0.18 | [5 empty] | 1.98
| STIRRUPS | 8 | 100 | 1 | 0.5 | 58 |  | 1.228 |  |  |  | 1.228 | 35.61 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 0.5 | 40 |  | 1.228 |  |  |  | 1.228 | 24.56 | 0 | 0 | 0 | 0 | 0
200X450 | B13 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 4.105 | 0.768 |  |  | 5.2363 | 0 | 0 | 0 | 10.47 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 1.6 | 0.768 |  |  | 3.136 | 0 | 0 | 0 | 6.27 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 5.935 | 0.768 |  |  | 7.0663 | 0 | 0 | 0 | 14.13 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 21 |  | 1.228 |  |  |  | 1.228 | 25.79 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 15 |  | 1.228 |  |  |  | 1.228 | 18.42 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 1 | 17 |  | 1.092 |  |  |  | 1.092 | 18.56 | 0 | 0 | 0 | 0 | 0
200X450 | B14 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 20 |  | 1 | 1 | 2 | 0.96 | 4.905 | 0.42667 |  |  | 6.2917 | 0 | 0 | 0 | 0 | 12.58 | 0
| TOP | 20 |  | 1 | 1 | 2 | 0.96 | 4.905 | 0.36333 |  |  | 6.2283 | 0 | 0 | 0 | 0 | 12.46 | 0
| TOP EXTRA | 16 |  | 1 | 1 | 2 |  | 2.785 |  |  |  | 2.785 | 0 | 0 | 0 | 5.57 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 2.785 |  |  |  | 2.785 | 0 | 0 | 5.57 | 0 | 0 | 0
| SPACER | 25 |  | 1 |  | 6 | [5 empty] | 0.18 | [5 empty] | 1.08
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 23 |  | 1.228 |  |  |  | 1.228 | 28.24 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 10 | 100 | 1 | 1 | 16 |  | 1.26 |  |  |  | 1.26 | 0 | 20.16 | 0 | 0 | 0 | 0
200X500 | B15 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 3.115 | 0.768 |  |  | 4.651 | 0 | 0 | 0 | 9.3 | 0 | 0
| TOP | 20 |  | 1 | 1 | 2 | 0.96 | 3.115 | 0.96 |  |  | 5.035 | 0 | 0 | 0 | 0 | 10.07 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 32 |  | 1.328 |  |  |  | 1.328 | 42.5 | 0 | 0 | 0 | 0 | 0
200X500 | B16 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.768 | 6.685 | 0.36333 |  |  | 7.8163 | 0 | 0 | 0 | 46.9 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.768 | 1.02 | 0.768 |  |  | 2.556 | 0 | 0 | 0 | 15.34 | 0 | 0
| TOP | 16 |  | 3 | 1 | 2 | 0.768 | 7.905 | 0.768 |  |  | 9.441 | 0 | 0 | 0 | 56.65 | 0 | 0
| BOTTOM EXTRA | 16 |  | 3 | 1 | 2 | 0.768 | 1.02 | 0.768 |  |  | 2.556 | 0 | 0 | 0 | 15.34 | 0 | 0
| BOTTOM EXTRA | 12 |  | 3 | 1 | 2 |  | 2.5 | 0.29667 |  |  | 2.7967 | 0 | 0 | 16.78 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 3 | 1 | 2 |  | 2.5 |  |  |  | 2.5 | 0 | 0 | 15 | 0 | 0 | 0
| TOP EXTRA | 16 |  | 3 | 1 | 2 | 0.768 | 1.3 |  |  |  | 2.068 | 0 | 0 | 0 | 12.41 | 0 | 0
| SPACER | 25 | 1000 | 3 |  | 10 | [5 empty] | 0.18 | [5 empty] | 5.4
| STIRRUPS 200X500 | 8 | 100 | 3 | 1 | 34 |  | 1.392 |  |  |  | 1.392 | 141.98 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 23 |  | 1.392 |  |  |  | 1.392 | 96.05 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 3 | 1 | 11 |  | 1.028 |  |  |  | 1.028 | 33.92 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 3 | 1 | 20 |  | 1.328 |  |  |  | 1.328 | 79.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 9 |  | 1.328 |  |  |  | 1.328 | 35.86 | 0 | 0 | 0 | 0 | 0
200X500 | B17 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 3.215 | 0.36333 |  |  | 4.3463 | 0 | 0 | 0 | 8.69 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 3.215 | 0.36333 |  |  | 4.3463 | 0 | 0 | 0 | 8.69 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 |  | 0.9 | 0.536 |  |  | 1.436 | 0 | 0 | 2.87 | 0 | 0 | 0
| SPACER | 25 | 1000 | 1 |  | 2 | [5 empty] | 0.18 | [5 empty] | 0.36
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 20 |  | 1.328 |  |  |  | 1.328 | 26.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 9 |  | 1.328 |  |  |  | 1.328 | 11.95 | 0 | 0 | 0 | 0 | 0
230X500 | B18 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 25 |  | 1 | 1 | 2 | 1.1 | 2.76 | 1.1 |  |  | 4.96 | 0 | 0 | 0 | 0 | 0 | 9.92
| BOTTOM | 20 |  | 1 | 1 | 1 | 1.06 | 2.76 | 1.06 |  |  | 4.88 | 0 | 0 | 0 | 0 | 4.88 | 0
| TOP | 25 |  | 1 | 1 | 3 | 1.1 | 2.76 | 1.1 |  |  | 4.96 | 0 | 0 | 0 | 0 | 0 | 14.88
| STIRRUPS 200X500 | 10 | 100 | 1 | 1 | 20 |  | 1.42 |  |  |  | 1.42 | 0 | 28.4 | 0 | 0 | 0 | 0
|  | 10 | 150 | 1 | 1 | 6 |  | 1.42 |  |  |  | 1.42 | 0 | 8.52 | 0 | 0 | 0 | 0
200X450 | B19 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 6.79 | 0.36333 |  |  | 7.9213 | 0 | 0 | 0 | 15.84 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 6.79 | 0.36333 |  |  | 7.9213 | 0 | 0 | 0 | 15.84 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 5.59 |  |  |  | 5.59 | 0 | 0 | 11.18 | 0 | 0 | 0
| TOP EXTRA | 16 |  | 1 | 1 | 2 |  | 2 | 0.708 |  |  | 2.708 | 0 | 0 | 0 | 5.42 | 0 | 0
| SPACER | 25 |  | 1 |  | 8 | [5 empty] | 0.18 | [5 empty] | 1.44
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 34 |  | 1.228 |  |  |  | 1.228 | 41.75 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 24 |  | 1.228 |  |  |  | 1.228 | 29.47 | 0 | 0 | 0 | 0 | 0
230X350 | B20 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 0.5 | 2 | 0.36333 | 5.05 | 0.36333 |  |  | 5.7767 | 0 | 0 | 0 | 5.78 | 0 | 0
| TOP | 20 |  | 1 | 0.5 | 2 | 0.42667 | 5.05 | 0.42667 |  |  | 5.9033 | 0 | 0 | 0 | 0 | 5.9 | 0
| STIRRUPS | 8 | 100 | 1 | 0.5 | 50 |  | 1.088 |  |  |  | 1.088 | 27.2 | 0 | 0 | 0 | 0 | 0
230X450 | B21 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 11.75 | 0.708 |  |  | 13.226 | 0 | 0 | 0 | 26.45 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 11.75 | 0.708 |  |  | 13.226 | 0 | 0 | 0 | 26.45 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 4 |  | 4.36 |  |  |  | 4.36 | 0 | 0 | 17.44 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 |  | 3.83 |  |  |  | 3.83 | 0 | 0 | 7.66 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 4 | 0.686 | 1.8 |  |  |  | 2.486 | 0 | 0 | 9.94 | 0 | 0 | 0
| SPACER | 25 |  | 1 | 1 | 10 | [5 empty] | 0.18 | [5 empty] | 1.8
| STIRRUPS | 8 | 100 | 1 | 1 | 60 |  | 1.288 |  |  |  | 1.288 | 77.28 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 1 | 1 | 46 |  | 1.288 |  |  |  | 1.288 | 59.25 | 0 | 0 | 0 | 0 | 0
200X450 | B22 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 2.22 | 0.708 |  |  | 3.696 | 0 | 0 | 0 | 7.39 | 0 | 0
| TOP | 20 |  | 1 | 1 | 2 | 0.8 | 2.22 | 0.88 |  |  | 3.9 | 0 | 0 | 0 | 0 | 7.8 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 23 |  | 1.228 |  |  |  | 1.228 | 28.24 | 0 | 0 | 0 | 0 | 0
200X450 | B23 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 5.63 | 0.708 |  |  | 7.046 | 0 | 0 | 0 | 14.09 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 5.63 | 0.708 |  |  | 7.046 | 0 | 0 | 0 | 14.09 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 4.53 |  |  |  | 4.53 | 0 | 0 | 9.06 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 4 | 0.536 | 1.6 |  |  |  | 2.136 | 0 | 0 | 8.54 | 0 | 0 | 0
| SPACER | 25 |  | 1 | 1 | 9 | [5 empty] | 0.18 | [5 empty] | 1.62
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 28 |  | 1.228 |  |  |  | 1.228 | 34.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 20 |  | 1.228 |  |  |  | 1.228 | 24.56 | 0 | 0 | 0 | 0 | 0
200X450 | B24 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 8.255 | 0.36333 |  |  | 8.9817 | 0 | 0 | 0 | 17.96 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 8.255 | 0.36333 |  |  | 8.9817 | 0 | 0 | 0 | 17.96 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 4.03 |  |  |  | 4.03 | 0 | 0 | 8.06 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 4 |  | 2.4 |  |  |  | 2.4 | 0 | 0 | 9.6 | 0 | 0 | 0
| SPACER | 25 | 1000 | 1 | 1 | 8 | [5 empty] | 0.18 | [5 empty] | 1.44
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 16 |  | 1.328 |  |  |  | 1.328 | 21.25 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 28 |  | 1.228 |  |  |  | 1.228 | 34.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 20 |  | 1.228 |  |  |  | 1.228 | 24.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 1 | 1 | 22 |  | 1.228 |  |  |  | 1.228 | 27.02 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
200x450 | B25 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.768 | 8.255 | 0.708 |  |  | 9.731 | 0 | 0 | 0 | 58.39 | 0 | 0
| TOP | 16 |  | 3 | 1 | 2 | 0.768 | 8.255 | 0.708 |  |  | 9.731 | 0 | 0 | 0 | 58.39 | 0 | 0
| BOTTOM EXTRA | 12 |  | 3 | 1 | 2 |  | 3.57 |  |  |  | 3.57 | 0 | 0 | 21.42 | 0 | 0 | 0
| TOP EXTRA | 16 |  | 3 | 1 | 2 |  | 2.5 |  |  |  | 2.5 | 0 | 0 | 0 | 15 | 0 | 0
| TOP EXTRA | 12 |  | 3 | 1 | 2 | 0.576 | 1.4 |  |  |  | 1.976 | 0 | 0 | 11.86 | 0 | 0 | 0
|  | 12 |  | 3 | 1 | 4 | 0.576 | 1 |  |  |  | 1.576 | 0 | 0 | 18.91 | 0 | 0 | 0
| SPACER | 25 | 1000 | 3 | 1 | [6 empty] | 0.18 | [5 empty] | 0.54
| STIRRUPS 200X450 | 8 | 100 | 3 | 1 | 14 |  | 1.228 |  |  |  | 1.228 | 51.58 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 10 |  | 1.228 |  |  |  | 1.228 | 36.84 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 3 | 1 | 20 |  | 1.228 |  |  |  | 1.228 | 73.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 3 | 1 | 9 |  | 1.228 |  |  |  | 1.228 | 33.16 | 0 | 0 | 0 | 0 | 0
200x500 | B26 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.768 | 3.165 | 0.708 |  |  | 4.641 | 0 | 0 | 0 | 27.85 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.768 | 2.58 | 0.708 |  |  | 4.056 | 0 | 0 | 0 | 24.34 | 0 | 0
| TOP | 20 |  | 3 | 1 | 2 | 0.96 | 5.745 | 0.96 |  |  | 7.665 | 0 | 0 | 0 | 0 | 45.99 | 0
| STIRRUPS 200X500 | 8 | 100 | 3 | 1 | 14 |  | 1.328 |  |  |  | 1.328 | 55.78 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 10 |  | 1.328 |  |  |  | 1.328 | 39.84 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 3 | 1 | 20 |  | 1.028 |  |  |  | 1.028 | 61.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 9 |  | 1.028 |  |  |  | 1.028 | 27.76 | 0 | 0 | 0 | 0 | 0
200X450 | B27 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.768 | 5.125 | 0.768 |  |  | 6.661 | 0 | 0 | 0 | 39.97 | 0 | 0
| BOTTOM EXTRA | 12 |  | 3 | 1 | 2 |  | 4.14 |  |  |  | 4.14 | 0 | 0 | 24.84 | 0 | 0 | 0
| TOP | 16 |  | 3 | 1 | 2 | 0.768 | 5.125 | 0.768 |  |  | 6.661 | 0 | 0 | 0 | 39.97 | 0 | 0
| TOP EXTRA | 12 |  | 3 | 1 | 4 | 0.676 | 1.5 | 0.676 |  |  | 2.852 | 0 | 0 | 34.22 | 0 | 0 | 0
| SPACER | 25 | 1000 | 3 | 1 | 8 | [5 empty] | 0.18 | [5 empty] | 4.32
| STIRRUPS 200X450 | 8 | 100 | 3 | 1 | 20 |  | 1.228 |  |  |  | 1.228 | 73.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 9 |  | 1.228 |  |  |  | 1.228 | 33.16 | 0 | 0 | 0 | 0 | 0
230X450 | B28 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 5.635 | 0.768 |  |  | 7.171 | 0 | 0 | 0 | 14.34 | 0 | 0
| TOP | 20 |  | 1 | 1 | 2 | 0.96 | 5.125 | 0.96 |  |  | 7.045 | 0 | 0 | 0 | 0 | 14.09 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 57 |  | 1.288 |  |  |  | 1.288 | 73.42 | 0 | 0 | 0 | 0 | 0
200X450/500/350 | B29 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 7.425 | 0.768 |  |  | 8.961 | 0 | 0 | 0 | 17.92 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 2.93 | 0.768 |  |  | 4.466 | 0 | 0 | 0 | 8.93 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 10.955 | 0.768 |  |  | 12.491 | 0 | 0 | 0 | 24.98 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 |  | 2.5 |  |  |  | 2.5 | 0 | 0 | 5 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 |  | 2.2 |  |  |  | 2.2 | 0 | 0 | 4.4 | 0 | 0 | 0
| SPACER | 25 |  | 1 | 1 | 4 | [5 empty] | 0.18 | [5 empty] | 0.72
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 30 |  | 1.228 |  |  |  | 1.228 | 36.84 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 29 |  | 1.328 |  |  |  | 1.328 | 38.51 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 1 | 15 |  | 1.028 |  |  |  | 1.028 | 15.42
|  | 8 | 150 | 1 | 1 | 11 |  | 1.028 |  |  |  | 1.028 | 11.31 | 0 | 0 | 0 | 0 | 0
230X450 | B30 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 4 | 0.768 |  |  | 5.536 | 0 | 0 | 0 | 11.07 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 4 | 0.768 |  |  | 5.536 | 0 | 0 | 0 | 11.07 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 30 |  | 1.228 |  |  |  | 1.228 | 36.84 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 30 |  | 1.228 |  |  |  | 1.228 | 36.84 | 0 | 0 | 0 | 0 | 0
200X350 | B31 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 5.035 | 0.36333 |  |  | 6.1663 | 0 | 0 | 0 | 12.33 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 5.035 | 0.36333 |  |  | 6.1663 | 0 | 0 | 0 | 12.33 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 | 0.576 | 0.9 |  |  |  | 1.476 |  |  | 2.95 |  |  | 0
| SPACER | 25 |  | 1 | 1 | 2 | [5 empty] | 0.18 | [5 empty] | 0.36
| STIRRUPS 200X350 | 8 | 100 | 1 | 2 | 21 |  | 1.028 |  |  |  | 1.028 | 43.18 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 1 | 2 | 21 |  | 1.028 |  |  |  | 1.028 | 43.18 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 8 |  | 1.028 |  |  |  | 1.028 | 16.45 | 0 | 0 | 0 | 0 | 0
200X450 | B32 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 10.5 | 0.768 |  |  | 12.036 | 0 | 0 | 0 | 24.07 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 10.5 | 0.768 |  |  | 12.036 | 0 | 0 | 0 | 24.07 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 4 |  | 3.85 |  |  |  | 3.85 | 0 | 0 | 15.4 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 |  | 3.3 |  |  |  | 3.3 | 0 | 0 | 6.6 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 4 |  | 1.5 | 0.536 |  |  | 2.036 | 0 | 0 | 8.14 | 0 | 0 | 0
| SPACER | 25 |  | 1 | 1 | 10 | [5 empty] | 0.18 | [5 empty] | 1.8
| STIRRUPS 200X450 | 8 | 100 | 1 | 2 | 26 |  | 1.2 |  |  |  | 1.2 | 62.4 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 18 |  | 1.2 |  |  |  | 1.2 | 43.2 | 0 | 0 | 0 | 0 | 0
200X500 | B33 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 6.68 | 0.36333 |  |  | 7.4067 | 0 | 0 | 0 | 14.81 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 6.68 | 0.36333 |  |  | 7.4067 | 0 | 0 | 0 | 14.81 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 |  | 2.1 |  |  |  | 2.1 | 0 | 0 | 4.2 | 0 | 0 | 0
| SPACER | 25 |  | 1 | 1 | 2 | [5 empty] | 0.18 | [5 empty] | 0.36
| STIRRUPS 200X500 | 8 | 100 | 1 | 2 | 20 |  | 1.328 |  |  |  | 1.328 | 53.12 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 9 |  | 1.328 |  |  |  | 1.328 | 23.9 | 0 | 0 | 0 | 0 | 0
200/230X500 | B34 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.768 | 8.225 | 0.36333 |  |  | 9.3563 | 0 | 0 | 0 | 56.14 | 0 | 0
| TOP | 16 |  | 3 | 1 | 2 | 0.768 | 8.225 | 0.36333 |  |  | 9.3563 | 0 | 0 | 0 | 56.14 | 0 | 0
| TOP EXTRA | 12 |  | 3 | 1 | 2 |  | 2.865 | 0.31333 |  |  | 3.1783 | 0 | 0 | 19.07 | 0 | 0 | 0
| SPACER | 25 |  | 3 | 1 | 3 | [5 empty] | 0.18 |  |  | 0 |  |  | 1.62
| STIRRUPS 230X500 | 8 | 100 | 3 | 2 | 5 |  | 1.388 |  |  |  | 1.388 | 41.64 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X500 | 8 | 100 | 3 | 2 | 19 |  | 1.388 |  |  |  | 1.388 | 158.23 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 3 | 2 | 20 |  | 1.392 |  |  |  | 1.392 | 167.04 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 2 | 15 |  | 1.392 |  |  |  | 1.392 | 125.28 | 0 | 0 | 0 | 0 | 0
200X450 | B35 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.36333 | 3.86 | 0.36333 |  |  | 4.5867 | 0 | 0 | 0 | 27.52 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.95 | 0.415 | 0.36333 |  |  | 1.7283 | 0 | 0 | 0 | 10.37 | 0 | 0
| TOP | 16 |  | 3 | 1 | 2 | 0.36333 | 4.475 | 0.36333 |  |  | 5.2017 | 0 | 0 | 0 | 31.21 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 3 | 1 | 19 |  | 1.228 |  |  |  | 1.228 | 70 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 14 |  | 1.228 |  |  |  | 1.228 | 51.58 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 100X350 | 8 | 100 | 3 | 1 | 5 |  | 0.828 |  |  |  | 0.828 | 12.42 | 0 | 0 | 0 | 0 | 0
200X450 | B36 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.768 | 3.52 | 0.36333 |  |  | 4.6513 | 0 | 0 | 0 | 27.91 | 0 | 0
| TOP | 16 |  | 3 | 1 | 2 | 0.768 | 3.52 | 0.36333 |  |  | 4.6513 | 0 | 0 | 0 | 27.91 | 0 | 0
| EXTRA TOP | 12 |  | 3 | 1 | 2 | 0.576 | 1 |  |  |  | 1.576 |  |  | 9.46
| STIRRUPS 200X450 | 8 | 100 | 3 | 1 | 18 |  | 1.228 |  |  |  | 1.228 | 66.31 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 12 |  | 1.228 |  |  |  | 1.228 | 44.21 | 0 | 0 | 0 | 0 | 0
200X450 | B37 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 2 | 2 | 0.36333 | 3.55 | 0.58 |  |  | 4.4933 | 0 | 0 | 0 | 53.92 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.768 | 2.955 | 0.768 |  |  | 4.491 | 0 | 0 | 0 | 26.95 | 0 | 0
| TOP | 16 |  | 3 | 1 | 2 | 0.36333 | 7.21 | 0.708 |  | 0.784 | 9.0653 | 0 | 0 | 0 | 54.39 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 3 | 2 | 20 |  | 1.028 |  |  |  | 1.028 | 123.36 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 2 | 17 |  | 1.028 |  |  |  | 1.028 | 104.86 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 3 | 1 | 16 |  | 1.228 |  |  |  | 1.228 | 58.94 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 1 | 14 |  | 1.228 |  |  |  | 1.228 | 51.58 | 0 | 0 | 0 | 0 | 0
200X450 | B38 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 4 | 0.36333 | 3 | 0.708 |  |  | 4.0713 | 0 | 0 | 0 | 16.29 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 4.13 | 0.768 |  |  | 5.666 | 0 | 0 | 0 | 11.33 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 11.63 | 0.36333 |  |  | 12.3567 | 0 | 0 | 0 | 24.71 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 3.33 |  |  |  | 3.33 | 0 | 0 | 6.66 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 4 |  | 2.85 |  |  |  | 2.85 | 0 | 0 | 11.4 | 0 | 0 | 0
| SPACER | 25 |  | 1 | 1 | 6 | [5 empty] | 0.18 | [5 empty] | 1.08
| STIRRUPS 200X450 | 8 | 100 | 1 | 2 | 18 |  | 1.228 |  |  |  | 1.228 | 44.21 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 9 |  | 1.228 |  |  |  | 1.228 | 22.1 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 1 | 21 |  | 1.028 |  |  |  | 1.028 | 21.59 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 15 |  | 1.028 |  |  |  | 1.028 | 15.42 | 0 | 0 | 0 | 0 | 0
200X500 | B39 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 3 | 1 | 2 | 0.768 | 3.31 | 0.768 |  |  | 4.846 | 0 | 0 | 0 | 29.08 | 0 | 0
| TOP | 16 |  | 3 | 1 | 2 | 0.768 | 3.31 | 0.768 |  |  | 4.846 | 0 | 0 | 0 | 29.08 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 3 | 2 | 20 |  | 1.328 |  |  |  | 1.328 | 159.36 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 3 | 2 | 11 |  | 1.328 |  |  |  | 1.328 | 87.65 | 0 | 0 | 0 | 0 | 0
200X450 | B40 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 4.79 | 0.36333 |  |  | 5.5167 | 0 | 0 | 0 | 11.03 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 4.79 | 0.36333 |  |  | 5.5167 | 0 | 0 | 0 | 11.03 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 2 | 23 |  | 1.228 |  |  |  | 1.228 | 56.49 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
200X450 | B41 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 7.795 | 0.708 |  |  | 8.8663 | 0 | 0 | 0 | 17.73 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 7.795 | 0.708 |  |  | 8.8663 | 0 | 0 | 0 | 17.73 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 3.995 |  |  |  | 3.995 | 0 | 0 | 7.99 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 2 | 2 |  | 3.25 |  |  |  | 3.25 | 0 | 0 | 13 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 2 | 2 |  | 1.5 | 0.536 |  |  | 2.036 | 0 | 0 | 8.14 | 0 | 0 | 0
| SPACER | 25 |  | 1 | 1 | 11 | [5 empty] | 0.18 | [5 empty] | 1.98
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 21 |  | 1.352 |  |  |  | 1.352 | 28.39 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 1 | 1 | 26 |  | 1.352 |  |  |  | 1.352 | 35.15 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 18 |  | 1.352 |  |  |  | 1.352 | 24.34 | 0 | 0 | 0 | 0 | 0
200X450/350 | B42 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 3 | 0.708 |  |  | 4.0713 | 0 | 0 | 0 | 8.14 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.58 | 1.95 | 0.36333 |  |  | 2.8933 | 0 | 0 | 0 | 5.79 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 5.7 | 0.36333 |  |  | 6.4267 | 0 | 0 | 0 | 12.85 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 31 |  | 1.328 |  |  |  | 1.328 | 41.17 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 1 | 21 |  | 1.028 |  |  |  | 1.028 | 21.59 | 0 | 0 | 0 | 0 | 0
200X500 | B43 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 2.23 | 0.74 |  |  | 3.3333 | 0 | 0 | 0 | 6.67 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 2.23 | 0.74 |  |  | 3.3333 | 0 | 0 | 0 | 6.67 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 | 0.576 | 0.6 |  |  |  | 1.176 |  |  | 2.35 |  |  | 0
| SPACER | 25 |  | 1 | 1 | 2 | [5 empty] | 0.18 | [5 empty] | 0.36
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 23 |  | 1.328 |  |  |  | 1.328 | 30.54 | 0 | 0 | 0 | 0 | 0
200X500 | B44 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 5.145 | 0.768 |  |  | 6.681 | 0 | 0 | 0 | 13.36 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 5.145 | 0.768 |  |  | 6.681 | 0 | 0 | 0 | 13.36 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 1 | 2 |  | 4.145 |  |  |  | 4.145 | 0 | 0 | 8.29 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 4 | 0.576 | 1.5 |  |  |  | 2.076 | 0 | 0 | 8.3 | 0 | 0 | 0
| SPACER | 25 |  | 1 | 1 | 8 | [5 empty] | 0.18 | [5 empty] | 1.44
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 26 |  | 1.328 |  |  |  | 1.328 | 34.53 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 18 |  | 1.328 |  |  |  | 1.328 | 23.9 | 0 | 0 | 0 | 0 | 0
200X450 | B45 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 3.8 | 0.768 |  |  | 5.336 | 0 | 0 | 0 | 10.67 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 3.8 | 0.768 |  |  | 5.336 | 0 | 0 | 0 | 10.67 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 20 |  | 1.228 |  |  |  | 1.228 | 24.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 13 |  | 1.228 |  |  |  | 1.228 | 15.96 | 0 | 0 | 0 | 0 | 0
200X450 | B46 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 2.95 | 0.36333 |  |  | 4.0813 | 0 | 0 | 0 | 8.16 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 2.95 | 0.36333 |  |  | 4.0813 | 0 | 0 | 0 | 8.16 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 1 | 15 |  | 1.228 |  |  |  | 1.228 | 18.42 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 11 |  | 1.228 |  |  |  | 1.228 | 13.51 | 0 | 0 | 0 | 0 | 0
200X450 | B47 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 4.55 | 0.768 |  |  | 6.086 | 0 | 0 | 0 | 12.17 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 4.55 | 0.768 |  |  | 6.086 | 0 | 0 | 0 | 12.17 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 23 |  | 1.228 |  |  |  | 1.228 | 28.24 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 16 |  | 1.228 |  |  |  | 1.228 | 19.65 | 0 | 0 | 0 | 0 | 0
200X500 | B49 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 3.05 | 0.768 |  |  | 4.586 | 0 | 0 | 0 | 9.17 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 3.05 | 0.768 |  |  | 4.586 | 0 | 0 | 0 | 9.17 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 1 | 1 | 20 |  | 1.328 |  |  |  | 1.328 | 26.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 8 |  | 1.328 |  |  |  | 1.328 | 10.62 | 0 | 0 | 0 | 0 | 0
200X350 | B48 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 2.515 | 0.36333 |  |  | 3.6463 | 0 | 0 | 0 | 7.29 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 2.515 | 0.36333 |  |  | 3.6463 | 0 | 0 | 0 | 7.29 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 25 |  | 1.028 |  |  |  | 1.028 | 25.7 | 0 | 0 | 0 | 0 | 0
230X500 | B50 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 3.115 | 0.36333 |  |  | 4.2463 | 0 | 0 | 0 | 8.49 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 3.115 | 0.36333 |  |  | 4.2463 | 0 | 0 | 0 | 8.49 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 1 | 19 |  | 1.388 |  |  |  | 1.388 | 26.37 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 10 |  | 1.388 |  |  |  | 1.388 | 13.88 | 0 | 0 | 0 | 0 | 0
230X450 | B51 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 1 | 1 | 2 | 0.29667 | 2.345 | 0.29667 |  |  | 2.9383 | 0 | 0 | 5.88 | 0 | 0 | 0
| TOP | 12 |  | 1 | 1 | 2 | 0.29667 | 2.345 | 0.29667 |  |  | 2.9383 | 0 | 0 | 5.88 | 0 | 0 | 0
| STIRRUPS 200X350 | 10 | 100 | 1 | 1 | 24 |  | 1.32 |  |  |  | 1.32 | 0 | 31.68 | 0 | 0 | 0 | 0
200X450 | B52 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 3.2 | 0.768 |  |  | 4.736 | 0 | 0 | 0 | 9.47 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 3.2 | 0.768 |  |  | 4.736 | 0 | 0 | 0 | 9.47 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 | 0.576 | 0.9 |  |  |  | 1.476 |  |  | 2.95
SPACER
| STIRRUPS 230X500 | 10 | 100 | 1 | 1 | 18 |  | 1.26 |  |  |  | 1.26 | 0 | 22.68 | 0 | 0 | 0 | 0
|  | 10 | 150 | 1 | 1 | 9 |  | 1.26 |  |  |  | 1.26 | 0 | 11.34 | 0 | 0 | 0 | 0
230X450 | B53 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.29667 | 0.35 | 0.29667 |  |  | 0.94333 | 0 | 0 | 0 | 1.89 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.29667 | 0.35 | 0.29667 |  |  | 0.94333 | 0 | 0 | 0 | 1.89 | 0 | 0
| TOP EXTRA | 16 |  | 1 | 1 | 2 |  | 1.93 |  |  |  | 1.93 | 0 | 0 | 0 | 3.86 | 0 | 0
| STIRRUPS 230X450 | 10 | 100 | 1 | 1 | 5 |  | 1.32 |  |  |  | 1.32 | 0 | 6.6 | 0 | 0 | 0 | 0
230X450 | B54 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 2.36 | 0.36333 |  |  | 3.4913 | 0 | 0 | 0 | 6.98 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 2.36 | 0.36333 |  |  | 3.4913 | 0 | 0 | 0 | 6.98 | 0 | 0
| TOP EXTRA | 16 |  | 1 | 1 | 2 | 0.768 | 0.8 |  |  |  | 1.568 | 0 | 0 | 0 | 3.14 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 18 |  | 1.288 |  |  |  | 1.288 | 23.18 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 1 | 1 | 5 |  | 1.288 |  |  |  | 1.288 | 6.44 | 0 | 0 | 0 | 0 | 0
200X450 | B55 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 5.775 | 0.36333 |  |  | 6.9063 | 0 | 0 | 0 | 13.81 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 5.775 | 0.36333 |  |  | 6.9063 | 0 | 0 | 0 | 13.81 | 0 | 0
| TO EXTRA | 16 |  | 1 | 1 | 2 |  | 1.93 |  |  |  | 1.93 |  |  |  | 3.86 |  | 0
| SPACER | 25 |  | 1 | 1 | 2 | [5 empty] | 0.18 | [5 empty] | 0.36
| STIRRUPS 230X450 | 8 | 100 | 1 | 1 | 18 |  | 1.228 |  |  |  | 1.228 | 22.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 10 |  | 1.228 |  |  |  | 1.228 | 12.28 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 1 | 19 |  | 1.228 |  |  |  | 1.228 | 23.33 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 5 |  | 1.228 |  |  |  | 1.228 | 6.14 | 0 | 0 | 0 | 0 | 0
230X500/450 | B56 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 6.27 | 0.768 |  |  | 7.806 | 0 | 0 | 0 | 15.61 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 6.27 | 0.768 |  |  | 7.806 | 0 | 0 | 0 | 15.61 | 0 | 0
| EXTRA TOP | 12 |  | 1 | 1 | 2 | 0.576 | 1 |  |  |  | 1.576 |  |  | 3.15 |  |  | 0
| SPACER | 25 |  | 1 | 1 | 2 | [5 empty] | 0.18 | [5 empty] | 0.36
| STIRRUPS 230X500 | 8 | 100 | 1 | 1 | 21 |  | 1.388 |  |  |  | 1.388 | 29.15 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 5 |  | 1.388 |  |  |  | 1.388 | 6.94 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 1 | 21 |  | 1.288 |  |  |  | 1.288 | 27.05 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 17 |  | 1.288 |  |  |  | 1.288 | 21.9 | 0 | 0 | 0 | 0 | 0
200X500 | B58 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 2 | 2 | 0.768 | 2.225 | 0.36333 |  |  | 3.3563 | 0 | 0 | 0 | 26.85 | 0 | 0
| TOP | 16 |  | 2 | 2 | 2 | 0.768 | 2.225 | 0.36333 |  |  | 3.3563 | 0 | 0 | 0 | 26.85 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 2 | 2 | 23 |  | 1.328 |  |  |  | 1.328 | 122.18 | 0 | 0 | 0 | 0 | 0
200X450 | B59 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.708 | 3.14 | 0.708 |  |  | 4.556 | 0 | 0 | 0 | 9.11 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.708 | 3.14 | 0.708 |  |  | 4.556 | 0 | 0 | 0 | 9.11 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 1 | 20 |  | 1.228 |  |  |  | 1.228 | 24.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 8 |  | 1.228 |  |  |  | 1.228 | 9.82 | 0 | 0 | 0 | 0 | 0
200X350 | B57 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 5.72 | 0.768 |  |  | 7.256 | 0 | 0 | 0 | 14.51 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 5.72 | 0.768 |  |  | 7.256 | 0 | 0 | 0 | 14.51 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 1 | 20 |  | 1.228 |  |  |  | 1.228 | 24.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 10 |  | 1.228 |  |  |  | 1.228 | 12.28 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 1 | 1 | 21 |  | 1.228 |  |  |  | 1.228 | 25.79
200X450 | B60 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.768 | 3.06 | 0.768 |  |  | 4.596 | 0 | 0 | 0 | 18.38 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.768 | 3.06 | 0.768 |  | 0.784 | 5.38 | 0 | 0 | 0 | 21.52 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 2 | 18 |  | 1.252 |  |  |  | 1.252 | 90.14 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 2 | 9 |  | 1.252 |  |  |  | 1.252 | 45.07 | 0 | 0 | 0 | 0 | 0
200X500 | B61 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.768 | 3.63 | 0.768 |  |  | 5.166 | 0 | 0 | 0 | 20.66 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.768 | 3.63 | 0.768 |  |  | 5.166 | 0 | 0 | 0 | 20.66 | 0 | 0
| SPACER | 25 |  | 2 | 1 | 4 | [5 empty] | 0.18 | [5 empty] | 1.44
| EXTRA TOP | 12 |  | 2 | 2 | 2 | 0.576 | 0.85 |  |  |  | 1.426 |  |  | 11.41
| STIRRUPS 200X350 | 8 | 100 | 2 | 2 | 4 |  | 1.028 |  |  |  | 1.028 | 16.45 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 2 | 2 | 16 |  | 1.028 |  |  |  | 1.028 | 65.79 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 2 | 11 |  | 1.028 |  |  |  | 1.028 | 45.23 | 0 | 0 | 0 | 0 | 0
200X350 | B62 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.36333 | 7 | 0.36333 |  |  | 7.7267 | 0 | 0 | 0 | 30.91 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.36333 | 7 | 0.36333 |  |  | 7.7267 | 0 | 0 | 0 | 30.91 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 2 | 40 |  | 1.028 |  |  |  | 1.028 | 164.48 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 2 | 16 |  | 1.028 |  |  |  | 1.028 | 65.79 | 0 | 0 | 0 | 0 | 0
200X450 | B63 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 2 | 2 | 0.768 | 5.15 | 0.36333 |  |  | 6.2813 | 0 | 0 | 0 | 25.13 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.768 | 3 | 0.768 |  |  | 4.536 | 0 | 0 | 0 | 9.07 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.768 | 13.9 | 0.768 |  | 0.79 | 16.226 | 0 | 0 | 0 | 32.45 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 2 | 18 |  | 1.228 |  |  |  | 1.228 | 44.21 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 11 |  | 1.228 |  |  |  | 1.228 | 27.02 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 1 | 2 | 18 |  | 1.228 |  |  |  | 1.228 | 44.21 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 2 | 15 |  | 1.028 |  |  |  | 1.028 | 30.84 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 12 |  | 1.228 |  |  |  | 1.228 | 29.47 | 0 | 0 | 0 | 0 | 0
200X450 | B64 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.768 | 5.05 | 0.36333 |  |  | 6.1813 | 0 | 0 | 0 | 24.73 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.768 | 5.05 | 0.36333 |  | 0.79 | 6.9713 | 0 | 0 | 0 | 27.89 | 0 | 0
| STIRRUPS 200X500 | 8 | 100 | 2 | 1 | 20 |  | 1.228 |  |  |  | 1.228 | 49.12 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 9 |  | 1.228 |  |  |  | 1.228 | 22.1 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.228 |  |  |  | 1.228 | 44.21 | 0 | 0 | 0 | 0 | 0
200X350 | B65 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.36333 | 3.17 | 0.36333 |  |  | 3.8967 | 0 | 0 | 0 | 7.79 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.36333 | 3.17 | 0.36333 |  | 0.79 | 4.6867 | 0 | 0 | 0 | 9.37 | 0 | 0
| STIRRUPS 200X350 | 8 | 100 | 1 | 1 | 16 |  | 1.028 |  |  |  | 1.028 | 16.45 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 1 | 12 |  | 1.028 |  |  |  | 1.028 | 12.34 | 0 | 0 | 0 | 0 | 0
200X450 | B66 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.36333 | 5.58 | 0.768 |  |  | 6.7113 | 0 | 0 | 0 | 26.85 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.36333 | 5.58 | 0.768 |  | 0.79 | 7.5013 | 0 | 0 | 0 | 30.01 | 0 | 0
|  | 16 |  | 2 | 1 | 2 | 0.768 | 1 |  |  |  | 1.768 |  |  |  | 7.07
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.228 |  |  |  | 1.228 | 44.21 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 13 |  | 1.228 |  |  |  | 1.228 | 31.93 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 42 |  | 1.228 |  |  |  | 1.228 | 103.15 | 0 | 0 | 0 | 0 | 0
100X350 | B3 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 3 | 1 | 2 | 0.456 | 1.525 | 0.456 |  |  | 2.437 | 0 | 0 | 14.62 | 0 | 0 | 0
| TOP | 12 |  | 3 | 1 | 2 | 0.456 | 1.525 | 0.456 |  |  | 2.437 | 0 | 0 | 14.62 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 3 | 1 | 11 |  | 0.828 |  |  |  | 0.828 | 27.32 | 0 | 0 | 0 | 0 | 0
100X350 | B3 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 5 | 1 | 2 | 0.456 | 1.9 | 0.456 |  |  | 2.812 | 0 | 0 | 28.12 | 0 | 0 | 0
| TOP | 12 |  | 5 | 1 | 2 | 0.456 | 1.9 | 0.456 |  |  | 2.812 | 0 | 0 | 28.12 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 5 | 1 | 14 |  | 0.828 |  |  |  | 0.828 | 57.96 | 0 | 0 | 0 | 0 | 0
200X350 | B3 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 3 | 1 | 2 | 0.456 | 0.315 | 0.456 |  |  | 1.227 | 0 | 0 | 7.36 | 0 | 0 | 0
| TOP | 12 |  | 3 | 1 | 2 | 0.456 | 0.315 | 0.456 |  |  | 1.227 | 0 | 0 | 7.36 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 3 | 1 | 3 |  | 0.928 |  |  |  | 0.928 | 8.35 | 0 | 0 | 0 | 0 | 0
115X350 | B3 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 1 | 1 | 2 | 0.456 | 1.305 | 0.456 |  |  | 2.217 | 0 | 0 | 4.43 | 0 | 0 | 0
| TOP | 12 |  | 1 | 1 | 2 | 0.456 | 1.305 | 0.456 |  |  | 2.217 | 0 | 0 | 4.43 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 1 | 1 | 10 |  | 0.858 |  |  |  | 0.858 | 8.58 | 0 | 0 | 0 | 0 | 0
100X350 | B3 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 3 | 1 | 2 | 0.456 | 1.385 | 0.456 |  |  | 2.297 | 0 | 0 | 13.78 | 0 | 0 | 0
| TOP | 12 |  | 3 | 1 | 2 | 0.456 | 1.385 | 0.456 |  |  | 2.297 | 0 | 0 | 13.78 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 3 | 1 | 10 |  | 0.828 |  |  |  | 0.828 | 24.84 | 0 | 0 | 0 | 0 | 0
100X350 | B3 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 1 | 1 | 2 | 0.456 | 1.885 | 0.456 |  |  | 2.797 | 0 | 0 | 5.59 | 0 | 0 | 0
| TOP | 12 |  | 1 | 1 | 2 | 0.456 | 1.885 | 0.456 |  |  | 2.797 | 0 | 0 | 5.59 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 1 | 1 | 9 |  | 0.828 |  |  |  | 0.828 | 7.45 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | [11 empty] | 6285.66 | 129.38 | 666.92 | 2432.3 | 163.26 | 73.81
| UNIT WT. | [11 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.47 | 3.85 | A
| TOTAL WT. | [11 empty] | 2482.8357 | 79.8275 | 592.225 | 3843.034 | 403.2522 | 284.1685 | 7685.3428
SLAB STEEL
FLAT NO- 4, 9
| S 02 Bed room (3200x3550) | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 19 |  | 3.55 |  |  |  | 3.55 | 67.45 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 17 |  | 4.425 |  |  |  | 4.425 | 75.23 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 10 |  | 1.2 |  |  |  | 1.2 | 12 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 |  | 0.65 |  |  |  | 0.65 | 5.85 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 17 | 0.1 | 0.725 |  |  |  | 0.825 | 14.03 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 6 |  | 1.2 |  |  |  | 1.2 | 7.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 6 |  | 0.65 |  |  |  | 0.65 | 3.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 9.5 |  | 1.3 |  |  |  | 1.3 | 12.35 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 9.5 |  | 0.7 |  |  |  | 0.7 | 6.65 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 3.55 | 0.3 | -1.9525 |  | 2.1975 | 15.38 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 3.55 | 0.3 | -1.9525 |  | 2.1975 | 15.38 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 3.2 | 0.3 | -1.76 |  | 2.04 | 8.16 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 3.2 | 0.3 | -1.76 |  | 2.04 | 14.28 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 7 | 0.1 | 0.725 |  |  |  | 0.825 | 5.78 | 0 | 0 | 0 | 0 | 0
0
| S 01 Bed room (3575x3550) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 19 |  | 3.925 |  |  |  | 3.925 | 74.58 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 17 |  | 4.425 |  |  |  | 4.425 | 75.23 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 19 | 0.1 | 0.775 |  |  |  | 0.875 | 16.63 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 18 | 0.1 | 0.775 |  |  |  | 0.875 | 15.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 11 | 0.1 | 0.775 |  |  |  | 0.875 | 9.63 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 3 |  | 1.3 |  |  |  | 1.3 | 3.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 3 |  | 0.7 |  |  |  | 0.7 | 2.1 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 |  | 1.3 |  |  |  | 1.3 | 11.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 |  | 0.7 |  |  |  | 0.7 | 6.3 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 2.9 | 0.3 | -1.595 |  | 1.905 | 7.62 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 2.9 | 0.3 | -1.595 |  | 1.905 | 13.34 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 2.6 | 0.3 | -1.43 |  | 1.77 | 7.08 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 2.6 | 0.3 | -1.43 |  | 1.77 | 12.39 | 0 | 0 | 0 | 0 | 0
0
| S 03 Passage (1200x2.785) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 15 |  | 1.55 |  |  |  | 1.55 | 23.25 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 7 |  | 3.135 |  |  |  | 3.135 | 21.95 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 6 |  | 1 |  |  |  | 1 | 6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 5 |  | 0.55 |  |  |  | 0.55 | 2.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 5 |  | 0.65 |  |  |  | 0.65 | 3.25 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 17 |  | 0.55 |  |  |  | 0.55 | 9.35 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.3 | 1.2 | 0.3 | -0.66 |  | 1.14 | 6.84 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 1.2 | 0.3 | -0.66 |  | 1.14 | 7.98 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 2.785 | 0.3 | -1.5318 |  | 1.8532 | 5.56 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 11 | 0.2 | 0.575 |  |  |  | 0.775 | 8.53 | 0 | 0 | 0 | 0 | 0
0
| S 03 Toilet (1570x3575) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 18 |  | 1.92 |  |  |  | 1.92 | 34.56 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 9 |  | 3.925 |  |  |  | 3.925 | 35.33 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 | 0.1 | 0.775 |  |  |  | 0.875 | 7.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.625 |  |  |  | 0.725 | 9.43 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.625 |  |  |  | 0.725 | 9.43 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 8 |  | 0.65 |  |  |  | 0.65 | 5.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 6 |  | 0.65 |  |  |  | 0.65 | 3.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 |  | 0.7 |  |  |  | 0.7 | 6.3 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 1.57 | 0.3 | -0.8635 |  | 1.3065 | 5.23 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 1.57 | 0.3 | -0.8635 |  | 1.3065 | 5.23 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 3.575 | 0.3 | -1.9663 |  | 2.2087 | 8.84 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 3.575 | 0.3 | -1.9663 |  | 2.2087 | 8.84 | 0 | 0 | 0 | 0 | 0
0
| S 04 Bed room (3050x3115) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 11 |  | 3.4 |  |  |  | 3.4 | 37.4 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 5 |  | 3.8 |  |  |  | 3.8 | 19 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 16 |  | 3.465 |  |  |  | 3.465 | 55.44 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 3 |  | 1.1 |  |  |  | 1.1 | 3.3 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 10 | 0.1 | 0.675 |  |  |  | 0.775 | 7.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 14 | 0.1 | 1.29 |  |  |  | 1.39 | 19.46 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 17 | 0.1 | 0.675 |  |  |  | 0.775 | 13.18 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 16 | 0.1 | 0.675 |  |  |  | 0.775 | 12.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 7 |  | 1.1 |  |  |  | 1.1 | 7.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 6 |  | 0.6 |  |  |  | 0.6 | 3.6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 3.05 | 0.3 | -1.6775 |  | 1.9725 | 7.89 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 3.45 | 0.3 | -1.8975 |  | 2.1525 | 8.61 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 3.115 | 0.3 | -1.7133 |  | 2.0017 | 8.01 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.3 | 2.245 | 0.3 | -1.2348 |  | 1.6102 | 9.66 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 1.05 | 0.3 | -0.5775 |  | 1.0725 | 3.22 | 0 | 0 | 0 | 0 | 0
0
| S 05 Toilet (1600x2515) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 13 |  | 1.95 |  |  |  | 1.95 | 25.35 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 9 |  | 2.865 |  |  |  | 2.865 | 25.79 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.625 |  |  |  | 0.725 | 9.43 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.625 |  |  |  | 0.725 | 9.43 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.625 |  |  |  | 0.725 | 5.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.675 |  |  |  | 0.775 | 6.2 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 1.6 | 0.3 | -0.88 |  | 1.32 | 3.96 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 1.6 | 0.3 | -0.88 |  | 1.32 | 3.96 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 2.515 | 0.3 | -1.3833 |  | 1.7317 | 5.2 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 2.515 | 0.3 | -1.3833 |  | 1.7317 | 5.2 | 0 | 0 | 0 | 0 | 0
0
| S 06 Drawing Room (4105x6165) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR a | 8 | 100 | 1 | 1 | 39 |  | 4.455 |  |  |  | 4.455 | 173.75 | 0 | 0 | 0 | 0 | 0
| MAIN BAR a | 8 | 100 | 1 | 1 | 23 |  | 3.305 |  |  |  | 3.305 | 76.02 | 0 | 0 | 0 | 0 | 0
| DIST. BAR c | 8 | 150 | 1 | 1 | 14 |  | 7.165 |  |  |  | 7.165 | 100.31 | 0 | 0 | 0 | 0 | 0
| DIST. BAR c | 8 | 150 | 1 | 1 | 13 |  | 4.665 |  |  |  | 4.665 | 60.65 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 22 | 0.1 | 1.125 |  |  |  | 1.225 | 26.95 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 13 |  | 1.3 |  |  |  | 1.3 | 16.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 12 |  | 1.3 |  |  |  | 1.3 | 15.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 6 |  | 1.4 |  |  |  | 1.4 | 8.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 6.5 |  | 0.75 |  |  |  | 0.75 | 4.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 15 | 0.1 | 0.825 |  |  |  | 0.925 | 13.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 14 |  | 2 |  |  |  | 2 | 28 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 13 |  | 1.05 |  |  |  | 1.05 | 13.65 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 27 | 0.1 | 0.825 |  |  |  | 0.925 | 24.98 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 11.5 |  | 1.4 |  |  |  | 1.4 | 16.1 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 11.5 |  | 0.75 |  |  |  | 0.75 | 8.63 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 11 | 0.3 | 4.105 | 0.3 | -2.2578 |  | 2.4472 | 26.92 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.3 | 4.105 | 0.3 | -2.2578 |  | 2.4472 | 14.68 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 6.165 | 0.3 | -3.3908 |  | 3.3742 | 23.62 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 8 | 0.3 | 6.165 | 0.3 | -3.3908 |  | 3.3742 | 26.99 | 0 | 0 | 0 | 0 | 0
0
| S 07 Kitchen (2335x2850) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 1 | 1 | 15 |  | 2.685 |  |  |  | 2.685 | 40.28 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 12 |  | 3.2 |  |  |  | 3.2 | 38.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.1 | 0.625 |  |  |  | 0.725 | 8.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 15 | 0.1 | 0.625 |  |  |  | 0.725 | 10.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 9 |  | 0.9 |  |  |  | 0.9 | 8.1 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 9 |  | 0.5 |  |  |  | 0.5 | 4.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 4 |  | 1 |  |  |  | 1 | 4 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 1.5 | 0.3 | 2.335 | 0.3 | -1.2843 |  | 1.6507 | 2.48 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 2.335 | 0.3 | -1.2843 |  | 1.6507 | 4.95 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 1.5 | 0.3 | 2.85 | 0.3 | -1.5675 |  | 1.8825 | 2.82 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 2.5 | 0.3 | 2.85 | 0.3 | -1.5675 |  | 1.8825 | 4.71 | 0 | 0 | 0 | 0 | 0
0
| S 08 Foyer (1035x1500) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 1 | 1 | 9 |  | 1.385 |  |  |  | 1.385 | 12.47 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 6 |  | 1.85 |  |  |  | 1.85 | 11.1 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 10 |  | 1.23 |  |  |  | 1.23 | 12.3 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 8 |  | 1.72 |  |  |  | 1.72 | 13.76 | 0 | 0 | 0 | 0 | 0
0
| S 024 Balcony Bedroom (2000x6300) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 43 | 0.25 | 2.13 | 0.4 |  |  | 2.78 | 0 | 119.54 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 11 | 0.1 | 6.25 | 0.1 |  |  | 6.45 | 70.95 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 32 |  | 4.475 | 0.1 |  |  | 4.575 | 0 | 0 | 146.4 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 31 |  | 3.55 |  |  |  | 3.55 | 0 | 110.05 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 12 |  | 6.25 |  |  |  | 6.25 | 150 | 0 | 0 | 0 | 0 | 0
0
| S 024 Balcony Drawing Room (2000x4065) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 29 | 0.25 | 2.13 | 0.4 |  |  | 2.78 | 0 | 80.62 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 11 |  | 4.015 | 0.1 |  |  | 4.115 | 45.27 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 21 |  | 4.475 | 0.1 |  |  | 4.575 | 0 | 0 | 96.08 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 30 |  | 3.55 |  |  |  | 3.55 | 0 | 106.5 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 12 |  | 4.015 |  |  |  | 4.015 | 96.36 | 0 | 0 | 0 | 0 | 0
| L-SHAPE IN LEDGE WALL | 10 | 150 | 1 | 1 | 17 | 0.1 | 0.3 | 0.49 |  |  | 0.89 | 0 | 15.13 | 0 | 0 | 0 | 0
0
| S 024 Balcony Kitchen (2000x1845) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 3 |  | 1.5 |  |  |  | 1.5 | 0 | 4.5 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 10 | 0.05 | 2.1 | 0.4 |  |  | 2.55 | 0 | 25.5 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 6 |  | 1.795 | 0.1 |  |  | 1.895 | 11.37 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 7 |  | 4.675 | 0.1 |  |  | 4.775 | 0 | 0 | 33.43 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 9.5 |  | 3.55 |  |  |  | 3.55 | 0 | 33.73 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 6 |  | 1.795 |  |  |  | 1.795 | 21.54 | 0 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 4 |  | 1.7 |  |  |  | 1.7 | 13.6 | 0 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 4 |  | 1.7 |  |  |  | 1.7 | 13.6 | 0 | 0 | 0 | 0 | 0
0
| FLAT NO- 5, 8 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S 09 Bed room (3205x3560) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 18 |  | 3.555 |  |  |  | 3.555 | 63.99 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 18 |  | 4.435 |  |  |  | 4.435 | 79.83 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 17 | 0.1 | 0.725 |  |  |  | 0.825 | 14.03 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 8 |  | 1.2 |  |  |  | 1.2 | 9.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 18 |  | 0.65 |  |  |  | 0.65 | 11.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 12.5 |  | 1.2 |  |  |  | 1.2 | 15 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 12 |  | 0.65 |  |  |  | 0.65 | 7.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 11 |  | 1.2 |  |  |  | 1.2 | 13.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 11 |  | 0.65 |  |  |  | 0.65 | 7.15 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 3.205 | 0.3 | -1.7628 |  | 2.0422 | 14.3 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 3.205 | 0.3 | -1.7628 |  | 2.0422 | 8.17 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 3.56 | 0.3 | -1.958 |  | 2.202 | 15.41 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 3.56 | 0.3 | -1.958 |  | 2.202 | 15.41 | 0 | 0 | 0 | 0 | 0
0
| S 05 Bed room Toilet (1500x2225) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 12 |  | 1.85 |  |  |  | 1.85 | 22.2 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 8 |  | 2.575 |  |  |  | 2.575 | 20.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.1 | 0.625 |  |  |  | 0.725 | 8.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.1 | 0.625 |  |  |  | 0.725 | 8.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 7 | 0.1 | 0.625 |  |  |  | 0.725 | 5.08 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 7 | 0.1 | 0.675 |  |  |  | 0.775 | 5.43 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 1.5 | 0.3 | -0.825 |  | 1.275 | 3.83 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 1.5 | 0.3 | -0.825 |  | 1.275 | 3.83 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 2.225 | 0.3 | -1.2238 |  | 1.6012 | 4.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 2.225 | 0.3 | -1.2238 |  | 1.6012 | 4.8 | 0 | 0 | 0 | 0 | 0
0
| S 011 Drawing Room | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 6 |  | 3.68 |  |  |  | 3.68 | 22.08 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 6.5 |  | 1.93 |  |  |  | 1.93 | 12.55 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 7 |  | 4.62 |  |  |  | 4.62 | 32.34 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 7 |  | 2.87 |  |  |  | 2.87 | 20.09 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 5 |  | 7.15 |  |  |  | 7.15 | 35.75 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 5 |  | 5.1 |  |  |  | 5.1 | 25.5 | 0 | 0 | 0 | 0 | 0
| Dist. Bar d | 8 | 175 | 1 | 1 | 15 |  | 1.82 |  |  |  | 1.82 | 27.3 | 0 | 0 | 0 | 0 | 0
| Dist. Bar d | 8 | 175 | 1 | 1 | 19 |  | 6.09 |  |  |  | 6.09 | 115.71 | 0 | 0 | 0 | 0 | 0
| Dist. Bar d | 8 | 175 | 1 | 1 | 6 |  | 3.75 |  |  |  | 3.75 | 22.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 20 | 0.1 | 0.975 |  |  |  | 1.075 | 21.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 13 |  | 1.2 |  |  |  | 1.2 | 15.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 13 |  | 0.65 |  |  |  | 0.65 | 8.45 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 6.5 |  | 1.2 |  |  |  | 1.2 | 7.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 6.5 |  | 0.65 |  |  |  | 0.65 | 4.23 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 4.5 |  | 1.5 |  |  |  | 1.5 | 6.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 4 |  | 0.8 |  |  |  | 0.8 | 3.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.875 |  |  |  | 0.975 | 12.68 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 14.5 |  | 1.7 |  |  |  | 1.7 | 24.65 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 14.5 |  | 0.9 |  |  |  | 0.9 | 13.05 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 17 |  | 1.67 |  |  |  | 1.67 | 28.39 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.3 | 3.05 | 0.3 | -1.6775 |  | 1.9725 | 9.86 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 3.76 | 0.3 | -2.068 |  | 2.292 | 16.04 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.3 | 3.2 | 0.3 | -1.76 |  | 2.04 | 12.24 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 9 | 0.3 | 6.79 | 0.3 | -3.7345 |  | 3.6555 | 32.9 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 8 | 0.3 | 1.47 | 0.3 | -0.8085 |  | 1.2615 | 10.09 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 8 | 0.3 | 2.55 | 0.3 | -1.4025 |  | 1.7475 | 13.98 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 3.76 | 0.3 | -2.068 |  | 2.292 | 16.04 | 0 | 0 | 0 | 0 | 0
0
| S 012 Kitchen (2365x3250) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 17 |  | 2.715 |  |  |  | 2.715 | 46.16 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 13 |  | 4.12 |  |  |  | 4.12 | 53.56 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.1 | 0.725 |  |  |  | 0.825 | 9.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.625 |  |  |  | 0.725 | 5.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 5.5 |  | 0.9 |  |  |  | 0.9 | 4.95 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 5 |  | 0.5 |  |  |  | 0.5 | 2.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8.5 |  | 0.9 |  |  |  | 0.9 | 7.65 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.5 |  |  |  | 0.5 | 4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 6 |  | 0.65 |  |  |  | 0.65 | 3.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 1.1 |  |  |  | 1.1 | 8.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 2.365 | 0.3 | -1.3008 |  | 1.6642 | 6.66 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.3 | 3.25 | 0.3 | -1.7875 |  | 2.0625 | 10.31 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.3 | 3.25 | 0.3 | -1.7875 |  | 2.0625 | 10.31 | 0 | 0 | 0 | 0 | 0
0
| S 013 Bed room (2925x3250) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 17 |  | 3.275 |  |  |  | 3.275 | 55.68 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 16 |  | 4.12 |  |  |  | 4.12 | 65.92 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 16 | 0.1 | 0.725 |  |  |  | 0.825 | 13.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.675 |  |  |  | 0.775 | 6.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4.5 |  | 1.1 |  |  |  | 1.1 | 4.95 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 0.6 |  |  |  | 0.6 | 2.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 10 |  | 1.1 |  |  |  | 1.1 | 11 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 10 |  | 0.6 |  |  |  | 0.6 | 6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 1.1 |  |  |  | 1.1 | 8.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.6 |  |  |  | 0.6 | 4.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.3 | 2.925 | 0.3 | -1.6088 |  | 1.9162 | 9.58 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.3 | 3.25 | 0.3 | -1.7875 |  | 2.0625 | 10.31 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.3 | 3.25 | 0.3 | -1.7875 |  | 2.0625 | 10.31 | 0 | 0 | 0 | 0 | 0
0
| S 14 Passege (1700x2925) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 1 | 1 | 15 |  | 2.05 |  |  |  | 2.05 | 30.75 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 9 |  | 3.275 |  |  |  | 3.275 | 29.48 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 16 |  | 0.7 |  |  |  | 0.7 | 11.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 15 | 0.1 | 0.675 |  |  |  | 0.775 | 11.63 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 5 |  | 1.1 |  |  |  | 1.1 | 5.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 0.6 |  |  |  | 0.6 | 2.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 3 |  | 1.1 |  |  |  | 1.1 | 3.3 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 3 |  | 0.6 |  |  |  | 0.6 | 1.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 2.925 | 0.3 | -1.6088 |  | 1.9162 | 7.67 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 2.925 | 0.3 | -1.6088 |  | 1.9162 | 7.67 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.3 | 1.7 | 0.3 | -0.935 |  | 1.365 | 6.83 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.3 | 1.7 | 0.3 | -0.935 |  | 1.365 | 6.83 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 0.725 | 0.3 | -0.39875 |  | 0.92625 | 2.78 | 0 | 0 | 0 | 0 | 0
0
| S 03 Bedroom Toilet (1425x3385) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 18 |  | 1.775 |  |  |  | 1.775 | 31.95 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 8 |  | 3.735 |  |  |  | 3.735 | 29.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.1 | 0.77 |  |  |  | 0.87 | 10.44 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.1 | 0.625 |  |  |  | 0.725 | 8.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.625 |  |  |  | 0.725 | 5.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 6 |  | 1.625 |  |  |  | 1.625 | 9.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.7 |  |  |  | 0.7 | 5.6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 1.42 | 0.3 | -0.781 |  | 1.239 | 4.96 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 1.42 | 0.3 | -0.781 |  | 1.239 | 4.96 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 3.575 | 0.3 | -1.9663 |  | 2.2087 | 8.84 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 3.575 | 0.3 | -1.9663 |  | 2.2087 | 8.84 | 0 | 0 | 0 | 0 | 0
0
| S 024 Balcony Drg. Room (2000x4665) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 32 | 0.25 | 2.13 | 0.4 |  |  | 2.78 | 0 | 88.96 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 11 |  | 4.615 |  |  |  | 4.615 | 50.77 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 24 |  | 4.475 | 0.1 |  |  | 4.575 | 0 | 0 | 109.8 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 23 |  | 3.55 |  |  |  | 3.55 | 0 | 81.65 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 12 |  | 4.615 |  |  |  | 4.615 | 110.76 | 0 | 0 | 0 | 0 | 0
0
| S 024 Balcony Bedroom & Kitchen (2000x5105) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 34 | 0.25 | 2.13 | 0.4 |  |  | 2.78 | 0 | 94.52 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 11 | 0.1 | 5.055 | 0.1 |  |  | 5.255 | 57.81 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 25 |  | 4.475 | 0.1 |  |  | 4.575 | 0 | 0 | 114.38 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 25 |  | 3.55 |  |  |  | 3.55 | 0 | 88.75 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 12 |  | 5.055 | 0.3 |  |  | 5.355 | 128.52 | 0 | 0 | 0 | 0 | 0
| L-SHAPE IN LEDGE WALL | 10 | 150 | 1 | 2 | 14 | 0.1 | 0.3 | 0.49 |  |  | 0.89 | 0 | 24.92 | 0 | 0 | 0 | 0
0
| S 15 Bedroom (3050x3580) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 1 | 1 | 18 |  | 3.4 |  |  |  | 3.4 | 61.2 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 16 |  | 3.93 |  |  |  | 3.93 | 62.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 16 | 0.1 | 0.775 |  |  |  | 0.875 | 14 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.7 |  |  |  | 0.7 | 5.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 7 |  | 1.3 |  |  |  | 1.3 | 9.1 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 2 | 10 |  | 0.6 |  |  |  | 0.6 | 12 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 2 | 9 |  | 1.1 |  |  |  | 1.1 | 19.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 3.05 | 0.3 | -1.6775 |  | 1.9725 | 7.89 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 3.05 | 0.3 | -1.6775 |  | 1.9725 | 13.81 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.3 | 3.58 | 0.3 | -1.969 |  | 2.211 | 13.27 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.3 | 3.58 | 0.3 | -1.969 |  | 2.211 | 13.27 | 0 | 0 | 0 | 0 | 0
0
| S 16 Dressing Area (1410x2430) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 1 | 1 | 13 |  | 1.78 |  |  |  | 1.78 | 23.14 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 8 |  | 0.75 |  |  |  | 0.75 | 6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 | 0.1 | 0.625 |  |  |  | 0.725 | 6.53 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 14 | 0.1 | 0.625 |  |  |  | 0.725 | 10.15 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 |  | 0.6 |  |  |  | 0.6 | 7.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.9 |  |  |  | 0.9 | 7.2 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 1.41 | 0.3 | -0.7755 |  | 1.2345 | 3.7 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.3 | 1.41 | 0.3 | -0.7755 |  | 1.2345 | 6.17 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 2.43 | 0.3 | -1.3365 |  | 1.6935 | 6.77 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 2.43 | 0.3 | -1.3365 |  | 1.6935 | 5.08 | 0 | 0 | 0 | 0 | 0
0
| S 05 Toilet (1540x2410) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 1 | 1 | 13 |  | 1.89 |  |  |  | 1.89 | 24.57 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 8 |  | 2.76 |  |  |  | 2.76 | 22.08 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 7 | 0.15 | 0.625 |  |  |  | 0.775 | 5.43 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 | 0.15 | 0.625 |  |  |  | 0.775 | 6.98 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.15 | 0.55 |  |  |  | 0.7 | 8.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.15 | 0.55 |  |  |  | 0.7 | 8.4 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 1.54 | 0.3 | -0.847 |  | 1.293 | 3.88 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 1.54 | 0.3 | -0.847 |  | 1.293 | 3.88 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 2.41 | 0.3 | -1.3255 |  | 1.6845 | 5.05 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 2.41 | 0.3 | -1.3255 |  | 1.6845 | 5.05 | 0 | 0 | 0 | 0 | 0
0
| S 024 Balcony Bedroom (2000x3265) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 22 | 0.25 | 2.13 | 0.4 |  |  | 2.78 | 0 | 61.16 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 11 |  | 3.215 |  |  |  | 3.215 | 35.37 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 16 |  | 4.475 | 0.1 |  |  | 4.575 | 0 | 0 | 73.2 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 15 |  | 3.55 |  |  |  | 3.55 | 0 | 53.25 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 11 |  | 3.215 |  |  |  | 3.215 | 70.73 | 0 | 0 | 0 | 0 | 0
0
| FLAT NO- 6, 7 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S 09 Bed room (3205x3560) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 19 |  | 3.555 |  |  |  | 3.555 | 67.55 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 17 |  | 4.435 |  |  |  | 4.435 | 75.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 17 | 0.1 | 0.725 |  |  |  | 0.825 | 14.03 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 12 |  | 1.2 |  |  |  | 1.2 | 14.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 11 |  | 0.65 |  |  |  | 0.65 | 7.15 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 10 |  | 1.2 |  |  |  | 1.2 | 12 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 10 |  | 0.65 |  |  |  | 0.65 | 6.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 11 |  | 1.2 |  |  |  | 1.2 | 13.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 11 |  | 0.65 |  |  |  | 0.65 | 7.15 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 3.205 | 0.3 | -1.7628 |  | 2.0422 | 14.3 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 3.205 | 0.3 | -1.7628 |  | 2.0422 | 8.17 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 3.56 | 0.3 | -1.958 |  | 2.202 | 15.41 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 3.56 | 0.3 | -1.958 |  | 2.202 | 15.41 | 0 | 0 | 0 | 0 | 0
0
| S 05 Bed room Toilet (1500x2225) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 13 |  | 1.85 |  |  |  | 1.85 | 24.05 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 8 |  | 2.575 |  |  |  | 2.575 | 20.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.625 |  |  |  | 0.725 | 9.43 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.625 |  |  |  | 0.725 | 9.43 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 7 | 0.1 | 0.625 |  |  |  | 0.725 | 5.08 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 7 | 0.1 | 0.675 |  |  |  | 0.775 | 5.43 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 1.5 | 0.3 | -0.825 |  | 1.275 | 3.83 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 1.5 | 0.3 | -0.825 |  | 1.275 | 3.83 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 2.225 | 0.3 | -1.2238 |  | 1.6012 | 4.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 2.225 | 0.3 | -1.2238 |  | 1.6012 | 4.8 | 0 | 0 | 0 | 0 | 0
0
| S 011 Drawing Room | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 6 |  | 3.68 |  |  |  | 3.68 | 22.08 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 6.5 |  | 1.93 |  |  |  | 1.93 | 12.55 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 7 |  | 4.62 |  |  |  | 4.62 | 32.34 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 6 |  | 2.87 |  |  |  | 2.87 | 17.22 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 5 |  | 7.15 |  |  |  | 7.15 | 35.75 | 0 | 0 | 0 | 0 | 0
| MAIN BAR c | 8 | 150 | 1 | 1 | 5.5 |  | 5.1 |  |  |  | 5.1 | 28.05 | 0 | 0 | 0 | 0 | 0
| Dist. Bar d | 8 | 175 | 1 | 1 | 15 |  | 1.82 |  |  |  | 1.82 | 27.3 | 0 | 0 | 0 | 0 | 0
| Dist. Bar d | 8 | 175 | 1 | 1 | 20 |  | 6.09 |  |  |  | 6.09 | 121.8 | 0 | 0 | 0 | 0 | 0
| Dist. Bar d | 8 | 175 | 1 | 1 | 6 |  | 3.75 |  |  |  | 3.75 | 22.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 20 | 0.1 | 0.975 |  |  |  | 1.075 | 21.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 14 |  | 1.2 |  |  |  | 1.2 | 16.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 14 |  | 0.65 |  |  |  | 0.65 | 9.1 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 6.5 |  | 1.2 |  |  |  | 1.2 | 7.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 6.5 |  | 0.65 |  |  |  | 0.65 | 4.23 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 4.5 |  | 1.5 |  |  |  | 1.5 | 6.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 4 |  | 0.8 |  |  |  | 0.8 | 3.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.875 |  |  |  | 0.975 | 12.68 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 14.5 |  | 1.7 |  |  |  | 1.7 | 24.65 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 14.5 |  | 0.9 |  |  |  | 0.9 | 13.05 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 17 |  | 1.67 |  |  |  | 1.67 | 28.39 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.3 | 3.05 | 0.3 | -1.6775 |  | 1.9725 | 9.86 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 3.76 | 0.3 | -2.068 |  | 2.292 | 16.04 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.3 | 3.2 | 0.3 | -1.76 |  | 2.04 | 12.24 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 9 | 0.3 | 6.79 | 0.3 | -3.7345 |  | 3.6555 | 32.9 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 8 | 0.3 | 1.47 | 0.3 | -0.8085 |  | 1.2615 | 10.09 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 8 | 0.3 | 2.55 | 0.3 | -1.4025 |  | 1.7475 | 13.98 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 3.76 | 0.3 | -2.068 |  | 2.292 | 16.04 | 0 | 0 | 0 | 0 | 0
0
| S 012 Kitchen (2365x3250) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 17 |  | 2.715 |  |  |  | 2.715 | 46.16 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 13 |  | 3.6 |  |  |  | 3.6 | 46.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.725 |  |  |  | 0.825 | 10.73 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 | 0.1 | 0.625 |  |  |  | 0.725 | 6.53 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 5.5 |  | 0.9 |  |  |  | 0.9 | 4.95 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 5 |  | 0.5 |  |  |  | 0.5 | 2.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8.5 |  | 0.9 |  |  |  | 0.9 | 7.65 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8.5 |  | 0.5 |  |  |  | 0.5 | 4.25 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 2.365 | 0.3 | -1.3008 |  | 1.6642 | 6.66 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.3 | 3.25 | 0.3 | -1.7875 |  | 2.0625 | 10.31 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.3 | 3.25 | 0.3 | -1.7875 |  | 2.0625 | 10.31 | 0 | 0 | 0 | 0 | 0
0
| S 013 Bed room (2925x3250) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 17 |  | 3.275 |  |  |  | 3.275 | 55.68 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 13 |  | 3.6 |  |  |  | 3.6 | 46.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 17 | 0.1 | 0.725 |  |  |  | 0.825 | 14.03 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 13 | 0.1 | 0.675 |  |  |  | 0.775 | 10.08 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 6 |  | 1.1 |  |  |  | 1.1 | 6.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 7 |  | 0.6 |  |  |  | 0.6 | 4.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 6 |  | 1.1 |  |  |  | 1.1 | 6.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.6 |  |  |  | 0.6 | 4.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 2.925 | 0.3 | -1.6088 |  | 1.9162 | 7.67 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.3 | 3.25 | 0.3 | -1.7875 |  | 2.0625 | 12.38 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.3 | 3.25 | 0.3 | -1.7875 |  | 2.0625 | 12.38 | 0 | 0 | 0 | 0 | 0
0
| S 14 Passege (1700x2925) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 1 | 1 | 15 |  | 2.05 |  |  |  | 2.05 | 30.75 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 9 |  | 3.275 |  |  |  | 3.275 | 29.48 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 15 |  | 0.7 |  |  |  | 0.7 | 10.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 15 | 0.1 | 0.675 |  |  |  | 0.775 | 11.63 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 5 |  | 1.1 |  |  |  | 1.1 | 5.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 0.6 |  |  |  | 0.6 | 2.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 9 | 0.1 | 0.675 |  |  |  | 0.775 | 6.98 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 2.925 | 0.3 | -1.6088 |  | 1.9162 | 7.67 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 2.925 | 0.3 | -1.6088 |  | 1.9162 | 7.67 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.3 | 1.7 | 0.3 | -0.935 |  | 1.365 | 8.19 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.3 | 1.7 | 0.3 | -0.935 |  | 1.365 | 8.19 | 0 | 0 | 0 | 0 | 0
0
| S 03 Bedroom Toilet (1425x3385) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 1 | 1 | 12 |  | 1.775 |  |  |  | 1.775 | 21.3 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 8 |  | 3.735 |  |  |  | 3.735 | 29.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.1 | 0.775 |  |  |  | 0.875 | 10.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 12 | 0.1 | 0.625 |  |  |  | 0.725 | 8.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 | 0.1 | 0.625 |  |  |  | 0.725 | 5.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 8 |  | 1.625 |  |  |  | 1.625 | 13 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.7 |  |  |  | 0.7 | 5.6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 1.425 | 0.3 | -0.78375 |  | 1.2412 | 4.97 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 1.425 | 0.3 | -0.78375 |  | 1.2412 | 4.97 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 3.575 | 0.3 | -1.9663 |  | 2.2087 | 8.84 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 3.575 | 0.3 | -1.9663 |  | 2.2087 | 8.84 | 0 | 0 | 0 | 0 | 0
0
| S 024 Balcony Drg. Room (2000x4665) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 32 | 0.25 | 2.13 | 0.4 |  |  | 2.78 | 0 | 88.96 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 11 |  | 4.615 |  |  |  | 4.615 | 50.77 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 24 |  | 4.475 | 0.1 |  |  | 4.575 | 0 | 0 | 109.8 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 24 |  | 3.55 |  |  |  | 3.55 | 0 | 85.2 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 11 |  | 4.615 |  |  |  | 4.615 | 101.53 | 0 | 0 | 0 | 0 | 0
0
| S 024 Balcony Bedroom & Kitchen (2000x5105) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 42 | 0.25 | 1.975 | 0.4 |  |  | 2.625 | 0 | 110.25 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 11 | 0.1 | 5.055 | 0.1 |  |  | 5.255 | 57.81 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 30 |  | 4.475 | 0.1 |  |  | 4.575 | 0 | 0 | 137.25 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 30 |  | 3.55 |  |  |  | 3.55 | 0 | 106.5 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 11 |  | 5.055 |  |  |  | 5.055 | 111.21 | 0 | 0 | 0 | 0 | 0
| L-SHAPE IN LEDGE WALL | 10 | 150 | 1 | 2 | 42 | 0.1 | 0.3 | 0.49 |  |  | 0.89 | 0 | 74.76 | 0 | 0 | 0 | 0
0
| S 15 Bedroom (3050x3580) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 1 | 1 | 18 |  | 3.4 |  |  |  | 3.4 | 61.2 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 16 |  | 3.93 |  |  |  | 3.93 | 62.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 16 | 0.1 | 0.775 |  |  |  | 0.875 | 14 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 8 |  | 0.7 |  |  |  | 0.7 | 5.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 7 |  | 1.3 |  |  |  | 1.3 | 9.1 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 2 | 10 |  | 0.6 |  |  |  | 0.6 | 12 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 2 | 9 |  | 1.1 |  |  |  | 1.1 | 19.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 3.05 | 0.3 | -1.6775 |  | 1.9725 | 7.89 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 7 | 0.3 | 3.05 | 0.3 | -1.6775 |  | 1.9725 | 13.81 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.3 | 3.58 | 0.3 | -1.969 |  | 2.211 | 13.27 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.3 | 3.58 | 0.3 | -1.969 |  | 2.211 | 13.27 | 0 | 0 | 0 | 0 | 0
0
| S 024 Balcony Bedroom (2000x3265) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 1 | 1 | 22 | 0.25 | 2.13 | 0.4 |  |  | 2.78 | 0 | 61.16 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 11 |  | 3.215 |  |  |  | 3.215 | 35.37 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 1 | 1 | 16 |  | 4.475 | 0.1 |  |  | 4.575 | 0 | 0 | 73.2 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 1 | 1 | 15 |  | 3.55 |  |  |  | 3.55 | 0 | 53.25 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 1 | 2 | 11 |  | 3.215 |  |  |  | 3.215 | 70.73 | 0 | 0 | 0 | 0 | 0
0
| FLAT NO- 1,2,3, 10,11,12 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S 20 Bed room (3250x3860) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 3 | 1 | 20 |  | 3.6 |  |  |  | 3.6 | 216 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 1 | 17 |  | 4.21 |  |  |  | 4.21 | 214.71 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 17 | 0.1 | 0.725 |  |  |  | 0.825 | 42.08 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 12 | 0.1 | 0.775 |  |  |  | 0.875 | 31.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 8.5 |  | 1.3 |  |  |  | 1.3 | 33.15 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 8 |  | 0.7 |  |  |  | 0.7 | 16.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 10 |  | 1.2 |  |  |  | 1.2 | 36 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 10 |  | 0.65 |  |  |  | 0.65 | 19.5 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 12 | 0.3 | 3.25 | 0.3 | -1.7875 |  | 2.0625 | 74.25 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 7 | 0.3 | 3.25 | 0.3 | -1.7875 |  | 2.0625 | 43.31 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 4 | 0.3 | 3.86 | 0.3 | -2.123 |  | 2.337 | 28.04 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 6 | 0.3 | 3.86 | 0.3 | -2.123 |  | 2.337 | 42.07 | 0 | 0 | 0 | 0 | 0
0
| S 20, 2nd Bed room (3335X3860) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 3 | 1 | 20 |  | 3.685 |  |  |  | 3.685 | 221.1 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 1 | 17 |  | 4.21 |  |  |  | 4.21 | 214.71 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 18 | 0.1 | 0.775 |  |  |  | 0.875 | 47.25 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 15 |  | 1.2 |  |  |  | 1.2 | 54 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 40 |  | 0.65 |  |  |  | 0.65 | 78 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 11 |  | 1.3 |  |  |  | 1.3 | 42.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 9 |  | 0.7 |  |  |  | 0.7 | 18.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 10 |  | 1.2 |  |  |  | 1.2 | 36 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 10 |  | 0.65 |  |  |  | 0.65 | 19.5 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 12 | 0.3 | 3.335 | 0.3 | -1.8343 |  | 2.1007 | 75.63 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 7 | 0.3 | 3.335 | 0.3 | -1.8343 |  | 2.1007 | 44.12 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 4 | 0.3 | 3.86 | 0.3 | -2.123 |  | 2.337 | 28.04 | 0 | 0 | 0 | 0 | 0
| BINDER | 8 | 200 | 3 | 1 | 7 | 0.3 | 3.86 | 0.3 | -2.123 |  | 2.337 | 49.08 | 0 | 0 | 0 | 0 | 0
0
| S 01, 3rd Bed room (3265x3550) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN BAR e | 8 | 200 | 3 | 1 | 18 |  | 3.615 |  |  |  | 3.615 | 195.21 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 1 | 17 |  | 4.425 |  |  |  | 4.425 | 225.68 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 18 | 0.1 | 0.775 |  |  |  | 0.875 | 47.25 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 17 | 0.1 | 0.775 |  |  |  | 0.875 | 44.63 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 12 | 0.1 | 0.775 |  |  |  | 0.875 | 31.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 3 | 1 | 3 |  | 1.3 |  |  |  | 1.3 | 11.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 3 | 1 | 3 |  | 0.65 |  |  |  | 0.65 | 5.85 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 8.5 |  | 1.2 |  |  |  | 1.2 | 30.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 8 |  | 0.65 |  |  |  | 0.65 | 15.6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 4 | 0.3 | 3.265 | 0.3 | -1.7958 |  | 2.0692 | 24.83 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 7 | 0.3 | 3.265 | 0.3 | -1.7958 |  | 2.0692 | 43.45 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 4 | 0.3 | 3.55 | 0.3 | -1.9525 |  | 2.1975 | 26.37 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 7 | 0.3 | 3.55 | 0.3 | -1.9525 |  | 2.1975 | 46.15 | 0 | 0 | 0 | 0 | 0
0
| S 03 Bedroom Toilet (1425X2275) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 3 | 2 | 12 |  | 1.775 |  |  |  | 1.775 | 127.8 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 2 | 8 |  | 3.195 |  |  |  | 3.195 | 153.36 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 2 | 8 | 0.1 | 0.75 |  |  |  | 0.85 | 40.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 2 | 12 | 0.1 | 0.625 |  |  |  | 0.725 | 52.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 2 | 12 | 0.1 | 0.625 |  |  |  | 0.725 | 52.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 3 | 2 | 7 |  | 0.65 |  |  |  | 0.65 | 27.3 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 2 | 7 |  | 0.65 |  |  |  | 0.65 | 27.3 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 2 | 8 |  | 0.7 |  |  |  | 0.7 | 33.6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 2 | 4 | 0.3 | 1.57 | 0.3 | -0.8635 |  | 1.3065 | 31.36 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 2 | 4 | 0.3 | 1.57 | 0.3 | -0.8635 |  | 1.3065 | 31.36 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 2 | 4 | 0.3 | 3.575 | 0.3 | -1.9663 |  | 2.2087 | 53.01 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 2 | 4 | 0.3 | 3.575 | 0.3 | -1.9663 |  | 2.2087 | 53.01 | 0 | 0 | 0 | 0 | 0
0
| S 19 Living Room | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar a | 8 | 100 | 3 | 1 | 15 |  | 3.665 |  |  |  | 3.665 | 164.93 | 0 | 0 | 0 | 0 | 0
| Main Bar a | 8 | 100 | 3 | 1 | 16 |  | 2.465 |  |  |  | 2.465 | 118.32 | 0 | 0 | 0 | 0 | 0
| Main Bar a | 8 | 100 | 3 | 1 | 16.5 |  | 5.475 |  |  |  | 5.475 | 271.01 | 0 | 0 | 0 | 0 | 0
| Main Bar a | 8 | 100 | 3 | 1 | 16 |  | 3.825 |  |  |  | 3.825 | 183.6 | 0 | 0 | 0 | 0 | 0
| Dist. Bar c | 8 | 150 | 3 | 1 | 22 |  | 7.11 |  |  |  | 7.11 | 469.26 | 0 | 0 | 0 | 0 | 0
| Dist. Bar c | 8 | 150 | 3 | 1 | 13 |  | 4.86 |  |  |  | 4.86 | 189.54 | 0 | 0 | 0 | 0 | 0
| Dist. Bar c | 8 | 150 | 3 | 1 | 9 |  | 3.52 |  |  |  | 3.52 | 95.04 | 0 | 0 | 0 | 0 | 0
| Dist. Bar c | 8 | 150 | 3 | 1 | 8 |  | 1.62 |  |  |  | 1.62 | 38.88 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 3 | 1 | 23 | 0.1 | 1.175 |  |  |  | 1.275 | 87.98 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA b | 8 | 125 | 3 | 1 | 26 | 0.1 | 0.7 |  |  |  | 0.8 | 62.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 33 |  | 1.7 |  |  |  | 1.7 | 168.3 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 32 |  | 0.9 |  |  |  | 0.9 | 86.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 3 | 1 | 10 |  | 2.1 |  |  |  | 2.1 | 63 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 3 | 1 | 12 |  | 1.1 |  |  |  | 1.1 | 39.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 3 | 1 | 22 | 0.1 | 1.17 |  |  |  | 1.27 | 83.82 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 3 | 1 | 12 |  | 0.6 |  |  |  | 0.6 | 21.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA b | 8 | 125 | 3 | 1 | 16 | 0.1 | 0.975 |  |  |  | 1.075 | 51.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 6 |  | 1.7 |  |  |  | 1.7 | 30.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 6.5 |  | 0.9 |  |  |  | 0.9 | 17.55 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 16 |  | 1.2 |  |  |  | 1.2 | 57.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 3 | 1 | 16 |  | 0.65 |  |  |  | 0.65 | 31.2 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 6 | 0.3 | 3.215 | 0.3 | -1.7683 |  | 2.0467 | 36.84 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 9 | 0.3 | 6.245 | 0.3 | -3.4348 |  | 3.4102 | 92.08 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 11 | 0.3 | 5.125 | 0.3 | -2.8188 |  | 2.9062 | 95.91 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 9 | 0.3 | 3.17 | 0.3 | -1.7435 |  | 2.0265 | 54.72 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 3 | 1 | 7 | 0.3 | 3.075 | 0.3 | -1.6913 |  | 1.9837 | 41.66 | 0 | 0 | 0 | 0 | 0
0
| S 21 Kitchen (2345x3435) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar e | 8 | 200 | 3 | 1 | 18 |  | 2.695 |  |  |  | 2.695 | 145.53 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 1 | 12 |  | 4.3 |  |  |  | 4.3 | 154.8 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 12 | 0.1 | 0.725 |  |  |  | 0.825 | 29.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 9 |  | 0.9 |  |  |  | 0.9 | 24.3 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 8 |  | 0.5 |  |  |  | 0.5 | 12 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 6 |  | 1.2 |  |  |  | 1.2 | 21.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 3 | 1 | 6 |  | 0.65 |  |  |  | 0.65 | 11.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 3 | 1 | 12 |  | 0.9 |  |  |  | 0.9 | 32.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 3 | 1 | 12 |  | 0.5 |  |  |  | 0.5 | 18 | 0 | 0 | 0 | 0 | 0
0
| S 024 Balcony Bedroom (2000x5845) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 3 | 1 | 39 | 0.25 | 2.175 | 0.4 |  |  | 2.825 | 0 | 330.53 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 1 | 11 | 0.1 | 5.795 | 0.1 |  |  | 5.995 | 197.84 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 3 | 1 | 30 |  | 4.475 | 0.1 |  |  | 4.575 | 0 | 0 | 411.75 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 3 | 1 | 29 |  | 3.55 |  |  |  | 3.55 | 0 | 308.85 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 3 | 2 | 11 |  | 5.795 |  |  |  | 5.795 | 382.47 | 0 | 0 | 0 | 0 | 0
| L-SHAPE IN LEDGE WALL | 10 | 150 | 1 | 2 | 14 | 0.1 | 0.3 | 0.49 |  |  | 0.89 | 0 | 24.92 | 0 | 0 | 0 | 0
0
| S 024 Balcony Drawing Room (2000x3630) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 3 | 1 | 25 | 0.25 | 1.975 | 0.4 |  |  | 2.625 | 0 | 196.88 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 1 | 11 |  | 3.58 | 0.1 |  |  | 3.68 | 121.44 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 3 | 1 | 18.5 |  | 4.475 |  |  |  | 4.475 | 0 | 0 | 248.36 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 3 | 1 | 18.5 |  | 3.55 |  |  |  | 3.55 | 0 | 197.03 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 3 | 2 | 11 |  | 3.58 |  |  |  | 3.58 | 236.28 | 0 | 0 | 0 | 0 | 0
| L-SHAPE IN LEDGE WALL | 10 | 150 | 1 | 1 | 14 | 0.1 | 0.3 | 0.49 |  |  | 0.89 | 0 | 12.46 | 0 | 0 | 0 | 0
0
| S 024 Balcony Kitchen (2000x1650) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar h | 10 | 150 | 3 | 1 | 12 | 0.25 | 1.975 | 0.4 |  |  | 2.625 | 0 | 94.5 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 3 | 1 | 11 |  | 1.6 | 0.1 |  |  | 1.7 | 56.1 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA m | 12 | 100 | 3 | 1 | 8 |  | 4.475 |  |  |  | 4.475 | 0 | 0 | 107.4 | 0 | 0 | 0
| TOP EXTRA m | 10 | 100 | 3 | 1 | 7 |  | 3.55 |  |  |  | 3.55 | 0 | 74.55 | 0 | 0 | 0 | 0
| binder e | 8 | 200 | 3 | 2 | 12 |  | 1.6 |  |  |  | 1.6 | 115.2 | 0 | 0 | 0 | 0 | 0
0
| Lobby S10 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 16 |  | 2.82 |  |  |  | 2.82 | 45.12 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 10 |  | 1.85 |  |  |  | 1.85 | 18.5 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 8 |  | 5.44 |  |  |  | 5.44 | 43.52 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 5 |  | 3.55 |  |  |  | 3.55 | 17.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 25 | 0.1 | 0.705 |  |  |  | 0.805 | 20.13 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 5.09 | 0.3 | -2.7995 |  | 2.8905 | 11.56 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 7 |  | 1.7 |  |  |  | 1.7 | 11.9 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 9 |  | 0.9 |  |  |  | 0.9 | 8.1 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 8 | 0.3 | 2 | 0.3 | -1.1 |  | 1.5 | 12 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA d | 8 | 175 | 1 | 1 | 19 |  | 0.8 |  |  |  | 0.8 | 15.2 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.3 | 3.14 | 0.3 | -1.727 |  | 2.013 | 10.07 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 14 |  | 0.6 |  |  |  | 0.6 | 8.4 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 | 0.3 | 1.95 | 0.3 | -1.0725 |  | 1.4775 | 5.91 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 9 |  | 1.7 |  |  |  | 1.7 | 15.3 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 9 | 0.3 | 1.95 | 0.3 | -1.0725 |  | 1.4775 | 13.3 | 0 | 0 | 0 | 0 | 0
0
0
| Lobby S17 (1610x3950) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 21 |  | 1.96 |  |  |  | 1.96 | 41.16 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 9 |  | 4.3 |  |  |  | 4.3 | 38.7 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 14 | 0.1 | 0.725 |  |  |  | 0.825 | 11.55 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 23 |  | 0.65 |  |  |  | 0.65 | 14.95 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.3 | 3.95 | 0.3 | -2.1725 |  | 2.3775 | 14.27 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4.5 |  | 1.3 |  |  |  | 1.3 | 5.85 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 0.7 |  |  |  | 0.7 | 2.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 6 | 0.3 | 1.61 | 0.3 | -0.8855 |  | 1.3245 | 7.95 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 200 | 1 | 1 | 4.5 |  | 1.3 |  |  |  | 1.3 | 5.85 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 4 |  | 0.7 |  |  |  | 0.7 | 2.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 150 | 1 | 1 | 7 | 0.3 | 1.61 | 0.3 | -0.8855 |  | 1.3245 | 9.27 | 0 | 0 | 0 | 0 | 0
0
| Lobby S18 (2440x5665) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 29 |  | 2.79 |  |  |  | 2.79 | 80.91 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 13 |  | 6.015 |  |  |  | 6.015 | 78.2 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 29 | 0.1 | 0.625 |  |  |  | 0.725 | 21.03 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 3 | 0.3 | 5.665 | 0.3 | -3.1158 |  | 3.1492 | 9.45 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 12.5 |  | 1.9 |  |  |  | 1.9 | 23.75 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA a | 8 | 100 | 1 | 1 | 12.5 |  | 1 |  |  |  | 1 | 12.5 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 10 | 0.3 | 2.44 | 0.3 | -1.342 |  | 1.698 | 16.98 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 22 | 0.1 | 0.625 |  |  |  | 0.725 | 15.95 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 0.9 |  |  |  | 0.9 | 3.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 0.5 |  |  |  | 0.5 | 2 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 5 | 0.3 | 1.4 | 0.3 | -0.77 |  | 1.23 | 6.15 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 1.9 |  |  |  | 1.9 | 7.6 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 6 |  | 1 |  |  |  | 1 | 6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 10 | 0.3 | 2.6 | 0.3 | -1.43 |  | 1.77 | 17.7 | 0 | 0 | 0 | 0 | 0
0
| Lobby S22 (3190x4790) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 3 | 0.1 | 1.98 |  |  |  | 2.08 | 6.24 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 1 | 1 | 25 |  | 3.54 |  |  |  | 3.54 | 88.5 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 8 |  | 5.845 |  |  |  | 5.845 | 46.76 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 1 | 1 | 9 |  | 5.14 |  |  |  | 5.14 | 46.26 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 16 | 0.1 | 0.7 |  |  |  | 0.8 | 12.8 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 10 | 0.3 | 5.445 | 0.3 | -2.9948 |  | 3.0502 | 30.5 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 1.6 |  |  |  | 1.6 | 6.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 4 |  | 0.85 |  |  |  | 0.85 | 3.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 10 |  | 1.2 |  |  |  | 1.2 | 12 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA e | 8 | 200 | 1 | 1 | 11 |  | 0.6 |  |  |  | 0.6 | 6.6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 9 | 0.3 | 1.9 | 0.3 | -1.045 |  | 1.455 | 13.1 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 6.5 |  | 1.6 |  |  |  | 1.6 | 10.4 | 0 | 0 | 0 | 0 | 0
| TOP EXTRA c | 8 | 150 | 1 | 1 | 6.5 |  | 0.85 |  |  |  | 0.85 | 5.53 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 9 | 0.3 | 1.95 | 0.3 | -1.0725 |  | 1.4775 | 13.3 | 0 | 0 | 0 | 0 | 0
0
| Chajja S23 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 4 | 1 | 8 | 0.07 | 1.13 |  |  |  | 1.2 | 38.4 | 0 | 0 | 0 | 0 | 0
| Main bar e | 8 | 200 | 4 | 1 | 6 | 0.2 | 1.48 |  |  |  | 1.68 | 40.32 | 0 | 0 | 0 | 0 | 0
| Dist. Bar e | 8 | 200 | 4 | 1 | 8 | 0.2 | 0.5 |  |  |  | 0.7 | 22.4 | 0 | 0 | 0 | 0 | 0
0
| FLAT NO.- 7 | [10 empty] | 0
| Toilet Beam at Drop (1425x2160) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar | 10 |  | 1 | 1 | 4 |  | 1.835 |  |  |  | 1.835 | 0 | 7.34 | 0 | 0 | 0 | 0
| Main Bar | 8 | 200 | 1 | 1 | 6 |  | 1.07 |  |  |  | 1.07 | 6.42 | 0 | 0 | 0 | 0 | 0
| stirrups | 8 | 200 | 1 | 1 | 8 |  | 0.63 |  |  |  | 0.63 | 5.04 | 0 | 0 | 0 | 0 | 0
| FLAT NO.- 8 | [10 empty] | 0
| Toilet Beam at Drop (1425x2160) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar | 10 |  | 1 | 1 | 4 |  | 1.835 |  |  |  | 1.835 | 0 | 7.34 | 0 | 0 | 0 | 0
| Main Bar | 8 | 200 | 1 | 1 | 6 |  | 1.07 |  |  |  | 1.07 | 6.42 | 0 | 0 | 0 | 0 | 0
| stirrups | 8 | 200 | 1 | 1 | 8 |  | 0.63 |  |  |  | 0.63 | 5.04 | 0 | 0 | 0 | 0 | 0
| Toilet Beam at Drop (2410x1910) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar | 10 |  | 1 | 1 | 4 |  | 2.82 |  |  |  | 2.82 | 0 | 11.28 | 0 | 0 | 0 | 0
| Main Bar | 8 | 200 | 1 | 1 | 11 |  | 1.07 |  |  |  | 1.07 | 11.77 | 0 | 0 | 0 | 0 | 0
| stirrups | 8 | 200 | 1 | 1 | 13 |  | 0.63 |  |  |  | 0.63 | 8.19 | 0 | 0 | 0 | 0 | 0
| FLAT NO.- 9 | [10 empty] | 0
| Toilet Beam at Drop (1510x2370) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar | 10 |  | 1 | 1 | 4 |  | 1.92 |  |  |  | 1.92 | 0 | 7.68 | 0 | 0 | 0 | 0
| Main Bar | 8 | 200 | 1 | 1 | 7 |  | 1.07 |  |  |  | 1.07 | 7.49 | 0 | 0 | 0 | 0 | 0
| stirrups | 8 | 200 | 1 | 1 | 9 |  | 0.63 |  |  |  | 0.63 | 5.67 | 0 | 0 | 0 | 0 | 0
| FLAT NO.- 10,11,12 | [10 empty] | 0
| Toilet Beam at Drop (1420x2275) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar | 10 |  | 3 | 2 | 4 |  | 1.83 |  |  |  | 1.83 | 0 | 43.92 | 0 | 0 | 0 | 0
| Main Bar | 8 | 200 | 3 | 2 | 6 |  | 1.07 |  |  |  | 1.07 | 38.52 | 0 | 0 | 0 | 0 | 0
| stirrups | 8 | 200 | 3 | 2 | 8 |  | 0.63 |  |  |  | 0.63 | 30.24 | 0 | 0 | 0 | 0 | 0
| Toilet Beam at Drop (1440x2275) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar | 10 |  | 3 | 1 | 4 |  | 1.85 |  |  |  | 1.85 | 0 | 22.2 | 0 | 0 | 0 | 0
| Main Bar | 8 | 200 | 3 | 1 | 6 |  | 1.07 |  |  |  | 1.07 | 19.26 | 0 | 0 | 0 | 0 | 0
| stirrups | 8 | 200 | 3 | 1 | 8 |  | 0.63 |  |  |  | 0.63 | 15.12 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIN Stairs case (03) | [10 empty] | 0
230X450 | LB1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 20 |  | 1 | 1 | 2 | 0.2 | 3.2 | 0.2 |  |  | 3.6 | 0 | 0 | 0 | 0 | 7.2 | 0
| TOP | 20 |  | 1 | 1 | 2 | 0.2 | 3.2 | 0.2 |  |  | 3.6 | 0 | 0 | 0 | 0 | 7.2 | 0
| STIRRUPS | 10 | 100 | 1 | 1 | 33 |  | 1.32 |  |  |  | 1.32 | 0 | 43.56 | 0 | 0 | 0 | 0
0
0
| Main Bottom | 12 | 100 | 1 | 2 | 16 | 0.1 | 4.705 |  |  |  | 4.805 | 0 | 0 | 153.76 | 0 | 0 | 0
| Main Bottom | 12 | 100 | 1 | 2 | 16 | 0.1 | 2.325 |  |  |  | 2.425 | 0 | 0 | 77.6 | 0 | 0 | 0
| Main Top | 10 | 150 | 1 | 2 | 11 | 0.2 | 2.3 |  |  |  | 2.5 | 0 | 55 | 0 | 0 | 0 | 0
| Main Top | 10 | 150 | 1 | 2 | 11 |  | 1.625 |  |  |  | 1.625 | 0 | 35.75 | 0 | 0 | 0 | 0
| Main Top | 10 | 200 | 1 | 2 | 9 |  | 2.7 | 0.2 |  |  | 2.9 | 0 | 52.2 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 2 | 43 |  | 1.45 |  |  |  | 1.45 | 124.7 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 2 | 11 |  | 3.36 |  |  |  | 3.36 | 73.92 | 0 | 0 | 0 | 0 | 0
0
| FIRE Stairs case (04) | [10 empty] | 0
230X450 | LB | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 20 |  | 1 | 1 | 2 | 0.1 | 4.12 | 0.3 |  |  | 4.52 | 0 | 0 | 0 | 0 | 9.04 | 0
| TOP | 20 |  | 1 | 1 | 2 | 0.3 | 4.12 | 0.3 |  |  | 4.72 | 0 | 0 | 0 | 0 | 9.44 | 0
| STIRRUPS | 10 | 100 | 1 | 1 | 33 |  | 1.32 |  |  |  | 1.32 | 0 | 43.56 | 0 | 0 | 0 | 0
0
0
| Main Bottom | 12 | 150 | 1 | 1 | 11 | 0.1 | 4.6 | 0.1 |  |  | 4.8 | 0 | 0 | 52.8 | 0 | 0 | 0
| Main Bottom | 10 | 150 | 1 | 1 | 8 | 0.1 | 4.1 |  |  |  | 4.2 | 0 | 33.6 | 0 | 0 | 0 | 0
| Main Top | 12 | 150 | 1 | 2 | 11 | 0.1 | 1.52 | 0.1 |  |  | 1.72 | 0 | 0 | 37.84 | 0 | 0 | 0
| Main Top | 12 | 150 | 1 | 2 | 11 |  | 1.4 | 0.45 |  |  | 1.85 | 0 | 0 | 40.7 | 0 | 0 | 0
| Main Top | 10 | 200 | 1 | 2 | 11 |  | 2.25 | 0.2 |  |  | 2.45 | 0 | 53.9 | 0 | 0 | 0 | 0
| Main Top | 12 | 200 | 1 | 2 | 11 |  | 2.1 | 0.1 |  |  | 2.2 | 0 | 0 | 48.4 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 4 |  | 1.5 |  |  |  | 1.5 | 6 | 0 | 0 | 0 | 0 | 0
| binder | 8 | 200 | 1 | 1 | 13 |  | 1.7 |  |  |  | 1.7 | 22.1 | 0 | 0 | 0 | 0 | 0
| Mid landing 2nd freight | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bottom | 12 | 150 | 1 | 1 | 11 |  | 4.6 |  |  |  | 4.6 | 0 | 0 | 50.6 | 0 | 0 | 0
| Main Bottom | 10 | 200 | 1 | 1 | 8 |  | 2.63 |  |  |  | 2.63 | 0 | 21.04 | 0 | 0 | 0 | 0
| BINDER | 10 | 200 | 1 | 1 | 8 |  | 1.5 |  |  |  | 1.5 | 0 | 12 | 0 | 0 | 0 | 0
| 2ND FREIGHT MAIN TOP | 12 | 200 | 1 | 1 | 11 |  | 1.4 |  |  |  | 1.4 | 0 | 0 | 15.4 | 0 | 0 | 0
0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Chair (in 125mm thk slab) | 10 |  | 1 | 1 | 196 | 0.3 | 0.6 | 0.3 |  |  | 1.2 | 0 | 235.2 | 0 | 0 | 0 | 0
| Chair (in 135mm thk slab) | 10 |  | 1 | 1 | 194 | 0.31 | 0.6 | 0.31 |  |  | 1.22 | 0 | 236.68 | 0 | 0 | 0 | 0
| Chair (in 150mm thk slab) | 10 |  | 1 | 1 | 122 | 0.325 | 0.6 | 0.325 |  |  | 1.25 | 0 | 152.5 | 0 | 0 | 0 | 0
| Chair (in 175mm thk slab) | 10 |  | 1 | 1 | 30 | 0.35 | 0.6 | 0.35 |  |  | 1.3 | 0 | 39 | 0 | 0 | 0 | 0
| Chair (in 200mm thk slab) | 10 |  | 1 | 1 | 172 | 0.375 | 0.6 | 0.375 |  |  | 1.35 | 0 | 232.2 | 0 | 0 | 0 | 0
0
0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | [11 empty] | 15859.2 | 4154.53 | 2138.15 | 0 | 32.88 | 0
| UNIT WT. | [11 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.47 | 3.85 | B
| TOTAL WT. | [11 empty] | 6264.384 | 2563.345 | 1898.6772 | 0 | 81.2136 | 0 | 10807.6198
[18 empty] | A+B | 18492.9626