## TOP SHEET
OMAXE LTD. |  |  |  |  | Tracker NO | Office NO
NAME OF PROJECT : OMAXE ANANDA TOWER-E (Location: Tower-E STILT + 14 FLOORS) |  |  |  | CONTRACT VALUE ; |  | 162074375
NATURE OF WORK : CIVIL STRUCTURE WORK |  |  |  | PROGRESS OF WORK: |  | 8.962%
NAME OF THE CONTRACTOR :- M/s MARCO-ENTERPRISES |  |  |  | VENDOR CODE:
WORK ORDER NO. & DATE : OPRL/ATE/11094106758 (14 FEB, 2025) |  |  |  | DATE OF START: 01.MAY.2025
THIS R/A BILL NO. & DATE : 7TH RA BILL, DATE 19-12-2025 |  |  |  | COMPLETION PERIOD : Upto 31-Aug-2026 (18 Months)
PERIOD OF BILL :- FROM 02-08-2025 TO 15-12-2025 |  |  |  | GST No. : 09BLDPK5228HIZ2
ERP PROJECT CODE : 127018 |  |  |  | PAN NO. : BLDPK5228H
DATE OF BILL REC. AT SITE :- |  | DATE OF BILL RECEIVED AT H.O. :- |  | DATE OF BILL CHECKING AT H.O. :-
S.NO. | PARTICULARS | CLAIMED BY CONTRACTOR | GROSS AMT | PREVIOUS AMT. | THIS BILL AMT | REMARKS
1 | WORK DONE(CIVIL) |  | 14525632.4502 | 12526168.1691 | 1999464.2812
2 | WORK DONE(ELECT/ PLUMBING)
3 | DIFF. OF CEMENT
4 | RATE DIFF OF TILES
| TOTAL (A) |  | 14525632.4502 | 12526168.1691 | 1999464.2812
5 | Add GST 18% On (A) |  | 2614613.841 | 2254710.2704 | 359903.5706
| TOTAL (B) |  | 17140246.2913 | 14780878.4395 | 2359367.8518
ADVANCES
7.1 | Add Mobilization Advance |  | 6000000 | 6000000
7.2 | Recover Mobilization Advance |  | -672174.3852 | -386433 | -285741.3852
| TOTAL (C) |  | 22468071.9061 | 20394445.4395 | 2073626.4665
DEDUCTIONS
8 | SECURITY @ 5 % (ON TOTAL A) |  | 726282 | 626308 | 99973
9 | TDS @ 1% (ON TOTAL A) |  | 198535 | 185262 | 13273
| Hold for RMC Rate Diff. (M-25) |  | 0 | 65000 | -65000
| Hold for RMC Short M-25 |  | 30000 | 0 | 30000
| TOTAL DEDUCTION (C) |  | 924817 | 876570 | 48246
11 | NET PAYABLE AMOUNT (D) |  | 21543254.9061 | 19517875.4395 | 2025380.4665
| NOW PAYABLE |  |  |  | 2025380.4665
PREPARED BY
PRIYANK BARANWAL
MANAGER (BILLING)
9988294677
| ACCOUNT (SITE) |  |  | PREVIOUS RA BILL NO:-
|  | ANUP SINGH |  | PREVIOUS RA GROSS AMOUNT:-
DY. MANAGER
9315403180
PROJECT INCHARGE {CPC/PC/ASST V.P./SR GM /GM}
S K PANDEY
G.M. - PROJECT
9711800470
HO BILL MONITORING
|  | UPENDER SINGH |  | GAURAV MAHESHWARI
|  | CHIEF MANAGER |  | G.M.-HO BILLING

## ABSTRACT
OMAXE PANCHAM REALCON PVT. LTD.
| WORK ORDER NO. & DATE : OPRL/ATE/11094106758 (14 FEB, 2025) | [7 empty] | ERP PROJECT CODE : 127018
| THIS R/A BILL NO. & DATE : 7TH RA BILL, DATE 19-12-2025 | [7 empty] | DATE OF BILL REC. AT SITE :-
| NATURE OF WORK : CIVIL STRUCTURE WORK | [7 empty] | PERIOD OF BILL :- FROM 02-08-2025 TO 15-12-2025
ABSTRACT OF COST
S.No. | DESCRIPTION OF ITEM | Unit | AS PER W.O. (R0) |  |  |  | Qty |  |  | Amount |  |  | Executed %
|  |  | Qty | Rate | Amount | Part Rate | Prev. Bill | This Bill | UpTo Date | Prev. Bill | This Bill | UpTo Date
1 | EARTH WORK
1.1. | Earth work in excavation in foundation trenches, column pits, plinth beam, under grade/ raft slab etc. by mechanical and/or manual means up to a depth of 1.5 mtr in soil from existing excavated soil level, stacking/spreading the excavated material within site premises (within a stretch of 1500 M) as per direction of Project Manager including dressing of bottom, sides strutting, timbering, shoring, trimming of sides, all leads and lifts, bailing or pumping out the water from the excavated areas collected from any source including subsoil water and keeping the excavated surface dry for subsequent works incidentals, etc. complete with ramming of bottom, surface preparation as per specifications to receive the PCC. | CUM | 1000 | 120 | 120000 |  |  | 0 |  |  | 0 | 0 | 0%
| Excavation shall be payable only for vertical cut up to the outer edge of foundation lean concrete as indicated in drawings for all depths. Cost of extra excavation required for working space, supporting side shuttering of foundations and retaining walls, planking, dewatering, strutting etc. and that required for making slopes for stability of excavation shall be deemed to be included in the rate quoted. This item is not for Mass Excavation. | [9 empty] | 0 | 0
1.2. | Prepare the surface for PCC by manual excavation upto 30 cm depth including dressing the surface, ramming the bottom, disposal and spreading of the surplus earth at the specified location within premises including proper levelling, watering and consolidation complete as directed by E I C. (The item shall be measured as per plan area of PCC, Working space shall not be taken into measurement, deemed to be included into rates) (This item is only applicable if excavation item is not being executed by contractor and excavation already done by client for the location) | SQM | 1500 | 65 | 97500 | 65 | 1500 | 381.385 | 1881.385 | 97499.7818 | 24790.24 | 122290.0218 | 125.4%
1.3. | Filling available excavated earth in trenches, plinth, sides of foundations etc. in layers not exceeding 20cm in depth: consolidating each deposited layer by ramming and watering, lead within the premises and upto any depth. (Compacted Volume shall be payable as per drawing) - Actual volume shall be paid incase excavation is done by Client. | CUM | 2400 | 100 | 240000 | 100 | 0 | 3986.87 | 3986.87 | 0 | 398687 | 398687 | 166.1%
| Total of Earthwork |  |  |  | 457500
2 | CONCRETE WORK
Rates for all cement concrete items plain and reinforced described below shall include work from Basement Level to top of last roof including roof of machine room, mumty, over head water tanks and parapets above at all floors and for all heights. The contractor should provide full time sufficient pipes with accessories and pumps based on the site requirement for pumping and laying of concrete as directed by the EIC. The rate inclusive of standard rigid pipe line and its supports, lifting, laying charges, etc., at all heights and levels. No additional payment shall be payable to the contractor on account of using or change in any size of coarse aggregate in PCC/ RCC work at any stage during currency of works. (This section covers cast in situ structural and architectural as well.)
2.1 | Plain Cement Concrete: Providing and laying plain cement concrete of specified grade as bed concrete under foundation, bases for rafts, underground water tank, building machine equipments, column footing, under floor landings, below road and pathways, cill, coping, screeding at roof to required slope and other locations as called for laid, consolidated and cured etc. complete including finishing the top surface to receive the next course / layer as per specification and drawing. (Shuttering shall be paid in Item No.3.1.1) M10 Grade (Basic Rate of PCC - Rs. 4200/cum) without pump | CUM | 100 | 5550 | 555000 | 5550 | 78.93 | -0.003345 | 78.9267 | 438037.52 | -0.00475 | 438037.5153 | 78.93%
2.2. | Providing and laying cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) for ledge wall below balcony railings, band, mullion, lintel etc. (Shuttering shall be paid separately in respective item) as per drawing and as directed by the Project Manager. | CUM | 50 | 5750 | 287500 |  |  | 0 | 0 |  | 0 | 0 | 0%
2.3. | Providing and laying damp proof course 40mm thick including shttering with cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) including mixing of water proofing compound @ 2% of cement content and applying two layers of bitumen @ 1.70 Kg/Sqm of grade 85/25 and as directed by the Project Manager. | SQM | 200 | 480 | 96000 |  |  | 0 | 0 |  | 0 | 0 | 0%
2.4. | RCC WORK
Providing & Laying RMC M-25 Grade as per approved design mix concrete (strictly controlled conditions) with flyash (as per approved design mix) with automatic batching plant machine mixed and machine vibrated RCC with melamine based plasticisers etc., upto any level, including finishing the exposed surface, fixing/ removal of pockets, fixing of sleeves and inserts (sleeves provided by client), curing etc complete, as per drawing (including all size and shape like circular, semi-circular, oval etc.) and as directed for all lead and lift, excluding cost of centering, shuttering and steel reinforcement but including cost of making shear keys and provision of construction / contraction / control joints in various locations. Checking from Client should not be considered as final and any defects arising during or after casting should be borne & bear by contractor at his own cost. This is inclusive of leaving shuttering & centring for pour strip, slab in slope, RCC members in curved, etc., nothing is payable extra on this account. RMC (M-25) Basic Rate - Rs. 5200/cum without pump excluding GST
2.4.1. | Foundation, column footings, raft slab, raft beams, plinth beam, lift pits, sump pits, pedestals / bases of column, column upto plinth, swimming pool, Retaining wall foundations, grade slab etc. | CUM | 2080 | 6600 | 13728000 | 6600 | 1616.4484 | 70.0988 | 1686.5471 | 10668559.1727 | 462651.8952 | 11131211.0679 | 81.08%
2.4.2. | Suspended floors, roofs, balconies, shelves/ counters, stair waist slabs, folded plate stairs and landings, swimming pool slab, lintel and floor beams, landing beams, girders (deep beams), RCC bands, swimming pool beam, cantilever projections, coping, cills, slab of tank etc at all levels.
2.4.2.1. | Stilt Floor level to 7th Floor level | CUM | 2200 | 6550 | 14410000 |  |  | 0 | 0 |  | 0 | 0 | 0%
2.4.2.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | CUM | 2440 | 6750 | 16470000 |  |  | 0 | 0 |  | 0 | 0 | 0%
2.4.2.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | CUM | 70 | 7300 | 511000 |  |  | 0 | 0 |  | 0 | 0 | 0%
2.5. | Columns, Wall, pillars, piers, abutments, posts and struts, offset and projection of columns, water tank walls, lift walls, Retaining Wall, swimming pool, Parapets, planters, vertical projection of pergolas, wall and ramp walls etc. at all levels.
2.5.1. | Stilt Floor level to 7th Floor level | CUM | 860 | 6850 | 5891000 | 6507.5 | 0 | 48.0455 | 48.0455 | 0 | 312656.0912 | 312656.0912 | 5.587%
2.5.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | CUM | 950 | 7050 | 6697500 |  |  | 0 | 0 |  | 0 | 0 | 0%
2.5.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | CUM | 30 | 7650 | 229500 |  |  | 0 | 0 |  | 0 | 0 | 0%
2.5.4. | Finishing vaccum dewatering continuous concrete flooring 100-150 mm thick with specified grade concrete including necessary formwork in required level, vibrating concrete both by poker vibrators / leveling vaccum processing of the concrete and planning the surface by skin powered floater trowels with broom/plain finish including groove cutting & filling etc. complete. (Concrete shall be paid in the respective items above). | SQM | 1625 | 100 | 162500 |  |  |  | 0
| Total of RCC Work |  |  |  | 59038000
3 | CENTRING AND SHUTTERING
Providing and fixing plywood or steel plate shuttering and centring for structural concrete work in locations called for including strutting, propping, bracing, bolting, wedging, casing, striking, removal etc. complete for any size, section, thickness. Props shall consist of well designed steel pipes adequately braced (wooden ballies as props shall not be permitted). The item to include centering and shuttering at all heights and levels. Allow for forming grooves, drip course, chamfers, cut-outs, openings etc. where called for and for dressing with approved shuttering oil to prevent adhesion. Unexposed concrete surfaces subsequently left untreated (in the condition obtained on removal of form work) shall not constitute exposed concrete work and shall be measured under this item only Irregular shapes with sides (like circular, semi-circular, oval etc.) which may not be perpendicular to each other for shapes not conforming to rectangle or square, and circular shuttering shall not be paid separately. Joints of soffits of the slab shall be made clean after concreting and de-shuttering. (quoted rate to include all staging upto 3.50 mtr height). Note:- Contractor shall take necessary precautions such as watertight shuttering. This is inclusive of RCC members, leaving shuttering & centring for pour strip, slab in slope, RCC members in curved (in plan), etc., nothing is payable extra on this account.
3.1.1. | Foundation, column footings, raft slab, raft beams, plinth beam, lift pits, sump pits, pedestals / bases of column, column up to plinth, swimming pool, Retaining wall foundations, grade slab etc. | SQM | 2150 | 360 | 774000 | 360 | 795.5231 | 849.9743 | 1645.4974 | 286388.316 | 305990.73 | 592379.046 | 76.53%
3.1.2. | Suspended floors, roofs, balconies, shelves/ counters, stair waist slabs, folded plate stairs and landings, swimming pool slab, lintel and floor beams, landing beams, girders (deep beams), RCC bands, swimming pool beam, cantilever projections, coping, cills, slab of tank etc at all levels.
3.1.2.1. | Stilt Floor level to 7th Floor level | SQM | 17600 | 465 | 8184000 |  |  | 0 | 0 |  | 0 | 0 | 0%
3.1.2.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | 18800 | 485 | 9118000 |  |  | 0 | 0 |  | 0 | 0 | 0%
3.1.2..3 | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | SQM | 400 | 550 | 220000 |  |  | 0 | 0 |  | 0 | 0 | 0%
[11 empty] | 0 | 0
3.2. | Columns, Wall, pillars, piers, abutments, posts and struts, offset and projection of columns, water tank walls, lift walls, Retaining Wall, swimming pool, Parapets, planters, vertical projection of pergolas, wall and ramp walls etc. at all levels.
3.2.1. | Stilt Floor level to 7th Floor level | SQM | 7825 | 465 | 3638625 |  |  | 246.825 | 246.825 |  | 114773.625 | 114773.625 | 3.154%
3.2.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | 8200 | 485 | 3977000 |  |  | 0 | 0 |  | 0 | 0 | 0%
3.2.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | SQM | 150 | 550 | 82500 |  |  | 0 | 0 |  | 0 | 0 | 0%
3.3. | Extra for additional height in centring, shuttering where ever required with adequate bracing, propping etc. including cost of de-shuttering and decentring at all levels, over and above height of 3.50 mtr (Plan area to be measured and shall be paid proportionately on actual height) – for every 1.0 mtr. height | SQM | 1000 | 115 | 115000 |  |  | 0 | 0 |  | 0 | 0 | 0%
| Total of Shuttering |  |  |  | 26109125
4 | REINFORCEMENT
Receiving, laying and fixing in position steel reinforcement in all reinforced concrete work, including straightening, cutting, removal of loose rust by wire brush and coating with cement slurry, bending, hoisting, laying in position to the shape and profile required at all levels and heights as per drawing and design and/ or as directed, binding with double folded steel wire as approved by EIC etc. complete. (Contractor shall prepare BBS and submit to EIC for approval prior to cutting, bending & laying of steel bars and payments shall be released as per approved BBS complete in all respect as per direction and approval of EIC Rate shall include cost of 18 gauge GI binding wire, cover blocks as per Indian Standards, unloading the steel & moving to the steel yard, moving site to site within project etc) (Only Steel reinforcement shall be provided by the owner free of cost at one point)
4.1. | Thermomechanically Treated Reinforcement (TMT) or High yield strength Deformed (Tor steel) bars of all size & grades.
4.1.1. | Up to Stilt Floor Level | MT | 150 | 8500 | 1275000 | 8500 | 122.1453 | 10.0233 | 132.1686 | 986323.0234 | 137110.0625 | 1123433.0859 | 88.11%
4.1.2. | Stilt Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet) | MT | 805 | 9400 | 7567000 | 9400 | 0 | 25.8303 | 25.8303 | 0 | 242804.6372 | 242804.6372 | 3.209%
4.1.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | MT | 10 | 11000 | 110000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Total of Reinforcement |  |  |  | 8952000
5 | MASONARY WORK
(Quoted Rates are for all heights, all depths, all levels, including basement to roof (mumty) & all leads and lifts, including curved or circular including elevation masonary work) (Basic Rate of Brick @ Rs. 7/No. FOR at site without GST)
5.1. | Brick work in Sub Structure (Up to Stilt Floor level):
| Providing and laying 230mm thick brick masonry using 1st quality burnt clay FPS bricks in Sub-Structure laid in cement mortar 1:6 (1 cement : 6 coarse sand) mix, joints finished, flush/ raked to 6mm depth including scaffolding, curing complete as per specification and drawing or as directed by Project Manager. | CUM | 100 | 6000 | 600000 |  |  | 0 | 0 |  | 0 | 0 | 0%
5.2. | Brick work in Sub Structure (Up to Stilt Floor level):
| Providing and laying of 115 mm thick brick work with 1st quality burnt clay FPS bricks in sub-superstructure laid in cement mortar 1:4 (1 cement : 4 coarse sand) mix, joints finished, including placing hoop iron as per specification at every third course, scaffolding, curing complete in all respect as per direction of EIC. (Hoop iron shall be provided by client free of cost) (Items of RCC bands like shuttering, concrete and reinforcement to be paid in respective items). | SQM | 1000 | 800 | 800000 | 560 | 88.1435 | 0 | 88.1435 | 49360.36 | 0 | 49360.36 | 8.814%
5.3. | Brick work in Super Structure (Above Stilt FLoor level)
5.3.1 | Providing and laying 230mm thick brick masonry using 1st quality burnt clay FPS bricks in Super-Structure laid in cement mortar 1:6 (1 cement : 6 coarse sand) mix, joints finished, flush/ raked to 6mm depth including scaffolding, curing complete as per specification and drawing or as directed by Project Manager. | [9 empty] | 0 | 0
(a) | Stilt Floor level to 7th Floor level | CUM | 1185 | 6300 | 7465500 |  |  | 0 | 0 |  | 0 | 0 | 0%
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | CUM | 1355 | 6500 | 8807500 |  |  | 0 | 0 |  | 0 | 0 | 0%
5.4. | Brick work in Super Structure (Above Stilt FLoor level)
5.4.1 | Providing and laying of 115 mm thick brick work with 1st quality burnt clay FPS bricks in Super-Superstructure laid in cement mortar 1:4 (1 cement : 4 coarse sand) mix, joints finished, including placing hoop iron as per specification at every third course, scaffolding, curing complete in all respect as per direction of EIC. (Hoop iron shall be provided by client free of cost) (Items of RCC bands like shuttering, concrete and reinforcement to be paid in respective items).
(a) | Stilt Floor level to 7th Floor level | SQM | 7100 | 875 | 6212500 |  |  | 0 | 0 |  | 0 | 0 | 0%
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | 8155 | 915 | 7461825 |  |  | 0 | 0 |  | 0 | 0 | 0%
5.8. | Brick work in staircase steps:
| Providing and laying and constructing brickwork in staircase steps using 1st quality burnt clay FPS bricks in cement mortar 1:3 (1 cement : 3 coarse sand) at all heights and levels including cutting, chamfering scaffolding, curing, complete as per specification. | CUM | 40 | 7000 | 280000 |  |  | 0 | 0 |  | 0 | 0 | 0%
| Total of Masonary Work |  |  |  | 31627325
6 | FINISHING WORKS (PLASTER)
(Quoted Rate shall be for all heights, depths, levels, leads and lifts and to include providing and fixing chicken wire mesh in junction RCC and brick / AAC Block walls and at all chased for electrical conduits & plumbing pipes etc. for internal and external plaster works including minor chipping of RCC, brickwork surface).
6.1. | Internal Plaster Super-Structure:
Wall Plaster: Providing and applying 12 to 15mm thick plaster to masonry and RCC walls, columns etc. in cement mortar 1:5 (1 cement : 5 screened coarse sand) finished smooth including hacking the surfaces, steel scaffolding, curing, making grooves at desired location etc. complete for all levels as per approved drawing.
(a) | Stilt Floor level to 7th Floor level | SQM | 19970 | 265 | 5292050 |  |  | 0 |  |  | 0 | 0 | 0%
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | 22825 | 280 | 6391000 |  |  | 0 |  |  | 0 | 0 | 0%
6.2. | Internal Plaster Super-Structure:
Ceiling Plaster: Providing and applying 6-10mm thick plaster to RCC slab, beam in cement mortar 1:4 (1 cement : 4 screened coarse sand) finished smooth including hacking the surfaces, steel scaffolding, curing, making grooves at desired location etc. complete for all levels as per approved drawing.
(a) | Stilt Floor level to 7th Floor level | SQM | 9135 | 255 | 2329425 |  |  | 0 |  |  | 0 | 0 | 0%
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | 10440 | 270 | 2818800 |  |  | 0 |  |  | 0 | 0 | 0%
6.3 | Double Layer External Plaster: Providing and applying 20 mm thick external cement plaster in two coats under layer 12 mm thick cement plaster 1:5 (1 cement : 5 screened coarse sand) finished with a top layer 8mm thick cement plaster 1:4 (1 cement : 4 screened coarse sand) including making of grooves, bands, drip coarse, design etc. as shown in drawing, steel scaffolding, curing, providing & mixing water proofing compound (CICO) in both layers as per manufacturer specification etc. complete as per approved drawing. | SQM | 19200 | 480 | 9216000 |  |  | 0 |  |  |  |  | 0%
6.4 | Single Layer (Shaft Plaster): Providing and applying 12-15 mm thick external cement plaster in single coat finished with cement plaster 1:4 (1 cement : 4 screened coarse sand) including making of grooves, bands, drip coarse as shown in drawing, steel scaffolding, curing, providing & mixing water proofing compound (CICO) as per manufacturer specification etc. complete as per approved drawing. | SQM | 1000 | 380 | 380000 |  |  | 0 |  |  | 0 | 0 | 0%
| Total of Finishing Work (Plaster) |  |  |  | 26427275
7 | STRUCTURE STEEL
7.1. | Structural steel work with solid/hollow sections: Providing and fixing M.S. work in built-up section such as staircase railing, balcony railing, grating, MS drain cover, MS mumty door including hold fast/fastener etc. with square/round MS Pipes, MS flats, MS Hollow section etc., as per design electrically welded and fixing in RCC/brick masonry or/and treads of steps with cement concrete 1:2:4 (1 cement : 2 corse sand : 4 grades stone aggregate 20 mm nominal sie), complete in all respect as per drawing & direction of EIC, including a coat of red oxide steel primer. (Basic Rate of Str. Steel - Rs. 60/- Per Kg. F.O.R excluding GST) | KG | 39665 | 110 | 4363150 |  |  | 0 |  |  | 0 | 0 | 0%
| Total of Strutural Steel Work |  |  |  | 4363150
8 | WOOD WORK
1 | Providing and Fixing seasoned Red Meranti door frame including painting the portion in contact with masonary / R.C.C. with 2 or more coats of Antitermite treatment paint and fixng the frames with suitable 3 Nos. M.S. holdfasts each side made out of 40 x 5 mm flat iron 230 mm long with bolts and nuts/ dash fasteners for RCC surfaces, duly embedded in C.C. Blocks of required size in (1:2:4 ) 1 cement : 2 coarse sand : 4 stone aggregate 20 mm nominal size) including tarring the hold fast etc.all complete as per direction of EIC. (Finished size to be confirmed by client before procurement) (Sample of wood shall be get approved by client before procurement) | CUM | 50 | 79000 | 3950000 |  |  | 0 |  |  | 0 | 0 | 0%
| Total of Wood Work |  |  |  | 3950000
9 | WATERPROOFING
TERRACE WATERPROOFING:
1 | Providing and laying 120 mm average thickness of brick bat Coba and 65 mm at Khurra on Terrace through an approved agency, approved by the Architect as per steps given. (a) Surface Preparation, Cleaning the mother slab, reapir of joints, Providing and applying URP with cement slurry as primer to fill all the pores etc on mother slab over primer Providing and applying two coats of Fast Flex @ 2kg/Sqm including sandwiching the layer with fiber mesh of 45 GSM between two layers. (It shall also be execute up to 300 mm height of wall) (b) laying cement concrete using broken bricks/ brick bats of size 25 mm to 100 mm size with 50 % of cement mortar 1:5 ( 1 cement : 5 coarse sand) admixed with proprietary water proofing compound conforming to IS:2645 over 20 mm thick layer of cement mortar of mix 1:5 ( 1 cement : 5 coarse sand) admixed with admixed with proprietary water proofing compound conforming to IS:2645 to required slope and treating similarly the adjoining wall upto 300 mm height including rounding of junctions of wall and slabs. (c) After two days of proper curing applying a second coat of cement slurry admixed with proprietary water proofing compound conforming to IS:2645 (d) Finishing the surface with 20 mm thick jointless cement mortar of mix 1:4 (1 cement : 4 coarse sand) admixed with proprietary water proofing compound conforming to IS:2645 and finally finishing the surface with trowel with neat cement slurry and making 300X300 mm square. (e) The whole terrace so finished sshall be looded with water for a minimum period of two weeks for curing and for final test. All above operations to be done in order and as directed and specified by the engineer in charge. With average thickness of 100 mm thickness and minimum thickness at khurra as 65 mm. | SQM | 1000 | 1150 | 1150000 |  |  | 0 |  |  | 0 | 0 | 0%
Providing gola in 1: 2: 4 cement concrete with 12 mm nominal size stone ballast, finished with cement plaster 1:2 (1 cement: 2 medium sand) laid, cured complete as per design. (Approx. Size 100mm x 100mm) Making khurras 450 x 450 mm with average min. thk. Of 50 mm over PVCsheet of 1m x 1m x 400 micron with cement concrete 1:2:4 (1 cement: 2 coarse sand: 4 graded stone aggregate of 12 mm nominal size) finished with 12 mm cement plaster 1:3 (1 cement: 3 coarse sand) and a coat of neat cement, rounding the edges, making and finishing complete. (Only plan area shall be paid).
| Total of Waterproofing Work |  |  |  | 1150000
| Grand Total (Excluding GST) |  |  |  | 162074375 |  | 4201.1902 | 5619.0487 | 9820.239 | 12526168.1738 | 1999464.2764 | 14525632.4502
12640000
27165632.4502
2.7166

## BASIC RATE
S.NO. | RMC PLANT NAME | UNIT | GRADE OF CONCRTE |  |  |  |  | TOTAL
|  |  | M10 | M25 | M30 | M35 | M40
| SHUBHAM RMC | CUM | 79.47 | 912.6 |  | 14 | 52.54 |  | 1058.61
|  | APP.RATE | 4400 | 5100 | 5300 | 5200 | 5300
|  | BASIC RATE | 4200 | 5200 | 5200 | 5200 | 5200
|  | DIFF.AMOUNT | 15894 | -91260 | 0 | 0 | 5254 | -70112
| SRIJAN | CUM | 0 | 147 | 0 | 38 |  |  | 185
|  | APP. RATE | 4600 | 5300 | 5550 | 5200
|  | BASIC RATE | 4200 | 5200 | 5200 | 5200
|  | DIFF. AMOUNT | 0 | 14700 | 0 | 0 | 0 | 14700
| ULTRATECH | CUM | 0 | 576 | 0 | 30 |  |  | 606
|  | APP. RATE | 4600 | 5300 | 5550 | 5200
|  | BASIC RATE | 4200 | 5200 | 5200 | 5200
|  | DIFF. AMOUNT | 0 | 57600 | 0 | 0 | 0 | 57600
[8 empty] | 2188 | 1849.61
|  |  | 79.47 | 1635.6 | 0 | 82 | 52.54

## EARTH WORK MB
COMPANY- OMAXE PANCHAM REALCON PVT LTD
PROJECT- TOWER-E
LOCATION- NAINI, PRAYAGRAJ
MB SHEET- SOIL SURFACE DRESSING BELOW PLINTH BEAM
& SOIL BACK FILLING WORK
S.NO. | DESCRIPTION | UNIT | NOS | NOS | MEASUREMENT |  |  | QTY. | REMARKS
[5 empty] | L | B | H/T
SOIL DRESSING FOR RAFT PCC
1 | GRID (22'-43'/A-Q') | SQM | 1 | 1 | 32.365 | 37.325 |  | 1208.0236 | 3RD RA
2 |  | SQM | 1 | 1 | 9.21 | 0.515 |  | 4.7431
3 | GRID (22'-26'/M'-Q') | SQM | -1 | 1 | 11.005 | 12.415 |  | -136.6271
4 | GRID (38'-43'/A-E') | SQM | -1 | 1 | 11.09 | 10.285 |  | -114.0606
5 | GRID (22'-30'/A-B') | SQM | -1 | 1 | 11.285 | 3.72 |  | -41.9802
6 |  | SQM | -1 | 1 | 1.695 | 2.315 |  | -3.9239
7 |  | SQM | -1 | 1 | 3.95 | 1.5 |  | -5.925
8 |  | SQM | -1 | 1 | 15.8 | 0.215 |  | -3.397
1 | GRID (1-22'/A-Q') | SQM | 1 | 1 | 32.365 | 41.495 |  | 1342.9857 | 4TH RA
2 |  | SQM | 1 | 1 | 9.21 | 0.515 |  | 4.7431
3 | GRID (17'-22'/M'-Q') | SQM | -1 | 1 | 15.175 | 12.415 |  | -188.3976
4 | GRID (1-5'/A-E') | SQM | -1 | 1 | 11.09 | 10.285 |  | -114.0606
5 | GRID (14'-22'/A-B') | SQM | -1 | 1 | 15.455 | 3.72 |  | -57.4926
6 |  | SQM | -1 | 1 | 1.695 | 2.315 |  | -3.9239
7 |  | SQM | -1 | 1 | 3.95 | 1.5 |  | -5.925
8 |  | SQM | -1 | 1 | 15.8 | 0.215 |  | -3.397
FLAT AREA SOIL DRESSING WORK GRID (22-43/A-Q)
7TH RA
| 1 | SQM | 1 | 1 | 5.15 | 3.15
| 2,3 | SQM | 1 | 2 | 3.17 | 2.41
| 2' | SQM | 1 | 1 | 3.55 | 3.17
| 4,10 | SQM | 1 | 1 | 5.49 | 3.25
| 5,9 | SQM | 1 | 1 | 2.925 | 1.7
| 6 | SQM | 1 | 1 | 3.385 | 1.425
| 7 | SQM | 1 | 1 | 1.455 | 1.425
| 8 | SQM | 1 | 1 | 1.7 | 1.425
| 11 | SQM | 1 | 1 | 3.33 | 1.83
|  | SQM | 1 | 1 | 4.27 | 1.93
|  | SQM | 1 | 1 | 7.665 | 3.14
| 12 | SQM | 1 | 1 | 4.27 | 1.7
| 13 | SQM | 1 | 1 | 1.6 | 1.44
| 14 | SQM | 1 | 1 | 1.69 | 1.6
| 15,16 | SQM | 1 | 2 | 3.56 | 3.275
| 17 | SQM | 1 | 1 | 2.25 | 1.525
| 18 | SQM | 1 | 1 | 6.165 | 3.72
|  | SQM | 1 | 1 | 3.915 | 0.385
| 19 | SQM | 1 | 1 | 3.55 | 3.2
| 20 | SQM | 1 | 1 | 5.35 | 3.575
| 21 | SQM | 1 | 1 | 2.815 | 1.8
|  | SQM | 1 | 1 | 4.945 | 2.1
|  | SQM | 1 | 1 | 3.115 | 0.95
| 22 | SQM | 1 | 1 | 5.935 | 2.345
|  | SQM | -1 | 1 | 1.3 | 0.5
|  | SQM | 1 | 1 | 2.03 | 1.5
| 23 | SQM | 1 | 1 | 5.7 | 3.2
| 24 | SQM | 1 | 1 | 3.95 | 1.61
|  | SQM | 1 | 1 | 1.92 | 1.5
| 25 | SQM | 1 | 1 | 2.225 | 1.495
| 26 | SQM | 1 | 1 | 3.95 | 3.845
| 27 | SQM | 1 | 1 | 5.72 | 2.44
|  | SQM | 1 | 1 | 1.2 | 0.35
| 28 | SQM | 1 | 1 | 3.23 | 3.075
|  | SQM | 1 | 1 | 5.14 | 3.17
| 29 | SQM | 1 | 1 | 3.86 | 3.335
| 30 | SQM | 1 | 1 | 4.92 | 3.86
| 31 | SQM | 1 | 1 | 3.55 | 3.265
| 32 | SQM | 1 | 1 | 3.52 | 3.08
| 33 | SQM | 1 | 1 | 3.435 | 2.345
| 34 | SQM | 1 | 1 | 3.435 | 2.245
| 35 | SQM | 1 | 1 | 4.79 | 3.19
|  | SQM | 1 | 1 | 1.4 | 0.655
| 36 | SQM | 1 | 1 | 3.475 | 2.23
| 37,42 | SQM | 1 | 2 | 3.55 | 3.265
| 38,41 | SQM | 1 | 2 | 3.55 | 3.08
| 39,40 | SQM | 1 | 2 | 5.15 | 3.27
|  | SQM | 1 | 2 | 3.24 | 3.075
| 43.46 | SQM | 1 | 2 | 4.92 | 3.86
| 44,45 | SQM | 1 | 2 | 3.86 | 3.335
[7 empty] | TOTAL | 1881.385
SOIL BACK FILLING GRID (1-43/A-Q)
| BACK FILLING | SQM | 1 | 1 | 2463.03 |  | 2.65 | 6527.0295 |  | Upto Road LVL. (HT From JK Bill)
| DED. PCC | SQM | -1 | 1 | 1851.82 |  | 0.1 | -185.182
| DED. RAFT RCC | SQM | -1 | 1 |  |  | 1552.4224 | -1552.4224
| DED. PADESTIAL RCC | SQM | -1 | 1 |  |  | 64.0259 | -64.0259
[7 empty] | TOTAL | 4725.3991

## CONCRETE SUMMARY
TOWER-E CONCRETE WORK SUMMARY
|  |  | QTY | [6 empty] | TOTAL
2 | CONCRETE WORK |  | 3rd RA | 4th RA | 5th RA | 6th RA | 7th RA | 8th RA | 9th RA
Rates for all cement concrete items plain and reinforced described below shall include work from Basement Level to top of last roof including roof of machine room, mumty, over head water tanks and parapets above at all floors and for all heights. The contractor should provide full time sufficient pipes with accessories and pumps based on the site requirement for pumping and laying of concrete as directed by the EIC. The rate inclusive of standard rigid pipe line and its supports, lifting, laying charges, etc., at all heights and levels. No additional payment shall be payable to the contractor on account of using or change in any size of coarse aggregate in PCC/ RCC work at any stage during currency of works. (This section covers cast in situ structural and architectural as well.)
2.1 | Plain Cement Concrete: Providing and laying plain cement concrete of specified grade as bed concrete under foundation, bases for rafts, underground water tank, building machine equipments, column footing, under floor landings, below road and pathways, cill, coping, screeding at roof to required slope and other locations as called for laid, consolidated and cured etc. complete including finishing the top surface to receive the next course / layer as per specification and drawing. (Shuttering shall be paid in Item No.3.1.1) M10 Grade (Basic Rate of PCC - Rs. 4200/cum) without pump | CUM | 56.7982 | 22.6685 | [5 empty] | 79.4667
2.2. | Providing and laying cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) for ledge wall below balcony railings, band, mullion, lintel etc. (Shuttering shall be paid separately in respective item) as per drawing and as directed by the Project Manager. | CUM | [7 empty] | 0
2.3. | Providing and laying damp proof course 40mm thick including shttering with cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) including mixing of water proofing compound @ 2% of cement content and applying two layers of bitumen @ 1.70 Kg/Sqm of grade 85/25 and as directed by the Project Manager. | SQM | [7 empty] | 0
2.4. | RCC WORK
Providing & Laying RMC M-25 Grade as per approved design mix concrete (strictly controlled conditions) with flyash (as per approved design mix) with automatic batching plant machine mixed and machine vibrated RCC with melamine based plasticisers etc., upto any level, including finishing the exposed surface, fixing/ removal of pockets, fixing of sleeves and inserts (sleeves provided by client), curing etc complete, as per drawing (including all size and shape like circular, semi-circular, oval etc.) and as directed for all lead and lift, excluding cost of centering, shuttering and steel reinforcement but including cost of making shear keys and provision of construction / contraction / control joints in various locations. Checking from Client should not be considered as final and any defects arising during or after casting should be borne & bear by contractor at his own cost. This is inclusive of leaving shuttering & centring for pour strip, slab in slope, RCC members in curved, etc., nothing is payable extra on this account. RMC (M-25) Basic Rate - Rs. 5200/cum without pump excluding GST
2.4.1. | Foundation, column footings, raft slab, raft beams, plinth beam, lift pits, sump pits, pedestals / bases of column, column upto plinth, swimming pool, Retaining wall foundations, grade slab etc. | CUM | 748.2097 | 792.1258 | 76.1129 |  | 70.0988 |  |  | 1686.5471
2.4.2. | Suspended floors, roofs, balconies, shelves/ counters, stair waist slabs, folded plate stairs and landings, swimming pool slab, lintel and floor beams, landing beams, girders (deep beams), RCC bands, swimming pool beam, cantilever projections, coping, cills, slab of tank etc at all levels.
2.4.2.1. | Stilt Floor level to 7th Floor level | CUM | [7 empty] | 0
2.4.2.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | CUM | [7 empty] | 0
2.4.2.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | CUM | [7 empty] | 0
2.5. | Columns, Wall, pillars, piers, abutments, posts and struts, offset and projection of columns, water tank walls, lift walls, Retaining Wall, swimming pool, Parapets, planters, vertical projection of pergolas, wall and ramp walls etc. at all levels.
2.5.1. | Stilt Floor level to 7th Floor level | CUM |  |  |  |  | 48.0455 |  |  | 48.0455
2.5.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | CUM | [7 empty] | 0
2.5.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | CUM | [7 empty] | 0
2.5.4. | Finishing vaccum dewatering continuous concrete flooring 100-150 mm thick with specified grade concrete including necessary formwork in required level, vibrating concrete both by poker vibrators / leveling vaccum processing of the concrete and planning the surface by skin powered floater trowels with broom/plain finish including groove cutting & filling etc. complete. (Concrete shall be paid in the respective items above). | SQM | [7 empty] | 0
[9 empty] | TOTAL | 1814.0593

## CONCRETE RECO.
RCC SUMMARY : OMAXE TOWER-E
M/s. MARCO ENTERPRISES
S.No. | Item Discription | Grade | Floor Name | NO | Unit Qty. | Quantity | Unit | M10 | M25 | M30 | M35 | M40
TOWER-E
1 | RAFT PCC GRID (A-Q/23-43) | M10 | AS SUB-STRUCTURE | 1 | 56.7982 | 56.7982 | Cum | 56.7982 | - | - | - | -
2 | RAFT RCC GRID (A-Q/23-43) | M25 | AS SUB-STRUCTURE | 1 | 748.2097 | 748.2097 | Cum | - | 748.2097 | - | - | -
3 | RAFT PCC GRID (A-Q/1-23) | M10 | AS SUB-STRUCTURE | 1 | 22.6685 | 22.6685 | Cum | 22.6685 | - | - | - | -
4 | RAFT RCC GRID (A-Q/1-43) | M25 | AS SUB-STRUCTURE | 1 | 792.1258 | 792.1258 | Cum | - | 792.1258 | - | - | -
5 | COMPENSATORY STRIP (22-23/B'-L') | M25 | AS SUB-STRUCTURE | 1 | 12.087 | 12.087 | Cum | - | 12.087 | - | - | -
6 | PADESTIAL & LIFT (1-43/A-Q) | M35 | AS SUB-STRUCTURE | 1 | 64.0259 | 64.0259 | Cum | - | - | - | 64.0259 | -
7 | PLINTH BEAM (1-43/A-Q) | M25 | AS SUB-STRUCTURE | 1 | 51.6018 | 51.6018 | Cum | - | 51.6018 | - | - | -
8 | COLUMN JUNCTION AT PLINTH BEAM LVL (1-43/A-Q) | M35 | AS SUB-STRUCTURE | 1 | 14 | 14 | Cum | - | - | - | 14 | -
9 | COLUMN JUNCTION AT PLINTH BEAM LVL (1-43/A-Q) | M40 | AS SUB-STRUCTURE | 1 | 4.497 | 4.497 | Cum | - | - | - | - | 4.497
10 | COLUMN FROM PLINTH BEAM LVL TO 1ST FLOOR LVL (22-43/A-Q) | M40 | AS SUPER-STRUCTURE | 1 | 48.0455 | 48.0455 | Cum | - | - | - | - | 48.0455
| TOTAL RCC QTY (THEORITICAL) |  |  |  |  | 1814.0593 | Cum | 79.4667 | 1604.0242 | 0 | 78.0259 | 52.5425
| TOTAL RCC QTY (CASTING) |  |  |  |  | 1857.98 | Cum | 83.4 | 1636.58 | 0 | 82 | 56
| DIFFERENCE (WASTAGE) |  |  |  |  | -43.9207 | Cum | -3.9333 | -32.5558 | 0 | -3.9741 | -3.4575
| WASTAGE % |  |  |  |  | -2.421% |  | -4.95% | -2.03% | #DIV/0! | -5.093% | -6.58%
| PREV. BILL RCC QTY (THEORITICAL) |  |  |  |  | 1695.915 | Cum | 79.4667 | 1552.4224 | 0 | 64.0259 | 0
| PREV. BILL RCC QTY (CASTING-ACTUAL) |  |  |  |  | 1735.4 | Cum | 83.4 | 1584 | 0 | 68 | 0
| DIFFERENCE (WASTAGE) |  |  |  |  | -39.485 | Cum | -3.9333 | -31.5776 | 0 | -3.9741 | 0
| WASTAGE % |  |  |  |  | -2.328% |  | -4.95% | -2.034% | #DIV/0! | -6.207% | #DIV/0!
| THIS BILL RCC QTY (THEORITICAL) |  |  |  |  | 118.1443 | Cum | 0 | 51.6018 | 0 | 14 | 52.5425
| THIS BILL RCC QTY (CASTING-ACTUAL) |  |  |  |  | 122.58 | Cum | 0 | 52.58 | 0 | 14 | 56
| DIFFERENCE (WASTAGE) |  |  |  |  | -4.4357 | Cum | 0 | -0.97821 | 0 | 0 | -3.4575
| WASTAGE % |  |  |  |  | -3.755% |  | #DIV/0! | -1.896% | #DIV/0! | 0% | -6.58%
29700

## PCC & RCC REC.
S.NO. | MONTH | DATE | RMC |  |  |  |  | ELSA |  |  |  |  | MANUAL |  |  |  |  | WORK IN PROGRSS | TOTAL | REMARK
|  |  | GRADE |  |  |  |  | GRADE |  |  |  |  | GRADE
|  |  | M10 | M25 | M30 | M35 | M40 | M10 | M25 | M30 | M35 | M40 | M10 | M25 | M30 | M35 | M40
1 | 2025-05-01 | 2025-05-14 | [5 empty] | 3.3 | [11 empty] | TOWER-E RAFT PCC
2 |  | 2025-05-20 | [5 empty] | 5.4 | [11 empty] | TOWER-E RAFT PCC
3 |  | 2025-05-09 | 40 | [16 empty] | TOWER-E RAFT PCC
4 |  | 2025-05-12 | 17.5 | [16 empty] | TOWER-E RAFT PCC
5 |  | 2025-05-25 | [5 empty] | 7.2 | [11 empty] | TOWER-E RAFT PCC
6 |  | 2025-05-26 | [5 empty] | 10 | [11 empty] | TOWER-E RAFT PCC
7 |  | 2025-05-29 |  | 70 | [15 empty] | TOWER-E RAFT RCC (23-43)
8 |  | 2025-05-30 |  | 329 | [15 empty] | TOWER-E RAFT RCC (23-43)
9 |  | 2025-05-31 |  | 364 | [15 empty] | TOWER-E RAFT RCC (23-43)
10 | 2025-06-01 | 2025-06-10 |  | 147 | [15 empty] | TOWER-E RAFT RCC (1-23)
11 |  | 2025-06-11 |  | 2 | [15 empty] | TOWER-E RAFT RCC (1-23)
12 |  | 2025-06-12 |  | 154 | [15 empty] | TOWER-E RAFT RCC (1-23)
13 |  | 2025-06-13 |  | 431 | [15 empty] | TOWER-E RAFT RCC (1-23)
14 |  | 2025-06-14 |  | 73 | [15 empty] | TOWER-E RAFT RCC (1-23)
15 |  | 2025-06-22 |  |  |  | 3 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
16 |  | 2025-06-23 |  |  |  | 4 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
17 |  | 2025-06-24 |  |  |  | 5 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
18 |  | 2025-06-25 |  |  |  | 5 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
19 |  | 2025-06-26 |  |  |  | 6 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
20 |  | 2025-06-27 |  |  |  | 4 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
21 |  | 2025-06-29 |  |  |  | 3 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
22 | 2025-07-01 | 2025-07-01 |  |  |  | 8 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
23 |  | 2025-07-02 |  |  |  | 4.5 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
24 |  | 2025-07-04 |  |  |  | 3.5 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
25 |  | 2025-07-05 |  |  |  | 8 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
26 |  | 2025-07-07 |  |  |  | 3 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
27 |  | 2025-07-08 |  |  |  | 4 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
28 |  | 2025-07-08 |  | 14 | [15 empty] | TOWER-E RAFT COMPENSATORY STRIP (22-23/B'-L')
29 |  | 2025-07-09 |  |  |  | 3.5 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
30 |  | 2025-07-10 |  |  |  | 3.5 | [13 empty] | TOWER-E PADESTIAL (1-42/A-Q)
31 | 2025-09-01 | 2025-09-25 |  |  |  | 3 | [13 empty] | COLUMN JUNCTION AT PLINTH BEAM
32 |  | 2025-09-25 |  | 4 | [15 empty] | PLINTH BEAM
33 |  | 2025-09-25 |  | 4.5 | [15 empty] | PLINTH BEAM
34 | 2025-10-01 | 2025-10-01 |  |  |  | 3 | [13 empty] | COLUMN JUNCTION AT PLINTH BEAM
35 |  | 2025-10-01 |  | 4 | [15 empty] | PLINTH BEAM
36 |  | 2025-10-01 |  | 3.5 | [15 empty] | PLINTH BEAM
37 |  | 2025-10-07 |  |  |  | 3 | [13 empty] | COLUMN JUNCTION AT PLINTH BEAM
38 |  | 2025-10-09 |  | 4 | [15 empty] | PLINTH BEAM
39 |  | 2025-10-09 |  |  |  | 2 | [13 empty] | COLUMN JUNCTION AT PLINTH BEAM
40 |  | 2025-10-09 |  | 3 | [15 empty] | PLINTH BEAM
41 |  | 2025-10-10 |  | 2 | [15 empty] | PLINTH BEAM
42 |  | 2025-10-29 |  |  |  | 3 | [13 empty] | COLUMN JUNCTION AT PLINTH BEAM
43 |  | 2025-10-30 |  | 4 | [15 empty] | PLINTH BEAM
|  | 2025-10-30 |  | 3.5
44 | 2025-11-01 | 2025-11-11 |  |  |  |  | 2.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
45 |  | 2025-11-17 |  | 4 | [15 empty] | PLINTH BEAM
|  | 2025-11-17 |  |  |  |  | 3.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
|  | 2025-11-18 |  |  |  |  | 4.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
|  | 2025-11-19 |  | 3 | [15 empty] | PLINTH BEAM
|  | 2025-11-19 |  |  |  |  | 3.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
|  | 2025-11-20 |  |  |  |  | 3.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
|  | 2025-11-24 | [6 empty] | 0.58 | [10 empty] | PLINTH BEAM
|  | 2025-11-28 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
|  | 2025-11-29 |  |  |  |  | 7 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
|  | 2025-11-30 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
| 2025-12-01 | 2025-12-02 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
|  | 2025-12-02 |  |  |  |  | 4.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
|  | 2025-12-03 |  |  |  |  | 6.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
|  | 2025-12-05 |  |  |  |  | 3 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
|  | 2025-12-06 |  |  |  |  | 6 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
|  | 2025-12-08 |  |  |  |  | 2.5 | [12 empty] | COLUMN PLINTH BEAM TO 1ST FLOOR LVL
|  | 2025-12-09 |  | 6.5 | [15 empty] | PLINTH BEAM
|  |  |  | 6 | [15 empty] | PLINTH BEAM
| TOTAL |  | 57.5 | 1636 | 0 | 82 | 56 | 25.9 | 0.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1857.98
| GRAND TOTAL |  | 57.5 | 1636 | 0 | 82 | 56 | 25.9 | 0.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1857.98
| TOTAL RCC BY RMC/ELSA /MANUAL |  | 1831.5 |  |  |  |  | 26.48 |  |  |  |  | 0 |  |  |  |  | 0 | 1857.98
| RCC BY RMC + ELSA |  | 1857.98

## RMC RECEIVING
M/s. MARCO ENTERPRISES : RMC RECEIVING AT OMAXE ANANDA TOWER-E -PRAYAGRAJ
SN | DATE | VEHICLE NO | CHALLAN NO/INVOICE NO. | MATERIAL GRADE | UNIT | RMC PLANT QTY (M 10) | RMC PLANT QTY (M 25) | RMC PLANT QTY (M 30) | RMC PLANT QTY (M 35) | RMC PLANT QTY (M 40) | ACTUAL CEMENT WEIGHT BY DESIGN MIX | CEMENT WEIGHT BY RMC PLANT | CEMENT DIFF (IN KG) | IN TIME | OUT TIME | TOWER NO | TYPE OF WORK | RMC SUPPLIER | REMARKS
1 | 2025-05-09 | UP32VN6145 | 449 | RMC10 | CUM | 7 |  |  |  |  | 1540 | 1540 | 0 | 10:50 | 12:15 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
2 | 2025-05-09 | UP32WN8332 | 450 | RMC10 | CUM | 7 |  |  |  |  | 1540 | 1540 | 0 | 12:30 | 13:40 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
3 | 2025-05-09 | UP53HT5034 | 451 | RMC10 | CUM | 7 |  |  |  |  | 1540 | 1540 | 0 | 13:52 | 14:40 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
4 | 2025-05-09 | UP32VN6145 | 453 | RMC10 | CUM | 7 |  |  |  |  | 1540 | 1540 | 0 | 14:50 | 16:00 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
5 | 2025-05-09 | UP32WN8334 | 454 | RMC10 | CUM | 6 |  |  |  |  | 1320 | 1320 | 0 | 16:30 | 17:45 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
6 | 2025-05-09 | UP53HT5034 | 457 | RMC10 | CUM | 6 |  |  |  |  | 1320 | 1320 | 0 | 18:35 | 19:30 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
7 | 2025-05-12 | UP32WN8334 | 487 | RMC10 | CUM | 5 |  |  |  |  | 1100 | 1096 | -4 | 18:35 | 19:30 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
8 | 2025-05-12 | UP32WN8334 | 488 | RMC10 | CUM | 5 |  |  |  |  | 1100 | 1096 | -4 | 18:35 | 19:30 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
9 | 2025-05-12 | UP32VN6144 | 490 | RMC10 | CUM | 5.5 |  |  |  |  | 1210 | 1210 | 0 | 18:35 | 19:30 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
10 | 2025-05-12 | UP32VN6144 | 494 | RMC10 | CUM | 2 |  |  |  |  | 440 | 440 | 0 | 18:35 | 19:30 | TOWER-E RAFT PCC | RAFT PCC | SHUBHAM
11 | 29.05.2025 | UP32VN6145 | 721 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 22:30 | 23:08 | TOWER-E (23-43) | RAFT | SHUBHAM
12 | 29.05.2025 | UP32WN8334 | 722 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 23:12 | 23:33 | TOWER-E (23-43) | RAFT | SHUBHAM
13 | 29.05.2025 | UP32WN8333 | 723 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 23:39 | 12:02PM | TOWER-E (23-43) | RAFT | SHUBHAM
14 | 29.05.2025 | UP32HT5032 | 724 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2574 | 19 | 12:05 | 0:19 | TOWER-E (23-43) | RAFT | SHUBHAM
15 | 29.05.2025 | UP32HT5034 | 725 | RMC 25 | CUM |  | 5.5 |  |  |  | 2007.5 | 2018 | 10.5 | 0:23 | 0:42 | TOWER-E (23-43) | RAFT | SHUBHAM
| 29.05.2025 | UP32HT5034 | 726 | RMC 25 | CUM |  | 1.5 |  |  |  | 547.5 | 548 | 0.5 | 0:23 | 0:42 | TOWER-E (23-43) | RAFT | SHUBHAM
16 | 29.05.2025 | UP70QT2013 | 905350012 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 22:30 | 23:07 | TOWER-E (23-43) | RAFT | ULTRATECH
17 | 29.05.2025 | UP70QT2341 | 905350013 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 23:13 | 23:41 | TOWER-E (23-43) | RAFT | ULTRATECH
18 | 29.05.2025 | UP70QT2015 | 905350014 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 23:41 | 24:12 | TOWER-E (23-43) | RAFT | ULTRATECH
19 | 29.05.2025 | UP70QT2342 | 905350015 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 1:16 | 1:43 | TOWER-E (23-43) | RAFT | ULTRATECH
20 | 29.05.2025 | UP70QT2014 | 905350016 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 1:49 | 2:05 | TOWER-E (23-43) | RAFT | ULTRATECH
21 | 30.05.2025 | UP32VN6145 | 727 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 1:02 | 1:50 | TOWER-E (23-43) | RAFT | SHUBHAM
22 | 30.05.2025 | UP32WN8334 | 728 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2551 | -4 | 1:52 | 2:15 | TOWER-E (23-43) | RAFT | SHUBHAM
23 | 30.05.2025 | UP32WN8332 | 729 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 2:19 | 2:33 | TOWER-E (23-43) | RAFT | SHUBHAM
24 | 30.05.2025 | UP32WN8333 | 730 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 2:35 | 3:03 | TOWER-E (23-43) | RAFT | SHUBHAM
25 | 30.05.2025 | UP32VN6144 | 731 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 3:03 | 3:23 | TOWER-E (23-43) | RAFT | SHUBHAM
26 | 30.05.2025 | UP53HT5032 | 732 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 3:26 | 3:48 | TOWER-E (23-43) | RAFT | SHUBHAM
27 | 30.05.2025 | UP32VN6145 | 733 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2570 | 15 | 3:53 | 4:06 | TOWER-E (23-43) | RAFT | SHUBHAM
28 | 30.05.2025 | UP32HT5034 | 734 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 4:14 | 4:25 | TOWER-E (23-43) | RAFT | SHUBHAM
29 | 30.05.2025 | UP32WN8334 | 735 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 4:39 | 4:59 | TOWER-E (23-43) | RAFT | SHUBHAM
30 | 30.05.2025 | UP53HT5034 | 736 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 5:05 | 6:32 | TOWER-E (23-43) | RAFT | SHUBHAM
31 | 30.05.2025 | UP32WN8332 | 737 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2559 | 4 | 6:37 | 7:24 | TOWER-E (23-43) | RAFT | SHUBHAM
32 | 30.05.2025 | UP32VN6144 | 738 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 7:27 | 7:49 | TOWER-E (23-43) | RAFT | SHUBHAM
33 | 30.05.2025 | UP53HT5032 | 739 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2559 | 4 | 7:19 | 8:17 | TOWER-E (23-43) | RAFT | SHUBHAM
34 | 30.05.2025 | UP53HT5034 | 740 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2573 | 18 | 8:25 | 9:10 | TOWER-E (23-43) | RAFT | SHUBHAM
35 | 30.05.2025 | UP32WN8334 | 741 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 9:15 | 9:45 | TOWER-E (23-43) | RAFT | SHUBHAM
36 | 30.05.2025 | UP32WN8333 | 742 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2574 | 19 | 9:50 | 10:46 | TOWER-E (23-43) | RAFT | SHUBHAM
37 | 30.05.2025 | UP32VN6145 | 743 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2552 | -3 | 10:45 | 12:05 | TOWER-E (23-43) | RAFT | SHUBHAM
38 | 30.05.2025 | UP32WN8332 | 744 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2569 | 14 | 12:11 | 13:00 | TOWER-E (23-43) | RAFT | SHUBHAM
39 | 30.05.2025 | UP32VN6144 | 745 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 13:00 | 13:38 | TOWER-E (23-43) | RAFT | SHUBHAM
40 | 30.05.2025 | UP53HT5032 | 746 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 13:41 | 14:00 | TOWER-E (23-43) | RAFT | SHUBHAM
41 | 30.05.2025 | UP53HT5034 | 747 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 14:00 | 14:26 | TOWER-E (23-43) | RAFT | SHUBHAM
42 | 30.05.2025 | UP32WN8334 | 748 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 14:30 | 14:57 | TOWER-E (23-43) | RAFT | SHUBHAM
43 | 30.05.2025 | UP32WN8333 | 749 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2559 | 4 | 15:03 | 15:35 | TOWER-E (23-43) | RAFT | SHUBHAM
44 | 30.05.2025 | UP32WN8332 | 751 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 15:38 | 16:00 | TOWER-E (23-43) | RAFT | SHUBHAM
45 | 30.05.2025 | UP32VN6144 | 752 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2568 | 13 | 16:52 | 17:28 | TOWER-E (23-43) | RAFT | SHUBHAM
46 | 30.05.2025 | UP53HT5032 | 753 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 16:30 | 16:45 | TOWER-E (23-43) | RAFT | SHUBHAM
47 | 30.05.2025 | UP53HT5034 | 754 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 17:32 | 17:45 | TOWER-E (23-43) | RAFT | SHUBHAM
48 | 30.05.2025 | UP32WN8334 | 755 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 17:46 | 18:06 | TOWER-E (23-43) | RAFT | SHUBHAM
49 | 30.05.2025 | UP32WN8333 | 756 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2570 | 15 | 18:15 | 18:30 | TOWER-E (23-43) | RAFT | SHUBHAM
50 | 30.05.2025 | UP32WN8332 | 757 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 18:48 | 19:40 | TOWER-E (23-43) | RAFT | SHUBHAM
51 | 30.05.2025 | UP32VN6144 | 758 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 19:50 | 20:07 | TOWER-E (23-43) | RAFT | SHUBHAM
52 | 30.05.2025 | UP53HT5032 | 759 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 20:31 | 21:05 | TOWER-E (23-43) | RAFT | SHUBHAM
53 | 30.05.2025 | UP53HT5034 | 760 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 21:11 | 23:30 | TOWER-E (23-43) | RAFT | SHUBHAM
54 | 30.05.2025 | UP32VN6145 | 761 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 24:07 | 24:24 | TOWER-E (23-43) | RAFT | SHUBHAM
55 | 30.05.2025 | UP32WN8334 | 762 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 24:06 | 24:46 | TOWER-E (23-43) | RAFT | SHUBHAM
56 | 30.05.2025 | UP32WN8333 | 763 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 24:51 | 1:08 | TOWER-E (23-43) | RAFT | SHUBHAM
57 | 30.05.2025 | UP32WN8332 | 764 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 1:10 | 1:40 | TOWER-E (23-43) | RAFT | SHUBHAM
58 | 30.05.2025 | UP32VN6144 | 765 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2552 | -3 | 1:43 | 2:07 | TOWER-E (23-43) | RAFT | SHUBHAM
59 | 30.05.2025 | UP53HT5032 | 766 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 2:10 | 2:48 | TOWER-E (23-43) | RAFT | SHUBHAM
60 | 30.05.2025 | UP70QT2013 | 905350017 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 2:11 | 2:29 | TOWER-E (23-43) | RAFT | ULTRATECH
61 | 30.05.2025 | UP70QT2341 | 905350018 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 2:37 | 2:53 | TOWER-E (23-43) | RAFT | ULTRATECH
62 | 30.05.2025 | UP70QT2015 | 905350019 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 2:58 | 3:14 | TOWER-E (23-43) | RAFT | ULTRATECH
63 | 30.05.2025 | UP70QT2342 | 905350020 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 3:27 | 3:40 | TOWER-E (23-43) | RAFT | ULTRATECH
64 | 30.05.2025 | UP70QT2014 | 905350021 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 3:54 | 4:36 | TOWER-E (23-43) | RAFT | ULTRATECH
65 | 30.05.2025 | UP70QT2013 | 905350022 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2552 | -3 | 4:45 | 5:03 | TOWER-E (23-43) | RAFT | ULTRATECH
66 | 30.05.2025 | UP70QT2341 | 905350023 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 5:10 | 5:31 | TOWER-E (23-43) | RAFT | ULTRATECH
67 | 30.05.2025 | UP70QT2015 | 905350024 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 5:36 | 5:51 | TOWER-E (23-43) | RAFT | ULTRATECH
68 | 31.05.2025 | UP32VN6140 | 767 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 3:09 | 3:33 | TOWER-E (23-43) | RAFT | SHUBHAM
69 | 31.05.2025 | UP53HT5034 | 768 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 3:43 | 4:11 | TOWER-E (23-43) | RAFT | SHUBHAM
70 | 31.05.2025 | UP32VN6144 | 771 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 10:50 | 11:06 | TOWER-E (23-43) | RAFT | SHUBHAM
71 | 31.05.2025 | UP32VN6140 | 772 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 11:17 | 11:39 | TOWER-E (23-43) | RAFT | SHUBHAM
72 | 31.05.2025 | UP32WN8332 | 773 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 11:40 | 12:01 | TOWER-E (23-43) | RAFT | SHUBHAM
73 | 31.05.2025 | UP53HT5034 | 774 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 12:03 | 12:16 | TOWER-E (23-43) | RAFT | SHUBHAM
74 | 31.05.2025 | UP32WN8334 | 775 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 12:28 | 12:39 | TOWER-E (23-43) | RAFT | SHUBHAM
75 | 31.05.2025 | UP32VN6145 | 776 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 13:18 | 13:32 | TOWER-E (23-43) | RAFT | SHUBHAM
76 | 31.05.2025 | UP53HT5034 | 777 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 13:35 | 14:04 | TOWER-E (23-43) | RAFT | SHUBHAM
77 | 31.05.2025 | UP32VN6140 | 778 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 14:09 | 14:39 | TOWER-E (23-43) | RAFT | SHUBHAM
78 | 31.05.2025 | UP32WN8332 | 779 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 14:41 | 15:02 | TOWER-E (23-43) | RAFT | SHUBHAM
79 | 31.05.2025 | UP32VN6144 | 780 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2571 | 16 | 15:11 | 15:36 | TOWER-E (23-43) | RAFT | SHUBHAM
80 | 31.05.2025 | UP53HT5032 | 781 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 15:38 | 16:28 | TOWER-E (23-43) | RAFT | SHUBHAM
81 | 31.05.2025 | UP32WN8334 | 782 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 16:30 | 17:00 | TOWER-E (23-43) | RAFT | SHUBHAM
82 | 31.05.2025 | UP32VN6145 | 783 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 17:18 | 17:32 | TOWER-E (23-43) | RAFT | SHUBHAM
83 | 31.05.2025 | UP53HT5034 | 784 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 17:43 | 17:53 | TOWER-E (23-43) | RAFT | SHUBHAM
84 | 31.05.2025 | UP32WN8333 | 785 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 18:00 | 18:55 | TOWER-E (23-43) | RAFT | SHUBHAM
85 | 31.05.2025 | UP32VN6144 | 786 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 19:05 | 19:15 | TOWER-E (23-43) | RAFT | SHUBHAM
86 | 31.05.2025 | UP32WN8332 | 787 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 19:20 | 19:32 | TOWER-E (23-43) | RAFT | SHUBHAM
87 | 31.05.2025 | UP32VN6144 | 788 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 19:39 | 19:55 | TOWER-E (23-43) | RAFT | SHUBHAM
88 | 31.05.2025 | UP53HT5032 | 789 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 19:56 | 20:16 | TOWER-E (23-43) | RAFT | SHUBHAM
89 | 31.05.2025 | UP32WN8334 | 790 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 20:34 | 20:54 | TOWER-E (23-43) | RAFT | SHUBHAM
90 | 31.05.2025 | UP32VN6145 | 791 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 21:05 | 21:40 | TOWER-E (23-43) | RAFT | SHUBHAM
91 | 31.05.2025 | UP32WN8333 | 792 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 22:00 | 22:30 | TOWER-E (23-43) | RAFT | SHUBHAM
92 | 31.05.2025 | UP32VN6140 | 793 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 22:35 | 23:23 | TOWER-E (23-43) | RAFT | SHUBHAM
93 | 31.05.2025 | UP53HT5034 | 794 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 23:28 | 23:47 | TOWER-E (23-43) | RAFT | SHUBHAM
94 | 31.05.2025 | UP70QT2014 | 905350025 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 1:27 | 2:05 | TOWER-E (23-43) | RAFT | ULTRATECH
95 | 31.05.2025 | UP70QT2341 | 905350026 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 2:10 | 2:36 | TOWER-E (23-43) | RAFT | ULTRATECH
96 | 31.05.2025 | UP70QT2015 | 905350028 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 10:58 | 11:30 | TOWER-E (23-43) | RAFT | ULTRATECH
97 | 31.05.2025 | UP70QT2013 | 905350029 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 12:19 | 13:18 | TOWER-E (23-43) | RAFT | ULTRATECH
98 | 31.05.2025 | UP70QT2342 | 905350030 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 11:50 | 12:08 | TOWER-E (23-43) | RAFT | ULTRATECH
99 | 31.05.2025 | UP70QT2014 | 905350031 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2552 | -3 | 13:28 | 13:58 | TOWER-E (23-43) | RAFT | ULTRATECH
100 | 31.05.2025 | UP70QT2341 | 905350032 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 14:07 | 14:38 | TOWER-E (23-43) | RAFT | ULTRATECH
101 | 31.05.2025 | UP70QT2015 | 905350033 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 14:43 | 15:24 | TOWER-E (23-43) | RAFT | ULTRATECH
102 | 31.05.2025 | UP70QT2342 | 905350034 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 15:31 | 15:48 | TOWER-E (23-43) | RAFT | ULTRATECH
103 | 31.05.2025 | UP70QT2013 | 905350035 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 15:54 | 16:16 | TOWER-E (23-43) | RAFT | ULTRATECH
104 | 31.05.2025 | UP70QT2014 | 905350036 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 16:27 | 16:48 | TOWER-E (23-43) | RAFT | ULTRATECH
105 | 31.05.2025 | UP70QT2341 | 905350037 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 16:54 | 17:33 | TOWER-E (23-43) | RAFT | ULTRATECH
106 | 31.05.2025 | UP70QT2015 | 905350038 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 17:39 | 18:33 | TOWER-E (23-43) | RAFT | ULTRATECH
107 | 31.05.2025 | UP70QT2342 | 905350039 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 18:39 | 19:05 | TOWER-E (23-43) | RAFT | ULTRATECH
108 | 31.05.2025 | UP70QT2013 | 905350041 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 19:10 | 19:31 | TOWER-E (23-43) | RAFT | ULTRATECH
109 | 31.05.2025 | UP70QT2014 | 905350042 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 19:36 | 20:16 | TOWER-E (23-43) | RAFT | ULTRATECH
110 | 31.05.2025 | UP70QT2341 | 905350043 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 20:25 | 21:00 | TOWER-E (23-43) | RAFT | ULTRATECH
111 | 31.05.2025 | UP70QT2015 | 905350044 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 21:08 | 21:40 | TOWER-E (23-43) | RAFT | ULTRATECH
112 | 31.05.2025 | UP70QT2342 | 905350045 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 22:00 | 22:25 | TOWER-E (23-43) | RAFT | ULTRATECH
113 | 31.05.2025 | UP70QT2013 | 905350046 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 22:28 | 23:05 | TOWER-E (23-43) | RAFT | ULTRATECH
114 | 31.05.2025 | UP70QT2014 | 905350047 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 23:50 | 1:12 | TOWER-E (23-43) | RAFT | ULTRATECH
115 | 31.05.2025 | UP70QT2341 | 905350048 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 23:55 | 1:12 | TOWER-E (23-43) | RAFT | ULTRATECH
116 | 31.05.2025 | UP70QT2015 | 905350049 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 1:20 | 1:30 | TOWER-E (23-43) | RAFT | ULTRATECH
117 | 31.05.2025 | UP70QT2342 | 905350050 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 1:35 | 1:45 | TOWER-E (23-43) | RAFT | ULTRATECH
118 | 31.05.2025 | UP70QT2013 | 905350051 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2553 | -2 | 1:55 | 2:15 | TOWER-E (23-43) | RAFT | ULTRATECH
119 | 31.05.2025 | UP70QT2014 | 905350052 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 2:00 | 2:20 | TOWER-E (23-43) | RAFT | ULTRATECH
120 | 10.06.2025 | UP70QT2015 | 905350080 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 14:10 | 14:30 | TOWER-E (1-23) | RAFT | ULTRATECH
121 | 10.06.2025 | UP70QT2342 | 905350081 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 14:38 | 14:48 | TOWER-E (1-23) | RAFT | ULTRATECH
122 | 10.06.2025 | UP70QT2013 | 905350082 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2552 | -3 | 14:52 | 15:04 | TOWER-E (1-23) | RAFT | ULTRATECH
123 | 10.06.2025 | UP70QT2341 | 905350083 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 15:37 | 15:47 | TOWER-E (1-23) | RAFT | ULTRATECH
124 | 10.06.2025 | UP70QT2014 | 905350084 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 15:50 | 16:19 | TOWER-E (1-23) | RAFT | ULTRATECH
125 | 10.06.2025 | UP70QT2015 | 905350085 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 16:35 | 16:47 | TOWER-E (1-23) | RAFT | ULTRATECH
126 | 10.06.2025 | UP70QT2342 | 905350086 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 16:54 | 17:01 | TOWER-E (1-23) | RAFT | ULTRATECH
127 | 10.06.2025 | UP70QT2013 | 905350087 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 17:10 | 17:20 | TOWER-E (1-23) | RAFT | ULTRATECH
128 | 10.06.2025 | UP70QT2341 | 905350094 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 21:44 | 21:56 | TOWER-E (1-23) | RAFT | ULTRATECH
129 | 10.06.2025 | UP70QT2014 | 905350089 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 18:19 | 18:30 | TOWER-E (1-23) | RAFT | ULTRATECH
130 | 10.06.2025 | UP70QT2015 | 905350090 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 18:34 | 18:51 | TOWER-E (1-23) | RAFT | ULTRATECH
131 | 10.06.2025 | UP70QT2013 | 905350091 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 19:14 | 19:25 | TOWER-E (1-23) | RAFT | ULTRATECH
132 | 10.06.2025 | UP70QT2014 | 905350092 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 19:30 | 19:40 | TOWER-E (1-23) | RAFT | ULTRATECH
133 | 10.06.2025 | UP70QT2342 | 905350093 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 21:44 | 21:54 | TOWER-E (1-23) | RAFT | ULTRATECH
134 | 10.06.2025 | UP70QT2015 | 905350095 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 22:30 | 23:10 | TOWER-E (1-23) | RAFT | ULTRATECH
135 | 10.06.2025 | UP70QT2013 | 905350096 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 22:00 | 22:23 | TOWER-E (1-23) | RAFT | ULTRATECH
136 | 10.06.2025 | UP70QT2341 | 905350097 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 23:18 | 23:53 | TOWER-E (1-23) | RAFT | ULTRATECH
137 | 10.06.2025 | UP70QT2014 | 905350098 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 24:12 | 24:32 | TOWER-E (1-23) | RAFT | ULTRATECH
138 | 10.06.2025 | UP70QT2015 | 905350099 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 24:36 | 1:05 | TOWER-E (1-23) | RAFT | ULTRATECH
139 | 10.06.2025 | UP70QT2013 | 905350100 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 1:10 | 1:25 | TOWER-E (1-23) | RAFT | ULTRATECH
140 | 10.06.2025 | UP70QT2342 | 905350101 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 1:33 | 1:48 | TOWER-E (1-23) | RAFT | ULTRATECH
141 | 11.06.2025 | UP70QT2341 | 905350102 | RMC 25 | CUM |  | 2 |  |  |  | 730 | 730 | 0 | 2:10 | 2:14 | TOWER-E (1-23) | RAFT | ULTRATECH
142 | 12.06.2025 | UP70QT2014 | 905350111 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 2:10 | 2:50 | TOWER-E (1-23) | RAFT | ULTRATECH
143 | 12.06.2025 | UP70QT2013 | 905350113 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 2:55 | 4:30 | TOWER-E (1-23) | RAFT | ULTRATECH
144 | 12.06.2025 | UP70QT2014 | 905350115 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 4:35 | 5:27 | TOWER-E (1-23) | RAFT | ULTRATECH
145 | 12.06.2025 | UP32VN6140 | 1033 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2568 | 13 | 12:00 | 12:47 | TOWER-E (1-23) | RAFT | SHUBHAM
146 | 12.06.2025 | UP32WN8332 | 1034 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 12:51 | 13:35 | TOWER-E (1-23) | RAFT | SHUBHAM
147 | 12.06.2025 | UP53HT5034 | 1036 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 13:44 | 14:02 | TOWER-E (1-23) | RAFT | SHUBHAM
148 | 12.06.2025 | UP32WN8333 | 1038 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 14:20 | 14:45 | TOWER-E (1-23) | RAFT | SHUBHAM
149 | 12.06.2025 | UP53HT5032 | 1040 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2570 | 15 | 15:08 | 15:40 | TOWER-E (1-23) | RAFT | SHUBHAM
150 | 12.06.2025 | UP53HT5034 | 1041 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 15:43 | 16:29 | TOWER-E (1-23) | RAFT | SHUBHAM
151 | 12.06.2025 | UP32WN8333 | 1042 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 16:32 | 17:44 | TOWER-E (1-23) | RAFT | SHUBHAM
152 | 12.06.2025 | UP32VN6145 | 1043 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 17:55 | 18:40 | TOWER-E (1-23) | RAFT | SHUBHAM
153 | 12.06.2025 | UP53HT5034 | 1044 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2567 | 12 | 18:43 | 19:04 | TOWER-E (1-23) | RAFT | SHUBHAM
154 | 12.06.2025 | UP32WN8332 | 1045 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 19:16 | 20:12 | TOWER-E (1-23) | RAFT | SHUBHAM
155 | 12.06.2025 | UP53HT5032 | 1046 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 20:38 | 21:24 | TOWER-E (1-23) | RAFT | SHUBHAM
156 | 12.06.2025 | UP32VN6144 | 1047 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2564 | 9 | 21:35 | 21:53 | TOWER-E (1-23) | RAFT | SHUBHAM
157 | 12.06.2025 | UP32VN6145 | 1048 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2559 | 4 | 22:00 | 22:31 | TOWER-E (1-23) | RAFT | SHUBHAM
158 | 12.06.2025 | UP32VN6140 | 1049 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2567 | 12 | 22:32 | 22:48 | TOWER-E (1-23) | RAFT | SHUBHAM
159 | 12.06.2025 | UP53HT5034 | 1050 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 22:53 | 23:41 | TOWER-E (1-23) | RAFT | SHUBHAM
160 | 12.06.2025 | UP32WN8333 | 1051 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 22:14 | 23:41 | TOWER-E (1-23) | RAFT | SHUBHAM
161 | 12.06.2025 | UP32WN8332 | 1052 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2568 | 13 | 23:45 | 24:04 | TOWER-E (1-23) | RAFT | SHUBHAM
162 | 12.06.2025 | UP53HT5032 | 1053 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 24:06 | 24:24 | TOWER-E (1-23) | RAFT | SHUBHAM
163 | 12.06.2025 | UP32VN6144 | 1054 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 24:27 | 24:54 | TOWER-E (1-23) | RAFT | SHUBHAM
164 | 13.06.2025 | UP70NT8335 | 471 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2552 | -3 | 12:43 | 13:00 | TOWER-E (1-23) | RAFT | SRIJAN
165 | 13.06.2025 | NEW 9655 | 472 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 13:04 | 13:15 | TOWER-E (1-23) | RAFT | SRIJAN
166 | 13.06.2025 | NEW 8917 | 473 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 13:19 | 13:32 | TOWER-E (1-23) | RAFT | SRIJAN
167 | 13.06.2025 | NEW 9048 | 474 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 13:35 | 13:45 | TOWER-E (1-23) | RAFT | SRIJAN
168 | 13.06.2025 | UP70NT8336 | 475 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 13:52 | 14:05 | TOWER-E (1-23) | RAFT | SRIJAN
169 | 13.06.2025 | UP70NT8335 | 476 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556.59 | 1.59 | 14:30 | 14:40 | TOWER-E (1-23) | RAFT | SRIJAN
170 | 13.06.2025 | NEW 9655 | 477 | RMC 25 | CUM |  | 8 |  |  |  | 2920 | 2921.3 | 1.3 | 14:30 | 14:40 | TOWER-E (1-23) | RAFT | SRIJAN
171 | 13.06.2025 | NEW 8917 | 478 | RMC 25 | CUM |  | 8 |  |  |  | 2920 | 2920.69 | 0.69 | 15:09 | 15:29 | TOWER-E (1-23) | RAFT | SRIJAN
172 | 13.06.2025 | NEW 9048 | 479 | RMC 25 | CUM |  | 8 |  |  |  | 2920 | 2916.79 | -3.21 | 15:33 | 15:45 | TOWER-E (1-23) | RAFT | SRIJAN
173 | 13.06.2025 | UP70NT8336 | 480 | RMC 25 | CUM |  | 8 |  |  |  | 2920 | 2918.69 | -1.31 | 16:03 | 16:35 | TOWER-E (1-23) | RAFT | SRIJAN
174 | 13.06.2025 | UP70NT8335 | 481 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554.5 | -0.5 | 17:13 | 17:13 | TOWER-E (1-23) | RAFT | SRIJAN
175 | 13.06.2025 | NEW 9655 | 482 | RMC 25 | CUM |  | 8 |  |  |  | 2920 | 2919 | -1 | 17:14 | 17:38 | TOWER-E (1-23) | RAFT | SRIJAN
176 | 13.06.2025 | NEW 8917 | 483 | RMC 25 | CUM |  | 8 |  |  |  | 2920 | 2919 | -1 | 17:40 | 18:10 | TOWER-E (1-23) | RAFT | SRIJAN
177 | 13.06.2025 | NEW 9048 | 484 | RMC 25 | CUM |  | 8 |  |  |  | 2920 | 2917 | -3 | 18:30 | 19:20 | TOWER-E (1-23) | RAFT | SRIJAN
178 | 13.06.2025 | NEW 9655 | 487 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555.6 | 0.6 | 20:02 | 19:20 | TOWER-E (1-23) | RAFT | SRIJAN
179 | 13.06.2025 | UP70NT8335 | 486 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555.6 | 0.6 | 20:06 | 20:58 | TOWER-E (1-23) | RAFT | SRIJAN
180 | 13.06.2025 | UP70NT8336 | 489 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2917.5 | 362.5 | 20:06 | 20:58 | TOWER-E (1-23) | RAFT | SRIJAN
181 | 13.06.2025 | NEW 8917 | 488 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554.59 | -0.41 | 21:30 | 22:02 | TOWER-E (1-23) | RAFT | SRIJAN
182 | 13.06.2025 | UP32VN6140 | 1055 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 24:57 | 1:11 | TOWER-E (1-23) | RAFT | SHUBHAM
183 | 13.06.2025 | UP32VN6145 | 1056 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 1:13 | 1:46 | TOWER-E (1-23) | RAFT | SHUBHAM
184 | 13.06.2025 | UP53HT5034 | 1057 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 1:48 | 2:02 | TOWER-E (1-23) | RAFT | SHUBHAM
185 | 13.06.2025 | UP32WN8332 | 1058 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 2:05 | 2:20 | TOWER-E (1-23) | RAFT | SHUBHAM
186 | 13.06.2025 | UP32VN6144 | 1059 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 2:23 | 2:39 | TOWER-E (1-23) | RAFT | SHUBHAM
187 | 13.06.2025 | UP32VN6145 | 1060 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 3:16 | 3:42 | TOWER-E (1-23) | RAFT | SHUBHAM
188 | 13.06.2025 | UP32WN8332 | 1062 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2562 | 7 | 3:45 | 3:57 | TOWER-E (1-23) | RAFT | SHUBHAM
189 | 13.06.2025 | UP32VN6144 | 1063 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 4:04 | 4:22 | TOWER-E (1-23) | RAFT | SHUBHAM
190 | 13.06.2025 | UP32VN6145 | 1064 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 5:05 | 5:21 | TOWER-E (1-23) | RAFT | SHUBHAM
191 | 13.06.2025 | UP32VN6145 | 1065 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 9:48 | 10:30 | TOWER-E (1-23) | RAFT | SHUBHAM
192 | 13.06.2025 | UP32WN8333 | 1066 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 10:35 | 10:50 | TOWER-E (1-23) | RAFT | SHUBHAM
193 | 13.06.2025 | UP53HT5034 | 1068 | RMC 25 | CUM |  | 4 |  |  |  | 1460 | 1463 | 3 | 11:30 | 11:36 | TOWER-E (1-23) | RAFT | SHUBHAM
194 | 13.06.2025 | UP53HT5034 | 1069 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 14:55 | 15:23 | TOWER-E (1-23) | RAFT | SHUBHAM
195 | 13.06.2025 | UP32VN6140 | 1070 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2559 | 4 | 15:28 | 15:40 | TOWER-E (1-23) | RAFT | SHUBHAM
196 | 13.06.2025 | UP32VN6145 | 1071 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 15:51 | 15:59 | TOWER-E (1-23) | RAFT | SHUBHAM
197 | 13.06.2025 | UP53HT5034 | 1073 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2560 | 5 | 16:37 | 16:48 | TOWER-E (1-23) | RAFT | SHUBHAM
198 | 13.06.2025 | UP32VN6145 | 1075 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 17:07 | 17:22 | TOWER-E (1-23) | RAFT | SHUBHAM
199 | 13.06.2025 | UP32VN6144 | 1076 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 17:47 | 18:15 | TOWER-E (1-23) | RAFT | SHUBHAM
200 | 13.06.2025 | UP53HT5034 | 1077 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2568 | 13 | 18:31 | 18:50 | TOWER-E (1-23) | RAFT | SHUBHAM
201 | 13.06.2025 | UP32WN8333 | 1079 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2571 | 16 | 18:57 | 19:12 | TOWER-E (1-23) | RAFT | SHUBHAM
202 | 13.06.2025 | UP32VN6144 | 1080 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 19:18 | 19:34 | TOWER-E (1-23) | RAFT | SHUBHAM
203 | 13.06.2025 | UP53HT5034 | 1081 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2565 | 10 | 19:42 | 20:02 | TOWER-E (1-23) | RAFT | SHUBHAM
204 | 13.06.2025 | UP32WN8333 | 1082 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 20:14 | 20:34 | TOWER-E (1-23) | RAFT | SHUBHAM
205 | 13.06.2025 | UP32VN6144 | 1083 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 20:41 | 21:11 | TOWER-E (1-23) | RAFT | SHUBHAM
206 | 13.06.2025 | UP53HT5034 | 1084 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 21:25 | 21:40 | TOWER-E (1-23) | RAFT | SHUBHAM
207 | 13.06.2025 | UP32WN8333 | 1085 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2568 | 13 | 21:46 | 22:40 | TOWER-E (1-23) | RAFT | SHUBHAM
208 | 13.06.2025 | UP32VN6145 | 1086 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2566 | 11 | 22:00 | 22:26 | TOWER-E (1-23) | RAFT | SHUBHAM
209 | 13.06.2025 | UP53HT5034 | 1087 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2558 | 3 | 22:48 | 23:23 | TOWER-E (1-23) | RAFT | SHUBHAM
210 | 13.06.2025 | UP32VN6144 | 1088 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 23:26 | 23:45 | TOWER-E (1-23) | RAFT | SHUBHAM
211 | 13.06.2025 | UP32VN6145 | 1089 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2569 | 14 | 24:04 | 24:20 | TOWER-E (1-23) | RAFT | SHUBHAM
212 | 13.06.2025 | UP32WN8333 | 1090 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2563 | 8 | 24:24 | 24:51 | TOWER-E (1-23) | RAFT | SHUBHAM
213 | 13.06.2025 | UP70QT2341 | 905350120 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 3:37 | 5:02 | TOWER-E (1-23) | RAFT | ULTRATECH
214 | 13.06.2025 | UP70QT2014 | 905350119 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 5:06 | 5:09 | TOWER-E (1-23) | RAFT | ULTRATECH
215 | 13.06.2025 | UP70QT2015 | 905350121 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 5:20 | 5:36 | TOWER-E (1-23) | RAFT | ULTRATECH
216 | 13.06.2025 | UP70QT2013 | 905350122 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 5:41 | 6:03 | TOWER-E (1-23) | RAFT | ULTRATECH
217 | 13.06.2025 | UP70QT2342 | 905350123 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2554 | -1 | 6:33 | 6:45 | TOWER-E (1-23) | RAFT | ULTRATECH
218 | 13.06.2025 | UP70QT2341 | 905350124 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 7:42 | 8:07 | TOWER-E (1-23) | RAFT | ULTRATECH
219 | 13.06.2025 | UP70QT2014 | 905350125 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2557 | 2 | 8:12 | 8:30 | TOWER-E (1-23) | RAFT | ULTRATECH
220 | 13.06.2025 | UP70QT2013 | 905350126 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 8:39 | 9:15 | TOWER-E (1-23) | RAFT | ULTRATECH
221 | 13.06.2025 | UP70QT2342 | 905350128 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 9:24 | 10:45 | TOWER-E (1-23) | RAFT | ULTRATECH
222 | 13.06.2025 | UP70QT2014 | 905350130 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 11:04 | 11:35 | TOWER-E (1-23) | RAFT | ULTRATECH
223 | 13.06.2025 | UP70QT2013 | 905350131 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 11:46 | 12:18 | TOWER-E (1-23) | RAFT | ULTRATECH
224 | 13.06.2025 | UP70QT2015 | 905350132 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 13:11 | 13:24 | TOWER-E (1-23) | RAFT | ULTRATECH
225 | 14.06.2025 | UP53HT5034 | 1091 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2561 | 6 | 24:56 | 1:07 | TOWER-E (1-23) | RAFT | SHUBHAM
226 | 14.06.2025 | UP32VN6144 | 1092 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2559 | 4 | 1:49 | 2:16 | TOWER-E (1-23) | RAFT | SHUBHAM
227 | 14.06.2025 | UP32VN6145 | 1093 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 2:24 | 3:08 | TOWER-E (1-23) | RAFT | SHUBHAM
228 | 14.06.2025 | UP32VN6144 | 1094 | RMC 25 | CUM |  | 3 |  |  |  | 1095 | 1097 | 2 | 5:12 | 5:12 | TOWER-E (1-23) | RAFT | SHUBHAM
229 | 14.06.2025 | UP70QT2342 | 905350133 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 13:37 | 13:45 | TOWER-E (1-23) | RAFT | ULTRATECH
230 | 14.06.2025 | UP70QT2341 | 905350134 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 14:21 | 15:09 | TOWER-E (1-23) | RAFT | ULTRATECH
231 | 14.06.2025 | UP70QT2013 | 905350135 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 15:19 | 16:09 | TOWER-E (1-23) | RAFT | ULTRATECH
232 | 14.06.2025 | UP70QT2015 | 905350136 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 15:25 | 16:20 | TOWER-E (1-23) | RAFT | ULTRATECH
233 | 14.06.2025 | UP70QT2342 | 905350137 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2556 | 1 | 16:25 | 16:50 | TOWER-E (1-23) | RAFT | ULTRATECH
234 | 14.06.2025 | UP70QT2341 | 905350138 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 16:55 | 17:15 | TOWER-E (1-23) | RAFT | ULTRATECH
235 | 14.06.2025 | UP70QT2013 | 905350139 | RMC 25 | CUM |  | 7 |  |  |  | 2555 | 2555 | 0 | 17:20 | 18:10 | TOWER-E (1-23) | RAFT | ULTRATECH
236 | 2025-06-22 | UP70QT2341 | 905350161 | RMC 35 | CUM |  |  |  | 3 |  | 1245 |  | -1245 |  |  | TOWER-E (1-43) | PADESTIAL | ULTRATECH
237 | 2025-06-23 | UP70QT2013 | 905350165 | RMC 35 | CUM |  |  |  | 4 |  | 1660 |  | -1660 |  |  | TOWER-E (1-43) | PADESTIAL | ULTRATECH
238 | 2025-06-24 | UP70QT2342 | 905350166 | RMC 35 | CUM |  |  |  | 5 |  | 2075 |  | -2075 |  |  | TOWER-E (1-43) | PADESTIAL | ULTRATECH
239 | 2025-06-25 | UP70QT2342 | 905350167 | RMC 35 | CUM |  |  |  | 5 |  | 2075 |  | -2075 |  |  | TOWER-E (1-43) | PADESTIAL | ULTRATECH
240 | 2025-06-26 | UP70QT2014 | 905350168 | RMC 35 | CUM |  |  |  | 6 |  | 2490 |  | -2490 |  |  | TOWER-E (1-43) | PADESTIAL | ULTRATECH
241 | 2025-06-27 | UP70QT2342 | 905350171 | RMC 35 | CUM |  |  |  | 4 |  | 1660 |  | -1660 |  |  | TOWER-E (1-43) | PADESTIAL | ULTRATECH
242 | 2025-06-29 | UP70QT2014 | 905350190 | RMC 35 | CUM |  |  |  | 3 |  | 1245 |  | -1245 |  |  | TOWER-E (1-43) | PADESTIAL | ULTRATECH
243 | 2025-07-01 | 9655 | 563 | RMC 35 | CUM |  |  |  | 4 |  | 1660 |  | -1660 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
244 | 2025-07-01 | UP70NT8336 | 564 | RMC 35 | CUM |  |  |  | 4 |  | 1660 |  | -1660 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
245 | 2025-07-02 | 9048 | 565 | RMC 35 | CUM |  |  |  | 4.5 |  | 1867.5 |  | -1867.5 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
246 | 2025-07-04 | 9048 | 571 | RMC 35 | CUM |  |  |  | 3.5 |  | 1452.5 |  | -1452.5 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
247 | 2025-07-05 | 9048 | 582 | RMC 35 | CUM |  |  |  | 4 |  | 1660 |  | -1660 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
248 | 2025-07-05 | 8917 | 583 | RMC 35 | CUM |  |  |  | 4 |  | 1660 |  | -1660 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
249 | 2025-07-07 | UP70NT8335 | 591 | RMC 35 | CUM |  |  |  | 3 |  | 1245 |  | -1245 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
250 | 2025-07-08 | UP70NT8335 | 600 | RMC 35 | CUM |  |  |  | 4 |  | 1660 |  | -1660 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
251 | 2025-07-08 | UP70NT8335 | 604 | RMC 25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E (1-43) | COMP. STRIP | SRIJAN
252 | 2025-07-08 | UP70NT8336 | 603 | RMC 25 | CUM |  | 7 |  |  |  | 2555 |  | -2555 |  |  | TOWER-E (1-43) | COMP. STRIP | SRIJAN
253 | 2025-07-09 | 9048 | 605 | RMC 35 | CUM |  |  |  | 3.5 |  | 1452.5 |  | -1452.5 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
254 | 2025-07-10 | 8917 | 6009 | RMC 35 | CUM |  |  |  | 3.5 |  | 1452.5 |  | -1452.5 |  |  | TOWER-E (1-43) | PADESTIAL | SRIJAN
255 | 25.09.2025 | UP32WN8333 | 1950 | M35 | CUM |  |  |  | 3 |  | 1245 |  | -1245 |  |  | TOWER-E | COL. JUN. | SHUBHAM
256 | 25.09.2025 | UP32WN8333 | 1957 | M25 | CUM |  | 4 |  |  |  | 1660 |  | -1660 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
257 | 25.09.2025 | UP32WN8333 | 1959 | M25 | CUM |  | 4.5 |  |  |  | 1867.5 |  | -1867.5 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
258 | 01.10.2025 | UP32VN6140 | 1990 | M35 | CUM |  |  |  | 3 |  | 1245 |  | -1245 |  |  | TOWER-E | COL. JUN. | SHUBHAM
259 | 01.10.2025 | UP32WN8334 | 1993 | M25 | CUM |  | 4 |  |  |  | 1660 |  | -1660 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
260 | 01.10.2025 | UP32VN6140 | 1994 | M25 | CUM |  | 3.5 |  |  |  | 1452.5 |  | -1452.5 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
261 | 07.10.2025 | UP32VN6140 | 2037 | M35 | CUM |  |  |  | 3 |  | 1245 |  | -1245 |  |  | TOWER-E | COL. JUN. | SHUBHAM
262 | 09.10.2025 | UP32WN8332 | 2071 | M25 | CUM |  | 4 |  |  |  | 1660 |  | -1660 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
263 | 09.10.2025 | UP32VN6140 | 2072 | M35 | CUM |  |  |  | 2 |  | 830 |  | -830 |  |  | TOWER-E | COL. JUN. | SHUBHAM
264 | 09.10.2025 | UP53HT5032 | 2073 | M25 | CUM |  | 3 |  |  |  | 1245 |  | -1245 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
265 | 10.10.2025 | UP32WN8334 | 2087 | M25 | CUM |  | 2 |  |  |  | 830 |  | -830 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
266 | 29.10.2025 | UP53HT5034 | 2316 | M35 | CUM |  |  |  | 3 |  | 1245 |  | -1245 |  |  | TOWER-E | COL. JUN. | SHUBHAM
267 | 30.10.2025 | UP32VN6144 | 2332 | M25 | CUM |  | 4 |  |  |  | 1660 |  | -1660 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
268 | 30.10.2025 | UP53HT5032 | 2338 | M25 | CUM |  | 3.5 |  |  |  | 1452.5 |  | -1452.5 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
269 | 11.11.2025 | UP53HT5034 | 2535 | M40 | CUM |  |  |  |  | 2.5 | 1037.5 |  | -1037.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
270 | 17.11.2025 | UP32WN8334 | 2615 | M25 | CUM |  | 4 |  |  |  | 1660 |  | -1660 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
271 | 17.11.2025 | UP32VN6144 | 2604 | M40 | CUM |  |  |  |  | 3.5 | 1452.5 |  | -1452.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
272 | 18.11.2025 | UP53HT5032 | 2633 | M40 | CUM |  |  |  |  | 4.5 | 1867.5 |  | -1867.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
273 | 19.11.2025 | UP32WN8333 | 2643 | M25 | CUM |  | 3 |  |  |  | 1245 |  | -1245 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
274 | 19.11.2025 | UP32WN8334 | 2661 | M40 | CUM |  |  |  |  | 3.5 | 1452.5 |  | -1452.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
275 | 20.11.2025 | UP32WN8334 | 2694 | M40 | CUM |  |  |  |  | 3.5 | 1452.5 |  | -1452.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
276 | 28.11.2025 | UP32WN8333 | 2831 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
277 | 29.11.2025 | UP32VN6144 | 2844 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
278 | 29.11.2025 | UP53HT5032 | 2855 | M40 | CUM |  |  |  |  | 4 | 1660 |  | -1660 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
279 | 30.11.2025 | UP32WN8334 | 2874 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
280 | 02.12.2025 | UP53HT5034 | 2912 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
281 | 02.12.2025 | UP32WN8332 | 2920 | M40 | CUM |  |  |  |  | 4.5 | 1867.5 |  | -1867.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
282 | 03.12.2025 | UP32WN8333 | 2931 | M40 | CUM |  |  |  |  | 3.5 | 1452.5 |  | -1452.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
283 | 03.12.2025 | UP32WN8333 | 2935 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
284 | 05.12.2025 | UP32VN6140 | 2954 | M40 | CUM |  |  |  |  | 3 | 1245 |  | -1245 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
285 | 06.12.2025 | UP32WN8332 | 2957 | M40 | CUM |  |  |  |  | 3.5 | 1452.5 |  | -1452.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
286 | 06.12.2025 | UP32WN8334 | 2966 | M40 | CUM |  |  |  |  | 2.5 | 1037.5 |  | -1037.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
287 | 08.12.2025 | UP53HT5032 | 2995 | M40 | CUM |  |  |  |  | 2.5 | 1037.5 |  | -1037.5 |  |  | TOWER-E | G.F. COLUMN | SHUBHAM
288 | 09.12.2025 | UP32VN6140 | 3009 | M25 | CUM |  | 3.5 |  |  |  | 1452.5 |  | -1452.5 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
289 | 09.12.2025 | UP32WN8333 | 3012 | M25 | CUM |  | 3 |  |  |  | 1245 |  | -1245 |  |  | TOWER-E | PLINTH BEAM | SHUBHAM
6
| Total Qty upto date |  |  |  |  | 57.5 | 1636 | 0 | 82 | 56 | 667170 | 586905.85 | -80264.15
[6 empty] | 1831.5 |  |  |  |  | 13343.4 | 11738.117 | BAGS
[6 empty] | 57.5 | 1636 | 0 | 82 | 56

## CONCRETE WORK MB
COMPANY- OMAXE PANCHAM REALCON PVT LTD
PROJECT- TOWER-E
LOCATION- NAINI, PRAYAGRAJ
MB SHEET- CONCRETE WORK
S.NO. | DESCRIPTION | UNIT | NOS | NOS | MEASUREMENT |  |  | QTY. | REMARKS
[5 empty] | L | B | H/T
RAFT PCC- M10 BELOW PLINTH BEAM
1 | GRID (22'-43'/A-Q') | CUM | 1 | 1 | 32.165 | 37.125 | 0.1 | 119.4126 | 3rd RA
2 |  | CUM | 1 | 1 | 9.01 | 0.515 | 0.1 | 0.46402
3 | GRID (22'-26'/M'-Q') | CUM | -1 | 1 | 11.005 | 12.415 | 0.1 | -13.6627
4 | GRID (38'-43'/A-E') | CUM | -1 | 1 | 11.09 | 10.285 | 0.1 | -11.4061
5 | GRID (22'-30'/A-B') | CUM | -1 | 1 | 11.285 | 3.72 | 0.1 | -4.198
6 |  | CUM | -1 | 1 | 1.695 | 2.315 | 0.1 | -0.39239
7 |  | CUM | -1 | 1 | 3.95 | 1.5 | 0.1 | -0.5925
|  |  | -1 | 1 | 15.8 | 0.115 | 0.1 | -0.1817
8 | EXISTING RAFT (DETAILS IN JMR) | CUM | -1 | 1 | 9 | 5.915 | 0.1 | -5.3235
9 |  | CUM | -1 | 1 | 19.05 | 10 | 0.1 | -19.05
10 |  | CUM | -1 | 1 | 6.2 | 6.2 | 0.1 | -3.844
11 |  | CUM | -1 | 1 | 5.5 | 8.05 | 0.1 | -4.4275
[7 empty] | TOTAL | 56.7982
1 | GRID (5'-20/A-C') (DETAILS IN JMR) | CUM | 1 | 1 | 3 | 1.5 | 0.1 | 0.45 | 4th RA
2 |  | CUM | 1 | 1 | 5.875 | 1.5 | 0.1 | 0.88125
3 |  | CUM | 1 | 1 | 9.825 | 0.815 | 0.1 | 0.80074
4 |  | CUM | 1 | 1 | 11.52 | 1.405 | 0.1 | 1.6186
5 |  | CUM | 1 | 1 | 16.5 | 1 | 0.1 | 1.65
6 | GRID (1-18/M'-Q') (DETAILS IN JMR) | CUM | 1 | 1 | 11.03 | 8.67 | 0.1 | 9.563
7 |  | CUM | 1 | 1 | 11.545 | 2.715 | 0.1 | 3.1345
8 |  | CUM | 1 | 1 | 6.065 | 2.515 | 0.1 | 1.5253
9 |  | CUM | 1 | 1 | 1.05 | 2 | 0.1 | 0.21
10 |  | CUM | 1 | 1 | 8.67 | 3.27 | 0.1 | 2.8351
[7 empty] | TOTAL | 22.6685
S.NO. | DESCRIPTION | UNIT | NOS | NOS | MEASUREMENT |  |  | QTY. | REMARKS
[5 empty] | L | B | H/T
RAFT RCC- M25 BELOW PLINTH BEAM
1 | GRID (22'-43'/A-Q') | CUM | 1 | 1 | 31.935 | 36.895 | 0.85 | 1001.5056 | 3rd RA
2 |  | CUM | 1 | 1 | 8.78 | 0.515 | 0.85 | 3.8434
3 | GRID (22'-26'/M'-Q') | CUM | -1 | 1 | 11.005 | 12.415 | 0.85 | -116.133
4 | GRID (38'-43'/A-E') | CUM | -1 | 1 | 11.09 | 10.285 | 0.85 | -96.9516
5 | GRID (22'-30'/A-B') | CUM | -1 | 1 | 11.285 | 3.72 | 0.85 | -35.6832
6 |  | CUM | -1 | 1 | 1.695 | 2.315 | 0.85 | -3.3353
7 |  | CUM | -1 | 1 | 3.95 | 1.5 | 0.85 | -5.0363
[7 empty] | TOTAL | 748.2097
1 | GRID (22'-43'/A-Q') | CUM | 1 | 1 | 31.935 | 40.165 | 0.85 | 1090.2689 | 4th RA
2 |  | CUM | 1 | 1 | 8.78 | 0.515 | 0.85 | 3.8434
3 | GRID (22'-26'/M'-Q') | CUM | -1 | 1 | 14.275 | 12.415 | 0.85 | -150.6405
4 | GRID (38'-43'/A-E') | CUM | -1 | 1 | 11.09 | 10.285 | 0.85 | -96.9516
5 | GRID (22'-30'/A-B') | CUM | -1 | 1 | 14.555 | 3.72 | 0.85 | -46.0229
6 |  | CUM | -1 | 1 | 1.695 | 2.315 | 0.85 | -3.3353
7 |  | CUM | -1 | 1 | 3.95 | 1.5 | 0.85 | -5.0363
[7 empty] | TOTAL | 792.1258
COMPENSATORY STRIP
1 | GRID (22-23/B'-L') | CUM | 1 | 1 | 15.8 | 0.9 | 0.85 | 12.087 | 5th RA
[7 empty] | TOTAL | 12.087
PADESTIAL GRID (1-43/A-Q)
1 | C1, C2, C3, C8 (300X600) | CUM | 46 | 1 | 0.3 | 0.6 | 1.48 | 12.2544
2 | C1 (300X600) | CUM | 6 | 1 | 0.3 | 0.6 | 1.68 | 1.8144
3 | C2 (300X600) | CUM | 6 | 1 | 0.3 | 0.6 | 1.68 | 1.8144
4 | C3 (300X600) | CUM | 2 | 1 | 0.3 | 0.6 | 1.68 | 0.6048
5 | C8 (300X600) | CUM | 2 | 1 | 0.3 | 0.6 | 1.68 | 0.6048
6 | C4, C5 (300X750) | CUM | 24 | 1 | 0.3 | 0.7 | 1.48 | 7.4592
7 | C4 (300X750) | CUM | 4 | 1 | 0.3 | 0.7 | 1.68 | 1.4112
8 | C5 (300X750) | CUM | 2 | 1 | 0.3 | 0.7 | 1.68 | 0.7056
9 | C6 (300X715) | CUM | 14 | 1 | 0.3 | 0.715 | 1.48 | 4.4444
10 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 1.48 | 0.7104
11 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 1.68 | 0.8064
12 | SW 1 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 1.48 | 0.44252
13 |  | CUM | 2 | 1 | 0.23 | 1.42 | 1.48 | 0.96674
14 | SW 2 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 1.48 | 0.44252
15 |  | CUM | 2 | 1 | 0.23 | 1.62 | 1.48 | 1.1029
16 | SW 3 (230x1000) | CUM | 2 | 1 | 0.23 | 1 | 1.48 | 0.6808
17 | SW 4 (230x1150) | CUM | 2 | 1 | 0.23 | 1.15 | 1.48 | 0.78292
18 | SW 5 (230x1700) | CUM | 4 | 1 | 0.23 | 1.7 | 1.68 | 2.6275
19 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 1.48 | 0.80675
20 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 1.68 | 0.91577
21 | SW 7 (230x1855) | CUM | 2 | 1 | 0.23 | 1.855 | 1.48 | 1.2629
22 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 1.48 | 1.2254
23 | SW 9 (L-SHAPE) | CUM | 6 | 1 | 0.23 | 0.65 | 1.48 | 1.3276
24 |  | CUM | 6 | 1 | 0.23 | 1.62 | 1.48 | 3.3087
25 | SW 10 (230x3445) | CUM | 2 | 1 | 0.23 | 3.445 | 1.68 | 2.6623
26 | SW 11 (230x4065) | CUM | 2 | 1 | 0.23 | 4.065 | 1.68 | 3.1414
27 | SW 12 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 1.68 | 0.50232
28 |  | CUM | 2 | 1 | 0.23 | 1.305 | 1.68 | 1.0085
29 | SW 13 (200x3445) | CUM | 2 | 1 | 0.2 | 3.445 | 1.68 | 2.315
30 | LIFT WALL | CUM | 8 | 1 | 0.23 | 1.9 | 1.68 | 5.8733
[7 empty] | TOTAL | 64.0259
[7 empty] | TOTAL | 76.1129
| PLINTH BEAM (1-43/A-Q) | [7 empty] | 7TH RA
1 | PB1 | CUM | 1 | 2 | 3.025 | 0.2 | 0.335 | 0.40535
2 | PB1 | CUM | 1 | 2 | 2.8 | 0.2 | 0.335 | 0.3752
3 | PB2 | CUM | 1 | 2 | 3.3 | 0.2 | 0.335 | 0.4422
4 | PB3 | CUM | 1 | 4 | 1.395 | 0.1 | 0.335 | 0.18693
5 | PB3 | CUM | 1 | 6 | 1.4 | 0.1 | 0.335 | 0.2814
6 | PB3 | CUM | 1 | 2 | 1.2 | 0.1 | 0.335 | 0.0804
7 | PB3 | CUM | 1 | 6 | 1.55 | 0.1 | 0.335 | 0.31155
8 | PB3 | CUM | 1 | 6 | 0.97 | 0.1 | 0.335 | 0.19497
9 | PB4 | CUM | 1 | 6 | 1.395 | 0.2 | 0.335 | 0.56079
10 | PB5 | CUM | 1 | 2 | 3.1 | 0.2 | 0.335 | 0.4154
11 | PB6 | CUM | 1 | 1 | 16.51 | 0.2 | 0.335 | 1.1062
12 | PB7 | CUM | 1 | 2 | 2.875 | 0.2 | 0.335 | 0.38525
13 | PB7 | CUM | 1 | 2 | 2.93 | 0.2 | 0.335 | 0.39262
14 | PB8 | CUM | 1 | 2 | 3.16 | 0.2 | 0.335 | 0.42344
15 | PB9 | CUM | 1 | 2 | 5.635 | 0.2 | 0.335 | 0.75509
16 | PB10 | CUM | 1 | 2 | 4.69 | 0.2 | 0.335 | 0.62846
17 | PB11 | CUM | 1 | 2 | 5.76 | 0.2 | 0.335 | 0.77184
18 | PB12 | CUM | 1 | 2 | 2.22 | 0.2 | 0.335 | 0.29748
19 | PB13 | CUM | 1 | 2 | 3.115 | 0.2 | 0.335 | 0.41741
20 | PB14 | CUM | 1 | 6 | 7.605 | 0.2 | 0.335 | 3.0572
21 | PB15 | CUM | 1 | 2 | 3.215 | 0.2 | 0.335 | 0.43081
22 | PB16 | CUM | 1 | 2 | 2.76 | 0.23 | 0.335 | 0.42532
23 | PB17 | CUM | 1 | 2 | 15.345 | 0.23 | 0.335 | 2.3647
24 | PB18 | CUM | 1 | 2 | 8.02 | 0.2 | 0.335 | 1.0747
25 | PB19 | CUM | 1 | 2 | 5.72 | 0.2 | 0.335 | 0.76648
26 | PB20 | CUM | 1 | 2 | 7.77 | 0.2 | 0.335 | 1.0412
27 | PB21 | CUM | 1 | 6 | 7.955 | 0.2 | 0.335 | 3.1979
28 | PB22 | CUM | 1 | 6 | 5.745 | 0.2 | 0.335 | 2.3095
29 | PB23 | CUM | 1 | 2 | 5.125 | 0.2 | 0.335 | 0.68675
30 | PB24 | CUM | 1 | 2 | 1.4 | 0.23 | 0.335 | 0.21574
31 | PB25 | CUM | 1 | 2 | 6.825 | 0.2 | 0.335 | 0.91455
32 | PB25 | CUM | 1 | 2 | 2.93 | 0.23 | 0.335 | 0.45151
33 | PB26 | CUM | 1 | 1 | 16.51 | 0.23 | 0.335 | 1.2721
34 | PB27 | CUM | 1 | 2 | 3.53 | 0.23 | 0.335 | 0.54397
35 | PB28 | CUM | 1 | 2 | 3.03 | 0.2 | 0.335 | 0.40602
36 | PB29 | CUM | 1 | 2 | 10.2 | 0.2 | 0.335 | 1.3668
37 | PB30 | CUM | 1 | 2 | 6.38 | 0.2 | 0.335 | 0.85492
38 | PB31 | CUM | 1 | 6 | 5.36 | 0.2 | 0.335 | 2.1547
39 | PB32 | CUM | 1 | 20 | 0.515 | 0.1 | 0.335 | 0.34505
40 | PB33 | CUM | 1 | 6 | 3.45 | 0.2 | 0.335 | 1.3869
41 | PB34 | CUM | 1 | 6 | 2.91 | 0.2 | 0.335 | 1.1698
42 | PB35 | CUM | 1 | 2 | 6.38 | 0.2 | 0.335 | 0.85492
43 | PB36 | CUM | 1 | 6 | 3.31 | 0.2 | 0.335 | 1.3306
44 | PB37 | CUM | 1 | 4 | 2.195 | 0.2 | 0.335 | 0.58826
45 | PB38 | CUM | 1 | 2 | 5.245 | 0.2 | 0.335 | 0.70283
46 | PB39 | CUM | 1 | 2 | 2.23 | 0.2 | 0.335 | 0.29882
47 | PB40 | CUM | 1 | 2 | 4.9 | 0.2 | 0.335 | 0.6566
48 | PB41 | CUM | 1 | 2 | 5.145 | 0.2 | 0.335 | 0.68943
49 | PB42 | CUM | 1 | 2 | 3.2 | 0.23 | 0.335 | 0.49312
50 | PB43 | CUM | 1 | 2 | 2.95 | 0.2 | 0.335 | 0.3953
51 | PB44 | CUM | 1 | 2 | 3.8 | 0.2 | 0.335 | 0.5092
52 | PB45 | CUM | 1 | 2 | 4.55 | 0.2 | 0.335 | 0.6097
53 | PB46 | CUM | 1 | 2 | 3.05 | 0.2 | 0.335 | 0.4087
54 | PB47 | CUM | 1 | 2 | 3.115 | 0.2 | 0.335 | 0.41741
55 | PB48 | CUM | 1 | 2 | 1.41 | 0.2 | 0.335 | 0.18894
56 | PB49 | CUM | 1 | 2 | 0.35 | 0.2 | 0.335 | 0.0469
57 | PB50 | CUM | 1 | 2 | 2.37 | 0.2 | 0.335 | 0.31758
58 | PB51 | CUM | 1 | 2 | 3.2 | 0.2 | 0.335 | 0.4288
59 | PB52 | CUM | 1 | 2 | 14.53 | 0.2 | 0.335 | 1.947
60 | PB53 | CUM | 1 | 4 | 2.225 | 0.2 | 0.335 | 0.5963
61 | PB54 | CUM | 1 | 2 | 3.06 | 0.2 | 0.335 | 0.41004
62 | PB55 | CUM | 1 | 2 | 3.06 | 0.2 | 0.335 | 0.41004
63 | PB56 | CUM | 1 | 2 | 1.6 | 0.2 | 0.335 | 0.2144
64 | PB57 | CUM | 1 | 4 | 3.05 | 0.2 | 0.335 | 0.8174
65 | PB58 | CUM | 1 | 2 | 6.54 | 0.2 | 0.335 | 0.87636
66 | PB59 | CUM | 1 | 2 | 6.17 | 0.2 | 0.335 | 0.82678
67 | PB60 | CUM | 1 | 4 | 3.05 | 0.2 | 0.335 | 0.8174
68 | PB60 | CUM | 1 | 4 | 1.7 | 0.2 | 0.335 | 0.4556
69 | PB61 | CUM | 1 | 2 | 3.17 | 0.2 | 0.335 | 0.42478
[7 empty] | TOTAL | 51.6018
COLUMN JUNCTION (1-43/A-Q) AT PLINTH BEAM LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 62 | 1 | 0.3 | 0.6 | 0.45 | 5.022
2 | C4, C5 (300X750) | CUM | 30 | 1 | 0.3 | 0.7 | 0.45 | 2.835
3 | C6, C11 (300X715) | CUM | 14 | 1 | 0.3 | 0.715 | 0.45 | 1.3514
4 | C7 (300X800) | CUM | 4 | 1 | 0.3 | 0.8 | 0.45 | 0.432
5 | SW 1 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.45 | 0.13455
6 |  | CUM | 2 | 1 | 0.23 | 1.42 | 0.45 | 0.29394
7 | SW 2 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.45 | 0.13455
8 |  | CUM | 2 | 1 | 0.23 | 1.62 | 0.45 | 0.33534
9 | SW 3 (230x1000) | CUM | 2 | 1 | 0.23 | 1 | 0.45 | 0.207
10 | SW 4 (230x1150) | CUM | 2 | 1 | 0.23 | 1.15 | 0.45 | 0.23805
11 | SW 5 (230x1700) | CUM | 4 | 1 | 0.23 | 1.7 | 0.45 | 0.7038
12 | SW 6 (230x1185) | CUM | 4 | 1 | 0.23 | 1.185 | 0.45 | 0.49059
13 | SW 7 (230x1855) | CUM | 2 | 1 | 0.23 | 1.855 | 0.45 | 0.38399
14 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 0.45 | 0.3726
15 | SW 9 (L-SHAPE) | CUM | 6 | 1 | 0.23 | 0.65 | 0.45 | 0.40365
16 |  | CUM | 6 | 1 | 0.23 | 1.62 | 0.45 | 1.006
17 | SW 10 (230x3445) | CUM | 2 | 1 | 0.23 | 3.445 | 0.45 | 0.71312
18 | SW 11 (230x4065) | CUM | 2 | 1 | 0.23 | 4.065 | 0.45 | 0.84146
19 | SW 12 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.45 | 0.13455
20 |  | CUM | 2 | 1 | 0.23 | 1.305 | 0.45 | 0.27013
21 | SW 13 (200x3445) | CUM | 2 | 1 | 0.2 | 3.445 | 0.45 | 0.6201
22 | LIFT WALL | CUM | 8 | 1 | 0.23 | 1.9 | 0.45 | 1.5732
[7 empty] | TOTAL | 18.497
COLUMN (22-43/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 31 | 1 | 0.3 | 0.6 | 2.5 | 13.95
2 | C4, C5 (300X750) | CUM | 15 | 1 | 0.3 | 0.7 | 2.5 | 7.875
3 | C6, C11 (300X715) | CUM | 7 | 1 | 0.3 | 0.715 | 2.5 | 3.7538
4 | C7 (300X800) | CUM | 2 | 1 | 0.3 | 0.8 | 2.5 | 1.2
5 | SW 1 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 2.5 | 0.37375
6 |  | CUM | 1 | 1 | 0.23 | 1.42 | 2.5 | 0.8165
7 | SW 2 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 2.5 | 0.37375
8 |  | CUM | 1 | 1 | 0.23 | 1.62 | 2.5 | 0.9315
9 | SW 3 (230x1000) | CUM | 1 | 1 | 0.23 | 1 | 2.5 | 0.575
10 | SW 4 (230x1150) | CUM | 1 | 1 | 0.23 | 1.15 | 2.5 | 0.66125
11 | SW 5 (230x1700) | CUM | 2 | 1 | 0.23 | 1.7 | 2.5 | 1.955
12 | SW 6 (230x1185) | CUM | 2 | 1 | 0.23 | 1.185 | 2.5 | 1.3628
13 | SW 7 (230x1855) | CUM | 1 | 1 | 0.23 | 1.855 | 2.5 | 1.0666
14 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 2.5 | 2.07
15 | SW 9 (L-SHAPE) | CUM | 3 | 1 | 0.23 | 0.65 | 2.5 | 1.1213
16 |  | CUM | 3 | 1 | 0.23 | 1.62 | 2.5 | 2.7945
17 | SW 10 (230x3445) | CUM | 1 | 1 | 0.23 | 3.445 | 2.5 | 1.9809
18 | SW 11 (230x4065) | CUM | 1 | 1 | 0.23 | 4.065 | 2.5 | 2.3374
19 | SW 12 (L-SHAPE) | CUM | 1 | 1 | 0.23 | 0.65 | 2.5 | 0.37375
20 |  | CUM | 1 | 1 | 0.23 | 1.305 | 2.5 | 0.75037
21 | SW 13 (200x3445) | CUM | 1 | 1 | 0.2 | 3.445 | 2.5 | 1.7225
[7 empty] | TOTAL | 48.0455
[7 empty] | TOTAL | 118.1443

## SHUTT. WORK SUMMARY
TOWER-E CENTERING & SHUTTERING WORK SUMMARY
|  |  | QTY | [6 empty] | TOTAL
3 | CENTRING AND SHUTTERING |  | 3rd RA | 4th RA | 5th RA | 6th RA | 7th RA | 8th RA | 9th RA
Providing and fixing plywood or steel plate shuttering and centring for structural concrete work in locations called for including strutting, propping, bracing, bolting, wedging, casing, striking, removal etc. complete for any size, section, thickness. Props shall consist of well designed steel pipes adequately braced (wooden ballies as props shall not be permitted). The item to include centering and shuttering at all heights and levels. Allow for forming grooves, drip course, chamfers, cut-outs, openings etc. where called for and for dressing with approved shuttering oil to prevent adhesion. Unexposed concrete surfaces subsequently left untreated (in the condition obtained on removal of form work) shall not constitute exposed concrete work and shall be measured under this item only Irregular shapes with sides (like circular, semi-circular, oval etc.) which may not be perpendicular to each other for shapes not conforming to rectangle or square, and circular shuttering shall not be paid separately. Joints of soffits of the slab shall be made clean after concreting and de-shuttering. (quoted rate to include all staging upto 3.50 mtr height). Note:- Contractor shall take necessary precautions such as watertight shuttering. This is inclusive of RCC members, leaving shuttering & centring for pour strip, slab in slope, RCC members in curved (in plan), etc., nothing is payable extra on this account.
3.1.1. | Foundation, column footings, raft slab, raft beams, plinth beam, lift pits, sump pits, pedestals / bases of column, column up to plinth, swimming pool, Retaining wall foundations, grade slab etc. | SQM | 93.6125 | 82.707 | 619.2036 |  | 849.9743 |  |  | 1645.4974
3.1.2. | Suspended floors, roofs, balconies, shelves/ counters, stair waist slabs, folded plate stairs and landings, swimming pool slab, lintel and floor beams, landing beams, girders (deep beams), RCC bands, swimming pool beam, cantilever projections, coping, cills, slab of tank etc at all levels.
3.1.2.1. | Stilt Floor level to 7th Floor level | SQM | [7 empty] | 0
3.1.2.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | [7 empty] | 0
3.1.2..3 | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | SQM | [7 empty] | 0
3.2. | Columns, Wall, pillars, piers, abutments, posts and struts, offset and projection of columns, water tank walls, lift walls, Retaining Wall, swimming pool, Parapets, planters, vertical projection of pergolas, wall and ramp walls etc. at all levels.
3.2.1. | Stilt Floor level to 7th Floor level | SQM |  |  |  |  | 246.825 |  |  | 246.825
3.2.2. | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | [7 empty] | 0
3.2.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | SQM | [7 empty] | 0
3.3. | Extra for additional height in centring, shuttering where ever required with adequate bracing, propping etc. including cost of de-shuttering and decentring at all levels, over and above height of 3.50 mtr (Plan area to be measured and shall be paid proportionately on actual height) – for every 1.0 mtr. height | SQM | [7 empty] | 0
[9 empty] | TOTAL | 1892.3224

## SHUTTERING WORK MB
COMPANY- OMAXE PANCHAM REALCON PVT LTD
PROJECT- TOWER-E
LOCATION- NAINI, PRAYAGRAJ
MB SHEET- SHUTTERING BELOW PLINTH BEAM
S.NO. | DESCRIPTION | UNIT | NOS | NOS | MEASUREMENT |  |  | QTY. | REMARKS
[5 empty] | L | B | H/T
PCC SHUTTERING
1 | GRID (26'/Q') | SQM | 1 | 1 | 0.7 |  | 0.1 | 0.07 |  | 3rd RA
2 | GRID (26'-43'/Q') | SQM | 1 | 1 | 26.92 |  | 0.1 | 2.692
3 | GRID (43'/E'-Q') | SQM | 1 | 1 | 21.65 |  | 0.1 | 2.165
4 | GRID (38'-43'/E') | SQM | 1 | 1 | 11.09 |  | 0.1 | 1.109
5 | GRID (38'/A-E') | SQM | 1 | 1 | 10.285 |  | 0.1 | 1.0285
6 | GRID (30-38'/A) | SQM | 1 | 1 | 8.875 |  | 0.1 | 0.8875
7 | GRID (30/A-A') | SQM | 1 | 1 | 1.5 |  | 0.1 | 0.15
8 | GRID (27'-30/A') | SQM | 1 | 1 | 3.95 |  | 0.1 | 0.395
9 | GRID (27'/A'-B) | SQM | 1 | 1 | 0.815 |  | 0.1 | 0.0815
10 | GRID (26'-27'/B) | SQM | 1 | 1 | 1.695 |  | 0.1 | 0.1695
11 | GRID (26'/B-B') | SQM | 1 | 1 | 1.405 |  | 0.1 | 0.1405
12 | GRID (22'-26'/B') | SQM | 1 | 1 | 2.285 |  | 0.1 | 0.2285 | -9mtr as per JMR
RAFT SHUTTERING
1 | GRID (22'-26'/M') | SQM | 1 | 1 | 11.005 |  | 0.55 | 6.0528
2 | GRID (26/M'-Q) | SQM | 1 | 1 | 12.415 |  | 0.55 | 6.8282
3 | GRID (26'-43'/Q') | SQM | 1 | 1 | 26.92 |  | 0.55 | 14.806
4 | GRID (43'/E'-Q') | SQM | 1 | 1 | 21.65 |  | 0.55 | 11.9075
5 | GRID (38'-43'/E') | SQM | 1 | 1 | 11.09 |  | 0.55 | 6.0995
6 | GRID (38'/A-E') | SQM | 1 | 1 | 10.285 |  | 0.55 | 5.6568
7 | GRID (30-38'/A) | SQM | 1 | 1 | 8.875 |  | 0.55 | 4.8813
8 | GRID (30/A-A') | SQM | 1 | 1 | 1.5 |  | 0.55 | 0.825
9 | GRID (27'-30/A') | SQM | 1 | 1 | 3.95 |  | 0.55 | 2.1725
10 | GRID (27'/A'-B) | SQM | 1 | 1 | 0.815 |  | 0.55 | 0.44825
11 | GRID (26'-27'/B) | SQM | 1 | 1 | 1.695 |  | 0.55 | 0.93225
12 | GRID (26'/B-B') | SQM | 1 | 1 | 1.405 |  | 0.55 | 0.77275
13 | GRID (22'-26'/B') | SQM | 1 | 1 | 11.285 |  | 0.55 | 6.2068
14 | GRID (22'-26'/B') | SQM | 1 | 1 | 15.8 |  | 1.07 | 16.906
[7 empty] | TOTAL | 93.6125
PCC SHUTTERING
1 | GRID (5'-20/A-C') (DETAILS IN JMR) | SQM | 1 | 1 | 1.5 |  | 0.1 | 0.15 |  | 4th RA
2 |  | SQM | 1 | 1 | 8.875 |  | 0.1 | 0.8875
3 |  | SQM | 1 | 1 | 1.5 |  | 0.1 | 0.15
4 |  | SQM | 1 | 1 | 3.95 |  | 0.1 | 0.395
5 |  | SQM | 1 | 1 | 0.815 |  | 0.1 | 0.0815
6 |  | SQM | 1 | 1 | 1.695 |  | 0.1 | 0.1695
7 |  | SQM | 1 | 1 | 1.405 |  | 0.1 | 0.1405
8 |  | SQM | 1 | 1 | 1.98 |  | 0.1 | 0.198
9 |  | SQM | 1 | 1 | 1 |  | 0.1 | 0.1
10 | GRID (1-18/M'-Q') (DETAILS IN JMR) | SQM | 1 | 1 | 11.03 |  | 0.1 | 1.103
11 |  | SQM | 1 | 1 | 8.67 |  | 0.1 | 0.867
12 |  | SQM | 1 | 1 | 0.515 |  | 0.1 | 0.0515
13 |  | SQM | 1 | 1 | 8.78 |  | 0.1 | 0.878
14 |  | SQM | 1 | 1 | 0.515 |  | 0.1 | 0.0515
15 |  | SQM | 1 | 1 | 9.72 |  | 0.1 | 0.972
16 |  | SQM | 1 | 1 | 3.27 |  | 0.1 | 0.327
RAFT SHUTTERING
1 | GRID (17'-22'/M') | SQM | 1 | 1 | 14.275 |  | 0.55 | 7.8513
2 | GRID (17'/M'-Q) | SQM | 1 | 1 | 12.415 |  | 0.55 | 6.8282
3 | GRID (1-17'/Q') | SQM | 1 | 1 | 26.92 |  | 0.55 | 14.806
4 | GRID (1-5'/E') | SQM | 1 | 1 | 11.09 |  | 0.55 | 6.0995
5 | GRID (5'/A-E') | SQM | 1 | 1 | 10.285 |  | 0.55 | 5.6568
6 | GRID (5'-14'/A) | SQM | 1 | 1 | 8.875 |  | 0.55 | 4.8813
7 | GRID (14'/A-A') | SQM | 1 | 1 | 1.5 |  | 0.55 | 0.825
8 | GRID (14'-16'/A') | SQM | 1 | 1 | 3.95 |  | 0.55 | 2.1725
9 | GRID (16'/A'-B) | SQM | 1 | 1 | 0.815 |  | 0.55 | 0.44825
10 | GRID (16'-17'/B) | SQM | 1 | 1 | 1.695 |  | 0.55 | 0.93225
11 | GRID (17'/B-B') | SQM | 1 | 1 | 1.405 |  | 0.55 | 0.77275
12 | GRID (17'-22'/B') | SQM | 1 | 1 | 14.555 |  | 0.55 | 8.0053
13 | GRID (22'-26'/B') | SQM | 1 | 1 | 15.8 |  | 1.07 | 16.906
[7 empty] | TOTAL | 82.707
COMPENSATORY STRIP
1 | GRID (22-23/B'-L') | SQM | 1 | 2 |  | 0.9 | 0.85 | 1.53 |  | 5th RA
PADESTIAL GRID (1-43/A-Q)
1 | C1, C2, C3, C8 (300X600) | SQM | 46 | 1 | 0.3 | 0.6 | 1.48 | 122.544
2 | C1 (300X600) | SQM | 6 | 1 | 0.3 | 0.6 | 1.68 | 18.144
3 | C2 (300X600) | SQM | 6 | 1 | 0.3 | 0.6 | 1.68 | 18.144
4 | C3 (300X600) | SQM | 2 | 1 | 0.3 | 0.6 | 1.68 | 6.048
5 | C3 (300X600) | SQM | 2 | 1 | 0.3 | 0.6 | 1.68 | 6.048
6 | C4, C5 (300X750) | SQM | 24 | 1 | 0.3 | 0.7 | 1.48 | 71.04
7 | C4 (300X750) | SQM | 4 | 1 | 0.3 | 0.7 | 1.68 | 13.44
8 | C5 (300X750) | SQM | 2 | 1 | 0.3 | 0.7 | 1.68 | 6.72
9 | C6 (300X715) | SQM | 14 | 1 | 0.3 | 0.715 | 1.48 | 42.0616
10 | C7 (300X800) | SQM | 2 | 1 | 0.3 | 0.8 | 1.48 | 6.512
11 | C7 (300X800) | SQM | 2 | 1 | 0.3 | 0.8 | 1.68 | 7.392
12 | SW 1 (L-SHAPE) | SQM | 2 | 1 | 0.23 | 0.65 | 1.48 | 5.2096
13 |  | SQM | 2 | 1 | 0 | 1.42 | 1.48 | 8.4064
14 | SW 2 (L-SHAPE) | SQM | 2 | 1 | 0.23 | 0.65 | 1.48 | 5.2096
15 |  | SQM | 2 | 1 | 0 | 1.62 | 1.48 | 9.5904
16 | SW 3 (230x1000) | SQM | 2 | 1 | 0.23 | 1 | 1.48 | 7.2816
17 | SW 4 (230x1150) | SQM | 2 | 1 | 0.23 | 1.15 | 1.48 | 8.1696
18 | SW 5 (230x1700) | SQM | 4 | 1 | 0.23 | 1.7 | 1.68 | 25.9392
19 | SW 6 (230x1185) | SQM | 2 | 1 | 0.23 | 1.185 | 1.48 | 8.3768
20 | SW 6 (230x1185) | SQM | 2 | 1 | 0.23 | 1.185 | 1.68 | 9.5088
21 | SW 7 (230x1855) | SQM | 2 | 1 | 0.23 | 1.855 | 1.48 | 12.3432
22 | SW 8 (230x3600) | SQM | 1 | 1 | 0.23 | 3.6 | 1.48 | 11.3368
23 | SW 9 (L-SHAPE) | SQM | 6 | 1 | 0.23 | 0.65 | 1.48 | 15.6288
24 |  | SQM | 6 | 1 | 0 | 1.62 | 1.48 | 28.7712
25 | SW 10 (230x3445) | SQM | 2 | 1 | 0.23 | 3.445 | 1.68 | 24.696
26 | SW 11 (230x4065) | SQM | 2 | 1 | 0.23 | 4.065 | 1.68 | 28.8624
27 | SW 12 (L-SHAPE) | SQM | 2 | 1 | 0.23 | 0.65 | 1.68 | 5.9136
28 |  | SQM | 2 | 1 | 0 | 1.305 | 1.68 | 8.7696
29 | SW 13 (200x3445) | SQM | 2 | 1 | 0.2 | 3.445 | 1.68 | 24.4944
30 | LIFT WALL | SQM | 8 | 1 | 0 | 1.9 | 1.68 | 51.072
[7 empty] | TOTAL | 619.2036
PLINTH BEAM (1-43/A-Q)
| PB1 | SQM | 4 |  | 3.025 |  | 0.335 | 4.0535 |  | 7th RA
|  | SQM | 4 |  | 2.8 |  | 0.335 | 3.752
| BOTTOM | SQM | 2 |  | 3.025 |  | 0.2 | 1.21
|  | SQM | 2 |  | 2.8 |  | 0.2 | 1.12
| PB2 | SQM | 4 |  | 3.3 |  | 0.335 | 4.422
| BOTTOM | SQM | 2 |  | 3.3 |  | 0.2 | 1.32
| PB3 | SQM | 8 |  | 1.395 |  | 0.335 | 3.7386
| BOTTOM | SQM | 4 |  | 1.395 |  | 0.1 | 0.558
| PB3 | SQM | 12 |  | 1.4 |  | 0.335 | 5.628
| BOTTOM | SQM | 6 |  | 1.4 |  | 0.1 | 0.84
| PB3 | SQM | 4 |  | 1.2 |  | 0.335 | 1.608
| BOTTOM | SQM | 2 |  | 1.2 |  | 0.1 | 0.24
| PB3 | SQM | 12 |  | 1.55 |  | 0.335 | 6.231
| BOTTOM | SQM | 6 |  | 1.55 |  | 0.1 | 0.93
| PB3 | SQM | 12 |  | 0.97 |  | 0.335 | 3.8994
| BOTTOM | SQM | 6 |  | 0.97 |  | 0.1 | 0.582
| PB4 | SQM | 4 |  | 1.395 |  | 0.335 | 1.8693
| BOTTOM | SQM | 6 |  | 1.395 |  | 0.2 | 1.674
| PB5 | SQM | 4 |  | 3.1 |  | 0.335 | 4.154
| BOTTOM | SQM | 2 |  | 3.1 |  | 0.2 | 1.24
| PB6 | SQM | 1 |  | 16.51 |  | 0.335 | 5.5309
| BOTTOM | SQM | 1 |  | 16.51 |  | 0.2 | 3.302
| PB7 | SQM | 4 |  | 2.875 |  | 0.335 | 3.8525
| BOTTOM | SQM | 2 |  | 2.875 |  | 0.2 | 1.15
| PB7 | SQM | 4 |  | 2.93 |  | 0.335 | 3.9262
| BOTTOM | SQM | 2 |  | 2.93 |  | 0.2 | 1.172
| PB8 | SQM | 4 |  | 3.16 |  | 0.335 | 4.2344
| BOTTOM | SQM | 2 |  | 3.16 |  | 0.2 | 1.264
| PB9 | SQM | 4 |  | 5.635 |  | 0.335 | 7.5509
| BOTTOM | SQM | 2 |  | 5.635 |  | 0.2 | 2.254
| PB10 | SQM | 4 |  | 4.69 |  | 0.335 | 6.2846
| BOTTOM | SQM | 2 |  | 4.69 |  | 0.2 | 1.876
| PB11 | SQM | 4 |  | 5.76 |  | 0.335 | 7.7184
| BOTTOM | SQM | 2 |  | 5.76 |  | 0.2 | 2.304
| PB12 | SQM | 4 |  | 2.22 |  | 0.335 | 2.9748
| BOTTOM | SQM | 2 |  | 2.22 |  | 0.2 | 0.888
| PB13 | SQM | 4 |  | 3.115 |  | 0.335 | 4.1741
| BOTTOM | SQM | 2 |  | 3.115 |  | 0.2 | 1.246
| PB14 | SQM | 12 |  | 7.605 |  | 0.335 | 30.5721
| BOTTOM | SQM | 6 |  | 7.605 |  | 0.2 | 9.126
| PB15 | SQM | 4 |  | 3.215 |  | 0.335 | 4.3081
| BOTTOM | SQM | 2 |  | 3.215 |  | 0.2 | 1.286
| PB16 | SQM | 4 |  | 2.76 |  | 0.335 | 3.6984
| BOTTOM | SQM | 2 |  | 2.76 |  | 0.23 | 1.2696
| PB17 | SQM | 4 |  | 15.345 |  | 0.335 | 20.5623
| BOTTOM | SQM | 2 |  | 15.345 |  | 0.23 | 7.0587
| PB18 | SQM | 4 |  | 8.02 |  | 0.335 | 10.7468
| BOTTOM | SQM | 2 |  | 8.02 |  | 0.2 | 3.208
| PB19 | SQM | 4 |  | 5.72 |  | 0.335 | 7.6648
| BOTTOM | SQM | 2 |  | 5.72 |  | 0.2 | 2.288
| PB20 | SQM | 4 |  | 7.77 |  | 0.335 | 10.4118
| BOTTOM | SQM | 2 |  | 7.77 |  | 0.2 | 3.108
| PB21 | SQM | 12 |  | 7.955 |  | 0.335 | 31.9791
| BOTTOM | SQM | 6 |  | 7.955 |  | 0.2 | 9.546
| PB22 | SQM | 12 |  | 5.745 |  | 0.335 | 23.0949
| BOTTOM | SQM | 6 |  | 5.745 |  | 0.2 | 6.894
| PB23 | SQM | 4 |  | 5.125 |  | 0.335 | 6.8675
| BOTTOM | SQM | 2 |  | 5.125 |  | 0.2 | 2.05
| PB24 | SQM | 4 |  | 1.4 |  | 0.335 | 1.876
| BOTTOM | SQM | 2 |  | 1.4 |  | 0.23 | 0.644
| PB25 | SQM | 4 |  | 6.825 |  | 0.335 | 9.1455
| BOTTOM | SQM | 2 |  | 6.825 |  | 0.2 | 2.73
| PB25 | SQM | 4 |  | 2.93 |  | 0.335 | 3.9262
| BOTTOM | SQM | 2 |  | 2.93 |  | 0.23 | 1.3478
| PB26 | SQM | 2 |  | 16.51 |  | 0.335 | 11.0617
| BOTTOM | SQM | 1 |  | 16.51 |  | 0.23 | 3.7973
| PB27 | SQM | 4 |  | 3.53 |  | 0.335 | 4.7302
| BOTTOM | SQM | 2 |  | 3.53 |  | 0.23 | 1.6238
| PB28 | SQM | 4 |  | 3.03 |  | 0.335 | 4.0602
| BOTTOM | SQM | 2 |  | 3.03 |  | 0.2 | 1.212
| PB29 | SQM | 4 |  | 10.2 |  | 0.335 | 13.668
| BOTTOM | SQM | 2 |  | 10.2 |  | 0.2 | 4.08
| PB30 | SQM | 4 |  | 6.38 |  | 0.335 | 8.5492
| BOTTOM | SQM | 2 |  | 6.38 |  | 0.2 | 2.552
| PB31 | SQM | 12 |  | 5.36 |  | 0.335 | 21.5472
| BOTTOM | SQM | 6 |  | 5.36 |  | 0.2 | 6.432
| PB32 | SQM | 40 |  | 0.515 |  | 0.335 | 6.901
| BOTTOM | SQM | 20 |  | 0.515 |  | 0.1 | 1.03
| PB33 | SQM | 12 |  | 3.45 |  | 0.335 | 13.869
| BOTTOM | SQM | 6 |  | 3.45 |  | 0.2 | 4.14
| PB34 | SQM | 12 |  | 2.91 |  | 0.335 | 11.6982
| BOTTOM | SQM | 6 |  | 2.91 |  | 0.2 | 3.492
| PB35 | SQM | 4 |  | 6.38 |  | 0.335 | 8.5492
| BOTTOM | SQM | 2 |  | 6.38 |  | 0.2 | 2.552
| PB36 | SQM | 12 |  | 3.31 |  | 0.335 | 13.3062
| BOTTOM | SQM | 6 |  | 3.31 |  | 0.2 | 3.972
| PB37 | SQM | 8 |  | 2.195 |  | 0.335 | 5.8826
| BOTTOM | SQM | 4 |  | 2.195 |  | 0.2 | 1.756
| PB38 | SQM | 4 |  | 5.245 |  | 0.335 | 7.0283
| BOTTOM | SQM | 2 |  | 5.245 |  | 0.2 | 2.098
| PB39 | SQM | 4 |  | 2.23 |  | 0.335 | 2.9882
| BOTTOM | SQM | 2 |  | 2.23 |  | 0.2 | 0.892
| PB40 | SQM | 4 |  | 4.9 |  | 0.335 | 6.566
| BOTTOM | SQM | 2 |  | 4.9 |  | 0.2 | 1.96
| PB41 | SQM | 4 |  | 5.145 |  | 0.335 | 6.8943
| BOTTOM | SQM | 2 |  | 5.145 |  | 0.2 | 2.058
| PB42 | SQM | 4 |  | 3.2 |  | 0.335 | 4.288
| BOTTOM | SQM | 2 |  | 3.2 |  | 0.23 | 1.472
| PB43 | SQM | 4 |  | 2.95 |  | 0.335 | 3.953
| BOTTOM | SQM | 2 |  | 2.95 |  | 0.2 | 1.18
| PB44 | SQM | 4 |  | 3.8 |  | 0.335 | 5.092
| BOTTOM | SQM | 2 |  | 3.8 |  | 0.2 | 1.52
| PB45 | SQM | 4 |  | 4.55 |  | 0.335 | 6.097
| BOTTOM | SQM | 2 |  | 4.55 |  | 0.2 | 1.82
| PB46 | SQM | 4 |  | 3.05 |  | 0.335 | 4.087
| BOTTOM | SQM | 2 |  | 3.05 |  | 0.2 | 1.22
| PB47 | SQM | 4 |  | 3.115 |  | 0.335 | 4.1741
| BOTTOM | SQM | 2 |  | 3.115 |  | 0.2 | 1.246
| PB48 | SQM | 4 |  | 1.41 |  | 0.335 | 1.8894
| BOTTOM | SQM | 2 |  | 1.41 |  | 0.2 | 0.564
| PB49 | SQM | 4 |  | 0.35 |  | 0.335 | 0.469
| BOTTOM | SQM | 2 |  | 0.35 |  | 0.2 | 0.14
| PB50 | SQM | 4 |  | 2.37 |  | 0.335 | 3.1758
| BOTTOM | SQM | 2 |  | 2.37 |  | 0.2 | 0.948
| PB51 | SQM | 4 |  | 3.2 |  | 0.335 | 4.288
| BOTTOM | SQM | 2 |  | 3.2 |  | 0.2 | 1.28
| PB52 | SQM | 4 |  | 14.53 |  | 0.335 | 19.4702
| BOTTOM | SQM | 2 |  | 14.53 |  | 0.2 | 5.812
| PB53 | SQM | 8 |  | 2.225 |  | 0.335 | 5.963
| BOTTOM | SQM | 4 |  | 2.225 |  | 0.2 | 1.78
| PB54 | SQM | 4 |  | 3.06 |  | 0.335 | 4.1004
| BOTTOM | SQM | 2 |  | 3.06 |  | 0.2 | 1.224
| PB55 | SQM | 4 |  | 3.06 |  | 0.335 | 4.1004
| BOTTOM | SQM | 2 |  | 3.06 |  | 0.2 | 1.224
| PB56 | SQM | 4 |  | 1.6 |  | 0.335 | 2.144
| BOTTOM | SQM | 2 |  | 1.6 |  | 0.2 | 0.64
| PB57 | SQM | 8 |  | 3.05 |  | 0.335 | 8.174
| BOTTOM | SQM | 4 |  | 3.05 |  | 0.2 | 2.44
| PB58 | SQM | 4 |  | 6.54 |  | 0.335 | 8.7636
| BOTTOM | SQM | 2 |  | 6.54 |  | 0.2 | 2.616
| PB59 | SQM | 4 |  | 6.17 |  | 0.335 | 8.2678
| BOTTOM | SQM | 2 |  | 6.17 |  | 0.2 | 2.468
| PB60 | SQM | 8 |  | 3.05 |  | 0.335 | 8.174
| BOTTOM | SQM | 4 |  | 3.05 |  | 0.2 | 2.44
| PB60 | SQM | 8 |  | 1.7 |  | 0.335 | 4.556
| BOTTOM | SQM | 4 |  | 1.7 |  | 0.2 | 1.36
| PB61 | SQM | 4 |  | 3.17 |  | 0.335 | 4.2478
| BOTTOM | SQM | 2 |  | 3.17 |  | 0.2 | 1.268
COLUMN JUNCTION (1-43/A-Q) AT PLINTH BEAM LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 62 | 1 | 0.3 | 0.6 | 0.45 | 50.22
2 | C4, C5 (300X750) | CUM | 30 | 1 | 0.3 | 0.7 | 0.45 | 27
3 | C6, C11 (300X715) | CUM | 14 | 1 | 0.3 | 0.715 | 0.45 | 12.789
4 | C7 (300X800) | CUM | 4 | 1 | 0.3 | 0.8 | 0.45 | 3.96
5 | SW 1 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.45 | 1.584
6 |  | CUM | 2 | 1 | 0.23 | 1.42 | 0.45 | 2.97
7 | SW 2 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.45 | 1.584
8 |  | CUM | 2 | 1 | 0.23 | 1.62 | 0.45 | 3.33
9 | SW 3 (230x1000) | CUM | 2 | 1 | 0.23 | 1 | 0.45 | 2.214
10 | SW 4 (230x1150) | CUM | 2 | 1 | 0.23 | 1.15 | 0.45 | 2.484
11 | SW 5 (230x1700) | CUM | 4 | 1 | 0.23 | 1.7 | 0.45 | 6.948
12 | SW 6 (230x1185) | CUM | 4 | 1 | 0.23 | 1.185 | 0.45 | 5.094
13 | SW 7 (230x1855) | CUM | 2 | 1 | 0.23 | 1.855 | 0.45 | 3.753
14 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 0.45 | 3.447
15 | SW 9 (L-SHAPE) | CUM | 6 | 1 | 0.23 | 0.65 | 0.45 | 4.752
16 |  | CUM | 6 | 1 | 0.23 | 1.62 | 0.45 | 9.99
17 | SW 10 (230x3445) | CUM | 2 | 1 | 0.23 | 3.445 | 0.45 | 6.615
18 | SW 11 (230x4065) | CUM | 2 | 1 | 0.23 | 4.065 | 0.45 | 7.731
19 | SW 12 (L-SHAPE) | CUM | 2 | 1 | 0.23 | 0.65 | 0.45 | 1.584
20 |  | CUM | 2 | 1 | 0.23 | 1.305 | 0.45 | 2.763
21 | SW 13 (200x3445) | CUM | 2 | 1 | 0.2 | 3.445 | 0.45 | 6.561
22 | LIFT WALL | CUM | 8 | 1 | 0.23 | 1.9 | 0.45 | 15.336
[7 empty] | TOTAL | 849.9743
COLUMN (22-43/A-Q) FROM PLINTH LVL TO 1ST FLOOR LVL
1 | C1, C2, C3, C8, C9, C10 (300X600) | CUM | 31 | 0.5 | 0.3 | 0.6 | 2.5 | 69.75
2 | C4, C5 (300X750) | CUM | 15 | 0.5 | 0.3 | 0.7 | 2.5 | 37.5
3 | C6, C11 (300X715) | CUM | 7 | 0.5 | 0.3 | 0.715 | 2.5 | 17.7625
4 | C7 (300X800) | CUM | 2 | 0.5 | 0.3 | 0.8 | 2.5 | 5.5
5 | SW 1 (L-SHAPE) | CUM | 1 | 0.5 | 0.23 | 0.65 | 2.5 | 2.2
6 |  | CUM | 1 | 0.5 | 0.23 | 1.42 | 2.5 | 4.125
7 | SW 2 (L-SHAPE) | CUM | 1 | 0.5 | 0.23 | 0.65 | 2.5 | 2.2
8 |  | CUM | 1 | 0.5 | 0.23 | 1.62 | 2.5 | 4.625
9 | SW 3 (230x1000) | CUM | 1 | 0.5 | 0.23 | 1 | 2.5 | 3.075
10 | SW 4 (230x1150) | CUM | 1 | 0.5 | 0.23 | 1.15 | 2.5 | 3.45
11 | SW 5 (230x1700) | CUM | 2 | 0.5 | 0.23 | 1.7 | 2.5 | 9.65
12 | SW 6 (230x1185) | CUM | 2 | 0.5 | 0.23 | 1.185 | 2.5 | 7.075
13 | SW 7 (230x1855) | CUM | 1 | 0.5 | 0.23 | 1.855 | 2.5 | 5.2125
14 | SW 8 (230x3600) | CUM | 1 | 1 | 0.23 | 3.6 | 2.5 | 19.15
15 | SW 9 (L-SHAPE) | CUM | 3 | 0.5 | 0.23 | 0.65 | 2.5 | 6.6
16 |  | CUM | 3 | 0.5 | 0.23 | 1.62 | 2.5 | 13.875
17 | SW 10 (230x3445) | CUM | 1 | 0.5 | 0.23 | 3.445 | 2.5 | 9.1875
18 | SW 11 (230x4065) | CUM | 1 | 0.5 | 0.23 | 4.065 | 2.5 | 10.7375
19 | SW 12 (L-SHAPE) | CUM | 1 | 0.5 | 0.23 | 0.65 | 2.5 | 2.2
20 |  | CUM | 1 | 0.5 | 0.23 | 1.305 | 2.5 | 3.8375
21 | SW 13 (200x3445) | CUM | 1 | 0.5 | 0.2 | 3.445 | 2.5 | 9.1125
[7 empty] | TOTAL | 246.825

## BRICK WORK SUMMARY
TOWER-E BRICK WORK SUMMARY
|  |  | QTY | [5 empty] | TOTAL
5 | MASONARY WORK |  | 3rd RA | 4th RA | 5th RA | 6th RA | 7th RA | 8th RA
(Quoted Rates are for all heights, all depths, all levels, including basement to roof (mumty) & all leads and lifts, including curved or circular including elevation masonary work) (Basic Rate of Brick @ Rs. 7/No. FOR at site without GST)
5.1. | Brick work in Sub Structure (Up to Stilt Floor level):
| Providing and laying 230mm thick brick masonry using 1st quality burnt clay FPS bricks in Sub-Structure laid in cement mortar 1:6 (1 cement : 6 coarse sand) mix, joints finished, flush/ raked to 6mm depth including scaffolding, curing complete as per specification and drawing or as directed by Project Manager. | CUM | [6 empty] | 0
5.2. | Brick work in Sub Structure (Up to Stilt Floor level):
| Providing and laying of 115 mm thick brick work with 1st quality burnt clay FPS bricks in sub-superstructure laid in cement mortar 1:4 (1 cement : 4 coarse sand) mix, joints finished, including placing hoop iron as per specification at every third course, scaffolding, curing complete in all respect as per direction of EIC. (Hoop iron shall be provided by client free of cost) (Items of RCC bands like shuttering, concrete and reinforcement to be paid in respective items). | SQM | 36.867 | 51.2765 |  |  |  |  | 88.1435
5.3. | Brick work in Super Structure (Above Stilt FLoor level)
5.3.1 | Providing and laying 230mm thick brick masonry using 1st quality burnt clay FPS bricks in Super-Structure laid in cement mortar 1:6 (1 cement : 6 coarse sand) mix, joints finished, flush/ raked to 6mm depth including scaffolding, curing complete as per specification and drawing or as directed by Project Manager.
(a) | Stilt Floor level to 7th Floor level | CUM | [6 empty] | 0
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | CUM | [6 empty] | 0
5.4. | Brick work in Super Structure (Above Stilt FLoor level)
5.4.1 | Providing and laying of 115 mm thick brick work with 1st quality burnt clay FPS bricks in Super-Superstructure laid in cement mortar 1:4 (1 cement : 4 coarse sand) mix, joints finished, including placing hoop iron as per specification at every third course, scaffolding, curing complete in all respect as per direction of EIC. (Hoop iron shall be provided by client free of cost) (Items of RCC bands like shuttering, concrete and reinforcement to be paid in respective items).
(a) | Stilt Floor level to 7th Floor level | SQM | [6 empty] | 0
(b) | 7th Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet | SQM | [6 empty] | 0
5.8. | Brick work in staircase steps:
| Providing and laying and constructing brickwork in staircase steps using 1st quality burnt clay FPS bricks in cement mortar 1:3 (1 cement : 3 coarse sand) at all heights and levels including cutting, chamfering scaffolding, curing, complete as per specification. | CUM | [6 empty] | 0
[8 empty] | TOTAL | 88.1435

## BRICK WORK MB
COMPANY- OMAXE PANCHAM REALCON PVT LTD
PROJECT- TOWER-E
LOCATION- NAINI, PRAYAGRAJ
MB SHEET- BRICK WORK BELOW PLINTH BEAM
S.NO. | DESCRIPTION | UNIT | NOS | NOS | MEASUREMENT |  |  | QTY. | REMARKS
[5 empty] | L | B | H/T
RAFT OUTTER 115MM BRICK WORK
1 | GRID (22'-26'/M') | SQM | 1 | 1 | 11.005 |  | 0.3 | 3.3015 |  | 3rd RA
2 | GRID (26/M'-Q) | SQM | 1 | 1 | 12.415 |  | 0.3 | 3.7245
3 | GRID (26'-43'/Q') | SQM | 1 | 1 | 26.92 |  | 0.3 | 8.076
4 | GRID (43'/E'-Q') | SQM | 1 | 1 | 21.65 |  | 0.3 | 6.495
5 | GRID (38'-43'/E') | SQM | 1 | 1 | 11.09 |  | 0.3 | 3.327
6 | GRID (38'/A-E') | SQM | 1 | 1 | 10.285 |  | 0.3 | 3.0855
7 | GRID (30-38'/A) | SQM | 1 | 1 | 8.875 |  | 0.3 | 2.6625
8 | GRID (30/A-A') | SQM | 1 | 1 | 1.5 |  | 0.3 | 0.45
9 | GRID (27'-30/A') | SQM | 1 | 1 | 3.95 |  | 0.3 | 1.185
10 | GRID (27'/A'-B) | SQM | 1 | 1 | 0.815 |  | 0.3 | 0.2445
11 | GRID (26'-27'/B) | SQM | 1 | 1 | 1.695 |  | 0.3 | 0.5085
12 | GRID (26'/B-B') | SQM | 1 | 1 | 1.405 |  | 0.3 | 0.4215
13 | GRID (22'-26'/B') | SQM | 1 | 1 | 11.285 |  | 0.3 | 3.3855
[7 empty] | TOTAL | 36.867
RAFT OUTTER 115MM BRICK WORK
1 | GRID (17'-22'/M') | SQM | 1 | 1 | 15.175 |  | 0.3 | 4.5525 |  | 4th RA
2 | GRID (17'/M'-Q) | SQM | 1 | 1 | 12.415 |  | 0.3 | 3.7245
3 | GRID (1-17'/Q') | SQM | 1 | 1 | 26.92 |  | 0.3 | 8.076
4 | GRID (1/E'-Q') | SQM | 1 | 1 | 21.65 |  | 0.85 | 18.4025
5 | GRID (1-5'/E') | SQM | 1 | 1 | 11.09 |  | 0.3 | 3.327
6 | GRID (5'/A-E') | SQM | 1 | 1 | 10.285 |  | 0.3 | 3.0855
7 | GRID (5'-14'/A) | SQM | 1 | 1 | 8.875 |  | 0.3 | 2.6625
8 | GRID (14'/A-A') | SQM | 1 | 1 | 1.5 |  | 0.3 | 0.45
9 | GRID (14'-16'/A') | SQM | 1 | 1 | 3.95 |  | 0.3 | 1.185
10 | GRID (16'/A'-B) | SQM | 1 | 1 | 0.815 |  | 0.3 | 0.2445
11 | GRID (16'-17'/B) | SQM | 1 | 1 | 1.695 |  | 0.3 | 0.5085
12 | GRID (17'/B-B') | SQM | 1 | 1 | 1.405 |  | 0.3 | 0.4215
13 | GRID (17'-22'/B') | SQM | 1 | 1 | 15.455 |  | 0.3 | 4.6365
[7 empty] | TOTAL | 51.2765

## TMT STEEL RECO.
MARCO ENTERPRISES
TOWER-E
Reconcialation of TMT Steel
S.NO. | Description | Unit | Dia wise | [6 empty] | Total
|  |  | 6mm | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm
A | Total Steel Received upto date | Kg | 0 | 33604 | 22710 | 25185 | 101293 | 56377 | 21974 | 261143
B | Consumption Detail
4.1.1 | Up To Stilt Floor Lvl. | Kg | 0 | 5122.9778 | 9115.7643 | 5609.2314 | 60025.5493 | 34914.6313 | 17380.4443 | 132168.5983
4.1.2 | Stilt Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet) | Kg | 0 | 4818.3996 | 6767.1141 | 2814.1651 | 5637.993 | 4369.6488 | 1422.96 | 25830.2805
4.1.3 | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level | Kg | 0 | 36.1504 | 0 | 0 | 0 | 0 | 0 | 36.1504
C | Total consumption |  | 0 | 9977.5278 | 15882.8784 | 8423.3964 | 65663.5423 | 39284.2801 | 18803.4043 | 158035.0293
D | Theoretical Balance | Kg | 0 | 23626.4722 | 6827.1216 | 16761.6036 | 35629.4577 | 17092.7199 | 3170.5957 | 103107.9707
E | Steel available at yard | Kg |  | 15800 | 3500 | 14000 | 32000 | 15500 | 2500 | 83300
F | Dowel Steel in column | Kg |  | 3250 | 2758.388 | 2100 | 2950 | 1462.5684 | 400 | 12920.9564
| W.I.P. Steel in stirupps | Kg |  | 3500 | 1000 |  |  |  |  | 4500
0
G | Total In Progress | Kg | 0 | 6750 | 3758.388 | 2100 | 2950 | 1462.5684 | 400 | 17420.9564
H | Wastage (D-E-G) | Kg | 0 | 1076.4722 | -431.2663 | 661.6036 | 679.4577 | 130.1515 | 270.5957 | 2387.0143 | 1.51%
| SCRAP SALE | [8 empty] | 0
| Allowed Wastage 2.5% | Kg | [7 empty] | 3950.8757

## TMT STEEL REC.
(OMAXE TOWER-E, PRAYAGRAJ )
TMT STEEL BAR ISSUE BY OMAXE
S.NO. | DATE | Unit | 6mm Dia. | 8mm Dia. | 10mm Dia. | 12mm Dia. | 16mm Dia. | 20mm Dia. | 25mm Dia. | TOTAL | COMULAT.
1 | RECEIVED FROM OMAXE AT 19/4/25 | KG |  |  |  | 7700 | 37621 | 9370 | 5474 | 60165 | 60165
2 | RECEIVED FROM OMAXE AT 13/5/25 | KG |  | 9070 | 6840 |  |  | 20010 |  | 35920 | 96085
3 | RECEIVED FROM OMAXE AT 17/5/25 | KG |  |  |  |  | 29850 |  | 9850 | 39700 | 135785
4 | RECEIVED FROM OMAXE AT 03/6/25 | KG |  |  |  | 3766 |  | 6282 | 3148 | 13196 | 148981
5 | RECEIVED FROM OMAXE AT 03/6/25 | KG | [5 empty] | 4800 |  | 4800 | 153781
6 | RECEIVED FROM OMAXE AT 29/6/25 | KG |  |  | 6101 |  | 10573 | 2344 |  | 19018 | 172799
7 | TRANSFER FROM LIG AT 5/8/25 | KG |  |  |  | 1505 | 1738 | 898 |  | 4141 | 176940
8 | TRANSFER TO LIG AT 7/8/25 | KG |  |  | -1419 |  |  |  |  | -1419 | 175521
9 | RECEIVED FROM OMAXE AT 7/8/25 | KG |  | 2874 | 2860 |  |  |  |  | 5734 | 181255
10 | RECEIVED FROM OMAXE AT 22/8/25 | KG |  | 26488 | 12498 | 3334 |  |  |  | 42320 | 223575
11 | GIVE TO OMAXE AT 21/9/25 | KG |  | -2730 | -3520 |  |  |  |  | -6250 | 217325
12 | GIVE TO OMAXE AT 08/10/25 | KG |  | -5620 | [5 empty] | -5620 | 211705
13 | RECEIVED FROM OMAXE AT 17/10/25 | KG |  |  |  |  | 14269 | 1506 | 3502 | 19277 | 230982
14 | RECEIVED FROM OMAXE AT 10/12/25 | KG |  | 5472 |  |  | 12742 |  |  | 18214 | 249196
15 | RECEIVED FROM OMAXE AT 13/12/25 | KG |  |  |  | 8880 |  | 11167 |  | 20047 | 269243
16 | TRANSFER TO LIG AT 14/12/25 | KG |  | -1950 | -650 |  | -5500 |  |  | -8100 | 261143
| TOTAL QTY. |  | 0 | 33604 | 22710 | 25185 | 101293 | 56377 | 21974 | 261143 | KG

## TMT SUMMARY
(OMAXE TOWER-E, PRAYAGRAJ )
STEEL CONSUMPTION SUMMARY
S.NO. | DESCRIPTION | LOCATION | Unit | NOS | 6mm Dia. | 8mm Dia. | 10mm Dia. | 12mm Dia. | 16mm Dia. | 20mm Dia. | 25mm Dia. | TOTAL
4.1 TMT REINFORCEMENT
4.1.1. | UPTO STILT FLOOR LVL
1 | TOWER-E COLUMN GRID (22-23/A-Q) | UPTO RAFT | KG | 1 |  | 0 | 752.9215 | 352.9001 | 875.3642 | 698.3468 | 76.6199 | 2756.1525
2 | TOWER-E RAFT GRID (22-23/A-Q) | AS SUB-STRUCTURE | KG | 1 |  | 0 | 574.2481 | 1139.0793 | 24893.957 | 15376.0061 | 8483.9735 | 50467.264
3 | TOWER-E COLUMN GRID (1-22/A-Q) | UPTO RAFT | KG | 1 |  | 0 | 752.9215 | 352.9001 | 875.3642 | 698.3468 | 76.6199 | 2756.1525
4 | TOWER-E RAFT GRID (1-22/A-Q) | AS SUB-STRUCTURE | KG | 1 |  | 0 | 574.2481 | 1152.783 | 25482.9494 | 15753.7631 | 8483.9735 | 51447.717
5 | TOWER-E PADESTIAL GRID (1-43/A-Q) | AS SUB-STRUCTURE | KG | 1 |  | 1630.8341 | 6329.7327 | 1135.8728 | 2996.767 | 2240.6669 | 259.2576 | 14593.1311
6 | COMPENSATORY STRIP GRID (22-23/B'-L') | AS SUB-STRUCTURE | KG | 1 |  | 0 | 0 | 0 | 139.849 | 0 | 0 | 139.849
7 | PLINTH BEAM GRID (1-43/A-Q) | AS SUB-STRUCTURE | KG | 1 |  | 3492.1437 | 131.6925 | 1475.6962 | 4761.2984 | 147.5016 | 0 | 10008.3323
[5 empty] | 0 | 5122.9778 | 9115.7643 | 5609.2314 | 60025.5493 | 34914.6313 | 17380.4443 | 132168.5983
4.1.2. | Stilt Floor level to to Terrace Including OHT, Mumty, Machine Room, Parapet)
1 | COLUMN PLINTH TO 1ST FLOOR LVL (1-43/A-Q) | AS SUPER-STRUCTURE | KG | 1 |  | 4818.3996 | 6767.1141 | 2814.1651 | 5637.993 | 4369.6488 | 1422.96 | 25830.2805
2 | [11 empty] | 0
[5 empty] | 0 | 4818.3996 | 6767.1141 | 2814.1651 | 5637.993 | 4369.6488 | 1422.96 | 25830.2805
4.1.3. | All type of Moulding, Bands, Elevation/Architectural Features as per drawing and as directed by EIC. at all level
1 | COLUMN CLIT FIXING WORK (RAFT COL., G.F.) |  | KG | 2 |  | 36.1504 | 0 | 0 | 0 | 0 | 0 | 36.1504
2 | [11 empty] | 0
[5 empty] | 0 | 36.1504 | 0 | 0 | 0 | 0 | 0 | 36.1504
158035.0293

## RAFT BBS
TOWER-E RAFT BBS
TOWER-E RAFT BBS GRID (22'-43/A-Q)
S.No. | Description | Shape of Bar in mm |  |  |  | Spacing c/c | Dia of Bar | No's of Set | No's of Bar | Actual Length | Lap | No. Of Bend | Deduction In mm | Cut Length | Total Length | TMT BAR Fe-500D or EQR | [5 empty] | Remarks
A | RAFT | [14 empty] | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm
BOTTOM MAIN BAR
1 | GRID (39'-43/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 18 | 21.55 | 1.568 | 2 | 0.064 | 22.486 | 406.316 |  |  |  | 406.316
1 | GRID (39'-43/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 17 | 21.55 | 0.784 | 2 | 0.064 | 22.486 | 383.046 |  |  |  | 383.046
2 | GRID (38'-39'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 6 | 22.065 | 1.568 | 2 | 0.064 | 23.001 | 139.574 |  |  |  | 139.574
2 | GRID (38'-39'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 5 | 22.065 | 0.784 | 2 | 0.064 | 23.001 | 115.789 |  |  |  | 115.789
3 | GRID (32'-38'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 13 | 32.35 | 2.352 | 2 | 0.064 | 33.286 | 435.07 |  |  |  | 435.07
3 | GRID (32'-38'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 12 | 32.35 | 1.568 | 2 | 0.064 | 33.286 | 401 |  |  |  | 401
4 | GRID (30'-32'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 6 | 31.835 | 2.352 | 2 | 0.064 | 32.771 | 198.978 |  |  |  | 198.978
4 | GRID (30'-32'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 5 | 31.835 | 1.568 | 2 | 0.064 | 32.771 | 165.423 |  |  |  | 165.423
5 | GRID (27'-30/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 9 | 30.35 | 2.352 | 2 | 0.064 | 31.286 | 283.926 |  |  |  | 283.926
5 | GRID (27'-30/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 8 | 30.35 | 1.568 | 2 | 0.064 | 31.286 | 251.856 |  |  |  | 251.856
6 | GRID (26'-27'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 4 | 29.535 | 2.352 | 2 | 0.064 | 30.471 | 124.236 |  |  |  | 124.236
6 | GRID (26'-27'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 3 | 29.535 | 1.568 | 2 | 0.064 | 30.471 | 92.981 |  |  |  | 92.981
7 | GRID (22'-26'/B-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 15.7 |  | 0.5 | 0.25 | 16 | 1 | 46 | 15.7 | 0.784 | 2 | 0.064 | 16.636 | 766.04 |  |  |  | 766.04
BOTTOM DISTRIBUTION BAR
1 | GRID (30-38'/A)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.775 |  | 0.5 | 0.25 | 16 | 1 | 7 | 8.775 | 0 | 2 | 0.064 | 9.711 | 67.977 |  |  |  | 67.977
2 | GRID (27'-38'/A-B)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 12.725 |  | 0.5 | 0.25 | 16 | 1 | 4 | 12.725 | 0.784 | 2 | 0.064 | 13.661 | 55.428 |  |  |  | 55.428
3 | GRID (26'-38'/B-B')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 14.42 |  | 0.5 | 0.25 | 16 | 1 | 7 | 14.42 | 0.784 | 2 | 0.064 | 15.356 | 108.276 |  |  |  | 108.276
4 | GRID (22'-38'/B'-E')
| DIST. BAR BOTTOM (ALTH.) |  | 25.755 |  | 0.5 | 0.25 | 16 | 1 | 27 | 25.755 | 1.568 | 1 | 0.016 | 26.239 | 710.021 |  |  |  | 710.021
5 | GRID (22'-43'/E'-K)
| DIST. BAR BOTTOM (ALTH.) |  | 36.84 |  | 0.5 | 0.25 | 16 | 1 | 30 | 36.84 | 2.352 | 1 | 0.016 | 37.324 | 1122.072 |  |  |  | 1122.072
6 | GRID (26'-43'/M-Q)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 25.79 |  | 0.5 | 0.25 | 16 | 1 | 51 | 25.79 | 1.568 | 2 | 0.064 | 26.726 | 1364.594 |  |  |  | 1364.594
7 | GRID (33-39/Q')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.68 |  | 0.5 | 0.25 | 16 | 1 | 3 | 8.68 | 0 | 2 | 0.064 | 9.616 | 28.848 |  |  |  | 28.848
TOP MAIN BAR
1 | GRID (39'-43/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 19 | 21.55 | 1.568 | 2 | 0.064 | 22.486 | 428.802 |  |  |  | 428.802
1 | GRID (39'-43/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 18 | 21.55 | 0.784 | 2 | 0.064 | 22.486 | 405.532 |  |  |  | 405.532
2 | GRID (38'-39'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 6 | 22.065 | 1.568 | 2 | 0.064 | 23.001 | 139.574 |  |  |  | 139.574
2 | GRID (38'-39'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 5 | 22.065 | 0.784 | 2 | 0.064 | 23.001 | 115.789 |  |  |  | 115.789
3 | GRID (32'-38'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 13 | 32.35 | 2.352 | 2 | 0.064 | 33.286 | 435.07 |  |  |  | 435.07
3 | GRID (32'-38'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 12 | 32.35 | 1.568 | 2 | 0.064 | 33.286 | 401 |  |  |  | 401
4 | GRID (30'-32'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 6 | 31.835 | 2.352 | 2 | 0.064 | 32.771 | 198.978 |  |  |  | 198.978
4 | GRID (30'-32'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 5 | 31.835 | 1.568 | 2 | 0.064 | 32.771 | 165.423 |  |  |  | 165.423
5 | GRID (27'-30/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 9 | 30.35 | 2.352 | 2 | 0.064 | 31.286 | 283.926 |  |  |  | 283.926
5 | GRID (27'-30/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 8 | 30.35 | 1.568 | 2 | 0.064 | 31.286 | 251.856 |  |  |  | 251.856
6 | GRID (26'-27'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 4 | 29.535 | 2.352 | 2 | 0.064 | 30.471 | 124.236 |  |  |  | 124.236
6 | GRID (26'-27'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 3 | 29.535 | 1.568 | 2 | 0.064 | 30.471 | 92.981 |  |  |  | 92.981
7 | GRID (22'-26'/B-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 15.7 |  | 0.5 | 0.25 | 16 | 1 | 46 | 15.7 | 0.784 | 2 | 0.064 | 16.636 | 766.04 |  |  |  | 766.04
TOP DISTRIBUTION BAR
1 | GRID (30-38'/A)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.775 |  | 0.5 | 0.25 | 16 | 1 | 7 | 8.775 | 0 | 2 | 0.064 | 9.711 | 67.977 |  |  |  | 67.977
2 | GRID (27'-38'/A-B)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 12.725 |  | 0.5 | 0.25 | 16 | 1 | 4 | 12.725 | 0.784 | 2 | 0.064 | 13.661 | 55.428 |  |  |  | 55.428
3 | GRID (26'-38'/B-B')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 14.42 |  | 0.5 | 0.25 | 16 | 1 | 7 | 14.42 | 0.784 | 2 | 0.064 | 15.356 | 108.276 |  |  |  | 108.276
4 | GRID (22'-38'/B'-E')
| DIST. BAR BOTTOM (ALTH.) |  | 25.755 |  | 0.5 | 0.25 | 16 | 1 | 27 | 25.755 | 1.568 | 1 | 0.016 | 26.239 | 710.021 |  |  |  | 710.021
5 | GRID (22'-43'/E'-K)
| DIST. BAR BOTTOM (ALTH.) |  | 36.84 |  | 0.5 | 0.25 | 16 | 1 | 30 | 36.84 | 2.352 | 1 | 0.016 | 37.324 | 1122.072 |  |  |  | 1122.072
6 | GRID (26'-43'/M-Q)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 25.79 |  | 0.5 | 0.25 | 16 | 1 | 51 | 25.79 | 1.568 | 2 | 0.064 | 26.726 | 1364.594 |  |  |  | 1364.594
7 | GRID (33-39/Q')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.68 |  | 0.5 | 0.25 | 16 | 1 | 3 | 8.68 | 0 | 2 | 0.064 | 9.616 | 28.848 |  |  |  | 28.848
BINDER
1 | GRID (38'/A-E') |  | 10.285 |  |  | 0.25 | 12 | 1 | 2 | 10.285 | 0 |  | 0 | 10.285 | 20.57 |  |  | 20.57
2 | GRID (38'-43/E') |  | 11.09 |  |  | 0.25 | 12 | 1 | 2 | 11.09 | 0 |  | 0 | 11.09 | 22.18 |  |  | 22.18
3 | GRID (43/E'-Q') |  | 21.55 |  |  | 0.25 | 12 | 1 | 2 | 21.55 | 0.588 |  | 0 | 21.55 | 44.276 |  |  | 44.276
5 | GRID (30-38'/A) |  | 8.775 |  |  | 0.25 | 12 | 1 | 2 | 8.775 | 0 |  | 0 | 8.775 | 17.55 |  |  | 17.55
6 | GRID (30/A-B) |  | 1.5 |  |  | 0.25 | 12 | 1 | 2 | 1.5 | 0 |  | 0 | 1.5 | 3 |  |  | 3
7 | GRID (27'-30/A-B) |  | 3.95 |  |  | 0.25 | 12 | 1 | 2 | 3.95 | 0 |  | 0 | 3.95 | 7.9 |  |  | 7.9
8 | GRID (27'/A-B) |  | 0.815 |  |  | 0.25 | 12 | 1 | 2 | 0.815 | 0 |  | 0 | 0.815 | 1.63 |  |  | 1.63
9 | GRID (26'-27'/B) |  | 1.695 |  |  | 0.25 | 12 | 1 | 2 | 1.695 | 0 |  | 0 | 1.695 | 3.39 |  |  | 3.39
10 | GRID (26'/B-C) |  | 1.405 |  |  | 0.25 | 12 | 1 | 2 | 1.405 | 0 |  | 0 | 1.405 | 2.81 |  |  | 2.81
11 | GRID ( 22'-26'/B') |  | 11.285 |  |  | 0.25 | 12 | 1 | 2 | 11.285 | 0 |  | 0 | 11.285 | 22.57 |  |  | 22.57
12 | GRID ( 22'-26'/M') |  | 11.005 |  |  | 0.25 | 12 | 1 | 2 | 11.005 | 0 |  | 0 | 11.005 | 22.01 |  |  | 22.01
13 | GRID (26/M'-Q') |  | 12.415 |  |  | 0.25 | 12 | 1 | 2 | 12.415 | 0.588 |  | 0 | 12.415 | 25.418 |  |  | 25.418
14 | GRID (26-43'/Q') |  | 25.79 |  |  | 0.25 | 12 | 1 | 2 | 25.79 | 0.588 |  | 0 | 25.79 | 52.168 |  |  | 52.168
| CHAIR |  |  | 0.95
1 | [6 empty] | 20 | 1 | 785 | 3 | 0 |  | 0 | 3 | 2355 |  |  |  |  | 2355
0.675
0.35
BOTTOM EXTRA BAR
1 | MAIN BOTTOM EXTRA BAR |  | 3.35 |  |  | 0.25 | 20 | 1 | 9 | 3.35 | 0 | 0 | 0 | 3.35 | 30.15 |  |  |  |  | 30.15
SW1 GRID (38/A-B)
2 | DIST. BOTTOM EXTRA BAR |  | 1.95 |  |  | 0.25 | 12 | 1 | 14 | 1.95 | 0 | 0 | 0 | 1.95 | 27.3 |  |  | 27.3
SW1 GRID (38/A-B)
3 | MAIN BOTTOM EXTRA BAR |  | 2.55 |  |  | 0.25 | 25 | 1 | 10 | 2.55 | 0 | 0 | 0 | 2.55 | 25.5 | [5 empty] | 25.5
C1 GRID (34-35/A)
4 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 11 | 2.3 | 0 | 0 | 0 | 2.3 | 25.3 |  |  |  |  | 25.3
C1 GRID (34-35/A)
5 | MAIN BOTTOM EXTRA BAR |  | 2 |  |  | 0.25 | 20 | 1 | 10 | 2 | 0 | 0 | 0 | 2 | 20 |  |  |  |  | 20
C1 GRID (32/A)
6 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 9 | 2.3 | 0 | 0 | 0 | 2.3 | 20.7 |  |  |  |  | 20.7
C1 GRID (32/A)
7 | MAIN BOTTOM EXTRA BAR |  | 3.55 |  |  | 0.25 | 20 | 1 | 11 | 3.55 | 0 | 0 | 0 | 3.55 | 39.05 |  |  |  |  | 39.05
SW2, C7 GRID (27,28/B-C)
7 | MAIN BOTTOM EXTRA BAR |  | 2.5 |  |  | 0.25 | 25 | 1 | 8 | 2.5 | 0 | 0 | 0 | 2.5 | 20 | [5 empty] | 20
SW2, C7 GRID (27,28/B-C)
8 | DIST. BOTTOM EXTRA BAR |  | 2.35 |  |  | 0.25 | 25 | 1 | 4 | 2.35 | 0 | 0 | 0 | 2.35 | 9.4 | [5 empty] | 9.4
SW2, C7 GRID (27,28/B-C)
9 | DIST. BOTTOM EXTRA BAR |  | 4.095 |  |  | 0.25 | 25 | 1 | 12 | 4.095 | 0 | 0 | 0 | 4.095 | 49.14 | [5 empty] | 49.14
SW2, C7 GRID (27,28/B-C)
10 | MAIN BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C1 GRID (32/C)
11 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (32/C)
12 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 11 | 2.25 | 0 | 0 | 0 | 2.25 | 24.75 | [5 empty] | 24.75
C2 GRID ( 25/C)
13 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C2 GRID (25/C)
14 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 13 | 2.25 | 0 | 0 | 0 | 2.25 | 29.25 | [5 empty] | 29.25
C3 GRID (23/C)
15 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C3 GRID (23/C)
16 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 9 | 2.3 | 0 | 0 | 0 | 2.3 | 20.7 |  |  |  |  | 20.7
C1 GRID (38/D)
17 | DIST. BOTTOM EXTRA BAR |  | 1.9 |  |  | 0.25 | 12 | 1 | 10 | 1.9 | 0 | 0 | 0 | 1.9 | 19 |  |  | 19
C1 GRID (38/D)
18 | MAIN BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C2 GRID (35/D)
19 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 11 | 2.3 | 0 | 0 | 0 | 2.3 | 25.3 |  |  |  |  | 25.3
C2 GRID (35/D)
20 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (28/D)
21 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C1 GRID (28/D)
22 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (26/D)
23 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C1 GRID (26/D)
24 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C6 GRID (37/E)
25 | DIST. BOTTOM EXTRA BAR |  | 2.715 |  |  | 0.25 | 20 | 1 | 10 | 2.715 | 0 | 0 | 0 | 2.715 | 27.15 |  |  |  |  | 27.15
C6 GRID (37/E)
26 | MAIN BOTTOM EXTRA BAR |  | 3.935 |  |  | 0.25 | 20 | 1 | 17 | 3.935 | 0 | 0 | 0 | 3.935 | 66.895 |  |  |  |  | 66.895
SW4, SW3 GRID (32,33/E)
27 | DIST. BOTTOM EXTRA BAR |  | 4.06 |  |  | 0.25 | 20 | 1 | 17 | 4.06 | 0 | 0 | 0 | 4.06 | 69.02 |  |  |  |  | 69.02
SW4, SW3 GRID (32,33/E)
28 | MAIN BOTTOM EXTRA BAR |  | 1.83 |  |  | 0.25 | 16 | 1 | 14 | 1.83 | 0 | 0 | 0 | 1.83 | 25.62 |  |  |  | 25.62
SW6 GRID (28/E)
29 | DIST. BOTTOM EXTRA BAR |  | 3.185 |  |  | 0.25 | 20 | 1 | 8 | 3.185 | 0 | 0 | 0 | 3.185 | 25.48 |  |  |  |  | 25.48
SW6 GRID ( 28/E)
30 | MAIN BOTTOM EXTRA BAR |  | 2.2 |  |  | 0.25 | 20 | 1 | 12 | 2.2 | 0 | 0 | 0 | 2.2 | 26.4 |  |  |  |  | 26.4
C2 GRID (26/E)
31 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (26/E)
32 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 11 | 2.8 | 0 | 0 | 0 | 2.8 | 30.8 | [5 empty] | 30.8
C2 GRID (25/D-E)
33 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 12 | 2.6 | 0 | 0 | 0 | 2.6 | 31.2 |  |  |  |  | 31.2
C2 GRID (25/D-E)
34 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C8 GRID (23/D-E)
35 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C8 GRID (23/D-E)
36 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/F, J)
37 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/F, J)
38 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 25 | 2.6 | 0 | 0 | 0 | 2.6 | 65 |  |  |  |  | 65
SW9, C1 GRID (43/F, J)
39 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C2 GRID (41/F)
40 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (41/F)
41 | MAIN BOTTOM EXTRA BAR |  | 1.835 |  |  | 0.25 | 20 | 1 | 10 | 1.835 | 0 | 0 | 0 | 1.835 | 18.35 |  |  |  |  | 18.35
C6 GRID (39/F)
42 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 8 | 2.3 | 0 | 0 | 0 | 2.3 | 18.4 |  |  |  |  | 18.4
C6 GRID (39/F)
43 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C5 GRID (37/H)
44 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 14 | 2.8 | 0 | 0 | 0 | 2.8 | 39.2 | [5 empty] | 39.2
C5 GRID (37/H)
45 | MAIN BOTTOM EXTRA BAR |  | 2.73 |  |  | 0.25 | 25 | 1 | 16 | 2.73 | 0 | 0 | 0 | 2.73 | 43.68 | [5 empty] | 43.68
SW5 GRID (34/F)
46 | DIST. BOTTOM EXTRA BAR |  | 3.7 |  |  | 0.25 | 20 | 1 | 12 | 3.7 | 0 | 0 | 0 | 3.7 | 44.4 |  |  |  |  | 44.4
SW5 GRID (34/F)
47 | MAIN BOTTOM EXTRA BAR |  | 2.23 |  |  | 0.25 | 20 | 1 | 16 | 2.23 | 0 | 0 | 0 | 2.23 | 35.68 |  |  |  |  | 35.68
SW5 GRID (29/F)
48 | DIST. BOTTOM EXTRA BAR |  | 3.7 |  |  | 0.25 | 20 | 1 | 10 | 3.7 | 0 | 0 | 0 | 3.7 | 37 |  |  |  |  | 37
SW5 GRID (29/F)
49 | MAIN BOTTOM EXTRA BAR |  | 5.6 |  |  | 0.25 | 20 | 1 | 20 | 5.6 | 0 | 0 | 0 | 5.6 | 112 |  |  |  |  | 112
C1, SW7 GRID (24/E,G,H)
50 | DIST. BOTTOM EXTRA BAR |  | 4.725 |  |  | 0.25 | 25 | 1 | 23 | 4.725 | 0 | 0 | 0 | 4.725 | 108.675 | [5 empty] | 108.675
C1, SW7 GRID (24/E,G,H)
51 | MAIN BOTTOM EXTRA BAR |  | 6.1 |  |  | 0.25 | 25 | 1 | 12 | 6.1 | 0 | 0 | 0 | 6.1 | 73.2 | [5 empty] | 73.2
SW8 GRID (22/G)
52 | DIST. BOTTOM EXTRA BAR |  | 2.73 |  |  | 0.25 | 25 | 1 | 25 | 2.73 | 0 | 0 | 0 | 2.73 | 68.25 | [5 empty] | 68.25
SW8 GRID (22/G)
53 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 25 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 | [5 empty] | 33
C4 GRID (41/J)
54 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (41/J)
55 | DIST. BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 25 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 | [5 empty] | 33
C4 GRID (41/J)
56 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (41/J)
57 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C5 GRID (39/J)
58 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (39/J)
59 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (35/J)
60 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (35/J)
61 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (35/J)
62 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (29/J)
63 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (29/J)
64 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (29/J)
65 | MAIN BOTTOM EXTRA BAR |  | 1.83 |  |  | 0.25 | 16 | 1 | 14 | 1.83 | 0 | 0 | 0 | 1.83 | 25.62 |  |  |  | 25.62
SW6 GRID (28/I)
66 | DIST. BOTTOM EXTRA BAR |  | 3.185 |  |  | 0.25 | 20 | 1 | 8 | 3.185 | 0 | 0 | 0 | 3.185 | 25.48 |  |  |  |  | 25.48
SW6 GRID (28/I)
67 | MAIN BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 12 | 2.6 | 0 | 0 | 0 | 2.6 | 31.2 |  |  |  |  | 31.2
C2 GRID (26/I)
68 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 11 | 2.8 | 0 | 0 | 0 | 2.8 | 30.8 | [5 empty] | 30.8
C2 GRID (26/I)
69 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 11 | 2.8 | 0 | 0 | 0 | 2.8 | 30.8 |  |  |  |  | 30.8
C2 GRID (25/J)
70 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 25 | 1 | 12 | 2.6 | 0 | 0 | 0 | 2.6 | 31.2 | [5 empty] | 31.2
C2 GRID (25/J)
71 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C8 GRID (23/J)
72 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C8 GRID (23/J)
73 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 11 | 2.3 | 0 | 0 | 0 | 2.3 | 25.3 |  |  |  |  | 25.3
C1 GRID (28/J-K)
74 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C1 GRID (28/J-K)
75 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C1 GRID (26/D)
76 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C1 GRID ( 26/D)
77 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 11 | 2.25 | 0 | 0 | 0 | 2.25 | 24.75 | [5 empty] | 24.75
C2 GRID (25/L)
78 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C2 GRID (25/L)
79 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 13 | 2.25 | 0 | 0 | 0 | 2.25 | 29.25 | [5 empty] | 29.25
C3 GRID (23/L)
80 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C3 GRID (23/L)
81 | MAIN BOTTOM EXTRA BAR |  | 3.65 |  |  | 0.25 | 20 | 1 | 17 | 3.65 | 0 | 0 | 0 | 3.65 | 62.05 |  |  |  |  | 62.05
SW12, C7 GRID (27,28/M-N)
82 | DIST. BOTTOM EXTRA BAR |  | 4.345 |  |  | 0.25 | 20 | 1 | 15 | 4.345 | 0 | 0 | 0 | 4.345 | 65.175 |  |  |  |  | 65.175
SW12, C7 GRID (27,28/M-N)
83 | MAIN BOTTOM EXTRA BAR |  | 1.915 |  |  | 0.25 | 12 | 1 | 7 | 1.915 | 0 | 0 | 0 | 1.915 | 13.405 |  |  | 13.405
C6 GRID (43/M)
84 | DIST. BOTTOM EXTRA BAR |  | 1.6 |  |  | 0.25 | 12 | 1 | 9 | 1.6 | 0 | 0 | 0 | 1.6 | 14.4 |  |  | 14.4
C6 GRID (43/M)
85 | MAIN BOTTOM EXTRA BAR |  | 1.915 |  |  | 0.25 | 12 | 1 | 7 | 1.915 | 0 | 0 | 0 | 1.915 | 13.405 |  |  | 13.405
C6 GRID (43/O)
86 | DIST. BOTTOM EXTRA BAR |  | 1.6 |  |  | 0.25 | 12 | 1 | 9 | 1.6 | 0 | 0 | 0 | 1.6 | 14.4 |  |  | 14.4
C6 GRID (43/O)
87 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 25 | 1 | 10 | 2.3 | 0 | 0 | 0 | 2.3 | 23 | [5 empty] | 23
C1 GRID (42/M)
88 | DIST. BOTTOM EXTRA BAR |  | 2.2 |  |  | 0.25 | 16 | 1 | 10 | 2.2 | 0 | 0 | 0 | 2.2 | 22 |  |  |  | 22
C1 GRID (42/M)
89 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 25 | 1 | 10 | 2.3 | 0 | 0 | 0 | 2.3 | 23 | [5 empty] | 23
C1 GRID (42/O)
90 | DIST. BOTTOM EXTRA BAR |  | 2.2 |  |  | 0.25 | 16 | 1 | 10 | 2.2 | 0 | 0 | 0 | 2.2 | 22 |  |  |  | 22
C1 GRID (42/O)
91 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C4 GRID (39/M)
92 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 14 | 2.8 | 0 | 0 | 0 | 2.8 | 39.2 | [5 empty] | 39.2
C4 GRID (39/M)
91 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C4 GRID (39/O)
92 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 14 | 2.8 | 0 | 0 | 0 | 2.8 | 39.2 |  |  |  |  | 39.2
C4 GRID (39/O)
93 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (39/O)
94 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C2 GRID (38/N)
95 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C2 GRID (38/N)
96 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 8 | 2.75 | 0 | 0 | 0 | 2.75 | 22 |  |  |  |  | 22
C5 GRID (37/L)
97 | DIST. BOTTOM EXTRA BAR |  | 1.85 |  |  | 0.25 | 20 | 1 | 12 | 1.85 | 0 | 0 | 0 | 1.85 | 22.2 |  |  |  |  | 22.2
C5 GRID (37/L)
98 | DIST. BOTTOM EXTRA BAR |  | 1.85 |  |  | 0.25 | 20 | 1 | 8 | 1.85 | 0 | 0 | 0 | 1.85 | 14.8 |  |  |  |  | 14.8
C5 GRID (37/L)
99 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C4 GRID (37/O)
100 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C4 GRID (37/O)
101 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 10 | 2.75 | 0 | 0 | 0 | 2.75 | 27.5 |  |  |  |  | 27.5
C5 GRID (32/O)
102 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C5 GRID (32/O)
103 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C5 GRID (32/O)
104 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (29/O)
105 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 20 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 |  |  |  |  | 31
C1 GRID (29/O)
106 | MAIN BOTTOM EXTRA BAR |  | 1.915 |  |  | 0.25 | 12 | 1 | 9 | 1.915 | 0 | 0 | 0 | 1.915 | 17.235 |  |  | 17.235
C6 GRID (27/O)
107 | DIST. BOTTOM EXTRA BAR |  | 2 |  |  | 0.25 | 20 | 1 | 9 | 2 | 0 | 0 | 0 | 2 | 18 |  |  |  |  | 18
C6 GRID (27/O)
108 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/P, Q)
109 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/P, Q)
110 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 25 | 2.6 | 0 | 0 | 0 | 2.6 | 65 |  |  |  |  | 65
SW9, C1 GRID (43/P, Q)
111 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 20 | 1 | 10 | 5.96 | 0 | 0 | 0 | 5.96 | 59.6 |  |  |  |  | 59.6
SW9, C1 GRID (27/P, Q)
112 | DIST. BOTTOM EXTRA BAR |  | 2.35 |  |  | 0.25 | 20 | 1 | 25 | 2.35 | 0 | 0 | 0 | 2.35 | 58.75 |  |  |  |  | 58.75
SW9, C1 GRID (27/P, Q)
113 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C2 GRID (41/Q)
114 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (41/Q)
115 | MAIN BOTTOM EXTRA BAR |  | 2.415 |  |  | 0.25 | 20 | 1 | 10 | 2.415 | 0 | 0 | 0 | 2.415 | 24.15 |  |  |  |  | 24.15
C6 GRID (39/Q)
116 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 8 | 2.3 | 0 | 0 | 0 | 2.3 | 18.4 |  |  |  |  | 18.4
C6 GRID (39/Q)
117 | MAIN BOTTOM EXTRA BAR |  | 2.415 |  |  | 0.25 | 20 | 1 | 10 | 2.415 | 0 | 0 | 0 | 2.415 | 24.15 |  |  |  |  | 24.15
C6 GRID (34/Q)
118 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 8 | 2.3 | 0 | 0 | 0 | 2.3 | 18.4 |  |  |  |  | 18.4
C6 GRID (34/Q)
119 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C2 GRID (30/Q)
120 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (30/Q)
121 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C5 GRID (37/P-Q)
122 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (37/P-Q)
123 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 25 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 | [5 empty] | 33
C4 GRID (41/P)
124 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (41/P)
125 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (41/P)
126 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (41/P)
127 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C5 GRID (39/P)
128 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (39/P)
129 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (30/P)
130 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (30/P)
131 | DIST. BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (30/P)
132 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C5 GRID (34/P)
133 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (34/P)
134 | MAIN BOTTOM EXTRA BAR |  | 5.145 |  |  | 0.25 | 20 | 1 | 26 | 5.145 | 0 | 0 | 0 | 5.145 | 133.77 |  |  |  |  | 133.77
SW10, SW11, SW13 GRID (31-36/K-N)
135 | DIST. BOTTOM EXTRA BAR |  | 6.165 |  |  | 0.25 | 20 | 1 | 22 | 6.165 | 0 | 0 | 0 | 6.165 | 135.63 |  |  |  |  | 135.63
SW10, SW11, SW13 GRID (31-36/K-N)
136 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (29/J)
137 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (25/J)
138 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (41/J)
139 | SPACER B/W EXTRA BAR |  | 2.8 |  |  |  | 20 | 1 | 3 | 2.8 | 0 | 0 | 0 | 2.8 | 8.4 |  |  |  |  | 8.4
C4 GRID (41/J)
140 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C5 GRID (37/L)
141 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C5 GRID (32/O)
142 | SPACER B/W EXTRA BAR |  | 3.25 |  |  |  | 20 | 1 | 3 | 3.25 | 0 | 0 | 0 | 3.25 | 9.75 |  |  |  |  | 9.75
C4 GRID (40/O)
143 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (29/P)
144 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (41/P)
145 | SPACER B/W EXTRA BAR |  | 2.8 |  |  |  | 20 | 1 | 3 | 2.8 | 0 | 0 | 0 | 2.8 | 8.4 |  |  |  |  | 8.4
C4 GRID (41/P)
146 | SPACER B/W EXTRA BAR |  | 6.165 |  |  |  | 20 | 1 | 4 | 6.165 | 0 | 0 | 0 | 6.165 | 24.66 |  |  |  |  | 24.66
SW10, SW11, SW13 GRID (31-36/K-N)
TOP EXTRA BAR
1 | MAIN TOP EXTRA BAR |  | 2.425 |  |  | 0.25 | 20 | 1 | 23 | 2.425 | 0 | 0 | 0 | 2.425 | 55.775 |  |  |  |  | 55.775
GRID (35-37/A-D)
2 | DIST. TOP EXTRA BAR |  | 3.95 |  |  | 0.25 | 16 | 1 | 11 | 3.95 | 0 | 0 | 0 | 3.95 | 43.45 |  |  |  | 43.45
GRID (35-37/A-D)
3 | MAIN TOP EXTRA BAR |  | 2.2 |  |  | 0.25 | 10 | 1 | 31 | 2.2 | 0 | 0 | 0 | 2.2 | 68.2 |  | 68.2
GRID (32-35/A-D)
4 | DIST. TOP EXTRA BAR |  | 6.165 |  |  | 0.25 | 16 | 1 | 10 | 6.165 | 0 | 0 | 0 | 6.165 | 61.65 |  |  |  | 61.65
GRID (32-35/A-D)
5 | MAIN TOP EXTRA BAR |  | 4.52 |  |  | 0.25 | 12 | 1 | 13 | 4.52 | 0 | 0 | 0 | 4.52 | 58.76 |  |  | 58.76
GRID (28-31/B-E)
6 | MAIN TOP EXTRA BAR |  | 2.275 |  |  | 0.25 | 10 | 1 | 22 | 2.275 | 0 | 0 | 0 | 2.275 | 50.05 |  | 50.05
GRID (26-28/B-E)
7 | DIST. TOP EXTRA BAR |  | 5.355 |  |  | 0.25 | 12 | 1 | 10 | 5.355 | 0 | 0 | 0 | 5.355 | 53.55 |  |  | 53.55
GRID (26-28/B-E)
8 | MAIN TOP EXTRA BAR |  | 2.45 |  |  | 0.25 | 12 | 1 | 10 | 2.45 | 0 | 0 | 0 | 2.45 | 24.5 |  |  | 24.5
GRID (25-26/B-E)
9 | MAIN TOP EXTRA BAR |  | 4.09 |  |  | 0.25 | 12 | 1 | 24 | 4.09 | 0 | 0 | 0 | 4.09 | 98.16 |  |  | 98.16
GRID (24-26/B-E)
10 | DIST. TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 10 | 1 | 17 | 3.8 | 0 | 0 | 0 | 3.8 | 64.6 |  | 64.6
GRID (24-26/B-E)
11 | MAIN TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 10 | 1 | 24 | 3.8 | 0 | 0 | 0 | 3.8 | 91.2 |  | 91.2
GRID (21-23 /B-E)
12 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 20 | 1 | 24 | 5.7 | 0 | 0 | 0 | 5.7 | 136.8 |  |  |  |  | 136.8
GRID (21-23 /B-E)
13 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 16 | 1 | 10 | 5.7 | 0 | 0 | 0 | 5.7 | 57 |  |  |  | 57
GRID (21-23 /B-E)
14 | MAIN TOP EXTRA BAR |  | 2.515 |  |  | 0.25 | 12 | 1 | 17 | 2.515 | 0 | 0 | 0 | 2.515 | 42.755 |  |  | 42.755
GRID (34-36 /D-F)
15 | MAIN TOP EXTRA BAR |  | 4.19 |  |  | 0.25 | 12 | 1 | 11 | 4.19 | 0 | 0 | 0 | 4.19 | 46.09 |  |  | 46.09
GRID (41-43 /E-I)
16 | MAIN TOP EXTRA BAR |  | 7.71 |  |  | 0.25 | 12 | 1 | 12 | 7.71 | 0 | 0 | 0 | 7.71 | 92.52 |  |  | 92.52
GRID (40-42 /E-K)
17 | MAIN TOP EXTRA BAR |  | 2.785 |  |  | 0.25 | 12 | 1 | 11 | 2.785 | 0 | 0 | 0 | 2.785 | 30.635 |  |  | 30.635
GRID (41-42 /E-I)
18 | DIST. TOP EXTRA BAR |  | 2.615 |  |  | 0.25 | 20 | 1 | 12 | 2.615 | 0 | 0 | 0 | 2.615 | 31.38 |  |  |  |  | 31.38
GRID (41-42 /E-I)
19 | MAIN TOP EXTRA BAR |  | 4.12 |  |  | 0.25 | 20 | 1 | 34 | 4.12 | 0 | 0 | 0 | 4.12 | 140.08 |  |  |  |  | 140.08
GRID (41-42 /E-L)
20 | DIST. TOP EXTRA BAR |  | 3.12 |  |  | 0.25 | 20 | 1 | 14 | 3.12 | 0 | 0 | 0 | 3.12 | 43.68 |  |  |  |  | 43.68
GRID (40-42 /J-L)
21 | DIST. TOP EXTRA BAR |  | 2.92 |  |  | 0.25 | 16 | 1 | 23 | 2.92 | 0 | 0 | 0 | 2.92 | 67.16 |  |  |  | 67.16
GRID (40-42 /J-L)
22 | MAIN TOP EXTRA BAR |  | 4.545 |  |  | 0.25 | 16 | 1 | 21 | 4.545 | 0 | 0 | 0 | 4.545 | 95.445 |  |  |  | 95.445
GRID (34-38 /H-K)
23 | DIST. TOP EXTRA BAR |  | 5 |  |  | 0.25 | 16 | 1 | 19 | 5 | 0 | 0 | 0 | 5 | 95 |  |  |  | 95
GRID (34-38 /H-K)
24 | MAIN TOP EXTRA BAR |  | 5.24 |  |  | 0.25 | 16 | 1 | 21 | 5.24 | 0 | 0 | 0 | 5.24 | 110.04 |  |  |  | 110.04
GRID (28-33 /H-K)
25 | DIST. TOP EXTRA BAR |  | 2.54 |  |  | 0.25 | 12 | 1 | 18 | 2.54 | 0 | 0 | 0 | 2.54 | 45.72 |  |  | 45.72
GRID (25-28 /E-I)
26 | DIST. TOP EXTRA BAR |  | 4.375 |  |  | 0.25 | 10 | 1 | 12 | 4.375 | 0 | 0 | 0 | 4.375 | 52.5 |  | 52.5
GRID (25-28 /I-K)
27 | DIST. TOP EXTRA BAR |  | 3.64 |  |  | 0.25 | 10 | 1 | 64 | 3.64 | 0 | 0 | 0 | 3.64 | 232.96 |  | 232.96
GRID (24-25 /B-M)
28 | DIST. TOP EXTRA BAR |  | 2.45 |  |  | 0.25 | 10 | 1 | 10 | 2.45 | 0 | 0 | 0 | 2.45 | 24.5 |  | 24.5
GRID (24-25 /J-K)
29 | DIST. TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 10 | 1 | 17 | 3.8 | 0 | 0 | 0 | 3.8 | 64.6 |  | 64.6
GRID (22-24 /J-M)
30 | MAIN TOP EXTRA BAR |  | 6.4 |  |  | 0.25 | 10 | 1 | 23 | 6.4 | 0 | 0 | 0 | 6.4 | 147.2 |  | 147.2
GRID (22-24 /E-J)
31 | DIST. TOP EXTRA BAR |  | 5.53 |  |  | 0.25 | 16 | 1 | 27 | 5.53 | 0 | 0 | 0 | 5.53 | 149.31 |  |  |  | 149.31
GRID (22-24 /E-J)
32 | MAIN TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 12 | 1 | 24 | 3.8 | 0 | 0 | 0 | 3.8 | 91.2 |  |  | 91.2
GRID (21-23 /I-M)
33 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 20 | 1 | 24 | 5.7 | 0 | 0 | 0 | 5.7 | 136.8 |  |  |  |  | 136.8
GRID (21-23 /I-M)
34 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 16 | 1 | 10 | 5.7 | 0 | 0 | 0 | 5.7 | 57 |  |  |  | 57
GRID (21-23 /I-M)
35 | MAIN TOP EXTRA BAR |  | 5.745 |  |  | 0.25 | 16 | 1 | 15 | 5.745 | 0 | 0 | 0 | 5.745 | 86.175 |  |  |  | 86.175
GRID (40-43/M-O)
36 | DIST. TOP EXTRA BAR |  | 2.5 |  |  | 0.25 | 20 | 1 | 14 | 2.5 | 0 | 0 | 0 | 2.5 | 35 |  |  |  |  | 35
GRID (40-43 /M-O)
37 | DIST. TOP EXTRA BAR |  | 3.46 |  |  | 0.25 | 20 | 1 | 24 | 3.46 | 0 | 0 | 0 | 3.46 | 83.04 |  |  |  |  | 83.04
GRID (40-43 /M-O)
38 | MAIN TOP EXTRA BAR |  | 3.045 |  |  | 0.25 | 20 | 1 | 19 | 3.045 | 0 | 0 | 0 | 3.045 | 57.855 |  |  |  |  | 57.855
GRID (37-40 /K-N)
39 | DIST. TOP EXTRA BAR |  | 4.525 |  |  | 0.25 | 16 | 1 | 13 | 4.525 | 0 | 0 | 0 | 4.525 | 58.825 |  |  |  | 58.825
GRID (37-40 /K-N)
40 | MAIN TOP EXTRA BAR |  | 3.12 |  |  | 0.25 | 20 | 1 | 14 | 3.12 | 0 | 0 | 0 | 3.12 | 43.68 |  |  |  |  | 43.68
GRID (40-43 /O-Q)
41 | MAIN TOP EXTRA BAR |  | 2.85 |  |  | 0.25 | 16 | 1 | 23 | 2.85 | 0 | 0 | 0 | 2.85 | 65.55 |  |  |  | 65.55
GRID (40-43 /O-Q)
42 | DIST. TOP EXTRA BAR |  | 4.12 |  |  | 0.25 | 20 | 1 | 34 | 4.12 | 0 | 0 | 0 | 4.12 | 140.08 |  |  |  |  | 140.08
GRID (40-43 /O-Q)
43 | DIST. TOP EXTRA BAR |  | 4.19 |  |  | 0.25 | 12 | 1 | 11 | 4.19 | 0 | 0 | 0 | 4.19 | 46.09 |  |  | 46.09
GRID (40-43 /O-Q)
44 | DIST. TOP EXTRA BAR |  | 7.68 |  |  | 0.25 | 12 | 1 | 12 | 7.68 | 0 | 0 | 0 | 7.68 | 92.16 |  |  | 92.16
GRID (40-43 /O-Q)
45 | DIST. TOP EXTRA BAR |  | 3.915 |  |  | 0.25 | 20 | 1 | 19 | 3.915 | 0 | 0 | 0 | 3.915 | 74.385 |  |  |  |  | 74.385
GRID (36-39 /N-P)
46 | DIST. TOP EXTRA BAR |  | 4.5 |  |  | 0.25 | 16 | 1 | 17 | 4.5 | 0 | 0 | 0 | 4.5 | 76.5 |  |  |  | 76.5
GRID (36-39 /N-P)
47 | DIST. TOP EXTRA BAR |  | 4.55 |  |  | 0.25 | 10 | 1 | 19 | 4.55 | 0 | 0 | 0 | 4.55 | 86.45 |  | 86.45
GRID (31-36 /O-P)
48 | MAIN TOP EXTRA BAR |  | 3.975 |  |  | 0.25 | 25 | 1 | 25 | 3.975 | 0 | 0 | 0 | 3.975 | 99.375 | [5 empty] | 99.375
GRID (33-38 /O'-P')
49 | DIST. TOP EXTRA BAR |  | 6.08 |  |  | 0.25 | 16 | 1 | 17 | 6.08 | 0 | 0 | 0 | 6.08 | 103.36 |  |  |  | 103.36
GRID (33-38 /O'-P')
50 | MAIN TOP EXTRA BAR |  | 1.95 |  |  | 0.25 | 12 | 1 | 25 | 1.95 | 0 | 0 | 0 | 1.95 | 48.75 |  |  | 48.75
GRID (33-38 /P'-Q)
51 | DIST. TOP EXTRA BAR |  | 6.08 |  |  | 0.25 | 12 | 1 | 9 | 6.08 | 0 | 0 | 0 | 6.08 | 54.72 |  |  | 54.72
GRID (33-38 /P'-Q)
52 | DIST. TOP EXTRA BAR |  | 7.71 |  |  | 0.25 | 12 | 1 | 12 | 7.71 | 0 | 0 | 0 | 7.71 | 92.52 |  |  | 92.52
GRID (29-32 /O-Q)
53 | MAIN TOP EXTRA BAR |  | 2.85 |  |  | 0.25 | 10 | 1 | 17 | 2.85 | 0 | 0 | 0 | 2.85 | 48.45 |  | 48.45
GRID (26-29 /O-Q)
54 | DIST. TOP EXTRA BAR |  | 5.47 |  |  | 0.25 | 20 | 1 | 34 | 5.47 | 0 | 0 | 0 | 5.47 | 185.98 |  |  |  |  | 185.98
GRID (26-29 /O-Q)
55 | DIST. TOP EXTRA BAR |  | 4.19 |  |  | 0.25 | 16 | 1 | 11 | 4.19 | 0 | 0 | 0 | 4.19 | 46.09 |  |  |  | 46.09
GRID (26-29 /O-Q)
| TOTAL LENGTH IN METRE | [14 empty] | 0 | 930.71 | 1282.747 | 15755.669 | 6227.625 | 2199.06
| UNIT WEIGHT (IN KG) | [14 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.469 | 3.858
| TOTAL WEIGHT (IN KG) | [14 empty] | 0 | 574.2481 | 1139.0793 | 24893.957 | 15376.0061 | 8483.9735 | 50467.264 | KG
TOWER-E RAFT BBS GRID (1-22'/A-Q)
S.No. | Description | Shape of Bar in mm |  |  |  | Spacing c/c | Dia of Bar | No's of Set | No's of Bar | Actual Length | Lap | No. Of Bend | Deduction In mm | Cut Length | Total Length | TMT BAR Fe-500D or EQR | [5 empty] | Remarks
A | RAFT | [14 empty] | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm
BOTTOM MAIN BAR
1 | GRID (1-4'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 18 | 21.55 | 1.568 | 2 | 0.064 | 22.486 | 406.316 |  |  |  | 406.316
1 | GRID (1-4'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 17 | 21.55 | 0.784 | 2 | 0.064 | 22.486 | 383.046 |  |  |  | 383.046
2 | GRID (4'-5'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 6 | 22.065 | 1.568 | 2 | 0.064 | 23.001 | 139.574 |  |  |  | 139.574
2 | GRID (4'-5'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 5 | 22.065 | 0.784 | 2 | 0.064 | 23.001 | 115.789 |  |  |  | 115.789
3 | GRID (5'-11'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 13 | 32.35 | 2.352 | 2 | 0.064 | 33.286 | 435.07 |  |  |  | 435.07
3 | GRID (5'-11'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 12 | 32.35 | 1.568 | 2 | 0.064 | 33.286 | 401 |  |  |  | 401
4 | GRID (11'-14'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 6 | 31.835 | 2.352 | 2 | 0.064 | 32.771 | 198.978 |  |  |  | 198.978
4 | GRID (11'-14'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 5 | 31.835 | 1.568 | 2 | 0.064 | 32.771 | 165.423 |  |  |  | 165.423
5 | GRID (14-16'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 9 | 30.35 | 2.352 | 2 | 0.064 | 31.286 | 283.926 |  |  |  | 283.926
5 | GRID (14-16'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 8 | 30.35 | 1.568 | 2 | 0.064 | 31.286 | 251.856 |  |  |  | 251.856
6 | GRID (16'-17'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 4 | 29.535 | 2.352 | 2 | 0.064 | 30.471 | 124.236 |  |  |  | 124.236
6 | GRID (16'-17'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 3 | 29.535 | 1.568 | 2 | 0.064 | 30.471 | 92.981 |  |  |  | 92.981
7 | GRID (1-22'/B-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 15.7 |  | 0.5 | 0.25 | 16 | 1 | 46 | 15.7 | 0.784 | 2 | 0.064 | 16.636 | 766.04 |  |  |  | 766.04
BOTTOM DISTRIBUTION BAR
1 | GRID (5'-14/A)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.775 |  | 0.5 | 0.25 | 16 | 1 | 7 | 8.775 | 0 | 2 | 0.064 | 9.711 | 67.977 |  |  |  | 67.977
2 | GRID (5'-16'/A-B)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 12.725 |  | 0.5 | 0.25 | 16 | 1 | 4 | 12.725 | 0.784 | 2 | 0.064 | 13.661 | 55.428 |  |  |  | 55.428
3 | GRID (5'-17'/B-B')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 14.42 |  | 0.5 | 0.25 | 16 | 1 | 7 | 14.42 | 0.784 | 2 | 0.064 | 15.356 | 108.276 |  |  |  | 108.276
4 | GRID (5'-22'/B'-E')
| DIST. BAR BOTTOM (ALTH.) |  | 29.025 |  | 0.5 | 0.25 | 16 | 1 | 27 | 29.025 | 1.568 | 1 | 0.016 | 29.509 | 798.311 |  |  |  | 798.311
5 | GRID (1-22'/E'-K)
| DIST. BAR BOTTOM (ALTH.) |  | 40.11 |  | 0.5 | 0.25 | 16 | 1 | 30 | 40.11 | 2.352 | 1 | 0.016 | 40.594 | 1220.172 |  |  |  | 1220.172
6 | GRID (1-17'/M-Q)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 25.79 |  | 0.5 | 0.25 | 16 | 1 | 51 | 25.79 | 1.568 | 2 | 0.064 | 26.726 | 1364.594 |  |  |  | 1364.594
7 | GRID (4'-11'/Q')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.68 |  | 0.5 | 0.25 | 16 | 1 | 3 | 8.68 | 0 | 2 | 0.064 | 9.616 | 28.848 |  |  |  | 28.848
TOP MAIN BAR
1 | GRID (1-4'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 19 | 21.55 | 1.568 | 2 | 0.064 | 22.486 | 428.802 |  |  |  | 428.802
1 | GRID (1-4'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 21.55 |  | 0.5 | 0.25 | 16 | 1 | 18 | 21.55 | 0.784 | 2 | 0.064 | 22.486 | 405.532 |  |  |  | 405.532
2 | GRID (4'-5'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 6 | 22.065 | 1.568 | 2 | 0.064 | 23.001 | 139.574 |  |  |  | 139.574
2 | GRID (4'-5'/E'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 22.065 |  | 0.5 | 0.25 | 16 | 1 | 5 | 22.065 | 0.784 | 2 | 0.064 | 23.001 | 115.789 |  |  |  | 115.789
3 | GRID (5'-11'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 13 | 32.35 | 2.352 | 2 | 0.064 | 33.286 | 435.07 |  |  |  | 435.07
3 | GRID (5'-11'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 32.35 |  | 0.5 | 0.25 | 16 | 1 | 12 | 32.35 | 1.568 | 2 | 0.064 | 33.286 | 401 |  |  |  | 401
4 | GRID (11'-14'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 6 | 31.835 | 2.352 | 2 | 0.064 | 32.771 | 198.978 |  |  |  | 198.978
4 | GRID (11'-14'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 31.835 |  | 0.5 | 0.25 | 16 | 1 | 5 | 31.835 | 1.568 | 2 | 0.064 | 32.771 | 165.423 |  |  |  | 165.423
5 | GRID (14-16'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 9 | 30.35 | 2.352 | 2 | 0.064 | 31.286 | 283.926 |  |  |  | 283.926
5 | GRID (14-16'/A-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 30.35 |  | 0.5 | 0.25 | 16 | 1 | 8 | 30.35 | 1.568 | 2 | 0.064 | 31.286 | 251.856 |  |  |  | 251.856
6 | GRID (16'-17'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 4 | 29.535 | 2.352 | 2 | 0.064 | 30.471 | 124.236 |  |  |  | 124.236
6 | GRID (16'-17'/A'-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 29.535 |  | 0.5 | 0.25 | 16 | 1 | 3 | 29.535 | 1.568 | 2 | 0.064 | 30.471 | 92.981 |  |  |  | 92.981
7 | GRID (1-22'/B-Q')
| MAIN BAR BOTTOM (ALTH.) | 0.5 | 15.7 |  | 0.5 | 0.25 | 16 | 1 | 46 | 15.7 | 0.784 | 2 | 0.064 | 16.636 | 766.04 |  |  |  | 766.04
TOP DISTRIBUTION BAR
1 | GRID (5'-14/A)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.775 |  | 0.5 | 0.25 | 16 | 1 | 7 | 8.775 | 0 | 2 | 0.064 | 9.711 | 67.977 |  |  |  | 67.977
2 | GRID (5'-16'/A-B)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 12.725 |  | 0.5 | 0.25 | 16 | 1 | 4 | 12.725 | 0.784 | 2 | 0.064 | 13.661 | 55.428 |  |  |  | 55.428
3 | GRID (5'-17'/B-B')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 14.42 |  | 0.5 | 0.25 | 16 | 1 | 7 | 14.42 | 0.784 | 2 | 0.064 | 15.356 | 108.276 |  |  |  | 108.276
4 | GRID (5'-22'/B'-E')
| DIST. BAR BOTTOM (ALTH.) |  | 29.025 |  | 0.5 | 0.25 | 16 | 1 | 27 | 29.025 | 1.568 | 1 | 0.016 | 29.509 | 798.311 |  |  |  | 798.311
5 | GRID (1-22'/E'-K)
| DIST. BAR BOTTOM (ALTH.) |  | 40.11 |  | 0.5 | 0.25 | 16 | 1 | 30 | 40.11 | 2.352 | 1 | 0.016 | 40.594 | 1220.172 |  |  |  | 1220.172
6 | GRID (1-17'/M-Q)
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 25.79 |  | 0.5 | 0.25 | 16 | 1 | 51 | 25.79 | 1.568 | 2 | 0.064 | 26.726 | 1364.594 |  |  |  | 1364.594
7 | GRID (4'-11'/Q')
| DIST. BAR BOTTOM (ALTH.) | 0.5 | 8.68 |  | 0.5 | 0.25 | 16 | 1 | 3 | 8.68 | 0 | 2 | 0.064 | 9.616 | 28.848 |  |  |  | 28.848
BINDER
1 | GRID (5'/A-E') |  | 10.285 |  |  | 0.25 | 12 | 1 | 2 | 10.285 | 0 |  | 0 | 10.285 | 20.57 |  |  | 20.57
2 | GRID (5'-1/E') |  | 11.09 |  |  | 0.25 | 12 | 1 | 2 | 11.09 | 0 |  | 0 | 11.09 | 22.18 |  |  | 22.18
3 | GRID (1/E'-Q') |  | 21.55 |  |  | 0.25 | 12 | 1 | 2 | 21.55 | 0.588 |  | 0 | 21.55 | 44.276 |  |  | 44.276
5 | GRID (5'-14/A) |  | 8.775 |  |  | 0.25 | 12 | 1 | 2 | 8.775 | 0 |  | 0 | 8.775 | 17.55 |  |  | 17.55
6 | GRID (14/A-B) |  | 1.5 |  |  | 0.25 | 12 | 1 | 2 | 1.5 | 0 |  | 0 | 1.5 | 3 |  |  | 3
7 | GRID (14-16'/A-B) |  | 3.95 |  |  | 0.25 | 12 | 1 | 2 | 3.95 | 0 |  | 0 | 3.95 | 7.9 |  |  | 7.9
8 | GRID (16'/A-B) |  | 0.815 |  |  | 0.25 | 12 | 1 | 2 | 0.815 | 0 |  | 0 | 0.815 | 1.63 |  |  | 1.63
9 | GRID (16'-17'/B) |  | 1.695 |  |  | 0.25 | 12 | 1 | 2 | 1.695 | 0 |  | 0 | 1.695 | 3.39 |  |  | 3.39
10 | GRID (17'/B-C) |  | 1.405 |  |  | 0.25 | 12 | 1 | 2 | 1.405 | 0 |  | 0 | 1.405 | 2.81 |  |  | 2.81
11 | GRID ( 17'-22'/B') |  | 14.555 |  |  | 0.25 | 12 | 1 | 2 | 14.555 | 0.588 |  | 0 | 14.555 | 30.286 |  |  | 30.286
12 | GRID ( 17'-22'/M') |  | 14.275 |  |  | 0.25 | 12 | 1 | 2 | 14.275 | 0.588 |  | 0 | 14.275 | 29.726 |  |  | 29.726
13 | GRID (18/M'-Q') |  | 12.415 |  |  | 0.25 | 12 | 1 | 2 | 12.415 | 0.588 |  | 0 | 12.415 | 25.418 |  |  | 25.418
14 | GRID (1-17'/Q') |  | 25.79 |  |  | 0.25 | 12 | 1 | 2 | 25.79 | 0.588 |  | 0 | 25.79 | 52.168 |  |  | 52.168
| CHAIR |  |  | 0.95
1 | [6 empty] | 20 | 1 | 836 | 3 | 0 |  | 0 | 3 | 2508 |  |  |  |  | 2508
0.675
0.35
BOTTOM EXTRA BAR
1 | MAIN BOTTOM EXTRA BAR |  | 3.35 |  |  | 0.25 | 20 | 1 | 9 | 3.35 | 0 | 0 | 0 | 3.35 | 30.15 |  |  |  |  | 30.15
SW1 GRID (38/A-B)
2 | DIST. BOTTOM EXTRA BAR |  | 1.95 |  |  | 0.25 | 12 | 1 | 14 | 1.95 | 0 | 0 | 0 | 1.95 | 27.3 |  |  | 27.3
SW1 GRID (38/A-B)
3 | MAIN BOTTOM EXTRA BAR |  | 2.55 |  |  | 0.25 | 25 | 1 | 10 | 2.55 | 0 | 0 | 0 | 2.55 | 25.5 | [5 empty] | 25.5
C1 GRID (34-35/A)
4 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 11 | 2.3 | 0 | 0 | 0 | 2.3 | 25.3 |  |  |  |  | 25.3
C1 GRID (34-35/A)
5 | MAIN BOTTOM EXTRA BAR |  | 2 |  |  | 0.25 | 20 | 1 | 10 | 2 | 0 | 0 | 0 | 2 | 20 |  |  |  |  | 20
C1 GRID (32/A)
6 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 9 | 2.3 | 0 | 0 | 0 | 2.3 | 20.7 |  |  |  |  | 20.7
C1 GRID (32/A)
7 | MAIN BOTTOM EXTRA BAR |  | 3.55 |  |  | 0.25 | 20 | 1 | 11 | 3.55 | 0 | 0 | 0 | 3.55 | 39.05 |  |  |  |  | 39.05
SW2, C7 GRID (27,28/B-C)
7 | MAIN BOTTOM EXTRA BAR |  | 2.5 |  |  | 0.25 | 25 | 1 | 8 | 2.5 | 0 | 0 | 0 | 2.5 | 20 | [5 empty] | 20
SW2, C7 GRID (27,28/B-C)
8 | DIST. BOTTOM EXTRA BAR |  | 2.35 |  |  | 0.25 | 25 | 1 | 4 | 2.35 | 0 | 0 | 0 | 2.35 | 9.4 | [5 empty] | 9.4
SW2, C7 GRID (27,28/B-C)
9 | DIST. BOTTOM EXTRA BAR |  | 4.095 |  |  | 0.25 | 25 | 1 | 12 | 4.095 | 0 | 0 | 0 | 4.095 | 49.14 | [5 empty] | 49.14
SW2, C7 GRID (27,28/B-C)
10 | MAIN BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C1 GRID (32/C)
11 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (32/C)
12 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 11 | 2.25 | 0 | 0 | 0 | 2.25 | 24.75 | [5 empty] | 24.75
C2 GRID ( 25/C)
13 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C2 GRID (25/C)
14 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 13 | 2.25 | 0 | 0 | 0 | 2.25 | 29.25 | [5 empty] | 29.25
C3 GRID (23/C)
15 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C3 GRID (23/C)
16 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 9 | 2.3 | 0 | 0 | 0 | 2.3 | 20.7 |  |  |  |  | 20.7
C1 GRID (38/D)
17 | DIST. BOTTOM EXTRA BAR |  | 1.9 |  |  | 0.25 | 12 | 1 | 10 | 1.9 | 0 | 0 | 0 | 1.9 | 19 |  |  | 19
C1 GRID (38/D)
18 | MAIN BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C2 GRID (35/D)
19 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 11 | 2.3 | 0 | 0 | 0 | 2.3 | 25.3 |  |  |  |  | 25.3
C2 GRID (35/D)
20 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (28/D)
21 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C1 GRID (28/D)
22 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (26/D)
23 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C1 GRID (26/D)
24 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C6 GRID (37/E)
25 | DIST. BOTTOM EXTRA BAR |  | 2.715 |  |  | 0.25 | 20 | 1 | 10 | 2.715 | 0 | 0 | 0 | 2.715 | 27.15 |  |  |  |  | 27.15
C6 GRID (37/E)
26 | MAIN BOTTOM EXTRA BAR |  | 3.935 |  |  | 0.25 | 20 | 1 | 17 | 3.935 | 0 | 0 | 0 | 3.935 | 66.895 |  |  |  |  | 66.895
SW4, SW3 GRID (32,33/E)
27 | DIST. BOTTOM EXTRA BAR |  | 4.06 |  |  | 0.25 | 20 | 1 | 17 | 4.06 | 0 | 0 | 0 | 4.06 | 69.02 |  |  |  |  | 69.02
SW4, SW3 GRID (32,33/E)
28 | MAIN BOTTOM EXTRA BAR |  | 1.83 |  |  | 0.25 | 16 | 1 | 14 | 1.83 | 0 | 0 | 0 | 1.83 | 25.62 |  |  |  | 25.62
SW6 GRID (28/E)
29 | DIST. BOTTOM EXTRA BAR |  | 3.185 |  |  | 0.25 | 20 | 1 | 8 | 3.185 | 0 | 0 | 0 | 3.185 | 25.48 |  |  |  |  | 25.48
SW6 GRID ( 28/E)
30 | MAIN BOTTOM EXTRA BAR |  | 2.2 |  |  | 0.25 | 20 | 1 | 12 | 2.2 | 0 | 0 | 0 | 2.2 | 26.4 |  |  |  |  | 26.4
C2 GRID (26/E)
31 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (26/E)
32 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 11 | 2.8 | 0 | 0 | 0 | 2.8 | 30.8 | [5 empty] | 30.8
C2 GRID (25/D-E)
33 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 12 | 2.6 | 0 | 0 | 0 | 2.6 | 31.2 |  |  |  |  | 31.2
C2 GRID (25/D-E)
34 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C8 GRID (23/D-E)
35 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C8 GRID (23/D-E)
36 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/F, J)
37 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/F, J)
38 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 25 | 2.6 | 0 | 0 | 0 | 2.6 | 65 |  |  |  |  | 65
SW9, C1 GRID (43/F, J)
39 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C2 GRID (41/F)
40 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (41/F)
41 | MAIN BOTTOM EXTRA BAR |  | 1.835 |  |  | 0.25 | 20 | 1 | 10 | 1.835 | 0 | 0 | 0 | 1.835 | 18.35 |  |  |  |  | 18.35
C6 GRID (39/F)
42 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 8 | 2.3 | 0 | 0 | 0 | 2.3 | 18.4 |  |  |  |  | 18.4
C6 GRID (39/F)
43 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C5 GRID (37/H)
44 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 14 | 2.8 | 0 | 0 | 0 | 2.8 | 39.2 | [5 empty] | 39.2
C5 GRID (37/H)
45 | MAIN BOTTOM EXTRA BAR |  | 2.73 |  |  | 0.25 | 25 | 1 | 16 | 2.73 | 0 | 0 | 0 | 2.73 | 43.68 | [5 empty] | 43.68
SW5 GRID (34/F)
46 | DIST. BOTTOM EXTRA BAR |  | 3.7 |  |  | 0.25 | 20 | 1 | 12 | 3.7 | 0 | 0 | 0 | 3.7 | 44.4 |  |  |  |  | 44.4
SW5 GRID (34/F)
47 | MAIN BOTTOM EXTRA BAR |  | 2.23 |  |  | 0.25 | 20 | 1 | 16 | 2.23 | 0 | 0 | 0 | 2.23 | 35.68 |  |  |  |  | 35.68
SW5 GRID (29/F)
48 | DIST. BOTTOM EXTRA BAR |  | 3.7 |  |  | 0.25 | 20 | 1 | 10 | 3.7 | 0 | 0 | 0 | 3.7 | 37 |  |  |  |  | 37
SW5 GRID (29/F)
49 | MAIN BOTTOM EXTRA BAR |  | 5.6 |  |  | 0.25 | 20 | 1 | 20 | 5.6 | 0 | 0 | 0 | 5.6 | 112 |  |  |  |  | 112
C1, SW7 GRID (24/E,G,H)
50 | DIST. BOTTOM EXTRA BAR |  | 4.725 |  |  | 0.25 | 25 | 1 | 23 | 4.725 | 0 | 0 | 0 | 4.725 | 108.675 | [5 empty] | 108.675
C1, SW7 GRID (24/E,G,H)
51 | MAIN BOTTOM EXTRA BAR |  | 6.1 |  |  | 0.25 | 25 | 1 | 12 | 6.1 | 0 | 0 | 0 | 6.1 | 73.2 | [5 empty] | 73.2
SW8 GRID (22/G)
52 | DIST. BOTTOM EXTRA BAR |  | 2.73 |  |  | 0.25 | 25 | 1 | 25 | 2.73 | 0 | 0 | 0 | 2.73 | 68.25 | [5 empty] | 68.25
SW8 GRID (22/G)
53 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 25 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 | [5 empty] | 33
C4 GRID (41/J)
54 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (41/J)
55 | DIST. BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 25 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 | [5 empty] | 33
C4 GRID (41/J)
56 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (41/J)
57 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C5 GRID (39/J)
58 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (39/J)
59 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (35/J)
60 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (35/J)
61 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (35/J)
62 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (29/J)
63 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (29/J)
64 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (29/J)
65 | MAIN BOTTOM EXTRA BAR |  | 1.83 |  |  | 0.25 | 16 | 1 | 14 | 1.83 | 0 | 0 | 0 | 1.83 | 25.62 |  |  |  | 25.62
SW6 GRID (28/I)
66 | DIST. BOTTOM EXTRA BAR |  | 3.185 |  |  | 0.25 | 20 | 1 | 8 | 3.185 | 0 | 0 | 0 | 3.185 | 25.48 |  |  |  |  | 25.48
SW6 GRID (28/I)
67 | MAIN BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 12 | 2.6 | 0 | 0 | 0 | 2.6 | 31.2 |  |  |  |  | 31.2
C2 GRID (26/I)
68 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 11 | 2.8 | 0 | 0 | 0 | 2.8 | 30.8 | [5 empty] | 30.8
C2 GRID (26/I)
69 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 11 | 2.8 | 0 | 0 | 0 | 2.8 | 30.8 |  |  |  |  | 30.8
C2 GRID (25/J)
70 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 25 | 1 | 12 | 2.6 | 0 | 0 | 0 | 2.6 | 31.2 | [5 empty] | 31.2
C2 GRID (25/J)
71 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C8 GRID (23/J)
72 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C8 GRID (23/J)
73 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 11 | 2.3 | 0 | 0 | 0 | 2.3 | 25.3 |  |  |  |  | 25.3
C1 GRID (28/J-K)
74 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C1 GRID (28/J-K)
75 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C1 GRID (26/D)
76 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C1 GRID ( 26/D)
77 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 11 | 2.25 | 0 | 0 | 0 | 2.25 | 24.75 | [5 empty] | 24.75
C2 GRID (25/L)
78 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 10 | 2.6 | 0 | 0 | 0 | 2.6 | 26 |  |  |  |  | 26
C2 GRID (25/L)
79 | MAIN BOTTOM EXTRA BAR |  | 2.25 |  |  | 0.25 | 25 | 1 | 13 | 2.25 | 0 | 0 | 0 | 2.25 | 29.25 | [5 empty] | 29.25
C3 GRID (23/L)
80 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 | [5 empty] | 31
C3 GRID (23/L)
81 | MAIN BOTTOM EXTRA BAR |  | 3.65 |  |  | 0.25 | 20 | 1 | 17 | 3.65 | 0 | 0 | 0 | 3.65 | 62.05 |  |  |  |  | 62.05
SW12, C7 GRID (27,28/M-N)
82 | DIST. BOTTOM EXTRA BAR |  | 4.345 |  |  | 0.25 | 20 | 1 | 15 | 4.345 | 0 | 0 | 0 | 4.345 | 65.175 |  |  |  |  | 65.175
SW12, C7 GRID (27,28/M-N)
83 | MAIN BOTTOM EXTRA BAR |  | 1.915 |  |  | 0.25 | 12 | 1 | 7 | 1.915 | 0 | 0 | 0 | 1.915 | 13.405 |  |  | 13.405
C6 GRID (43/M)
84 | DIST. BOTTOM EXTRA BAR |  | 1.6 |  |  | 0.25 | 12 | 1 | 9 | 1.6 | 0 | 0 | 0 | 1.6 | 14.4 |  |  | 14.4
C6 GRID (43/M)
85 | MAIN BOTTOM EXTRA BAR |  | 1.915 |  |  | 0.25 | 12 | 1 | 7 | 1.915 | 0 | 0 | 0 | 1.915 | 13.405 |  |  | 13.405
C6 GRID (43/O)
86 | DIST. BOTTOM EXTRA BAR |  | 1.6 |  |  | 0.25 | 12 | 1 | 9 | 1.6 | 0 | 0 | 0 | 1.6 | 14.4 |  |  | 14.4
C6 GRID (43/O)
87 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 25 | 1 | 10 | 2.3 | 0 | 0 | 0 | 2.3 | 23 | [5 empty] | 23
C1 GRID (42/M)
88 | DIST. BOTTOM EXTRA BAR |  | 2.2 |  |  | 0.25 | 16 | 1 | 10 | 2.2 | 0 | 0 | 0 | 2.2 | 22 |  |  |  | 22
C1 GRID (42/M)
89 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 25 | 1 | 10 | 2.3 | 0 | 0 | 0 | 2.3 | 23 | [5 empty] | 23
C1 GRID (42/O)
90 | DIST. BOTTOM EXTRA BAR |  | 2.2 |  |  | 0.25 | 16 | 1 | 10 | 2.2 | 0 | 0 | 0 | 2.2 | 22 |  |  |  | 22
C1 GRID (42/O)
91 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C4 GRID (39/M)
92 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 14 | 2.8 | 0 | 0 | 0 | 2.8 | 39.2 | [5 empty] | 39.2
C4 GRID (39/M)
91 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C4 GRID (39/O)
92 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 14 | 2.8 | 0 | 0 | 0 | 2.8 | 39.2 |  |  |  |  | 39.2
C4 GRID (39/O)
93 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (39/O)
94 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 13 | 2.8 | 0 | 0 | 0 | 2.8 | 36.4 | [5 empty] | 36.4
C2 GRID (38/N)
95 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 25 | 1 | 12 | 3.1 | 0 | 0 | 0 | 3.1 | 37.2 | [5 empty] | 37.2
C2 GRID (38/N)
96 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 8 | 2.75 | 0 | 0 | 0 | 2.75 | 22 |  |  |  |  | 22
C5 GRID (37/L)
97 | DIST. BOTTOM EXTRA BAR |  | 1.85 |  |  | 0.25 | 20 | 1 | 12 | 1.85 | 0 | 0 | 0 | 1.85 | 22.2 |  |  |  |  | 22.2
C5 GRID (37/L)
98 | DIST. BOTTOM EXTRA BAR |  | 1.85 |  |  | 0.25 | 20 | 1 | 8 | 1.85 | 0 | 0 | 0 | 1.85 | 14.8 |  |  |  |  | 14.8
C5 GRID (37/L)
99 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C4 GRID (37/O)
100 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C4 GRID (37/O)
101 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 10 | 2.75 | 0 | 0 | 0 | 2.75 | 27.5 |  |  |  |  | 27.5
C5 GRID (32/O)
102 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C5 GRID (32/O)
103 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 12 | 2.3 | 0 | 0 | 0 | 2.3 | 27.6 |  |  |  |  | 27.6
C5 GRID (32/O)
104 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C1 GRID (29/O)
105 | DIST. BOTTOM EXTRA BAR |  | 3.1 |  |  | 0.25 | 20 | 1 | 10 | 3.1 | 0 | 0 | 0 | 3.1 | 31 |  |  |  |  | 31
C1 GRID (29/O)
106 | MAIN BOTTOM EXTRA BAR |  | 1.915 |  |  | 0.25 | 12 | 1 | 9 | 1.915 | 0 | 0 | 0 | 1.915 | 17.235 |  |  | 17.235
C6 GRID (27/O)
107 | DIST. BOTTOM EXTRA BAR |  | 2 |  |  | 0.25 | 20 | 1 | 9 | 2 | 0 | 0 | 0 | 2 | 18 |  |  |  |  | 18
C6 GRID (27/O)
108 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/P, Q)
109 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 25 | 1 | 11 | 5.96 | 0 | 0 | 0 | 5.96 | 65.56 | [5 empty] | 65.56
SW9, C1 GRID (43/P, Q)
110 | DIST. BOTTOM EXTRA BAR |  | 2.6 |  |  | 0.25 | 20 | 1 | 25 | 2.6 | 0 | 0 | 0 | 2.6 | 65 |  |  |  |  | 65
SW9, C1 GRID (43/P, Q)
111 | MAIN BOTTOM EXTRA BAR |  | 5.96 |  |  | 0.25 | 20 | 1 | 10 | 5.96 | 0 | 0 | 0 | 5.96 | 59.6 |  |  |  |  | 59.6
SW9, C1 GRID (27/P, Q)
112 | DIST. BOTTOM EXTRA BAR |  | 2.35 |  |  | 0.25 | 20 | 1 | 25 | 2.35 | 0 | 0 | 0 | 2.35 | 58.75 |  |  |  |  | 58.75
SW9, C1 GRID (27/P, Q)
113 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C2 GRID (41/Q)
114 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (41/Q)
115 | MAIN BOTTOM EXTRA BAR |  | 2.415 |  |  | 0.25 | 20 | 1 | 10 | 2.415 | 0 | 0 | 0 | 2.415 | 24.15 |  |  |  |  | 24.15
C6 GRID (39/Q)
116 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 8 | 2.3 | 0 | 0 | 0 | 2.3 | 18.4 |  |  |  |  | 18.4
C6 GRID (39/Q)
117 | MAIN BOTTOM EXTRA BAR |  | 2.415 |  |  | 0.25 | 20 | 1 | 10 | 2.415 | 0 | 0 | 0 | 2.415 | 24.15 |  |  |  |  | 24.15
C6 GRID (34/Q)
118 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 8 | 2.3 | 0 | 0 | 0 | 2.3 | 18.4 |  |  |  |  | 18.4
C6 GRID (34/Q)
119 | MAIN BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 13 | 2.3 | 0 | 0 | 0 | 2.3 | 29.9 |  |  |  |  | 29.9
C2 GRID (30/Q)
120 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 10 | 2.8 | 0 | 0 | 0 | 2.8 | 28 | [5 empty] | 28
C2 GRID (30/Q)
121 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 12 | 3.25 | 0 | 0 | 0 | 3.25 | 39 | [5 empty] | 39
C5 GRID (37/P-Q)
122 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (37/P-Q)
123 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 25 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 | [5 empty] | 33
C4 GRID (41/P)
124 | MAIN BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (41/P)
125 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (41/P)
126 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 20 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 |  |  |  |  | 33.6
C4 GRID (41/P)
127 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C5 GRID (39/P)
128 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (39/P)
129 | MAIN BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (30/P)
130 | DIST. BOTTOM EXTRA BAR |  | 2.8 |  |  | 0.25 | 25 | 1 | 12 | 2.8 | 0 | 0 | 0 | 2.8 | 33.6 | [5 empty] | 33.6
C4 GRID (30/P)
131 | DIST. BOTTOM EXTRA BAR |  | 2.75 |  |  | 0.25 | 20 | 1 | 12 | 2.75 | 0 | 0 | 0 | 2.75 | 33 |  |  |  |  | 33
C4 GRID (30/P)
132 | MAIN BOTTOM EXTRA BAR |  | 3.25 |  |  | 0.25 | 25 | 1 | 10 | 3.25 | 0 | 0 | 0 | 3.25 | 32.5 | [5 empty] | 32.5
C5 GRID (34/P)
133 | DIST. BOTTOM EXTRA BAR |  | 2.3 |  |  | 0.25 | 20 | 1 | 14 | 2.3 | 0 | 0 | 0 | 2.3 | 32.2 |  |  |  |  | 32.2
C5 GRID (34/P)
134 | MAIN BOTTOM EXTRA BAR |  | 5.145 |  |  | 0.25 | 20 | 1 | 26 | 5.145 | 0 | 0 | 0 | 5.145 | 133.77 |  |  |  |  | 133.77
SW10, SW11, SW13 GRID (31-36/K-N)
135 | DIST. BOTTOM EXTRA BAR |  | 6.165 |  |  | 0.25 | 20 | 1 | 22 | 6.165 | 0 | 0 | 0 | 6.165 | 135.63 |  |  |  |  | 135.63
SW10, SW11, SW13 GRID (31-36/K-N)
136 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (29/J)
137 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (25/J)
138 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (41/J)
139 | SPACER B/W EXTRA BAR |  | 2.8 |  |  |  | 20 | 1 | 3 | 2.8 | 0 | 0 | 0 | 2.8 | 8.4 |  |  |  |  | 8.4
C4 GRID (41/J)
140 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C5 GRID (37/L)
141 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C5 GRID (32/O)
142 | SPACER B/W EXTRA BAR |  | 3.25 |  |  |  | 20 | 1 | 3 | 3.25 | 0 | 0 | 0 | 3.25 | 9.75 |  |  |  |  | 9.75
C4 GRID (40/O)
143 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (29/P)
144 | SPACER B/W EXTRA BAR |  | 2.75 |  |  |  | 20 | 1 | 3 | 2.75 | 0 | 0 | 0 | 2.75 | 8.25 |  |  |  |  | 8.25
C4 GRID (41/P)
145 | SPACER B/W EXTRA BAR |  | 2.8 |  |  |  | 20 | 1 | 3 | 2.8 | 0 | 0 | 0 | 2.8 | 8.4 |  |  |  |  | 8.4
C4 GRID (41/P)
146 | SPACER B/W EXTRA BAR |  | 6.165 |  |  |  | 20 | 1 | 4 | 6.165 | 0 | 0 | 0 | 6.165 | 24.66 |  |  |  |  | 24.66
SW10, SW11, SW13 GRID (31-36/K-N)
TOP EXTRA BAR
1 | MAIN TOP EXTRA BAR |  | 2.425 |  |  | 0.25 | 20 | 1 | 23 | 2.425 | 0 | 0 | 0 | 2.425 | 55.775 |  |  |  |  | 55.775
GRID (35-37/A-D)
2 | DIST. TOP EXTRA BAR |  | 3.95 |  |  | 0.25 | 16 | 1 | 11 | 3.95 | 0 | 0 | 0 | 3.95 | 43.45 |  |  |  | 43.45
GRID (35-37/A-D)
3 | MAIN TOP EXTRA BAR |  | 2.2 |  |  | 0.25 | 10 | 1 | 31 | 2.2 | 0 | 0 | 0 | 2.2 | 68.2 |  | 68.2
GRID (32-35/A-D)
4 | DIST. TOP EXTRA BAR |  | 6.165 |  |  | 0.25 | 16 | 1 | 10 | 6.165 | 0 | 0 | 0 | 6.165 | 61.65 |  |  |  | 61.65
GRID (32-35/A-D)
5 | MAIN TOP EXTRA BAR |  | 4.52 |  |  | 0.25 | 12 | 1 | 13 | 4.52 | 0 | 0 | 0 | 4.52 | 58.76 |  |  | 58.76
GRID (28-31/B-E)
6 | MAIN TOP EXTRA BAR |  | 2.275 |  |  | 0.25 | 10 | 1 | 22 | 2.275 | 0 | 0 | 0 | 2.275 | 50.05 |  | 50.05
GRID (26-28/B-E)
7 | DIST. TOP EXTRA BAR |  | 5.355 |  |  | 0.25 | 12 | 1 | 10 | 5.355 | 0 | 0 | 0 | 5.355 | 53.55 |  |  | 53.55
GRID (26-28/B-E)
8 | MAIN TOP EXTRA BAR |  | 2.45 |  |  | 0.25 | 12 | 1 | 10 | 2.45 | 0 | 0 | 0 | 2.45 | 24.5 |  |  | 24.5
GRID (25-26/B-E)
9 | MAIN TOP EXTRA BAR |  | 4.09 |  |  | 0.25 | 12 | 1 | 24 | 4.09 | 0 | 0 | 0 | 4.09 | 98.16 |  |  | 98.16
GRID (24-26/B-E)
10 | DIST. TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 10 | 1 | 17 | 3.8 | 0 | 0 | 0 | 3.8 | 64.6 |  | 64.6
GRID (24-26/B-E)
11 | MAIN TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 10 | 1 | 24 | 3.8 | 0 | 0 | 0 | 3.8 | 91.2 |  | 91.2
GRID (21-23 /B-E)
12 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 20 | 1 | 24 | 5.7 | 0 | 0 | 0 | 5.7 | 136.8 |  |  |  |  | 136.8
GRID (21-23 /B-E)
13 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 16 | 1 | 10 | 5.7 | 0 | 0 | 0 | 5.7 | 57 |  |  |  | 57
GRID (21-23 /B-E)
14 | MAIN TOP EXTRA BAR |  | 2.515 |  |  | 0.25 | 12 | 1 | 17 | 2.515 | 0 | 0 | 0 | 2.515 | 42.755 |  |  | 42.755
GRID (34-36 /D-F)
15 | MAIN TOP EXTRA BAR |  | 4.19 |  |  | 0.25 | 12 | 1 | 11 | 4.19 | 0 | 0 | 0 | 4.19 | 46.09 |  |  | 46.09
GRID (41-43 /E-I)
16 | MAIN TOP EXTRA BAR |  | 7.71 |  |  | 0.25 | 12 | 1 | 12 | 7.71 | 0 | 0 | 0 | 7.71 | 92.52 |  |  | 92.52
GRID (40-42 /E-K)
17 | MAIN TOP EXTRA BAR |  | 2.785 |  |  | 0.25 | 12 | 1 | 11 | 2.785 | 0 | 0 | 0 | 2.785 | 30.635 |  |  | 30.635
GRID (41-42 /E-I)
18 | DIST. TOP EXTRA BAR |  | 2.615 |  |  | 0.25 | 20 | 1 | 12 | 2.615 | 0 | 0 | 0 | 2.615 | 31.38 |  |  |  |  | 31.38
GRID (41-42 /E-I)
19 | MAIN TOP EXTRA BAR |  | 4.12 |  |  | 0.25 | 20 | 1 | 34 | 4.12 | 0 | 0 | 0 | 4.12 | 140.08 |  |  |  |  | 140.08
GRID (41-42 /E-L)
20 | DIST. TOP EXTRA BAR |  | 3.12 |  |  | 0.25 | 20 | 1 | 14 | 3.12 | 0 | 0 | 0 | 3.12 | 43.68 |  |  |  |  | 43.68
GRID (40-42 /J-L)
21 | DIST. TOP EXTRA BAR |  | 2.92 |  |  | 0.25 | 16 | 1 | 23 | 2.92 | 0 | 0 | 0 | 2.92 | 67.16 |  |  |  | 67.16
GRID (40-42 /J-L)
22 | MAIN TOP EXTRA BAR |  | 4.545 |  |  | 0.25 | 16 | 1 | 21 | 4.545 | 0 | 0 | 0 | 4.545 | 95.445 |  |  |  | 95.445
GRID (34-38 /H-K)
23 | DIST. TOP EXTRA BAR |  | 5 |  |  | 0.25 | 16 | 1 | 19 | 5 | 0 | 0 | 0 | 5 | 95 |  |  |  | 95
GRID (34-38 /H-K)
24 | MAIN TOP EXTRA BAR |  | 5.24 |  |  | 0.25 | 16 | 1 | 21 | 5.24 | 0 | 0 | 0 | 5.24 | 110.04 |  |  |  | 110.04
GRID (28-33 /H-K)
25 | DIST. TOP EXTRA BAR |  | 2.54 |  |  | 0.25 | 12 | 1 | 18 | 2.54 | 0 | 0 | 0 | 2.54 | 45.72 |  |  | 45.72
GRID (25-28 /E-I)
26 | DIST. TOP EXTRA BAR |  | 4.375 |  |  | 0.25 | 10 | 1 | 12 | 4.375 | 0 | 0 | 0 | 4.375 | 52.5 |  | 52.5
GRID (25-28 /I-K)
27 | DIST. TOP EXTRA BAR |  | 3.64 |  |  | 0.25 | 10 | 1 | 64 | 3.64 | 0 | 0 | 0 | 3.64 | 232.96 |  | 232.96
GRID (24-25 /B-M)
28 | DIST. TOP EXTRA BAR |  | 2.45 |  |  | 0.25 | 10 | 1 | 10 | 2.45 | 0 | 0 | 0 | 2.45 | 24.5 |  | 24.5
GRID (24-25 /J-K)
29 | DIST. TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 10 | 1 | 17 | 3.8 | 0 | 0 | 0 | 3.8 | 64.6 |  | 64.6
GRID (22-24 /J-M)
30 | MAIN TOP EXTRA BAR |  | 6.4 |  |  | 0.25 | 10 | 1 | 23 | 6.4 | 0 | 0 | 0 | 6.4 | 147.2 |  | 147.2
GRID (22-24 /E-J)
31 | DIST. TOP EXTRA BAR |  | 5.53 |  |  | 0.25 | 16 | 1 | 27 | 5.53 | 0 | 0 | 0 | 5.53 | 149.31 |  |  |  | 149.31
GRID (22-24 /E-J)
32 | MAIN TOP EXTRA BAR |  | 3.8 |  |  | 0.25 | 12 | 1 | 24 | 3.8 | 0 | 0 | 0 | 3.8 | 91.2 |  |  | 91.2
GRID (21-23 /I-M)
33 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 20 | 1 | 24 | 5.7 | 0 | 0 | 0 | 5.7 | 136.8 |  |  |  |  | 136.8
GRID (21-23 /I-M)
34 | DIST. TOP EXTRA BAR |  | 5.7 |  |  | 0.25 | 16 | 1 | 10 | 5.7 | 0 | 0 | 0 | 5.7 | 57 |  |  |  | 57
GRID (21-23 /I-M)
35 | MAIN TOP EXTRA BAR |  | 5.745 |  |  | 0.25 | 16 | 1 | 15 | 5.745 | 0 | 0 | 0 | 5.745 | 86.175 |  |  |  | 86.175
GRID (40-43/M-O)
36 | DIST. TOP EXTRA BAR |  | 2.5 |  |  | 0.25 | 20 | 1 | 14 | 2.5 | 0 | 0 | 0 | 2.5 | 35 |  |  |  |  | 35
GRID (40-43 /M-O)
37 | DIST. TOP EXTRA BAR |  | 3.46 |  |  | 0.25 | 20 | 1 | 24 | 3.46 | 0 | 0 | 0 | 3.46 | 83.04 |  |  |  |  | 83.04
GRID (40-43 /M-O)
38 | MAIN TOP EXTRA BAR |  | 3.045 |  |  | 0.25 | 20 | 1 | 19 | 3.045 | 0 | 0 | 0 | 3.045 | 57.855 |  |  |  |  | 57.855
GRID (37-40 /K-N)
39 | DIST. TOP EXTRA BAR |  | 4.525 |  |  | 0.25 | 16 | 1 | 13 | 4.525 | 0 | 0 | 0 | 4.525 | 58.825 |  |  |  | 58.825
GRID (37-40 /K-N)
40 | MAIN TOP EXTRA BAR |  | 3.12 |  |  | 0.25 | 20 | 1 | 14 | 3.12 | 0 | 0 | 0 | 3.12 | 43.68 |  |  |  |  | 43.68
GRID (40-43 /O-Q)
41 | MAIN TOP EXTRA BAR |  | 2.85 |  |  | 0.25 | 16 | 1 | 23 | 2.85 | 0 | 0 | 0 | 2.85 | 65.55 |  |  |  | 65.55
GRID (40-43 /O-Q)
42 | DIST. TOP EXTRA BAR |  | 4.12 |  |  | 0.25 | 20 | 1 | 34 | 4.12 | 0 | 0 | 0 | 4.12 | 140.08 |  |  |  |  | 140.08
GRID (40-43 /O-Q)
43 | DIST. TOP EXTRA BAR |  | 4.19 |  |  | 0.25 | 12 | 1 | 11 | 4.19 | 0 | 0 | 0 | 4.19 | 46.09 |  |  | 46.09
GRID (40-43 /O-Q)
44 | DIST. TOP EXTRA BAR |  | 7.68 |  |  | 0.25 | 12 | 1 | 12 | 7.68 | 0 | 0 | 0 | 7.68 | 92.16 |  |  | 92.16
GRID (40-43 /O-Q)
45 | DIST. TOP EXTRA BAR |  | 3.915 |  |  | 0.25 | 20 | 1 | 19 | 3.915 | 0 | 0 | 0 | 3.915 | 74.385 |  |  |  |  | 74.385
GRID (36-39 /N-P)
46 | DIST. TOP EXTRA BAR |  | 4.5 |  |  | 0.25 | 16 | 1 | 17 | 4.5 | 0 | 0 | 0 | 4.5 | 76.5 |  |  |  | 76.5
GRID (36-39 /N-P)
47 | DIST. TOP EXTRA BAR |  | 4.55 |  |  | 0.25 | 10 | 1 | 19 | 4.55 | 0 | 0 | 0 | 4.55 | 86.45 |  | 86.45
GRID (31-36 /O-P)
48 | MAIN TOP EXTRA BAR |  | 3.975 |  |  | 0.25 | 25 | 1 | 25 | 3.975 | 0 | 0 | 0 | 3.975 | 99.375 | [5 empty] | 99.375
GRID (33-38 /O'-P')
49 | DIST. TOP EXTRA BAR |  | 6.08 |  |  | 0.25 | 16 | 1 | 17 | 6.08 | 0 | 0 | 0 | 6.08 | 103.36 |  |  |  | 103.36
GRID (33-38 /O'-P')
50 | MAIN TOP EXTRA BAR |  | 1.95 |  |  | 0.25 | 12 | 1 | 25 | 1.95 | 0 | 0 | 0 | 1.95 | 48.75 |  |  | 48.75
GRID (33-38 /P'-Q)
51 | DIST. TOP EXTRA BAR |  | 6.08 |  |  | 0.25 | 12 | 1 | 9 | 6.08 | 0 | 0 | 0 | 6.08 | 54.72 |  |  | 54.72
GRID (33-38 /P'-Q)
52 | DIST. TOP EXTRA BAR |  | 7.71 |  |  | 0.25 | 12 | 1 | 12 | 7.71 | 0 | 0 | 0 | 7.71 | 92.52 |  |  | 92.52
GRID (29-32 /O-Q)
53 | MAIN TOP EXTRA BAR |  | 2.85 |  |  | 0.25 | 10 | 1 | 17 | 2.85 | 0 | 0 | 0 | 2.85 | 48.45 |  | 48.45
GRID (26-29 /O-Q)
54 | DIST. TOP EXTRA BAR |  | 5.47 |  |  | 0.25 | 20 | 1 | 34 | 5.47 | 0 | 0 | 0 | 5.47 | 185.98 |  |  |  |  | 185.98
GRID (26-29 /O-Q)
55 | DIST. TOP EXTRA BAR |  | 4.19 |  |  | 0.25 | 16 | 1 | 11 | 4.19 | 0 | 0 | 0 | 4.19 | 46.09 |  |  |  | 46.09
GRID (26-29 /O-Q)
| TOTAL LENGTH IN METRE | [14 empty] | 0 | 930.71 | 1298.179 | 16128.449 | 6380.625 | 2199.06
| UNIT WEIGHT (IN KG) | [14 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.469 | 3.858
| TOTAL WEIGHT (IN KG) | [14 empty] | 0 | 574.2481 | 1152.783 | 25482.9494 | 15753.7631 | 8483.9735 | 51447.717 | KG
COMPENSATORY STRIP (22-23/B'-L')
A | RAFT | [14 empty] | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm
1 | GRID (22-23/B'-L')
| MAIN BAR BOTTOM (ALTH.) |  | 0.9 |  |  | 0.25 | 16 | 1 | 26 | 0.9 | 0 | 2 | 0.064 | 0.836 | 21.736 |  |  |  | 21.736
2 | GRID (22-23/B'-L')
| MAIN BAR BOTTOM (ALTH.) |  | 0.9 |  |  | 0.25 | 16 | 1 | 26 | 0.9 | 0.784 | 2 | 0.064 | 0.836 | 22.52 |  |  |  | 22.52
1 | GRID (22-23/B'-L')
| MAIN BAR TOP (ALTH.) |  | 0.9 |  |  | 0.25 | 16 | 1 | 26 | 0.9 | 0 | 2 | 0.064 | 0.836 | 21.736 |  |  |  | 21.736
2 | GRID (22-23/B'-L')
| MAIN BAR TOP (ALTH.) |  | 0.9 |  |  | 0.25 | 16 | 1 | 26 | 0.9 | 0.784 | 2 | 0.064 | 0.836 | 22.52 |  |  |  | 22.52
| TOTAL LENGTH IN METRE | [14 empty] | 0 | 0 | 0 | 88.512 | 0 | 0
| UNIT WEIGHT (IN KG) | [14 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.469 | 3.858
| TOTAL WEIGHT (IN KG) | [14 empty] | 0 | 0 | 0 | 139.849 | 0 | 0 | 139.849 | KG
COLUMN CLIT FIXING (22-23/B'-L')
A | COLUMN CLIT FIXING | [14 empty] | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm
1 | GRID (22-23/B'-L')
| MAIN BAR BOTTOM (ALTH.) |  | 0.04 |  |  |  | 8 | 143 | 8 | 0.04 | 0 |  | 0 | 0.04 | 45.76 | 45.76
| TOTAL LENGTH IN METRE | [14 empty] | 45.76 | 0 | 0 | 0 | 0 | 0
| UNIT WEIGHT (IN KG) | [14 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.469 | 3.858
| TOTAL WEIGHT (IN KG) | [14 empty] | 18.0752 | 0 | 0 | 0 | 0 | 0 | 18.0752 | KG

## COL BBS
TOWER-E COLUMN FOUNDATION BBS (BELOW PLINTH BEAM)
S.No. | Description | Shape of Bar in mm |  |  | Spacing c/c | Dia of Bar | Nos of Columns | Nos of Bar | Actual Length | Lap | No. Of Bend | Deduction | Cut Length | Total Length | TMT BAR Fe-500D or EQR | [5 empty] | Remarks
[15 empty] | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm
1 | Column C1 (300x600)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 16 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 64.704 |  |  |  | 64.704
| VERTICAL BARS B |  |  |  |  | 12 | 16 | 2 | 0.743 | 0 | 1 | 0.024 | 1.019 | 32.608 |  |  | 32.608
| VERTICAL BARS C |  |  | 0.3 |  | 16 | 16 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 64.704 |  |  |  | 64.704
| VERTICAL BARS D |  |  |  |  | 12 | 16 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 65.216 |  |  | 65.216
0.08
| Stirupps a |  |  | 0.52 |  | 10 | 16 | 4 | 1.64 |  | 5 | 0.1 | 1.56 | 99.84 |  | 99.84
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 16 | 1 | 0.8656 |  | 5 | 0.1 | 0.7856 | 12.5696 |  | 12.5696
0.22
| Stirupps c |  |  |  |  | 10 | 16 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 10.4 |  | 10.4
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 16 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 10.4 |  | 10.4
|  | 0.175 |  | 0.175
0.22
2 | Column C2 (300x600)
| VERTICAL BARS A |  | 0.743 |  |  | 20 | 11 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 44.132 |  |  |  |  | 44.132
| VERTICAL BARS B |  |  |  |  | 20 | 11 | 2 | 0.743 | 0 | 1 | 0.04 | 1.003 | 22.066 |  |  |  |  | 22.066
| VERTICAL BARS C |  |  | 0.3 |  | 16 | 11 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 44.484 |  |  |  | 44.484
| VERTICAL BARS D |  |  |  |  | 16 | 11 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 44.484 |  |  |  | 44.484
0.08
| Stirupps a |  |  | 0.52 |  | 10 | 11 | 4 | 1.64 |  | 5 | 0.1 | 1.54 | 67.76 |  | 67.76
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 11 | 1 | 0.8656 |  | 5 | 0.1 | 0.7656 | 8.4216 |  | 8.4216
0.22
| Stirupps c |  |  |  |  | 10 | 11 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 7.15 |  | 7.15
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 11 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 7.15 |  | 7.15
|  | 0.175 |  | 0.175
0.22
3 | Column C3 (300x600)
| VERTICAL BARS A |  | 0.743 |  |  | 25 | 2 | 4 | 0.743 | 0 | 1 | 0.05 | 0.993 | 7.944 | [5 empty] | 7.944
| VERTICAL BARS B |  |  |  |  | 25 | 2 | 2 | 0.743 | 0 | 1 | 0.05 | 0.993 | 3.972 | [5 empty] | 3.972
| VERTICAL BARS C |  |  | 0.3 |  | 25 | 2 | 4 | 0.743 | 0 | 1 | 0.05 | 0.993 | 7.944 | [5 empty] | 7.944
| VERTICAL BARS D |  |  |  |  | 20 | 2 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 8.024 |  |  |  |  | 8.024
0.08
| Stirupps a |  |  | 0.52 |  | 10 | 2 | 4 | 1.64 |  | 5 | 0.1 | 1.54 | 12.32 |  | 12.32
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 2 | 1 | 0.8656 |  | 5 | 0.1 | 0.7656 | 1.5312 |  | 1.5312
0.22
| Stirupps c |  |  |  |  | 10 | 2 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 1.3 |  | 1.3
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 2 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 1.3 |  | 1.3
|  | 0.175 |  | 0.175
0.22
4 | Column C4 (300x750)
| VERTICAL BARS A |  | 0.743 |  |  | 20 | 8 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 32.096 |  |  |  |  | 32.096
| VERTICAL BARS B |  |  |  |  | 20 | 8 | 2 | 0.743 | 0 | 1 | 0.04 | 1.003 | 16.048 |  |  |  |  | 16.048
| VERTICAL BARS C |  |  | 0.3 |  | 20 | 8 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 32.096 |  |  |  |  | 32.096
| VERTICAL BARS D |  |  |  |  | 20 | 8 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 32.096 |  |  |  |  | 32.096
| VERTICAL BARS E |  |  |  |  | 20 | 8 | 2 | 0.743 | 0 | 1 | 0.04 | 1.003 | 16.048 |  |  |  |  | 16.048
0.08
| Stirupps a |  |  | 0.67 |  | 10 | 8 | 4 | 1.94 |  | 5 | 0.1 | 1.84 | 58.88 |  | 58.88
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 10 | 8 | 1 | 1.1 |  | 5 | 0.1 | 1 | 8 |  | 8
0.22
| Stirupps c |  |  |  |  | 10 | 8 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 5.2 |  | 5.2
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 8 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 5.2 |  | 5.2
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 8 | 1 | 0.38 |  | 2 | 0.04 | 0.34 | 2.72 |  | 2.72
0.08
5 | Column C5 (300x750)
| VERTICAL BARS A |  | 0.743 |  |  | 20 | 7 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 28.084 |  |  |  |  | 28.084
| VERTICAL BARS B |  |  |  |  | 16 | 7 | 2 | 0.743 | 0 | 1 | 0.032 | 1.011 | 14.154 |  |  |  | 14.154
| VERTICAL BARS C |  |  | 0.3 |  | 16 | 7 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 28.308 |  |  |  | 28.308
| VERTICAL BARS D |  |  |  |  | 16 | 7 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 28.308 |  |  |  | 28.308
| VERTICAL BARS E |  |  |  |  | 16 | 7 | 2 | 0.743 | 0 | 1 | 0.032 | 1.011 | 14.154 |  |  |  | 14.154
0.08
| Stirupps a |  |  | 0.67 |  | 10 | 7 | 4 | 1.94 |  | 5 | 0.1 | 1.84 | 51.52 |  | 51.52
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 10 | 7 | 1 | 1.1 |  | 5 | 0.1 | 1 | 7 |  | 7
0.22
| Stirupps c |  |  |  |  | 10 | 7 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 4.55 |  | 4.55
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 7 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 4.55 |  | 4.55
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 7 | 1 | 0.38 |  | 2 | 0.04 | 0.34 | 2.38 |  | 2.38
0.08
6 | Column C6 (300x715)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 7 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 28.308 |  |  |  | 28.308
| VERTICAL BARS B |  |  |  |  | 12 | 7 | 2 | 0.743 | 0 | 1 | 0.024 | 1.019 | 14.266 |  |  | 14.266
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 7 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 28.532 |  |  | 28.532
| VERTICAL BARS D |  |  |  |  | 12 | 7 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 28.532 |  |  | 28.532
| VERTICAL BARS E |  |  |  |  | 12 | 7 | 2 | 0.743 | 0 | 1 | 0.024 | 1.019 | 14.266 |  |  | 14.266
0.08
| Stirupps a |  |  | 0.635 |  | 10 | 7 | 4 | 1.87 |  | 5 | 0.1 | 1.77 | 49.56 |  | 49.56
0.22
0.08
| Stirupps b |  |  | 0.23833 |  | 10 | 7 | 1 | 1.0767 |  | 5 | 0.1 | 0.97667 | 6.8367 |  | 6.8367
0.22
| Stirupps c |  |  |  |  | 10 | 7 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 4.55 |  | 4.55
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 7 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 4.55 |  | 4.55
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 7 | 1 | 0.38 |  | 2 | 0.04 | 0.34 | 2.38 |  | 2.38
0.08
7 | Column C7 (300x800)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 2 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 2 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 2 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
0.08
| Stirupps a |  |  | 0.72 |  | 10 | 2 | 4 | 2.04 |  | 5 | 0.1 | 1.94 | 15.52 |  | 15.52
0.22
0.08
| Stirupps b |  |  | 0.13257 |  | 10 | 2 | 1 | 0.86514 |  | 5 | 0.1 | 0.76514 | 1.5303 |  | 1.5303
0.22
0.08
| Stirupps c |  |  | 0.13257 |  | 10 | 2 | 1 | 0.86514 |  | 5 | 0.1 | 0.76514 | 1.5303 |  | 1.5303
0.22
| Stirupps d |  |  |  |  | 10 | 2 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 1.3 |  | 1.3
|  | 0.175 |  | 0.175
0.22
| Stirupps e |  |  |  |  | 10 | 2 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 1.3 |  | 1.3
|  | 0.175 |  | 0.175
0.22
8 | Column C8 (300x600)
| VERTICAL BARS A |  | 0.743 |  |  | 20 | 2 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 8.024 |  |  |  |  | 8.024
| VERTICAL BARS B |  |  |  |  | 20 | 2 | 2 | 0.743 | 0 | 1 | 0.04 | 1.003 | 4.012 |  |  |  |  | 4.012
| VERTICAL BARS C |  |  | 0.3 |  | 20 | 2 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 8.024 |  |  |  |  | 8.024
| VERTICAL BARS D |  |  |  |  | 20 | 2 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 8.024 |  |  |  |  | 8.024
0.08
| Stirupps a |  |  | 0.52 |  | 10 | 2 | 4 | 1.64 |  | 5 | 0.1 | 1.54 | 12.32 |  | 12.32
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 2 | 1 | 0.8656 |  | 5 | 0.1 | 0.7656 | 1.5312 |  | 1.5312
0.22
| Stirupps c |  |  |  |  | 10 | 2 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 1.3 |  | 1.3
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 2 | 1 | 0.73 |  | 4 | 0.08 | 0.65 | 1.3 |  | 1.3
|  | 0.175 |  | 0.175
0.22
9 | SW1 (230x650/1650)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 12 | 1 | 16 | 0.743 | 0 | 1 | 0.024 | 1.019 | 16.304 |  |  | 16.304
| VERTICAL BARS C |  |  | 0.3 |  | 10 | 1 | 8 | 0.743 | 0 | 1 | 0.02 | 1.023 | 8.184 |  | 8.184
0.08
| Stirupps a |  |  | 0.6 |  | 10 | 1 | 4 | 1.72 |  | 5 | 0.1 | 1.62 | 6.48 |  | 6.48
0.18
0.08
| Stirupps b |  |  | 1.6 |  | 10 | 1 | 4 | 3.72 |  | 5 | 0.1 | 3.62 | 14.48 |  | 14.48
0.18
0.08
| Stirupps c |  |  | 0.2656 |  | 10 | 1 | 1 | 1.0512 |  | 5 | 0.1 | 0.9512 | 0.9512 |  | 0.9512
0.18
0.08
| Stirupps d |  |  | 0.46655 |  | 10 | 1 | 1 | 1.4531 |  | 5 | 0.1 | 1.3531 | 1.3531 |  | 1.3531
0.18
0.08
| Stirupps e |  |  | 0.75091 |  | 10 | 1 | 1 | 2.0218 |  | 5 | 0.1 | 1.9218 | 1.9218 |  | 1.9218
0.18
0.08
| Stirupps f |  |  | 0.17618 |  | 10 | 1 | 1 | 0.87236 |  | 5 | 0.1 | 0.77236 | 0.77236 |  | 0.77236
0.18
0.08
| Stirupps g |  | 0.18 |  |  | 10 | 1 | 4 | 0.34 |  | 2 | 0.04 | 0.3 | 1.2 |  | 1.2
0.08
10 | SW2 (230x650/1850)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 12 | 1 | 16 | 0.743 | 0 | 1 | 0.024 | 1.019 | 16.304 |  |  | 16.304
| VERTICAL BARS C |  |  | 0.3 |  | 10 | 1 | 10 | 0.743 | 0 | 1 | 0.02 | 1.023 | 10.23 |  | 10.23
0.08
| Stirupps a |  |  | 0.6 |  | 10 | 1 | 4 | 1.72 |  | 5 | 0.1 | 1.62 | 6.48 |  | 6.48
0.18
0.08
| Stirupps b |  |  | 1.8 |  | 10 | 1 | 4 | 4.12 |  | 5 | 0.1 | 4.02 | 16.08 |  | 16.08
0.18
0.08
| Stirupps c |  |  | 0.2656 |  | 10 | 1 | 1 | 1.0512 |  | 5 | 0.1 | 0.9512 | 0.9512 |  | 0.9512
0.18
0.08
| Stirupps d |  |  | 0.468 |  | 10 | 1 | 1 | 1.456 |  | 5 | 0.1 | 1.356 | 1.356 |  | 1.356
0.18
0.08
| Stirupps e |  |  | 0.75333 |  | 10 | 1 | 1 | 2.0267 |  | 5 | 0.1 | 1.9267 | 1.9267 |  | 1.9267
0.18
0.08
| Stirupps f |  |  | 0.17667 |  | 10 | 1 | 1 | 0.87333 |  | 5 | 0.1 | 0.77333 | 0.77333 |  | 0.77333
0.18
0.08
| Stirupps g |  | 0.18 |  |  | 10 | 1 | 4 | 0.34 |  | 2 | 0.04 | 0.3 | 1.2 |  | 1.2
0.08
11 | SW3 (230x1000)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS B |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS D |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS E |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
0.08
| Stirupps a |  |  | 0.95 |  | 10 | 1 | 4 | 2.42 |  | 5 | 0.1 | 2.32 | 9.28 |  | 9.28
0.18
0.08
| Stirupps b |  |  | 0.13578 |  | 10 | 1 | 4 | 0.79156 |  | 5 | 0.1 | 0.69156 | 2.7662 |  | 2.7662
0.18
12 | SW4 (230x1150)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS B |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS D |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS E |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS F |  |  |  |  | 12 | 1 | 2 | 0.743 | 0 | 1 | 0.024 | 1.019 | 2.038 |  |  | 2.038
0.08
| Stirupps a |  |  | 1.1 |  | 10 | 1 | 4 | 2.72 |  | 5 | 0.1 | 2.62 | 10.48 |  | 10.48
0.18
0.08
| Stirupps b |  |  | 0.1404 |  | 10 | 1 | 4 | 0.8008 |  | 5 | 0.1 | 0.7008 | 2.8032 |  | 2.8032
0.18
0.08
| Stirupps c |  | 0.18 |  |  | 10 | 1 | 1 | 0.34 |  | 2 | 0.04 | 0.3 | 0.3 |  | 0.3
0.08
13 | SW5 (230x1700)
| VERTICAL BARS A |  | 0.743 |  |  | 20 | 2 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 8.024 |  |  |  |  | 8.024
| VERTICAL BARS B |  |  |  |  | 20 | 2 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 8.024 |  |  |  |  | 8.024
| VERTICAL BARS C |  |  | 0.3 |  | 20 | 2 | 4 | 0.743 | 0 | 1 | 0.04 | 1.003 | 8.024 |  |  |  |  | 8.024
| VERTICAL BARS D |  |  |  |  | 16 | 2 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS E |  |  |  |  | 16 | 2 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS F |  |  |  |  | 16 | 2 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 16.176 |  |  |  | 16.176
| VERTICAL BARS G |  |  |  |  | 16 | 2 | 6 | 0.743 | 0 | 1 | 0.032 | 1.011 | 12.132 |  |  |  | 12.132
0.08
| Stirupps a |  |  | 1.65 |  | 10 | 2 | 4 | 3.82 |  | 5 | 0.1 | 3.72 | 29.76 |  | 29.76
0.18
0.08
| Stirupps b |  |  | 0.13787 |  | 10 | 2 | 6 | 0.79575 |  | 5 | 0.1 | 0.69575 | 8.349 |  | 8.349
0.18
0.08
| Stirupps c |  |  | 0.23975 |  | 10 | 2 | 6 | 0.9995 |  | 5 | 0.1 | 0.8995 | 10.794 |  | 10.794
0.18
0.08
| Stirupps d |  | 0.18 |  |  | 10 | 2 | 1 | 0.34 |  | 2 | 0.04 | 0.3 | 0.6 |  | 0.6
0.08
14 | SW6 (230x1185)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS B |  |  |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS C |  |  | 0.3 |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS D |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS E |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS F |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
0.08
| Stirupps a |  |  | 1.135 |  | 10 | 1 | 4 | 2.79 |  | 5 | 0.1 | 2.69 | 10.76 |  | 10.76
0.18
0.08
| Stirupps b |  |  | 0.13773 |  | 10 | 1 | 5 | 0.79545 |  | 5 | 0.1 | 0.69545 | 3.4773 |  | 3.4773
0.18
15 | SW7 (230x1855)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS B |  |  |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS C |  |  | 0.3 |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS D |  |  |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS E |  |  |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS F |  |  |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS G |  |  |  |  | 16 | 1 | 4 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS H |  |  |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
0.08
| Stirupps a |  |  | 1.805 |  | 10 | 1 | 4 | 4.13 |  | 5 | 0.1 | 4.03 | 16.12 |  | 16.12
0.18
0.08
| Stirupps b |  |  | 0.14124 |  | 10 | 1 | 8 | 0.80247 |  | 5 | 0.1 | 0.70247 | 5.6198 |  | 5.6198
0.18
16 | SW9 (230x650/1850)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 16 | 1 | 16 | 0.743 | 0 | 1 | 0.032 | 1.011 | 16.176 |  |  |  | 16.176
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 1 | 10 | 0.743 | 0 | 1 | 0.024 | 1.019 | 10.19 |  |  | 10.19
0.08
| Stirupps a |  |  | 0.6 |  | 10 | 1 | 4 | 1.72 |  | 5 | 0.1 | 1.62 | 6.48 |  | 6.48
0.18
0.08
| Stirupps b |  |  | 1.8 |  | 10 | 1 | 4 | 4.12 |  | 5 | 0.1 | 4.02 | 16.08 |  | 16.08
0.18
0.08
| Stirupps c |  |  | 0.2456 |  | 10 | 1 | 1 | 1.0112 |  | 5 | 0.1 | 0.9112 | 0.9112 |  | 0.9112
0.18
0.08
| Stirupps d |  |  | 0.468 |  | 10 | 1 | 1 | 1.456 |  | 5 | 0.1 | 1.356 | 1.356 |  | 1.356
0.18
0.08
| Stirupps e |  |  | 0.75333 |  | 10 | 1 | 1 | 2.0267 |  | 5 | 0.1 | 1.9267 | 1.9267 |  | 1.9267
0.18
0.08
| Stirupps f |  |  | 0.17667 |  | 10 | 1 | 1 | 0.87333 |  | 5 | 0.1 | 0.77333 | 0.77333 |  | 0.77333
0.18
0.08
| Stirupps g |  | 0.18 |  |  | 10 | 1 | 4 | 0.34 |  | 2 | 0.04 | 0.3 | 1.2 |  | 1.2
0.08
17 | SW10 (230x3445)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 1 | 8 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS D |  |  |  |  | 12 | 1 | 4 | 0.743 | 0 | 1 | 0.024 | 1.019 | 4.076 |  |  | 4.076
| VERTICAL BARS E |  |  |  |  | 12 | 1 | 20 | 0.743 | 0 | 1 | 0.024 | 1.019 | 20.38 |  |  | 20.38
0.08
| Stirupps a |  |  | 0.91748 |  | 10 | 1 | 8 | 2.355 |  | 5 | 0.1 | 2.255 | 18.0397 |  | 18.0397
0.18
0.08
| Stirupps b |  |  | 1.652 |  | 10 | 1 | 4 | 3.8241 |  | 5 | 0.1 | 3.7241 | 14.8963 |  | 14.8963
0.18
0.08
| Stirupps c |  |  | 0.18291 |  | 10 | 1 | 4 | 0.88583 |  | 5 | 0.1 | 0.78583 | 3.1433 |  | 3.1433
0.18
0.08
| Stirupps d |  | 0.18 |  |  | 10 | 1 | 7 | 0.34 |  | 2 | 0.04 | 0.3 | 2.1 |  | 2.1
0.08
18 | SW11 (230x4065)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 1 | 8 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS D |  |  |  |  | 12 | 1 | 8 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS E |  |  |  |  | 12 | 1 | 8 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS F |  |  |  |  | 10 | 1 | 20 | 0.743 | 0 | 1 | 0.02 | 1.023 | 20.46 |  | 20.46
0.08
| Stirupps a |  |  | 1.2771 |  | 10 | 1 | 8 | 3.0741 |  | 5 | 0.1 | 2.9741 | 23.7931 |  | 23.7931
0.18
0.08
| Stirupps b |  |  | 1.5529 |  | 10 | 1 | 4 | 3.6257 |  | 5 | 0.1 | 3.5257 | 14.1029 |  | 14.1029
0.18
0.08
| Stirupps c |  |  | 0.1739 |  | 10 | 1 | 8 | 0.86779 |  | 5 | 0.1 | 0.76779 | 6.1423 |  | 6.1423
0.18
0.08
| Stirupps d |  | 0.18 |  |  | 10 | 1 | 5 | 0.34 |  | 2 | 0.04 | 0.3 | 1.5 |  | 1.5
0.08
19 | SW12 (230x650/1535)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 12 | 1 | 16 | 0.743 | 0 | 1 | 0.024 | 1.019 | 16.304 |  |  | 16.304
| VERTICAL BARS C |  |  | 0.3 |  | 10 | 1 | 8 | 0.743 | 0 | 1 | 0.02 | 1.023 | 8.184 |  | 8.184
0.08
| Stirupps a |  |  | 0.6 |  | 10 | 1 | 4 | 1.72 |  | 5 | 0.1 | 1.62 | 6.48 |  | 6.48
0.18
0.08
| Stirupps b |  |  | 1.485 |  | 10 | 1 | 4 | 3.49 |  | 5 | 0.1 | 3.39 | 13.56 |  | 13.56
0.18
0.08
| Stirupps c |  |  | 0.2656 |  | 10 | 1 | 1 | 1.0512 |  | 5 | 0.1 | 0.9512 | 0.9512 |  | 0.9512
0.18
0.08
| Stirupps d |  |  | 0.43518 |  | 10 | 1 | 1 | 1.3904 |  | 5 | 0.1 | 1.2904 | 1.2904 |  | 1.2904
0.18
0.08
| Stirupps e |  |  | 0.69864 |  | 10 | 1 | 1 | 1.9173 |  | 5 | 0.1 | 1.8173 | 1.8173 |  | 1.8173
0.18
0.08
| Stirupps f |  |  | 0.16573 |  | 10 | 1 | 1 | 0.85145 |  | 5 | 0.1 | 0.75145 | 0.75145 |  | 0.75145
0.18
0.08
| Stirupps g |  | 0.18 |  |  | 10 | 1 | 4 | 0.34 |  | 2 | 0.04 | 0.3 | 1.2 |  | 1.2
0.08
20 | SW13 (230x3445)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 1 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 8.088 |  |  |  | 8.088
| VERTICAL BARS B |  |  |  |  | 12 | 1 | 8 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS C |  |  | 0.3 |  | 12 | 1 | 8 | 0.743 | 0 | 1 | 0.024 | 1.019 | 8.152 |  |  | 8.152
| VERTICAL BARS D |  |  |  |  | 10 | 1 | 22 | 0.743 | 0 | 1 | 0.02 | 1.023 | 22.506 |  | 22.506
0.08
| Stirupps a |  |  | 0.80395 |  | 10 | 1 | 8 | 2.1279 |  | 5 | 0.1 | 2.0279 | 16.2233 |  | 16.2233
0.18
0.08
| Stirupps b |  |  | 1.8791 |  | 10 | 1 | 4 | 4.2782 |  | 5 | 0.1 | 4.1782 | 16.7127 |  | 16.7127
0.18
0.08
| Stirupps c |  |  | 0.18959 |  | 10 | 1 | 4 | 0.89918 |  | 5 | 0.1 | 0.79918 | 3.1967 |  | 3.1967
0.18
0.08
| Stirupps d |  | 0.18 |  |  | 10 | 1 | 5 | 0.34 |  | 2 | 0.04 | 0.3 | 1.5 |  | 1.5
0.08
21 | LIFT WALL |  | 0.1
| VERTICAL BARS |  | 2.7 |  |  | 10 | 4 | 26.3333 | 2.7 | 0 | 1 | 0.02 | 2.78 | 292.8267 |  | 292.8267
22 | SW8 (230x3600)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 0.5 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS B |  |  |  |  | 16 | 0.5 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS C |  |  | 0.3 |  | 16 | 0.5 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS D |  |  |  |  | 16 | 0.5 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS E |  |  |  |  | 16 | 0.5 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS F |  |  |  |  | 16 | 0.5 | 8 | 0.743 | 0 | 1 | 0.032 | 1.011 | 4.044 |  |  |  | 4.044
| VERTICAL BARS G |  |  |  |  | 12 | 0.5 | 12 | 0.743 | 0 | 1 | 0.024 | 1.019 | 6.114 |  |  | 6.114
0.08
| Stirupps a |  |  | 0.91748 |  | 10 | 0.5 | 8 | 2.355 |  | 5 | 0.1 | 2.255 | 9.0198 |  | 9.0198
0.18
0.08
| Stirupps b |  |  | 1.652 |  | 10 | 0.5 | 4 | 3.8241 |  | 5 | 0.1 | 3.7241 | 7.4482 |  | 7.4482
0.18
0.08
| Stirupps c |  |  | 0.18291 |  | 10 | 0.5 | 4 | 0.88583 |  | 5 | 0.1 | 0.78583 | 1.5717 |  | 1.5717
0.18
0.08
| Stirupps d |  | 0.18 |  |  | 10 | 0.5 | 7 | 0.34 |  | 2 | 0.04 | 0.3 | 1.05 |  | 1.05
0.08
TOTAL
| TOTAL LENGTH IN METRE | [13 empty] | 0 | 1220.2942 | 397.41 | 554.028 | 282.846 | 19.86
| UNIT WEIGHT (IN KG) | [13 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.469 | 3.858
| TOTAL WEIGHT (IN KG) | [13 empty] | 0 | 752.9215 | 352.9001 | 875.3642 | 698.3468 | 76.6199 | 2756.1525
FROM FOUNDATION TOP TO PLINTH BEAM TOP
1 | Column C1 (300x600)
| VERTICAL BARS A |  | 1.48 |  |  | 16 | 20 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 118.4 |  |  |  | 118.4
| VERTICAL BARS B |  |  |  |  | 12 | 20 | 2 | 1.48 | 0 | 0 | 0 | 1.48 | 59.2 |  |  | 59.2
| VERTICAL BARS C |  |  |  |  | 16 | 20 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 118.4 |  |  |  | 118.4
| VERTICAL BARS D |  |  |  |  | 12 | 20 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 118.4 |  |  | 118.4
| ZONE A | 0.08
| Stirupps a |  |  | 0.52 |  | 10 | 20 | 18 | 1.64 |  | 5 | 0.1 | 1.56 | 561.6 |  | 561.6
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 20 | 18 | 0.8656 |  | 5 | 0.1 | 0.7856 | 282.816 |  | 282.816
0.22
| Stirupps c |  |  |  |  | 10 | 20 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 234 |  | 234
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 20 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 234 |  | 234
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.52 |  | 8 | 20 | 2.8667 | 1.608 |  | 5 | 0.08 | 1.548 | 88.752 | 88.752
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 8 | 20 | 2.8667 | 0.8336 |  | 5 | 0.08 | 0.7736 | 44.3531 | 44.3531
0.22
| Stirupps c |  |  |  |  | 8 | 20 | 2.8667 | 0.698 |  | 4 | 0.064 | 0.634 | 36.3493 | 36.3493
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 20 | 2.8667 | 0.698 |  | 4 | 0.064 | 0.634 | 36.3493 | 36.3493
|  | 0.175 |  | 0.175
0.22
1 | Column C1 (300x600)
| VERTICAL BARS A |  | 1.68 |  |  | 16 | 12 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 80.64 |  |  |  | 80.64
| VERTICAL BARS B |  |  |  |  | 12 | 12 | 2 | 1.68 | 0 | 0 | 0 | 1.68 | 40.32 |  |  | 40.32
| VERTICAL BARS C |  |  |  |  | 16 | 12 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 80.64 |  |  |  | 80.64
| VERTICAL BARS D |  |  |  |  | 12 | 12 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 80.64 |  |  | 80.64
| ZONE A | 0.08
| Stirupps a |  |  | 0.52 |  | 10 | 12 | 18 | 1.64 |  | 5 | 0.1 | 1.56 | 336.96 |  | 336.96
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 12 | 18 | 0.8656 |  | 5 | 0.1 | 0.7856 | 169.6896 |  | 169.6896
0.22
| Stirupps c |  |  |  |  | 10 | 12 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 140.4 |  | 140.4
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 12 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 140.4 |  | 140.4
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.52 |  | 8 | 12 | 4.2 | 1.608 |  | 5 | 0.08 | 1.548 | 78.0192 | 78.0192
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 8 | 12 | 4.2 | 0.8336 |  | 5 | 0.08 | 0.7736 | 38.9894 | 38.9894
0.22
| Stirupps c |  |  |  |  | 8 | 12 | 4.2 | 0.698 |  | 4 | 0.064 | 0.634 | 31.9536 | 31.9536
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 12 | 4.2 | 0.698 |  | 4 | 0.064 | 0.634 | 31.9536 | 31.9536
|  | 0.175 |  | 0.175
0.22
2 | Column C2 (300x600)
| VERTICAL BARS A |  | 1.48 |  |  | 20 | 12 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 71.04 |  |  |  |  | 71.04
| VERTICAL BARS B |  |  |  |  | 20 | 12 | 2 | 1.48 | 0 | 0 | 0 | 1.48 | 35.52 |  |  |  |  | 35.52
| VERTICAL BARS C |  |  |  |  | 16 | 12 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 71.04 |  |  |  | 71.04
| VERTICAL BARS D |  |  |  |  | 16 | 12 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 71.04 |  |  |  | 71.04
| ZONE A | 0.08
| Stirupps a |  |  | 0.52 |  | 10 | 12 | 18 | 1.64 |  | 5 | 0.1 | 1.54 | 332.64 |  | 332.64
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 12 | 18 | 0.8656 |  | 5 | 0.1 | 0.7656 | 165.3696 |  | 165.3696
0.22
| Stirupps c |  |  |  |  | 10 | 12 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 140.4 |  | 140.4
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 12 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 140.4 |  | 140.4
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.52 |  | 8 | 12 | 2.8667 | 1.608 |  | 5 | 0.08 | 1.528 | 52.5632 | 52.5632
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 8 | 12 | 2.8667 | 0.8336 |  | 5 | 0.08 | 0.7536 | 25.9238 | 25.9238
0.22
| Stirupps c |  |  |  |  | 8 | 12 | 2.8667 | 0.698 |  | 4 | 0.064 | 0.634 | 21.8096 | 21.8096
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 12 | 2.8667 | 0.698 |  | 4 | 0.064 | 0.634 | 21.8096 | 21.8096
|  | 0.175 |  | 0.175
0.22
2 | Column C2 (300x600)
| VERTICAL BARS A |  | 1.68 |  |  | 20 | 10 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 67.2 |  |  |  |  | 67.2
| VERTICAL BARS B |  |  |  |  | 20 | 10 | 2 | 1.68 | 0 | 0 | 0 | 1.68 | 33.6 |  |  |  |  | 33.6
| VERTICAL BARS C |  |  |  |  | 16 | 10 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 67.2 |  |  |  | 67.2
| VERTICAL BARS D |  |  |  |  | 16 | 10 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 67.2 |  |  |  | 67.2
| ZONE A | 0.08
| Stirupps a |  |  | 0.52 |  | 10 | 10 | 18 | 1.64 |  | 5 | 0.1 | 1.54 | 277.2 |  | 277.2
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 10 | 18 | 0.8656 |  | 5 | 0.1 | 0.7656 | 137.808 |  | 137.808
0.22
| Stirupps c |  |  |  |  | 10 | 10 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 117 |  | 117
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 10 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 117 |  | 117
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.52 |  | 8 | 10 | 4.2 | 1.608 |  | 5 | 0.08 | 1.528 | 64.176 | 64.176
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 8 | 10 | 4.2 | 0.8336 |  | 5 | 0.08 | 0.7536 | 31.6512 | 31.6512
0.22
| Stirupps c |  |  |  |  | 8 | 10 | 4.2 | 0.698 |  | 4 | 0.064 | 0.634 | 26.628 | 26.628
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 10 | 4.2 | 0.698 |  | 4 | 0.064 | 0.634 | 26.628 | 26.628
|  | 0.175 |  | 0.175
0.22
3 | Column C3 (300x600)
| VERTICAL BARS A |  | 1.68 |  |  | 25 | 4 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 | [5 empty] | 26.88
| VERTICAL BARS B |  |  |  |  | 25 | 4 | 2 | 1.68 | 0 | 0 | 0 | 1.68 | 13.44 | [5 empty] | 13.44
| VERTICAL BARS C |  |  |  |  | 25 | 4 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 | [5 empty] | 26.88
| VERTICAL BARS D |  |  |  |  | 20 | 4 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  |  | 26.88
| ZONE A | 0.08
| Stirupps a |  |  | 0.52 |  | 10 | 4 | 18 | 1.64 |  | 5 | 0.1 | 1.54 | 110.88 |  | 110.88
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 4 | 18 | 0.8656 |  | 5 | 0.1 | 0.7656 | 55.1232 |  | 55.1232
0.22
| Stirupps c |  |  |  |  | 10 | 4 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 46.8 |  | 46.8
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 4 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 46.8 |  | 46.8
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.52 |  | 8 | 4 | 4.2 | 1.608 |  | 5 | 0.08 | 1.528 | 25.6704 | 25.6704
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 8 | 4 | 4.2 | 0.8336 |  | 5 | 0.08 | 0.7536 | 12.6605 | 12.6605
0.22
| Stirupps c |  |  |  |  | 8 | 4 | 4.2 | 0.698 |  | 4 | 0.064 | 0.634 | 10.6512 | 10.6512
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 4 | 4.2 | 0.698 |  | 4 | 0.064 | 0.634 | 10.6512 | 10.6512
|  | 0.175 |  | 0.175
0.22
4 | Column C4 (300x750)
| VERTICAL BARS A |  | 1.48 |  |  | 20 | 8 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 47.36 |  |  |  |  | 47.36
| VERTICAL BARS B |  |  |  |  | 20 | 8 | 2 | 1.48 | 0 | 0 | 0 | 1.48 | 23.68 |  |  |  |  | 23.68
| VERTICAL BARS C |  |  |  |  | 20 | 8 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 47.36 |  |  |  |  | 47.36
| VERTICAL BARS D |  |  |  |  | 20 | 8 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 47.36 |  |  |  |  | 47.36
| VERTICAL BARS E |  |  |  |  | 20 | 8 | 2 | 1.48 | 0 | 0 | 0 | 1.48 | 23.68 |  |  |  |  | 23.68
| ZONE A | 0.08
| Stirupps a |  |  | 0.67 |  | 10 | 8 | 22 | 1.94 |  | 5 | 0.1 | 1.84 | 323.84 |  | 323.84
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 10 | 8 | 22 | 1.1 |  | 5 | 0.1 | 1 | 176 |  | 176
0.22
| Stirupps c |  |  |  |  | 10 | 8 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 114.4 |  | 114.4
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 8 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 114.4 |  | 114.4
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 8 | 22 | 0.38 |  | 2 | 0.04 | 0.34 | 59.84 |  | 59.84
0.08
| ZONE B | 0.08
| Stirupps a |  |  | 0.67 |  | 8 | 8 | 0.86667 | 1.908 |  | 5 | 0.08 | 1.828 | 12.6741 | 12.6741
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 8 | 8 | 0.86667 | 1.068 |  | 5 | 0.08 | 0.988 | 6.8501 | 6.8501
0.22
| Stirupps c |  |  |  |  | 8 | 8 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 4.3957 | 4.3957
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 8 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 4.3957 | 4.3957
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 8 | 8 | 0.86667 | 0.38 |  | 2 | 0.032 | 0.348 | 2.4128 | 2.4128
0.08
4 | Column C4 (300x750)
| VERTICAL BARS A |  | 1.68 |  |  | 20 | 8 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 53.76 |  |  |  |  | 53.76
| VERTICAL BARS B |  |  |  |  | 20 | 8 | 2 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  |  | 26.88
| VERTICAL BARS C |  |  |  |  | 20 | 8 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 53.76 |  |  |  |  | 53.76
| VERTICAL BARS D |  |  |  |  | 20 | 8 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 53.76 |  |  |  |  | 53.76
| VERTICAL BARS E |  |  |  |  | 20 | 8 | 2 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  |  | 26.88
| ZONE A | 0.08
| Stirupps a |  |  | 0.67 |  | 10 | 8 | 22 | 1.94 |  | 5 | 0.1 | 1.84 | 323.84 |  | 323.84
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 10 | 8 | 22 | 1.1 |  | 5 | 0.1 | 1 | 176 |  | 176
0.22
| Stirupps c |  |  |  |  | 10 | 8 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 114.4 |  | 114.4
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 8 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 114.4 |  | 114.4
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 8 | 22 | 0.38 |  | 2 | 0.04 | 0.34 | 59.84 |  | 59.84
0.08
| ZONE B | 0.08
| Stirupps a |  |  | 0.67 |  | 8 | 8 | 2.2 | 1.908 |  | 5 | 0.08 | 1.828 | 32.1728 | 32.1728
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 8 | 8 | 2.2 | 1.068 |  | 5 | 0.08 | 0.988 | 17.3888 | 17.3888
0.22
| Stirupps c |  |  |  |  | 8 | 8 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 11.1584 | 11.1584
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 8 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 11.1584 | 11.1584
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 8 | 8 | 2.2 | 0.38 |  | 2 | 0.032 | 0.348 | 6.1248 | 6.1248
0.08
5 | Column C5 (300x750)
| VERTICAL BARS A |  | 1.68 |  |  | 20 | 10 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 67.2 |  |  |  |  | 67.2
| VERTICAL BARS B |  |  |  |  | 16 | 10 | 2 | 1.68 | 0 | 0 | 0 | 1.68 | 33.6 |  |  |  | 33.6
| VERTICAL BARS C |  |  |  |  | 16 | 10 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 67.2 |  |  |  | 67.2
| VERTICAL BARS D |  |  |  |  | 16 | 10 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 67.2 |  |  |  | 67.2
| VERTICAL BARS E |  |  |  |  | 16 | 10 | 2 | 1.68 | 0 | 0 | 0 | 1.68 | 33.6 |  |  |  | 33.6
| ZONE A | 0.08
| Stirupps a |  |  | 0.67 |  | 10 | 10 | 22 | 1.94 |  | 5 | 0.1 | 1.84 | 404.8 |  | 404.8
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 10 | 10 | 22 | 1.1 |  | 5 | 0.1 | 1 | 220 |  | 220
0.22
| Stirupps c |  |  |  |  | 10 | 10 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 143 |  | 143
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 10 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 143 |  | 143
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 10 | 22 | 0.38 |  | 2 | 0.04 | 0.34 | 74.8 |  | 74.8
0.08
| ZONE B | 0.08
| Stirupps a |  |  | 0.67 |  | 8 | 10 | 0.86667 | 1.908 |  | 5 | 0.08 | 1.828 | 15.8427 | 15.8427
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 8 | 10 | 0.86667 | 1.068 |  | 5 | 0.08 | 0.988 | 8.5627 | 8.5627
0.22
| Stirupps c |  |  |  |  | 8 | 10 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 5.4947 | 5.4947
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 10 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 5.4947 | 5.4947
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 8 | 10 | 0.86667 | 0.38 |  | 2 | 0.032 | 0.348 | 3.016 | 3.016
0.08
5 | Column C5 (300x750)
| VERTICAL BARS A |  | 1.68 |  |  | 20 | 4 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  |  | 26.88
| VERTICAL BARS B |  |  |  |  | 16 | 4 | 2 | 1.68 | 0 | 0 | 0 | 1.68 | 13.44 |  |  |  | 13.44
| VERTICAL BARS C |  |  |  |  | 16 | 4 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  | 26.88
| VERTICAL BARS D |  |  |  |  | 16 | 4 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  | 26.88
| VERTICAL BARS E |  |  |  |  | 16 | 4 | 2 | 1.68 | 0 | 0 | 0 | 1.68 | 13.44 |  |  |  | 13.44
| ZONE A | 0.08
| Stirupps a |  |  | 0.67 |  | 10 | 4 | 22 | 1.94 |  | 5 | 0.1 | 1.84 | 161.92 |  | 161.92
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 10 | 4 | 22 | 1.1 |  | 5 | 0.1 | 1 | 88 |  | 88
0.22
| Stirupps c |  |  |  |  | 10 | 4 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 57.2 |  | 57.2
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 4 | 22 | 0.73 |  | 4 | 0.08 | 0.65 | 57.2 |  | 57.2
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 4 | 22 | 0.38 |  | 2 | 0.04 | 0.34 | 29.92 |  | 29.92
0.08
| ZONE B | 0.08
| Stirupps a |  |  | 0.67 |  | 8 | 4 | 2.2 | 1.908 |  | 5 | 0.08 | 1.828 | 16.0864 | 16.0864
0.22
0.08
| Stirupps b |  |  | 0.25 |  | 8 | 4 | 2.2 | 1.068 |  | 5 | 0.08 | 0.988 | 8.6944 | 8.6944
0.22
| Stirupps c |  |  |  |  | 8 | 4 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 5.5792 | 5.5792
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 4 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 5.5792 | 5.5792
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 8 | 4 | 2.2 | 0.38 |  | 2 | 0.032 | 0.348 | 3.0624 | 3.0624
0.08
6 | Column C6 (300x715)
| VERTICAL BARS A |  | 1.48 |  |  | 16 | 14 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 82.88 |  |  |  | 82.88
| VERTICAL BARS B |  |  |  |  | 12 | 14 | 2 | 1.48 | 0 | 0 | 0 | 1.48 | 41.44 |  |  | 41.44
| VERTICAL BARS C |  |  |  |  | 12 | 14 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 82.88 |  |  | 82.88
| VERTICAL BARS D |  |  |  |  | 12 | 14 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 82.88 |  |  | 82.88
| VERTICAL BARS E |  |  |  |  | 12 | 14 | 2 | 1.48 | 0 | 0 | 0 | 1.48 | 41.44 |  |  | 41.44
| ZONE A | 0.08
| Stirupps a |  |  | 0.635 |  | 10 | 14 | 21.0667 | 1.87 |  | 5 | 0.1 | 1.77 | 522.032 |  | 522.032
0.22
0.08
| Stirupps b |  |  | 0.23833 |  | 10 | 14 | 21.0667 | 1.0767 |  | 5 | 0.1 | 0.97667 | 288.0516 |  | 288.0516
0.22
| Stirupps c |  |  |  |  | 10 | 14 | 21.0667 | 0.73 |  | 4 | 0.08 | 0.65 | 191.7067 |  | 191.7067
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 14 | 21.0667 | 0.73 |  | 4 | 0.08 | 0.65 | 191.7067 |  | 191.7067
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 10 | 14 | 21.0667 | 0.38 |  | 2 | 0.04 | 0.34 | 100.2773 |  | 100.2773
0.08
| ZONE B | 0.08
| Stirupps a |  |  | 0.635 |  | 8 | 14 | 0.86667 | 1.838 |  | 5 | 0.08 | 1.758 | 21.3304 | 21.3304
0.22
0.08
| Stirupps b |  |  | 0.23833 |  | 8 | 14 | 0.86667 | 1.0447 |  | 5 | 0.08 | 0.96467 | 11.7046 | 11.7046
0.22
| Stirupps c |  |  |  |  | 8 | 14 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 7.6925 | 7.6925
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 14 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 7.6925 | 7.6925
|  | 0.175 |  | 0.175
0.22
0.08
| Stirupps e |  | 0.22 |  |  | 8 | 14 | 0.86667 | 0.38 |  | 2 | 0.032 | 0.348 | 4.2224 | 4.2224
0.08
7 | Column C7 (300x800)
| VERTICAL BARS A |  | 1.48 |  |  | 16 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 2 | 1.48 | 0 | 0 | 0 | 1.48 | 5.92 |  |  | 5.92
| VERTICAL BARS C |  |  |  |  | 12 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  | 11.84
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  | 11.84
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  | 11.84
| ZONE A | 0.08
| Stirupps a |  |  | 0.72 |  | 10 | 2 | 23.3333 | 2.04 |  | 5 | 0.1 | 1.94 | 90.5333 |  | 90.5333
0.22
0.08
| Stirupps b |  |  | 0.13257 |  | 10 | 2 | 23.3333 | 0.86514 |  | 5 | 0.1 | 0.76514 | 35.7067 |  | 35.7067
0.22
0.08
| Stirupps c |  |  | 0.13257 |  | 10 | 2 | 23.3333 | 0.86514 |  | 5 | 0.1 | 0.76514 | 35.7067 |  | 35.7067
0.22
| Stirupps d |  |  |  |  | 10 | 2 | 23.3333 | 0.73 |  | 4 | 0.08 | 0.65 | 30.3333 |  | 30.3333
|  | 0.175 |  | 0.175
0.22
| Stirupps e |  |  |  |  | 10 | 2 | 23.3333 | 0.73 |  | 4 | 0.08 | 0.65 | 30.3333 |  | 30.3333
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.72 |  | 8 | 2 | 0.86667 | 2.008 |  | 5 | 0.08 | 1.928 | 3.3419 | 3.3419
0.22
0.08
| Stirupps b |  |  | 0.13257 |  | 8 | 2 | 0.86667 | 0.83314 |  | 5 | 0.08 | 0.75314 | 1.3054 | 1.3054
0.22
0.08
| Stirupps c |  |  | 0.13257 |  | 8 | 2 | 0.86667 | 0.83314 |  | 5 | 0.08 | 0.75314 | 1.3054 | 1.3054
0.22
| Stirupps d |  |  |  |  | 8 | 2 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 1.0989 | 1.0989
|  | 0.175 |  | 0.175
0.22
| Stirupps e |  |  |  |  | 8 | 2 | 0.86667 | 0.698 |  | 4 | 0.064 | 0.634 | 1.0989 | 1.0989
|  | 0.175 |  | 0.175
0.22
7 | Column C7 (300x800)
| VERTICAL BARS A |  | 1.68 |  |  | 16 | 2 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 13.44 |  |  |  | 13.44
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 2 | 1.68 | 0 | 0 | 0 | 1.68 | 6.72 |  |  | 6.72
| VERTICAL BARS C |  |  |  |  | 12 | 2 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 13.44 |  |  | 13.44
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 13.44 |  |  | 13.44
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 13.44 |  |  | 13.44
| ZONE A | 0.08
| Stirupps a |  |  | 0.72 |  | 10 | 2 | 23.3333 | 2.04 |  | 5 | 0.1 | 1.94 | 90.5333 |  | 90.5333
0.22
0.08
| Stirupps b |  |  | 0.13257 |  | 10 | 2 | 23.3333 | 0.86514 |  | 5 | 0.1 | 0.76514 | 35.7067 |  | 35.7067
0.22
0.08
| Stirupps c |  |  | 0.13257 |  | 10 | 2 | 23.3333 | 0.86514 |  | 5 | 0.1 | 0.76514 | 35.7067 |  | 35.7067
0.22
| Stirupps d |  |  |  |  | 10 | 2 | 23.3333 | 0.73 |  | 4 | 0.08 | 0.65 | 30.3333 |  | 30.3333
|  | 0.175 |  | 0.175
0.22
| Stirupps e |  |  |  |  | 10 | 2 | 23.3333 | 0.73 |  | 4 | 0.08 | 0.65 | 30.3333 |  | 30.3333
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.72 |  | 8 | 2 | 2.2 | 2.008 |  | 5 | 0.08 | 1.928 | 8.4832 | 8.4832
0.22
0.08
| Stirupps b |  |  | 0.13257 |  | 8 | 2 | 2.2 | 0.83314 |  | 5 | 0.08 | 0.75314 | 3.3138 | 3.3138
0.22
0.08
| Stirupps c |  |  | 0.13257 |  | 8 | 2 | 2.2 | 0.83314 |  | 5 | 0.08 | 0.75314 | 3.3138 | 3.3138
0.22
| Stirupps d |  |  |  |  | 8 | 2 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 2.7896 | 2.7896
|  | 0.175 |  | 0.175
0.22
| Stirupps e |  |  |  |  | 8 | 2 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 2.7896 | 2.7896
|  | 0.175 |  | 0.175
0.22
8 | Column C8 (300x600)
| VERTICAL BARS A |  | 1.68 |  |  | 20 | 4 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  |  | 26.88
| VERTICAL BARS B |  |  |  |  | 20 | 4 | 2 | 1.68 | 0 | 0 | 0 | 1.68 | 13.44 |  |  |  |  | 13.44
| VERTICAL BARS C |  |  |  |  | 20 | 4 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  |  | 26.88
| VERTICAL BARS D |  |  |  |  | 20 | 4 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  |  | 26.88
| ZONE A | 0.08
| Stirupps a |  |  | 0.52 |  | 10 | 4 | 18 | 1.64 |  | 5 | 0.1 | 1.54 | 110.88 |  | 110.88
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 10 | 4 | 18 | 0.8656 |  | 5 | 0.1 | 0.7656 | 55.1232 |  | 55.1232
0.22
| Stirupps c |  |  |  |  | 10 | 4 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 46.8 |  | 46.8
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 10 | 4 | 18 | 0.73 |  | 4 | 0.08 | 0.65 | 46.8 |  | 46.8
|  | 0.175 |  | 0.175
0.22
| ZONE B | 0.08
| Stirupps a |  |  | 0.52 |  | 8 | 4 | 2.2 | 1.608 |  | 5 | 0.08 | 1.528 | 13.4464 | 13.4464
0.22
0.08
| Stirupps b |  |  | 0.1328 |  | 8 | 4 | 2.2 | 0.8336 |  | 5 | 0.08 | 0.7536 | 6.6317 | 6.6317
0.22
| Stirupps c |  |  |  |  | 8 | 4 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 5.5792 | 5.5792
|  | 0.175 |  | 0.175
0.22
| Stirupps d |  |  |  |  | 8 | 4 | 2.2 | 0.698 |  | 4 | 0.064 | 0.634 | 5.5792 | 5.5792
|  | 0.175 |  | 0.175
0.22
9 | SW1 (230x650/1650)
| VERTICAL BARS A |  | 1.48 |  |  | 16 | 2 | 8 | 1.48 | 0 | 0 | 0 | 1.48 | 23.68 |  |  |  | 23.68
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 16 | 1.48 | 0 | 0 | 0 | 1.48 | 47.36 |  |  | 47.36
| VERTICAL BARS C |  |  |  |  | 10 | 2 | 8 | 1.48 | 0 | 0 | 0 | 1.48 | 23.68 |  | 23.68
0.08
| BE MAIN |  |  | 0.6 |  | 8 | 2 | 15.8 | 1.688 |  | 5 | 0.08 | 1.608 | 50.8128 | 50.8128
0.18
0.08
| BE OTHERS |  |  | 0.2656 |  | 8 | 2 | 15.8 | 1.0192 |  | 5 | 0.08 | 0.9392 | 29.6787 | 29.6787
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 2 | 15.8 | 0.34 |  | 2 | 0.032 | 0.308 | 9.7328 | 9.7328
0.08
0.08
| BE MAIN |  |  | 0.391 |  | 8 | 2 | 31.6 | 1.27 |  | 5 | 0.08 | 1.19 | 75.208 | 75.208
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 2 | 31.6 | 0.34 |  | 2 | 0.032 | 0.308 | 19.4656 | 19.4656
0.08
0.08
| MID MAIN |  |  | 0.882 |  | 8 | 2 | 8.4 | 2.252 |  | 5 | 0.08 | 2.172 | 36.4896 | 36.4896
0.18
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 2 | 9.4 | 0.34 |  | 2 | 0.032 | 0.308 | 5.7904 | 5.7904
0.08
10 | SW2 (230x650/1850)
| VERTICAL BARS A |  | 1.48 |  |  | 16 | 2 | 8 | 1.48 | 0 | 0 | 0 | 1.48 | 23.68 |  |  |  | 23.68
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 16 | 1.48 | 0 | 0 | 0 | 1.48 | 47.36 |  |  | 47.36
| VERTICAL BARS C |  |  |  |  | 10 | 2 | 10 | 1.48 | 0 | 0 | 0 | 1.48 | 29.6 |  | 29.6
0.08
| BE MAIN |  |  | 0.6 |  | 8 | 2 | 15.8 | 1.688 |  | 5 | 0.08 | 1.608 | 50.8128 | 50.8128
0.18
0.08
| BE OTHERS |  |  | 0.2656 |  | 8 | 2 | 15.8 | 1.0192 |  | 5 | 0.08 | 0.9392 | 29.6787 | 29.6787
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 2 | 15.8 | 0.34 |  | 2 | 0.032 | 0.308 | 9.7328 | 9.7328
0.08
0.08
| BE MAIN |  |  | 0.391 |  | 8 | 2 | 31.6 | 1.27 |  | 5 | 0.08 | 1.19 | 75.208 | 75.208
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 2 | 31.6 | 0.34 |  | 2 | 0.032 | 0.308 | 19.4656 | 19.4656
0.08
0.08
| MID MAIN |  |  | 1.082 |  | 8 | 2 | 8.4 | 2.652 |  | 5 | 0.08 | 2.572 | 43.2096 | 43.2096
0.18
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 2 | 9.4 | 0.34 |  | 2 | 0.032 | 0.308 | 5.7904 | 5.7904
0.08
11 | SW3 (230x1000)
| VERTICAL BARS A |  | 1.48 |  |  | 16 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  | 11.84
| VERTICAL BARS C |  |  |  |  | 12 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  | 11.84
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  | 11.84
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  | 11.84
0.08
| Stirupps a |  |  | 0.95 |  | 10 | 2 | 15.8 | 2.42 |  | 5 | 0.1 | 2.32 | 73.312 |  | 73.312
0.18
0.08
| Stirupps b |  |  | 0.13578 |  | 10 | 2 | 15.8 | 0.79156 |  | 5 | 0.1 | 0.69156 | 21.8532 |  | 21.8532
0.18
12 | SW4 (230x1150)
| VERTICAL BARS A |  | 1.48 |  |  | 16 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  | 11.84
| VERTICAL BARS C |  |  |  |  | 12 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  | 11.84
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  | 11.84
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  | 11.84
| VERTICAL BARS F |  |  |  |  | 12 | 2 | 2 | 1.48 | 0 | 0 | 0 | 1.48 | 5.92 |  |  | 5.92
0.08
| Stirupps a |  |  | 1.1 |  | 10 | 2 | 15.8 | 2.72 |  | 5 | 0.1 | 2.62 | 82.792 |  | 82.792
0.18
0.08
| Stirupps b |  |  | 0.1404 |  | 10 | 2 | 15.8 | 0.8008 |  | 5 | 0.1 | 0.7008 | 22.1453 |  | 22.1453
0.18
0.08
| Stirupps c |  | 0.18 |  |  | 10 | 2 | 15.8 | 0.34 |  | 2 | 0.04 | 0.3 | 9.48 |  | 9.48
0.08
13 | SW5 (230x1700)
| VERTICAL BARS A |  | 1.68 |  |  | 20 | 4 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  |  | 26.88
| VERTICAL BARS B |  |  |  |  | 20 | 4 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  |  | 26.88
| VERTICAL BARS C |  |  |  |  | 20 | 4 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  |  | 26.88
| VERTICAL BARS D |  |  |  |  | 16 | 4 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  | 26.88
| VERTICAL BARS E |  |  |  |  | 16 | 4 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  | 26.88
| VERTICAL BARS F |  |  |  |  | 16 | 4 | 8 | 1.68 | 0 | 0 | 0 | 1.68 | 53.76 |  |  |  | 53.76
| VERTICAL BARS G |  |  |  |  | 16 | 4 | 6 | 1.68 | 0 | 0 | 0 | 1.68 | 40.32 |  |  |  | 40.32
0.08
| Stirupps a |  |  | 1.65 |  | 10 | 4 | 17.8 | 3.82 |  | 5 | 0.1 | 3.72 | 264.864 |  | 264.864
0.18
0.08
| Stirupps b |  |  | 0.13787 |  | 10 | 4 | 17.8 | 0.79575 |  | 5 | 0.1 | 0.69575 | 49.5374 |  | 49.5374
0.18
0.08
| Stirupps c |  |  | 0.23975 |  | 10 | 4 | 17.8 | 0.9995 |  | 5 | 0.1 | 0.8995 | 64.0444 |  | 64.0444
0.18
0.08
| Stirupps d |  | 0.18 |  |  | 10 | 4 | 17.8 | 0.34 |  | 2 | 0.04 | 0.3 | 21.36 |  | 21.36
0.08
14 | SW6 (230x1185)
| VERTICAL BARS A |  | 1.48 |  |  | 16 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS B |  |  |  |  | 16 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS C |  |  |  |  | 16 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  | 11.84
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  | 11.84
| VERTICAL BARS F |  |  |  |  | 12 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  | 11.84
0.08
| Stirupps a |  |  | 1.135 |  | 10 | 2 | 15.8 | 2.79 |  | 5 | 0.1 | 2.69 | 85.004 |  | 85.004
0.18
0.08
| Stirupps b |  |  | 0.13773 |  | 10 | 2 | 15.8 | 0.79545 |  | 5 | 0.1 | 0.69545 | 21.9764 |  | 21.9764
0.18
14 | SW6 (230x1185)
| VERTICAL BARS A |  | 1.68 |  |  | 16 | 2 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 13.44 |  |  |  | 13.44
| VERTICAL BARS B |  |  |  |  | 16 | 2 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 13.44 |  |  |  | 13.44
| VERTICAL BARS C |  |  |  |  | 16 | 2 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 13.44 |  |  |  | 13.44
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 13.44 |  |  | 13.44
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 13.44 |  |  | 13.44
| VERTICAL BARS F |  |  |  |  | 12 | 2 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 13.44 |  |  | 13.44
0.08
| Stirupps a |  |  | 1.135 |  | 10 | 2 | 17.8 | 2.79 |  | 5 | 0.1 | 2.69 | 95.764 |  | 95.764
0.18
0.08
| Stirupps b |  |  | 0.13773 |  | 10 | 2 | 17.8 | 0.79545 |  | 5 | 0.1 | 0.69545 | 24.7582 |  | 24.7582
0.18
15 | SW7 (230x1855)
| VERTICAL BARS A |  | 1.48 |  |  | 16 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS B |  |  |  |  | 16 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS C |  |  |  |  | 16 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS D |  |  |  |  | 16 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS E |  |  |  |  | 16 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS F |  |  |  |  | 16 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS G |  |  |  |  | 16 | 2 | 4 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS H |  |  |  |  | 16 | 2 | 8 | 1.48 | 0 | 0 | 0 | 1.48 | 23.68 |  |  |  | 23.68
0.08
| Stirupps a |  |  | 1.805 |  | 10 | 2 | 15.8 | 4.13 |  | 5 | 0.1 | 4.03 | 127.348 |  | 127.348
0.18
0.08
| Stirupps b |  |  | 0.14124 |  | 10 | 2 | 15.8 | 0.80247 |  | 5 | 0.1 | 0.70247 | 22.1981 |  | 22.1981
0.18
16 | SW9 (230x650/1850)
| VERTICAL BARS A |  | 1.48 |  |  | 16 | 6 | 8 | 1.48 | 0 | 0 | 0 | 1.48 | 71.04 |  |  |  | 71.04
| VERTICAL BARS B |  |  |  |  | 16 | 6 | 16 | 1.48 | 0 | 0 | 0 | 1.48 | 142.08 |  |  |  | 142.08
| VERTICAL BARS C |  |  |  |  | 12 | 6 | 10 | 1.48 | 0 | 0 | 0 | 1.48 | 88.8 |  |  | 88.8
0.08
| BE MAIN |  |  | 0.6 |  | 8 | 6 | 15.8 | 1.688 |  | 5 | 0.08 | 1.608 | 152.4384 | 152.4384
0.18
0.08
| BE OTHERS |  |  | 0.2656 |  | 8 | 6 | 15.8 | 1.0192 |  | 5 | 0.08 | 0.9392 | 89.0362 | 89.0362
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 6 | 15.8 | 0.34 |  | 2 | 0.032 | 0.308 | 29.1984 | 29.1984
0.08
0.08
| BE MAIN |  |  | 0.391 |  | 8 | 6 | 31.6 | 1.27 |  | 5 | 0.08 | 1.19 | 225.624 | 225.624
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 6 | 31.6 | 0.34 |  | 2 | 0.032 | 0.308 | 58.3968 | 58.3968
0.08
0.08
| MID MAIN |  |  | 1.082 |  | 8 | 6 | 8.4 | 2.652 |  | 5 | 0.08 | 2.572 | 129.6288 | 129.6288
0.18
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 6 | 9.4 | 0.34 |  | 2 | 0.032 | 0.308 | 17.3712 | 17.3712
0.08
17 | SW10 (230x3445)
| VERTICAL BARS A |  | 1.68 |  |  | 16 | 2 | 8 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  | 26.88
| VERTICAL BARS B |  |  |  |  | 16 | 2 | 8 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  | 26.88
| VERTICAL BARS C |  |  |  |  | 12 | 2 | 8 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  | 26.88
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 4 | 1.68 | 0 | 0 | 0 | 1.68 | 13.44 |  |  | 13.44
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 20 | 1.68 | 0 | 0 | 0 | 1.68 | 67.2 |  |  | 67.2
0.08
| BE MAIN |  |  | 0.691 |  | 8 | 2 | 35.6 | 1.87 |  | 5 | 0.08 | 1.79 | 127.448 | 127.448
0.18
0.08
| MID MAIN |  |  | 2.052 |  | 8 | 2 | 9.4 | 4.592 |  | 5 | 0.08 | 4.512 | 84.8256 | 84.8256
0.18
0.08
| BE OTHERS |  |  | 0.11517 |  | 8 | 2 | 71.2 | 0.71833 |  | 5 | 0.08 | 0.63833 | 90.8987 | 90.8987
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 2 | 35.6 | 0.34 |  | 2 | 0.032 | 0.308 | 21.9296 | 21.9296
0.08
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 2 | 26 | 0.34 |  | 2 | 0.032 | 0.308 | 16.016 | 16.016
0.08
18 | SW11 (230x4065)
| VERTICAL BARS A |  | 1.68 |  |  | 16 | 2 | 8 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  | 26.88
| VERTICAL BARS B |  |  |  |  | 16 | 2 | 8 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  | 26.88
| VERTICAL BARS C |  |  |  |  | 12 | 2 | 8 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  | 26.88
| VERTICAL BARS D |  |  |  |  | 12 | 2 | 8 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  | 26.88
| VERTICAL BARS E |  |  |  |  | 12 | 2 | 8 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  | 26.88
| VERTICAL BARS F |  |  |  |  | 10 | 2 | 20 | 1.68 | 0 | 0 | 0 | 1.68 | 67.2 |  | 67.2
0.08
| BE MAIN |  |  | 0.991 |  | 8 | 2 | 35.6 | 2.47 |  | 5 | 0.08 | 2.39 | 170.168 | 170.168
0.18
0.08
| MID MAIN |  |  | 2.072 |  | 8 | 2 | 9.4 | 4.632 |  | 5 | 0.08 | 4.552 | 85.5776 | 85.5776
0.18
0.08
| BE OTHERS |  |  | 0.11011 |  | 8 | 2 | 142.4 | 0.70822 |  | 5 | 0.08 | 0.62822 | 178.9177 | 178.9177
0.18
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 2 | 26 | 0.34 |  | 2 | 0.032 | 0.308 | 16.016 | 16.016
0.08
19 | SW12 (230x650/1535)
| VERTICAL BARS A |  | 1.68 |  |  | 16 | 2 | 8 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  |  |  | 26.88
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 16 | 1.68 | 0 | 0 | 0 | 1.68 | 53.76 |  |  | 53.76
| VERTICAL BARS C |  |  |  |  | 10 | 2 | 8 | 1.68 | 0 | 0 | 0 | 1.68 | 26.88 |  | 26.88
0.08
| BE MAIN |  |  | 0.6 |  | 8 | 2 | 17.8 | 1.688 |  | 5 | 0.08 | 1.608 | 57.2448 | 57.2448
0.18
0.08
| BE OTHERS |  |  | 0.2656 |  | 8 | 2 | 17.8 | 1.0192 |  | 5 | 0.08 | 0.9392 | 33.4355 | 33.4355
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 2 | 17.8 | 0.34 |  | 2 | 0.032 | 0.308 | 10.9648 | 10.9648
0.08
0.08
| BE MAIN |  |  | 0.391 |  | 8 | 2 | 35.6 | 1.27 |  | 5 | 0.08 | 1.19 | 84.728 | 84.728
0.18
0.08
| BE OTHERS |  | 0.18 |  |  | 8 | 2 | 35.6 | 0.34 |  | 2 | 0.032 | 0.308 | 21.9296 | 21.9296
0.08
0.08
| MID MAIN |  |  | 0.767 |  | 8 | 2 | 9.4 | 2.022 |  | 5 | 0.08 | 1.942 | 36.5096 | 36.5096
0.18
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 2 | 10.4 | 0.34 |  | 2 | 0.032 | 0.308 | 6.4064 | 6.4064
0.08
20 | SW13 (230x3445)
| VERTICAL BARS A |  | 0.743 |  |  | 16 | 2 | 8 | 0.743 | 0 | 0 | 0 | 0.743 | 11.888 |  |  |  | 11.888
| VERTICAL BARS B |  |  |  |  | 12 | 2 | 8 | 0.743 | 0 | 0 | 0 | 0.743 | 11.888 |  |  | 11.888
| VERTICAL BARS C |  |  |  |  | 12 | 2 | 8 | 0.743 | 0 | 0 | 0 | 0.743 | 11.888 |  |  | 11.888
| VERTICAL BARS D |  |  |  |  | 10 | 2 | 22 | 0.743 | 0 | 0 | 0 | 0.743 | 32.692 |  | 32.692
0.08
| BE MAIN |  |  | 0.591 |  | 8 | 2 | 35.6 | 1.67 |  | 5 | 0.08 | 1.59 | 113.208 | 113.208
0.18
0.08
| MID MAIN |  |  | 2.252 |  | 8 | 2 | 9.4 | 4.992 |  | 5 | 0.08 | 4.912 | 92.3456 | 92.3456
0.18
0.08
| BE OTHERS |  |  | 0.1182 |  | 8 | 2 | 71.2 | 0.7244 |  | 5 | 0.08 | 0.6444 | 91.7626 | 91.7626
0.18
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 2 | 26 | 0.34 |  | 2 | 0.032 | 0.308 | 16.016 | 16.016
0.08
21 | LIFT WALL
| VERTICAL BARS |  | 1.68 |  |  | 10 | 8 | 26.3333 | 1.68 | 0 | 1 | 0.02 | 1.66 | 349.7067 |  | 349.7067
| BINDER |  | 1.9 |  | 0.2 | 8 | 8 | 17.8 | 1.9 | 0 | 1 | 0.016 | 1.884 | 268.2816 | 268.2816
| KENDA |  | 0.23 |  |  | 8 | 8 | 40 | 0.23 | 0 | 1 | 0.016 | 0.214 | 68.48 | 68.48
22 | SW8 (230x3600)
| VERTICAL BARS A |  | 1.48 |  |  | 16 | 1 | 8 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS B |  |  |  |  | 16 | 1 | 8 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS C |  |  |  |  | 16 | 1 | 8 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS D |  |  |  |  | 16 | 1 | 8 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS E |  |  |  |  | 16 | 1 | 8 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS F |  |  |  |  | 16 | 1 | 8 | 1.48 | 0 | 0 | 0 | 1.48 | 11.84 |  |  |  | 11.84
| VERTICAL BARS G |  |  |  |  | 12 | 1 | 12 | 1.48 | 0 | 0 | 0 | 1.48 | 17.76 |  |  | 17.76
0.08
| BE MAIN |  |  | 1.191 |  | 8 | 1 | 31.6 | 2.87 |  | 5 | 0.08 | 2.79 | 88.164 | 88.164
0.18
0.08
| MID MAIN |  |  | 1.207 |  | 8 | 1 | 8.4 | 2.902 |  | 5 | 0.08 | 2.822 | 23.7048 | 23.7048
0.18
0.08
| BE OTHERS |  |  | 0.2382 |  | 8 | 1 | 158 | 0.9644 |  | 5 | 0.08 | 0.8844 | 139.7352 | 139.7352
0.18
0.08
| MID OTHERS |  | 0.18 |  |  | 8 | 1 | 15.6 | 0.34 |  | 2 | 0.032 | 0.308 | 4.8048 | 4.8048
0.08
TOTAL
| TOTAL LENGTH IN METRE | [13 empty] | 4128.694 | 10258.886 | 1279.136 | 1896.688 | 907.52 | 67.2
| UNIT WEIGHT (IN KG) | [13 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.469 | 3.858
| TOTAL WEIGHT (IN KG) | [13 empty] | 1630.8341 | 6329.7327 | 1135.8728 | 2996.767 | 2240.6669 | 259.2576 | 14593.1311

## PLINTH BEAM BBS
Reinforcement
Sr. No. | Designation | Dia | C/C (mm) | No | No | No of Bars | Bar Length (mtr) |  |  | Lap Length | One Bar Length (MTR) | Dia Wise Weight (Kg)
[7 empty] | a | b | c |  |  | 8mm | 10mm | 12mm | 16mm | 20MM | 25mm
Typical Beam
200X450 | PB1 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 7.315 | 0.3 |  | 7.915 | 0 | 0 | 0 | 31.66 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 7.315 | 0.3 |  | 7.915 | 0 | 0 | 0 | 31.66 | 0 | 0
| TOP EXTRA | 0 |  | 2 | 1 | 2 | 0.3 | 1.52 |  |  | 1.82 | 0 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 9 |  | 1.188 |  |  | 1.188 | 21.38 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 8 |  | 1.188 |  |  | 1.188 | 19.01 | 0 | 0 | 0 | 0 | 0
200X450 | PB2 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 4.09 | 0.3 |  | 4.69 | 0 | 0 | 0 | 18.76 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 4.09 | 0.3 |  | 4.69 | 0 | 0 | 0 | 18.76 | 0 | 0
| TOP EXTRA | 0 |  | 2 | 1 | 2 | 0.3 | 1.52 |  |  | 1.82 | 0 | 0 | 0 | 0 | 0 | 0
3.3 | STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 11 |  | 1.188 |  |  | 1.188 | 26.14 | 0 | 0 | 0 | 0 | 0
100X450 | PB3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 10 |  | 4 | 1 | 2 | 0.3 | 1.865 | 0.3 |  | 2.465 | 0 | 19.72 | 0 | 0 | 0 | 0
| TOP | 10 |  | 4 | 1 | 2 | 0.3 | 1.865 | 0.3 |  | 2.465 | 0 | 19.72 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 4 | 1 | 10 |  | 1.008 |  |  | 1.008 | 40.32 | 0 | 0 | 0 | 0 | 0
100X450 | PB3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 10 |  | 2 | 1 | 2 | 0.3 | 1.47 | 0.3 |  | 2.07 | 0 | 8.28 | 0 | 0 | 0 | 0
| TOP | 10 |  | 2 | 1 | 2 | 0.3 | 1.47 | 0.3 |  | 2.07 | 0 | 8.28 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 2 | 1 | 9 |  | 1.008 |  |  | 1.008 | 18.14 | 0 | 0 | 0 | 0 | 0
100X450 | PB3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 10 |  | 6 | 1 | 2 | 0.3 | 1.64 | 0.3 |  | 2.24 | 0 | 26.88 | 0 | 0 | 0 | 0
| TOP | 10 |  | 6 | 1 | 2 | 0.3 | 1.64 | 0.3 |  | 2.24 | 0 | 26.88 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 6 | 1 | 10 |  | 1.008 |  |  | 1.008 | 60.48 | 0 | 0 | 0 | 0 | 0
100X450 | PB3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 10 |  | 6 | 1 | 2 | 0.3 | 1.81 | 0.3 |  | 2.41 | 0 | 28.92 | 0 | 0 | 0 | 0
| TOP | 10 |  | 6 | 1 | 2 | 0.3 | 1.81 | 0.3 |  | 2.41 | 0 | 28.92 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 6 | 1 | 11 |  | 1.008 |  |  | 1.008 | 66.53 | 0 | 0 | 0 | 0 | 0
100X450 | PB3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 10 |  | 6 | 1 | 2 | 0.3 | 1.31 | 0.3 |  | 1.91 | 0 | 22.92 | 0 | 0 | 0 | 0
| TOP | 10 |  | 6 | 1 | 2 | 0.3 | 1.31 | 0.3 |  | 1.91 | 0 | 22.92 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 150 | 6 | 1 | 7 |  | 1.008 |  |  | 1.008 | 42.34 | 0 | 0 | 0 | 0 | 0
200X450 | PB4 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 1.865 | 0.3 |  | 2.465 | 0 | 0 | 0 | 9.86 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 1.865 | 0.3 |  | 2.465 | 0 | 0 | 0 | 9.86 | 0 | 0
| STIRRUPS | 8 | 125 | 2 | 1 | 12 |  | 1.188 |  |  | 1.188 | 28.51 | 0 | 0 | 0 | 0 | 0
200X450 | PB5 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 3.54 | 0.3 |  | 4.14 | 0 | 0 | 16.56 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 3.54 | 0.3 |  | 4.14 | 0 | 0 | 16.56 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.188 |  |  | 1.188 | 23.76 | 0 | 0 | 0 | 0 | 0
200X450 | PB6 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 1 | 1 | 2 | 0.3 | 18.91 | 0.3 | 0.588 | 20.098 | 0 | 0 | 40.2 | 0 | 0 | 0
| TOP | 12 |  | 1 | 1 | 2 | 0.3 | 18.91 | 0.3 | 0.588 | 20.098 | 0 | 0 | 40.2 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 2 | 23 |  | 1.188 |  |  | 1.188 | 54.65 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 17 |  | 1.188 |  |  | 1.188 | 40.39 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 2 | 32 |  | 1.188 |  |  | 1.188 | 76.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 22 |  | 1.188 |  |  | 1.188 | 52.27 | 0 | 0 | 0 | 0 | 0
200X450 | PB7 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 7.145 | 0.3 |  | 7.745 | 0 | 0 | 0 | 30.98 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 7.145 | 0.3 |  | 7.745 | 0 | 0 | 0 | 30.98 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 8 |  | 1.188 |  |  | 1.188 | 19.01 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 9 |  | 1.188 |  |  | 1.188 | 21.38 | 0 | 0 | 0 | 0 | 0
200X450 | PB8 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 4.06 | 0.3 |  | 4.66 | 0 | 0 | 0 | 18.64 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 4.06 | 0.3 |  | 4.66 | 0 | 0 | 0 | 18.64 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.188 |  |  | 1.188 | 23.76 | 0 | 0 | 0 | 0 | 0
200X450 | PB9 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 6.305 | 0.3 |  | 6.905 | 0 | 0 | 0 | 27.62 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 6.305 | 0.3 |  | 6.905 | 0 | 0 | 0 | 27.62 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 21 |  | 1.188 |  |  | 1.188 | 49.9 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 15 |  | 1.188 |  |  | 1.188 | 35.64 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 16 |  | 1.188 |  |  | 1.188 | 38.02 | 0 | 0 | 0 | 0 | 0
200X450 | PB10 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 5.83 | 0.3 |  | 6.43 | 0 | 0 | 0 | 25.72 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 5.83 | 0.3 |  | 6.43 | 0 | 0 | 0 | 25.72 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 23 |  | 1.188 |  |  | 1.188 | 54.65 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 17 |  | 1.188 |  |  | 1.188 | 40.39 | 0 | 0 | 0 | 0 | 0
200X450 | PB11 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.3 | 12.89 | 0.3 | 0.784 | 14.274 | 0 | 0 | 0 | 28.55 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.3 | 12.89 | 0.3 | 0.784 | 14.274 | 0 | 0 | 0 | 28.55 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 2 | 2 |  | 1.46 |  |  | 1.46 | 0 | 0 | 5.84 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 1 | 2 |  | 3.83 |  |  | 3.83 | 0 | 0 | 7.66 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 1 | 2 | 2 | 0.3 | 2.37 |  |  | 2.67 | 0 | 0 | 10.68 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 1 | 2 | 29 |  | 1.188 |  |  | 1.188 | 68.9 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 20 |  | 1.188 |  |  | 1.188 | 47.52 | 0 | 0 | 0 | 0 | 0
200X450 | PB12 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 3.645 | 0.3 |  | 4.245 | 0 | 0 | 0 | 16.98 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 3.645 | 0.3 |  | 4.245 | 0 | 0 | 0 | 16.98 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 23 |  | 1.188 |  |  | 1.188 | 54.65 | 0 | 0 | 0 | 0 | 0
200X450 | PB13 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 4 | 0.3 |  | 4.6 | 0 | 0 | 0 | 18.4 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 4 | 0.3 |  | 4.6 | 0 | 0 | 0 | 18.4 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 31 |  | 1.188 |  |  | 1.188 | 73.66 | 0 | 0 | 0 | 0 | 0
200X450 | PB14 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 6 | 1 | 2 | 0.3 | 8.795 | 0.3 |  | 9.395 | 0 | 0 | 0 | 112.74 | 0 | 0
| TOP | 16 |  | 6 | 1 | 2 | 0.3 | 8.795 | 0.3 |  | 9.395 | 0 | 0 | 0 | 112.74 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 22 |  | 1.188 |  |  | 1.188 | 156.82 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 1 | 16 |  | 1.188 |  |  | 1.188 | 114.05 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 18 |  | 1.188 |  |  | 1.188 | 128.3 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 1 | 11 |  | 1.188 |  |  | 1.188 | 78.41 | 0 | 0 | 0 | 0 | 0
200X450 | PB15 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 3.655 | 0.3 |  | 4.255 | 0 | 0 | 17.02 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 3.655 | 0.3 |  | 4.255 | 0 | 0 | 17.02 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.188 |  |  | 1.188 | 23.76 | 0 | 0 | 0 | 0 | 0
230X450 | PB16 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 6.1 | 0.3 |  | 6.7 | 0 | 0 | 0 | 26.8 | 0 | 0
| TOP | 20 |  | 2 | 1 | 3 | 0.3 | 6.1 | 0.3 |  | 6.7 | 0 | 0 | 0 | 0 | 40.2 | 0
| STIRRUPS 230X450 | 8 | 100 | 2 | 1 | 18 |  | 1.248 |  |  | 1.248 | 44.93 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 7 |  | 1.248 |  |  | 1.248 | 17.47 | 0 | 0 | 0 | 0 | 0
230X450 | PB17 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.3 | 35.49 | 0.3 | 1.568 | 37.658 | 0 | 0 | 0 | 75.32 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.3 | 35.49 | 0.3 | 1.568 | 37.658 | 0 | 0 | 0 | 75.32 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 2 | 2 |  | 4.165 |  |  | 4.165 | 0 | 0 | 16.66 | 0 | 0 | 0
| BOTTOM EXTRA | 12 |  | 1 | 2 | 2 |  | 4.06 |  |  | 4.06 | 0 | 0 | 16.24 | 0 | 0 | 0
| TOP EXTRA | 16 |  | 1 | 1 | 2 |  | 3.63 | 0.3 |  | 3.93 | 0 | 0 | 0 | 7.86 | 0 | 0
| TOP EXTRA | 16 |  | 1 | 2 | 2 |  | 4 | 0.3 |  | 4.3 | 0 | 0 | 0 | 17.2 | 0 | 0
| TOP EXTRA | 16 |  | 1 | 2 | 2 |  | 2.7 | 0.3 |  | 3 | 0 | 0 | 0 | 12 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 2 | 39 |  | 1.248 |  |  | 1.248 | 97.34 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 2 | 29 |  | 1.248 |  |  | 1.248 | 72.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 21 |  | 1.248 |  |  | 1.248 | 52.42 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 2 | 29 |  | 1.248 |  |  | 1.248 | 72.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 1 | 2 | 20 |  | 1.248 |  |  | 1.248 | 49.92 | 0 | 0 | 0 | 0 | 0
200X450 | PB18 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 9.36 | 0.3 |  | 9.96 | 0 | 0 | 0 | 39.84 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 9.36 | 0.3 |  | 9.96 | 0 | 0 | 0 | 39.84 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 3.54 |  |  | 3.54 | 0 | 0 | 14.16 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 1 | 2 |  | 2.9 |  |  | 2.9 | 0 | 0 | 11.6 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 1 | 2 |  | 1.97 | 0.3 |  | 2.27 | 0 | 0 | 9.08 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 11 |  | 1.188 |  |  | 1.188 | 26.14 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 23 |  | 1.188 |  |  | 1.188 | 54.65 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 17 |  | 1.188 |  |  | 1.188 | 40.39 | 0 | 0 | 0 | 0 | 0
200X450 | PB19 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 6.17 | 0.3 |  | 6.77 | 0 | 0 | 0 | 27.08 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 6.17 | 0.3 |  | 6.77 | 0 | 0 | 0 | 27.08 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 4.53 |  |  | 4.53 | 0 | 0 | 18.12 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 2 | 2 |  | 1.87 | 0.3 |  | 2.17 | 0 | 0 | 17.36 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 28 |  | 1.188 |  |  | 1.188 | 66.53 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 20 |  | 1.188 |  |  | 1.188 | 47.52 | 0 | 0 | 0 | 0 | 0
200X450 | PB20 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 8.54 | 0.3 |  | 9.14 | 0 | 0 | 0 | 36.56 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 8.54 | 0.3 |  | 9.14 | 0 | 0 | 0 | 36.56 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 4.28 |  |  | 4.28 | 0 | 0 | 17.12 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 1 | 2 |  | 1.97 | 0.3 |  | 2.27 | 0 | 0 | 9.08 | 0 | 0 | 0
|  | 12 |  | 2 | 1 | 2 |  | 2.5 |  |  | 2.5 | 0 | 0 | 10 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 22 |  | 1.188 |  |  | 1.188 | 52.27 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 28 |  | 1.188 |  |  | 1.188 | 66.53 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 20 |  | 1.188 |  |  | 1.188 | 47.52 | 0 | 0 | 0 | 0 | 0
200X450 | PB21 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 6 | 1 | 2 | 0.3 | 8.795 | 0.3 |  | 9.395 | 0 | 0 | 0 | 112.74 | 0 | 0
| TOP | 16 |  | 6 | 1 | 2 | 0.3 | 8.795 | 0.3 |  | 9.395 | 0 | 0 | 0 | 112.74 | 0 | 0
| BOTTOM EXTRA | 12 |  | 6 | 1 | 2 |  | 3.57 |  |  | 3.57 | 0 | 0 | 42.84 | 0 | 0 | 0
| TOP EXTRA | 16 |  | 6 | 1 | 2 |  | 2.6 |  |  | 2.6 | 0 | 0 | 0 | 31.2 | 0 | 0
|  | 16 |  | 6 | 1 | 2 | 0.3 | 1.67 |  |  | 1.97 | 0 | 0 | 0 | 23.64 | 0 | 0
|  | 12 |  | 6 | 1 | 2 |  | 1.17 | 0.3 |  | 1.47 | 0 | 0 | 17.64 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 24 |  | 1.188 |  |  | 1.188 | 171.07 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 1 | 17 |  | 1.188 |  |  | 1.188 | 121.18 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 18 |  | 1.188 |  |  | 1.188 | 128.3 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 6 | 1 | 11 |  | 1.188 |  |  | 1.188 | 78.41 | 0 | 0 | 0 | 0 | 0
200X450 | PB22 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 6 | 1 | 2 | 0.3 | 6.885 | 0.3 |  | 7.485 | 0 | 0 | 0 | 89.82 | 0 | 0
| TOP | 16 |  | 6 | 1 | 2 | 0.3 | 6.885 | 0.3 |  | 7.485 | 0 | 0 | 0 | 89.82 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 18 |  | 1.188 |  |  | 1.188 | 128.3 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 1 | 10 |  | 1.188 |  |  | 1.188 | 71.28 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 18 |  | 1.188 |  |  | 1.188 | 128.3 | 0 | 0 | 0 | 0 | 0
|  | 8 | 100 | 6 | 1 | 6 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
200X450 | PB23 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 5.665 | 0.3 |  | 6.265 | 0 | 0 | 0 | 25.06 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 5.665 | 0.3 |  | 6.265 | 0 | 0 | 0 | 25.06 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 4.14 |  |  | 4.14 | 0 | 0 | 16.56 | 0 | 0 | 0
| TOP EXTRA | 16 |  | 2 | 2 | 2 | 0.3 | 1.77 |  |  | 2.07 | 0 | 0 | 0 | 16.56 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 23 |  | 1.188 |  |  | 1.188 | 54.65 | 0 | 0 | 0 | 0 | 0
200X450 | PB24 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 20 |  | 2 | 1 | 2 | 0.3 | 1.87 | 0.3 |  | 2.47 | 0 | 0 | 0 | 0 | 9.88 | 0
| TOP | 20 |  | 2 | 1 | 2 | 0.3 | 1.87 | 0.3 |  | 2.47 | 0 | 0 | 0 | 0 | 9.88 | 0
| STIRRUPS 200X450 | 8 | 125 | 2 | 1 | 12 |  | 1.188 |  |  | 1.188 | 28.51 | 0 | 0 | 0 | 0 | 0
200X450 | PB25 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 11.295 | 0.3 |  | 11.895 | 0 | 0 | 0 | 47.58 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 11.295 | 0.3 |  | 11.895 | 0 | 0 | 0 | 47.58 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 41 |  | 1.188 |  |  | 1.188 | 97.42 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 30 |  | 1.188 |  |  | 1.188 | 71.28 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 2 | 1 | 18 |  | 1.312 |  |  | 1.312 | 47.23 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 150 | 2 | 1 | 9 |  | 1.312 |  |  | 1.312 | 23.62 | 0 | 0 | 0 | 0 | 0
230X450 | PB26 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 1 | 1 | 2 | 0.3 | 18.85 | 0.3 | 0.784 | 20.234 | 0 | 0 | 0 | 40.47 | 0 | 0
| TOP | 16 |  | 1 | 1 | 2 | 0.3 | 18.85 | 0.3 | 0.784 | 20.234 | 0 | 0 | 0 | 40.47 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 2 | 4 |  | 1.248 |  |  | 1.248 | 9.98 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 2 | 23 |  | 1.248 |  |  | 1.248 | 57.41 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 150 | 1 | 2 | 17 |  | 1.248 |  |  | 1.248 | 42.43 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 1 | 1 | 32 |  | 1.248 |  |  | 1.248 | 39.94 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 230X450 | 8 | 150 | 1 | 1 | 22 |  | 1.248 |  |  | 1.248 | 27.46 | 0 | 0 | 0 | 0 | 0
230X450 | PB27 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 4.35 | 0.3 |  | 4.95 | 0 | 0 | 0 | 19.8 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 4.35 | 0.3 |  | 4.95 | 0 | 0 | 0 | 19.8 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 2 | 1 | 18 |  | 1.248 |  |  | 1.248 | 44.93 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 13 |  | 1.248 |  |  | 1.248 | 32.45 | 0 | 0 | 0 | 0 | 0
200X450 | PB28 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 3.775 | 0.3 |  | 4.375 | 0 | 0 | 17.5 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 3.775 | 0.3 |  | 4.375 | 0 | 0 | 17.5 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 9 |  | 1.188 |  |  | 1.188 | 21.38 | 0 | 0 | 0 | 0 | 0
200X450 | PB29 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 11.04 | 0.3 |  | 11.64 | 0 | 0 | 0 | 46.56 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 11.04 | 0.3 |  | 11.64 | 0 | 0 | 0 | 46.56 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 3.85 |  |  | 3.85 | 0 | 0 | 15.4 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 1 | 2 |  | 3.3 |  |  | 3.3 | 0 | 0 | 13.2 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 2 | 2 | 0.3 | 1.77 |  |  | 2.07 | 0 | 0 | 16.56 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 2 | 26 |  | 1.188 |  |  | 1.188 | 123.55 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 2 | 18 |  | 1.188 |  |  | 1.188 | 85.54 | 0 | 0 | 0 | 0 | 0
200X450 | PB30 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 7.02 | 0.3 |  | 7.62 | 0 | 0 | 0 | 30.48 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 7.02 | 0.3 |  | 7.62 | 0 | 0 | 0 | 30.48 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 2 | 18 |  | 1.188 |  |  | 1.188 | 85.54 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 2 | 10 |  | 1.188 |  |  | 1.188 | 47.52 | 0 | 0 | 0 | 0 | 0
200X450 | PB31 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 6 | 1 | 2 | 0.3 | 8.98 | 0.3 |  | 9.58 | 0 | 0 | 114.96 | 0 | 0 | 0
| TOP | 12 |  | 6 | 1 | 2 | 0.3 | 8.98 | 0.3 |  | 9.58 | 0 | 0 | 114.96 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 18 |  | 1.188 |  |  | 1.188 | 128.3 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 1 | 13 |  | 1.188 |  |  | 1.188 | 92.66 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 19 |  | 1.188 |  |  | 1.188 | 135.43 | 0 | 0 | 0 | 0 | 0
100X450 | PB32 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 18 | 1 | 2 | 0.3 | 0.655 | 0.3 |  | 1.255 | 0 | 0 | 45.18 | 0 | 0 | 0
| TOP | 12 |  | 18 | 1 | 2 | 0.3 | 0.655 | 0.3 |  | 1.255 | 0 | 0 | 45.18 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 18 | 1 | 5 |  | 1.008 |  |  | 1.008 | 90.72 | 0 | 0 | 0 | 0 | 0
200X450 | PB33 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 6 | 1 | 2 | 0.3 | 3.89 | 0.3 |  | 4.49 | 0 | 0 | 53.88 | 0 | 0 | 0
| TOP | 12 |  | 6 | 1 | 2 | 0.3 | 3.89 | 0.3 |  | 4.49 | 0 | 0 | 53.88 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 2 | 18 |  | 1.188 |  |  | 1.188 | 256.61 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 2 | 12 |  | 1.188 |  |  | 1.188 | 171.07 | 0 | 0 | 0 | 0 | 0
200X450 | PB34 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 6 | 1 | 2 | 0.3 | 4.2 | 0.3 |  | 4.8 | 0 | 0 | 0 | 57.6 | 0 | 0
| TOP | 16 |  | 6 | 1 | 2 | 0.3 | 4.2 | 0.3 |  | 4.8 | 0 | 0 | 0 | 57.6 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 18 |  | 1.188 |  |  | 1.188 | 128.3 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 1 | 9 |  | 1.188 |  |  | 1.188 | 64.15 | 0 | 0 | 0 | 0 | 0
200X450 | PB35 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 11.97 | 0.3 | 0.784 | 13.354 | 0 | 0 | 0 | 53.42 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 11.97 | 0.3 | 0.784 | 13.354 | 0 | 0 | 0 | 53.42 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 2.93 |  |  | 2.93 | 0 | 0 | 11.72 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 2 | 2 |  | 2.85 |  |  | 2.85 | 0 | 0 | 22.8 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 31 |  | 1.188 |  |  | 1.188 | 73.66 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 21 |  | 1.188 |  |  | 1.188 | 49.9 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 15 |  | 1.188 |  |  | 1.188 | 35.64 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 9 |  | 1.188 |  |  | 1.188 | 21.38 | 0 | 0 | 0 | 0 | 0
200X450 | PB36 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 6 | 1 | 2 | 0.3 | 4.715 | 0.3 |  | 5.315 | 0 | 0 | 0 | 63.78 | 0 | 0
| TOP | 16 |  | 6 | 1 | 2 | 0.3 | 4.715 | 0.3 |  | 5.315 | 0 | 0 | 0 | 63.78 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 20 |  | 1.188 |  |  | 1.188 | 142.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 6 | 1 | 10 |  | 1.188 |  |  | 1.188 | 71.28 | 0 | 0 | 0 | 0 | 0
200X450 | PB37 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 6 | 1 | 2 | 0.3 | 5.13 | 0.3 |  | 5.73 | 0 | 0 | 68.76 | 0 | 0 | 0
| TOP | 12 |  | 6 | 1 | 2 | 0.3 | 5.13 | 0.3 |  | 5.73 | 0 | 0 | 68.76 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 6 | 1 | 47 |  | 1.188 |  |  | 1.188 | 335.02 | 0 | 0 | 0 | 0 | 0
200X450 | PB38 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 6.685 | 0.3 |  | 7.285 | 0 | 0 | 29.14 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 6.685 | 0.3 |  | 7.285 | 0 | 0 | 29.14 | 0 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 4.245 |  |  | 4.245 | 0 | 0 | 16.98 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 2 | 2 |  | 2.22 | 0.3 |  | 2.52 | 0 | 0 | 20.16 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 26 |  | 1.188 |  |  | 1.188 | 61.78 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
200X450 | PB39 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 2.4 | 0.944 |  | 3.644 | 0 | 0 | 14.58 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 2.4 | 0.944 |  | 3.644 | 0 | 0 | 14.58 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 23 |  | 1.188 |  |  | 1.188 | 54.65 | 0 | 0 | 0 | 0 | 0
200X450 | PB40 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 6.07 | 0.3 |  | 6.67 | 0 | 0 | 0 | 26.68 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 6.07 | 0.3 |  | 6.67 | 0 | 0 | 0 | 26.68 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 51 |  | 1.188 |  |  | 1.188 | 121.18 | 0 | 0 | 0 | 0 | 0
200X450 | PB41 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 6.585 | 0.3 |  | 7.185 | 0 | 0 | 0 | 28.74 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 6.585 | 0.3 |  | 7.185 | 0 | 0 | 0 | 28.74 | 0 | 0
| BOTTOM EXTRA | 12 |  | 2 | 1 | 2 |  | 4.245 |  |  | 4.245 | 0 | 0 | 16.98 | 0 | 0 | 0
| TOP EXTRA | 12 |  | 2 | 2 | 2 |  | 2.22 | 0.3 |  | 2.52 | 0 | 0 | 20.16 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 26 |  | 1.188 |  |  | 1.188 | 61.78 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
230X450 | PB42 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 4.12 | 0.3 |  | 4.72 | 0 | 0 | 0 | 18.88 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 4.12 | 0.3 |  | 4.72 | 0 | 0 | 0 | 18.88 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 2 | 1 | 18 |  | 1.248 |  |  | 1.248 | 44.93 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.248 |  |  | 1.248 | 24.96 | 0 | 0 | 0 | 0 | 0
200X450 | PB43 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 3.39 | 0.3 |  | 3.99 | 0 | 0 | 15.96 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 3.39 | 0.3 |  | 3.99 | 0 | 0 | 15.96 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 9 |  | 1.188 |  |  | 1.188 | 21.38 | 0 | 0 | 0 | 0 | 0
200X450 | PB44 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 5.69 | 0.3 |  | 6.29 | 0 | 0 | 0 | 25.16 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 5.69 | 0.3 |  | 6.29 | 0 | 0 | 0 | 25.16 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 19 |  | 1.188 |  |  | 1.188 | 45.14 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 14 |  | 1.188 |  |  | 1.188 | 33.26 | 0 | 0 | 0 | 0 | 0
200X450 | PB45 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 5.69 | 0.3 |  | 6.29 | 0 | 0 | 0 | 25.16 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 5.69 | 0.3 |  | 6.29 | 0 | 0 | 0 | 25.16 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 23 |  | 1.188 |  |  | 1.188 | 54.65 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 16 |  | 1.188 |  |  | 1.188 | 38.02 | 0 | 0 | 0 | 0 | 0
200X450 | PB46 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 3.89 | 0.3 |  | 4.49 | 0 | 0 | 0 | 17.96 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 3.89 | 0.3 |  | 4.49 | 0 | 0 | 0 | 17.96 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 9 |  | 1.188 |  |  | 1.188 | 21.38 | 0 | 0 | 0 | 0 | 0
200X450 | PB47 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 4.255 | 0.3 |  | 4.855 | 0 | 0 | 19.42 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 4.255 | 0.3 |  | 4.855 | 0 | 0 | 19.42 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.188 |  |  | 1.188 | 23.76 | 0 | 0 | 0 | 0 | 0
200X450 | PB48 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.2 | 2.715 | 0.2 |  | 3.115 | 0 | 0 | 12.46 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.2 | 2.715 | 0.2 |  | 3.115 | 0 | 0 | 12.46 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 15 |  | 1.188 |  |  | 1.188 | 35.64 | 0 | 0 | 0 | 0 | 0
230X450 | PB49 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 0.69 | 0.3 |  | 1.29 | 0 | 0 | 5.16 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 0.69 | 0.3 |  | 1.29 | 0 | 0 | 5.16 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 8 |  | 1.248 |  |  | 1.248 | 19.97 | 0 | 0 | 0 | 0 | 0
230X450 | PB50 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.944 | 2.33 | 0.3 |  | 3.574 | 0 | 0 | 14.3 | 0 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.944 | 2.33 | 0.3 |  | 3.574 | 0 | 0 | 0 | 14.3 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 23 |  | 1.248 |  |  | 1.248 | 57.41 | 0 | 0 | 0 | 0 | 0
230X450 | PB51 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 4.12 | 0.3 |  | 4.72 | 0 | 0 | 0 | 18.88 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 4.12 | 0.3 |  | 4.72 | 0 | 0 | 0 | 18.88 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 2 | 1 | 18 |  | 1.248 |  |  | 1.248 | 44.93 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.248 |  |  | 1.248 | 24.96 | 0 | 0 | 0 | 0 | 0
230X450 | PB 52 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 18.915 | 0.3 | 0.784 | 20.299 | 0 | 0 | 0 | 81.2 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 18.915 | 0.3 | 0.784 | 20.299 | 0 | 0 | 0 | 81.2 | 0 | 0
| STIRRUPS 230X450 | 8 | 100 | 2 | 1 | 18 |  | 1.248 |  |  | 1.248 | 44.93 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 6 |  | 1.248 |  |  | 1.248 | 14.98 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 2 | 18 |  | 1.188 |  |  | 1.188 | 85.54 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 2 | 12 |  | 1.188 |  |  | 1.188 | 57.02 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.188 |  |  | 1.188 | 23.76 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 2 | 1 | 20 |  | 1.188 |  |  | 1.188 | 47.52 | 0 | 0 | 0 | 0 | 0
200X450 | PB53 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 4 | 1 | 2 | 0.3 | 3.165 | 0.3 |  | 3.765 | 0 | 0 | 30.12 | 0 | 0 | 0
| TOP | 12 |  | 4 | 1 | 2 | 0.3 | 3.165 | 0.3 |  | 3.765 | 0 | 0 | 30.12 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 4 | 1 | 23 |  | 1.188 |  |  | 1.188 | 109.3 | 0 | 0 | 0 | 0 | 0
200X450 | PB54 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 3.9 | 0.3 |  | 4.5 | 0 | 0 | 18 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 3.9 | 0.3 |  | 4.5 | 0 | 0 | 18 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 8 |  | 1.188 |  |  | 1.188 | 19.01 | 0 | 0 | 0 | 0 | 0
200X450 | PB55 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 3.9 | 0.3 |  | 4.5 | 0 | 0 | 0 | 18 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 3.9 | 0.3 |  | 4.5 | 0 | 0 | 0 | 18 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 8 |  | 1.188 |  |  | 1.188 | 19.01 | 0 | 0 | 0 | 0 | 0
200X450 | PB56 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 2.03 | 0.3 |  | 2.63 | 0 | 0 | 10.52 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 2.03 | 0.3 |  | 2.63 | 0 | 0 | 10.52 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 19 |  | 1.188 |  |  | 1.188 | 45.14 | 0 | 0 | 0 | 0 | 0
200X450 | PB57 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 4 | 1 | 2 | 0.3 | 3.59 | 0.3 |  | 4.19 | 0 | 0 | 0 | 33.52 | 0 | 0
| TOP | 16 |  | 4 | 1 | 2 | 0.3 | 3.59 | 0.3 |  | 4.19 | 0 | 0 | 0 | 33.52 | 0 | 0
| STIRRUPS | 8 | 100 | 4 | 1 | 18 |  | 1.188 |  |  | 1.188 | 85.54 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
200X450 | PB58 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 16 |  | 2 | 1 | 2 | 0.3 | 7.34 | 0.3 |  | 7.94 | 0 | 0 | 0 | 31.76 | 0 | 0
| TOP | 16 |  | 2 | 1 | 2 | 0.3 | 7.34 | 0.3 |  | 7.94 | 0 | 0 | 0 | 31.76 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 34 |  | 1.188 |  |  | 1.188 | 80.78 | 0 | 0 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 12 |  | 1.188 |  |  | 1.188 | 28.51 | 0 | 0 | 0 | 0 | 0
200X450 | PB59 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 7.34 | 0.3 |  | 7.94 | 0 | 0 | 31.76 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 7.34 | 0.3 |  | 7.94 | 0 | 0 | 31.76 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 65 |  | 1.188 |  |  | 1.188 | 154.44 | 0 | 0 | 0 | 0 | 0
200X450 | PB60 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 4 | 1 | 2 | 0.3 | 5.49 | 0.3 |  | 6.09 | 0 | 0 | 48.72 | 0 | 0 | 0
| TOP | 12 |  | 4 | 1 | 2 | 0.3 | 5.49 | 0.3 |  | 6.09 | 0 | 0 | 48.72 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 4 | 1 | 18 |  | 1.188 |  |  | 1.188 | 85.54 | 0 | 0 | 0 | 0 | 0
| STIRRUPS 200X450 | 8 | 100 | 4 | 1 | 18 |  | 1.188 |  |  | 1.188 | 85.54 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
200X450 | PB61 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BOTTOM | 12 |  | 2 | 1 | 2 | 0.3 | 3.54 | 0.3 |  | 4.14 | 0 | 0 | 16.56 | 0 | 0 | 0
| TOP | 12 |  | 2 | 1 | 2 | 0.3 | 3.54 | 0.3 |  | 4.14 | 0 | 0 | 16.56 | 0 | 0 | 0
| STIRRUPS | 8 | 100 | 2 | 1 | 18 |  | 1.188 |  |  | 1.188 | 42.77 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 2 | 1 | 10 |  | 1.188 |  |  | 1.188 | 23.76 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL UPTO PLINTH | [10 empty] | 3492.1437 | 131.6925 | 1475.6962 | 4761.2984 | 147.5016 | 0 | 10008.3323
[6 empty] | 178.6 | 6 | 1071.6
[6 empty] | 160 | 5 | 800
[6 empty] | 87 | 4.5 | 391.5
[6 empty] | 78.6 | 4.5 | 353.7
[6 empty] | 135 | 4.5 | 607.5
[6 empty] | 20 | 8.5 | 170
[6 empty] | 90 | 4.5 | 405
[6 empty] | 90 | 4.5 | 405
[6 empty] | 137.5 | 4.5 | 618.75
[6 empty] | 100 | 4.5 | 450
[6 empty] | 92 | 4.5 | 414
[6 empty] | 50 | 6 | 300
[6 empty] | 60 | 6 | 360
[6 empty] | 129 | 5 | 645
[6 empty] | 118 | 4.5 | 531
[6 empty] | 115 | 4.5 | 517.5
[6 empty] | 95 | 4.5 | 427.5
[6 empty] | 86 | 4.5 | 387
[6 empty] | 156 | 4.5 | 702
[6 empty] | 153 | 6 | 918
[6 empty] | 78 | 4.5 | 351
[6 empty] | 61 | 4.5 | 274.5
[8 empty] | 11100.55 | 119486.3202

## TYP COL BBS
Reinforcement
Sr. No. | Designation | Dia | C/C (mm) | No | No | No of Bars | Bar Length (mtr) |  |  | Lap Length | One Bar Length (MTR) | Dia Wise Weight (Kg)
[7 empty] | a | b | c |  |  | 8mm | 10mm | 12mm | 16mm | 20MM | 25mm
Column From Plinth Level to 1st Floor Lvl (103.25-100.15)
28 | C 1 (300X600) | 16 |  | 28 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 789.82 | 0 | 0 | 224
|  | 12 |  | 28 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 568.18 | 0 | 0 | 0 | 168
| Stirrups ZONE A | 10 | 75 | 28 | 2 | 12 |  | 1.64 |  |  | 1.64 | 0 | 1102.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 389.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 4 | 8 |  | 0.716 |  |  | 0.716 | 0 | 641.54 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 28 | 1 | 10 |  | 1.608 |  |  | 1.608 | 450.24 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 1 | 10 |  | 0.828 |  |  | 0.828 | 231.84 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 2 | 10 |  | 0.684 |  |  | 0.684 | 383.04 | 0 | 0 | 0 | 0 | 0
12 | C 2 (300X600) | 20 |  | 12 | 1 | 6 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 264.24 | 0 | 72
|  | 16 |  | 12 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 338.5 | 0 | 0 | 96
| Stirrups ZONE A | 10 | 75 | 12 | 2 | 12 |  | 1.64 |  |  | 1.64 | 0 | 472.32 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 167.04 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 4 | 8 |  | 0.716 |  |  | 0.716 | 0 | 274.94 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 12 | 1 | 10 |  | 1.608 |  |  | 1.608 | 192.96 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 1 | 10 |  | 0.828 |  |  | 0.828 | 99.36 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 2 | 10 |  | 0.684 |  |  | 0.684 | 164.16 | 0 | 0 | 0 | 0 | 0
4 | C 3 (300X600) | 25 |  | 4 | 1 | 14 |  | 2.95 |  | 0.9 | 3.85 | 0 | 0 | 0 | 0 | 0 | 215.6 | 56
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 12 |  | 1.64 |  |  | 1.64 | 0 | 157.44 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 55.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.716 |  |  | 0.716 | 0 | 91.65 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 10 |  | 1.608 |  |  | 1.608 | 64.32 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 10 |  | 0.838 |  |  | 0.838 | 33.52 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 10 |  | 0.684 |  |  | 0.684 | 54.72 | 0 | 0 | 0 | 0 | 0
16 | C 4 (300X750) | 20 |  | 16 | 1 | 16 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 939.52 | 0 | 256
| Stirrups ZONE A | 10 | 75 | 16 | 2 | 14 |  | 1.94 |  |  | 1.94 | 0 | 869.12 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 1.1 |  |  | 1.1 | 0 | 352 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 4 | 10 |  | 0.716 |  |  | 0.716 | 0 | 458.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 134.4 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 16 | 1 | 8 |  | 1.908 |  |  | 1.908 | 244.22 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 8 |  | 1.068 |  |  | 1.068 | 136.7 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 2 | 8 |  | 0.684 |  |  | 0.684 | 175.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 8 |  | 0.38 |  |  | 0.38 | 48.64 | 0 | 0 | 0 | 0 | 0
14 | C 5 (300X750) | 16 |  | 14 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 493.64 | 0 | 0 | 140
|  | 12 |  | 14 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 284.09 | 0 | 0 | 0 | 84
| Stirrups ZONE A | 10 | 75 | 14 | 2 | 14 |  | 1.94 |  |  | 1.94 | 0 | 760.48 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 1.1 |  |  | 1.1 | 0 | 308 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 4 | 10 |  | 0.716 |  |  | 0.716 | 0 | 400.96 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 117.6 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 14 | 1 | 8 |  | 1.908 |  |  | 1.908 | 213.7 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 8 |  | 1.068 |  |  | 1.068 | 119.62 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 2 | 8 |  | 0.684 |  |  | 0.684 | 153.22 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 8 |  | 0.38 |  |  | 0.38 | 42.56 | 0 | 0 | 0 | 0 | 0
10 | C 6 (300X715) | 16 |  | 10 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0 | 40
|  | 12 |  | 10 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 405.84 | 0 | 0 | 0 | 120
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 14 |  | 1.87 |  |  | 1.87 | 0 | 523.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 1.07 |  |  | 1.07 | 0 | 214 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 10 |  | 0.716 |  |  | 0.716 | 0 | 286.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 84 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 9 |  | 1.838 |  |  | 1.838 | 165.42 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 9 |  | 1.038 |  |  | 1.038 | 93.42 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 9 |  | 0.684 |  |  | 0.684 | 123.12 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 9 |  | 0.38 |  |  | 0.38 | 34.2 | 0 | 0 | 0 | 0 | 0
4 | C 7 (300X800) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 4 | 1 | 14 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 189.39 | 0 | 0 | 0 | 56
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 15 |  | 2.04 |  |  | 2.04 | 0 | 244.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.87 |  |  | 0.87 | 0 | 153.12 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.716 |  |  | 0.716 | 0 | 126.02 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 8 |  | 2.008 |  |  | 2.008 | 64.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 8 |  | 0.828 |  |  | 0.828 | 52.99 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 8 |  | 0.684 |  |  | 0.684 | 43.78 | 0 | 0 | 0 | 0 | 0
4 | C 8 (300X600) | 20 |  | 4 | 1 | 10 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 146.8 | 0 | 40
|  | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 12 |  | 1.64 |  |  | 1.64 | 0 | 157.44 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 55.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.716 |  |  | 0.716 | 0 | 91.65 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 10 |  | 1.608 |  |  | 1.608 | 64.32 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 10 |  | 0.828 |  |  | 0.828 | 33.12 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 10 |  | 0.684 |  |  | 0.684 | 54.72 | 0 | 0 | 0 | 0 | 0
4 | C 9 (300X600) | 20 |  | 4 | 1 | 4 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 58.72 | 0 | 16
|  | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0 | 32
|  | 12 |  | 4 | 1 | 2 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 27.06 | 0 | 0 | 0 | 8
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 12 |  | 1.64 |  |  | 1.64 | 0 | 157.44 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 55.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.716 |  |  | 0.716 | 0 | 91.65 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 10 |  | 1.608 |  |  | 1.608 | 64.32 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 10 |  | 0.828 |  |  | 0.828 | 33.12 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 10 |  | 0.684 |  |  | 0.684 | 54.72 | 0 | 0 | 0 | 0 | 0
10 | C 10 (300X600) | 25 |  | 10 | 1 | 4 |  | 2.95 |  | 0.9 | 3.85 | 0 | 0 | 0 | 0 | 0 | 154 | 40
|  | 20 |  | 10 | 1 | 10 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 367 | 0 | 100
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 12 |  | 1.64 |  |  | 1.64 | 0 | 393.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 139.2 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 8 |  | 0.716 |  |  | 0.716 | 0 | 229.12 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 10 |  | 1.608 |  |  | 1.608 | 160.8 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 10 |  | 0.828 |  |  | 0.828 | 82.8 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 10 |  | 0.684 |  |  | 0.684 | 136.8 | 0 | 0 | 0 | 0 | 0
4 | C 11 (300X715) | 16 |  | 4 | 1 | 14 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 197.46 | 0 | 0 | 56
|  | 12 |  | 4 | 1 | 2 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 27.06 | 0 | 0 | 0 | 8
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 14 |  | 1.87 |  |  | 1.87 | 0 | 209.44 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 1.07 |  |  | 1.07 | 0 | 85.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 10 |  | 0.716 |  |  | 0.716 | 0 | 114.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 33.6 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.838 |  |  | 1.838 | 66.17 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 1.102 |  |  | 1.102 | 39.67 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.684 |  |  | 0.684 | 49.25 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.38 |  |  | 0.38 | 13.68 | 0 | 0 | 0 | 0 | 0
| Shear wall from plinth level to 1st floor LVL | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | SW 1 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0 | 32
|  | 10 |  | 2 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 52.96 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 31 |  | 1.688 |  |  | 1.688 | 104.66 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X256) | 8 | 100 | 2 | 1 | 27 |  | 1 |  |  | 1 | 54 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 27 |  | 0.34 |  |  | 0.34 | 18.36 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 4 |  | 1.258 |  |  | 1.258 | 20.13 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 27 |  | 1.024 |  |  | 1.024 | 55.3 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 27 |  | 0.34 |  |  | 0.34 | 18.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X866) | 8 | 200 | 2 | 1 | 18 |  | 2.22 |  |  | 2.22 | 79.92 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
2 | SW 2 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0 | 32
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 31 |  | 1.688 |  |  | 1.688 | 104.66 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X256) | 8 | 100 | 2 | 1 | 27 |  | 1 |  |  | 1 | 54 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 27 |  | 0.34 |  |  | 0.34 | 18.36 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 31 |  | 1.258 |  |  | 1.258 | 155.99 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 27 |  | 1.024 |  |  | 1.024 | 55.3 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 27 |  | 0.34 |  |  | 0.34 | 18.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 2 | 1 | 18 |  | 2.62 |  |  | 2.62 | 94.32 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
2 | SW 3 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0 | 8
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0 | 32
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X950) | 8 | 100 | 2 | 1 | 31 |  | 2.388 |  |  | 2.388 | 148.06 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 2 | 4 | 27 |  | 0.728 |  |  | 0.728 | 157.25 | 0 | 0 | 0 | 0 | 0
2 | SW 4 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0 | 8
|  | 12 |  | 2 | 1 | 18 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 121.75 | 0 | 0 | 0 | 36
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1100) | 8 | 100 | 2 | 1 | 31 |  | 2.688 |  |  | 2.688 | 166.66 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X125) | 8 | 100 | 2 | 4 | 27 |  | 0.738 |  |  | 0.738 | 159.41 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 27 |  | 0.34 |  |  | 0.34 | 18.36 | 0 | 0 | 0 | 0 | 0
4 | SW 5A | 16 |  | 4 | 1 | 24 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 338.5 | 0 | 0 | 96
|  | 12 |  | 4 | 1 | 4 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0 | 16
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X583) | 8 | 100 | 4 | 2 | 31 |  | 1.654 |  |  | 1.654 | 410.19 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 4 | 4 | 27 |  | 0.728 |  |  | 0.728 | 314.5 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X516) | 8 | 200 | 4 | 1 | 18 |  | 1.52 |  |  | 1.52 | 109.44 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 4 | 2 | 7 |  | 0.34 |  |  | 0.34 | 19.04 | 0 | 0 | 0 | 0 | 0
4 | SW 6 | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0 | 32
|  | 12 |  | 4 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 216.45 | 0 | 0 | 0 | 64
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1135) | 8 | 100 | 4 | 1 | 31 |  | 2.758 |  |  | 2.758 | 341.99 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X118) | 8 | 100 | 4 | 5 | 27 |  | 0.724 |  |  | 0.724 | 390.96 | 0 | 0 | 0 | 0 | 0
2 | SW 7A | 16 |  | 2 | 1 | 24 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 169.25 | 0 | 0 | 48
|  | 12 |  | 2 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 40.58 | 0 | 0 | 0 | 12
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X583) | 8 | 100 | 2 | 2 | 31 |  | 1.654 |  |  | 1.654 | 205.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 2 | 4 | 27 |  | 0.732 |  |  | 0.732 | 158.11 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X671) | 8 | 200 | 2 | 1 | 18 |  | 1.83 |  |  | 1.83 | 65.88 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 1 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
1 | SW 8 | 16 |  | 1 | 1 | 40 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0 | 40
|  | 12 |  | 1 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 67.64 | 0 | 0 | 0 | 20
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1183) | 8 | 100 | 1 | 2 | 31 |  | 2.854 |  |  | 2.854 | 176.95 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 1 | 10 | 27 |  | 0.732 |  |  | 0.732 | 197.64 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1216) | 8 | 200 | 1 | 1 | 18 |  | 2.92 |  |  | 2.92 | 52.56 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 1 | 3 | 7 |  | 0.34 |  |  | 0.34 | 7.14 | 0 | 0 | 0 | 0 | 0
6 | SW 9 | 16 |  | 6 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 169.25 | 0 | 0 | 48
|  | 12 |  | 6 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0 | 96
|  | 10 |  | 6 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 198.6 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 6 | 1 | 31 |  | 1.688 |  |  | 1.688 | 313.97 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 6 | 1 | 27 |  | 0.984 |  |  | 0.984 | 159.41 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 27 |  | 0.34 |  |  | 0.34 | 55.08 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 6 | 2 | 31 |  | 1.258 |  |  | 1.258 | 467.98 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 6 | 1 | 27 |  | 1.024 |  |  | 1.024 | 165.89 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 27 |  | 0.34 |  |  | 0.34 | 55.08 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 6 | 1 | 18 |  | 2.62 |  |  | 2.62 | 282.96 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 6 | 2 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
2 | SW 10 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 2 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0 | 40
|  | 10 |  | 2 | 1 | 20 |  | 2.95 |  | 0.36 | 3.31 | 0 | 132.4 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X683) | 8 | 100 | 2 | 2 | 31 |  | 1.854 |  |  | 1.854 | 229.9 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X128) | 8 | 100 | 2 | 4 | 27 |  | 0.744 |  |  | 0.744 | 160.7 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 27 |  | 0.34 |  |  | 0.34 | 36.72 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2061) | 8 | 200 | 2 | 1 | 18 |  | 4.61 |  |  | 4.61 | 165.96 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 5 | 7 |  | 0.34 |  |  | 0.34 | 23.8 | 0 | 0 | 0 | 0 | 0
2 | SW 11 | 16 |  | 2 | 1 | 16 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0 | 32
|  | 12 |  | 2 | 1 | 24 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 162.34 | 0 | 0 | 0 | 48
|  | 10 |  | 2 | 1 | 20 |  | 2.95 |  | 0.36 | 3.31 | 0 | 132.4 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X983) | 8 | 100 | 2 | 2 | 31 |  | 2.454 |  |  | 2.454 | 304.3 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X124) | 8 | 100 | 2 | 8 | 27 |  | 0.736 |  |  | 0.736 | 317.95 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2081) | 8 | 200 | 2 | 1 | 18 |  | 4.65 |  |  | 4.65 | 167.4 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 5 | 7 |  | 0.34 |  |  | 0.34 | 23.8 | 0 | 0 | 0 | 0 | 0
2 | SW 12 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0 | 32
|  | 10 |  | 2 | 1 | 6 |  | 2.95 |  | 0.36 | 3.31 | 0 | 39.72 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 31 |  | 1.688 |  |  | 1.688 | 104.66 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 27 |  | 0.984 |  |  | 0.984 | 53.14 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 27 |  | 0.34 |  |  | 0.34 | 18.36 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 31 |  | 1.258 |  |  | 1.258 | 155.99 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 27 |  | 1.024 |  |  | 1.024 | 55.3 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 27 |  | 0.34 |  |  | 0.34 | 18.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X751) | 8 | 200 | 2 | 1 | 18 |  | 1.99 |  |  | 1.99 | 71.64 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 1 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
2 | SW 13 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0 | 32
|  | 10 |  | 2 | 1 | 22 |  | 2.95 |  | 0.36 | 3.31 | 0 | 145.64 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (140X583) | 8 | 100 | 2 | 2 | 31 |  | 1.608 |  |  | 1.608 | 199.39 | 0 | 0 | 0 | 0 | 0
| BE OTHER (140X133) | 8 | 100 | 2 | 4 | 27 |  | 0.674 |  |  | 0.674 | 145.58 | 0 | 0 | 0 | 0 | 0
| MID MAIN (140X2261) | 8 | 200 | 2 | 1 | 18 |  | 4.93 |  |  | 4.93 | 177.48 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 5 | 7 |  | 0.3 |  |  | 0.3 | 21 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL FROM PLINTH TO 1ST FLOOR LVL | [10 empty] | 4818.3996 | 6767.1141 | 2814.1651 | 5637.993 | 4369.6488 | 1422.96 | 25830.2805
Column From 1st Floor Lvl TO 2ND FLOOR LVL (103.25-106.2)
| C 1 (300X600) | 16 |  | 28 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 394.91 | 0 | 0
|  | 12 |  | 28 | 1 | 10 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 946.96 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 28 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 770.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 407.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 485.99 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 28 | 1 | 9 |  | 1.672 |  |  | 1.672 | 421.34 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 1 | 9 |  | 0.862 |  |  | 0.862 | 217.22 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 272.97 | 0 | 0 | 0 | 0 | 0
| C 2 (300X600) | 16 |  | 12 | 1 | 14 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 592.37 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 12 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 330.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 174.72 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 208.28 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 12 | 1 | 9 |  | 1.672 |  |  | 1.672 | 180.58 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 1 | 9 |  | 0.862 |  |  | 0.862 | 93.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 116.99 | 0 | 0 | 0 | 0 | 0
| C 3 (300X600) | 25 |  | 4 | 1 | 12 |  | 2.95 |  |  | 2.95 | 0 | 0 | 0 | 0 | 0 | 141.6
|  | 20 |  | 4 | 1 | 2 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 29.36 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  | 0.36 | 2.08 | 0 | 133.12 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 4 (300X750) | 20 |  | 16 | 1 | 10 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 587.2 | 0
|  | 16 |  | 16 | 1 | 6 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 338.5 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 16 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 646.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 302.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 353.28 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 134.4 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 16 | 1 | 7 |  | 1.972 |  |  | 1.972 | 220.86 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.896 |  |  | 0.896 | 100.35 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 123.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.38 |  |  | 0.38 | 42.56 | 0 | 0 | 0 | 0 | 0
| C 5 (300X750) | 16 |  | 14 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 197.46 | 0 | 0
|  | 12 |  | 14 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 568.18 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 14 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 565.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 264.32 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 309.12 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 117.6 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 14 | 1 | 7 |  | 1.972 |  |  | 1.972 | 193.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.896 |  |  | 0.896 | 87.81 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 108.11 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.38 |  |  | 0.38 | 37.24 | 0 | 0 | 0 | 0 | 0
| C 6 (300X715) | 16 |  | 10 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
|  | 12 |  | 10 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 405.84 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 10 |  | 1.95 |  |  | 1.95 | 0 | 390 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 188.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 220.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 84 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 8 |  | 1.902 |  |  | 1.902 | 152.16 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.896 |  |  | 0.896 | 71.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 8 |  | 0.5516 |  |  | 0.5516 | 88.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.38 |  |  | 0.38 | 30.4 | 0 | 0 | 0 | 0 | 0
| C 7 (300X800) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 14 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 189.39 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 11 |  | 2.12 |  |  | 2.12 | 0 | 186.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.91 |  |  | 0.91 | 0 | 160.16 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.552 |  |  | 0.552 | 0 | 97.15 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 6 |  | 2.072 |  |  | 2.072 | 49.73 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.862 |  |  | 0.862 | 41.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.5516 |  |  | 0.5516 | 26.48 | 0 | 0 | 0 | 0 | 0
| C 8 (300X600) | 20 |  | 4 | 1 | 4 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 58.72 | 0
|  | 16 |  | 4 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 110.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 9 (300X600) | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0 | 32
|  | 12 |  | 4 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 81.17 | 0 | 0 | 0 | 24
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 104.96 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 55.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 94.21 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 10 |  | 1.608 |  |  | 1.608 | 64.32 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 10 |  | 0.83 |  |  | 0.83 | 33.2 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 10 |  | 0.7 |  |  | 0.7 | 56 | 0 | 0 | 0 | 0 | 0
| C 10 (300X600) | 20 |  | 10 | 1 | 14 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 513.8 | 0 | 140
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 262.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 139.2 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 235.52 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 10 |  | 1.608 |  |  | 1.608 | 160.8 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 10 |  | 0.83 |  |  | 0.83 | 83 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 10 |  | 0.7 |  |  | 0.7 | 140 | 0 | 0 | 0 | 0 | 0
| C 11 (300X715) | 16 |  | 4 | 1 | 12 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 169.25 | 0 | 0 | 48
|  | 12 |  | 4 | 1 | 4 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0 | 16
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 10 |  | 1.87 |  |  | 1.87 | 0 | 149.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 1.072 |  |  | 1.072 | 0 | 85.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 10 |  | 0.736 |  |  | 0.736 | 0 | 117.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 0.4 |  |  | 0.4 | 0 | 32 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.886 |  |  | 1.886 | 67.9 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 1.082 |  |  | 1.082 | 38.95 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.74 |  |  | 0.74 | 53.28 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.404 |  |  | 0.404 | 14.54 | 0 | 0 | 0 | 0 | 0
| Shear wall from 1st floor LVL to 2nd floor lvl | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SW 1 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 52.96 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X866) | 8 | 200 | 2 | 1 | 13 |  | 2.284 |  |  | 2.284 | 59.38 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 2 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 2 | 1 | 13 |  | 2.684 |  |  | 2.684 | 69.78 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 3 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X950) | 8 | 100 | 2 | 1 | 26 |  | 2.452 |  |  | 2.452 | 127.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 2 | 4 | 26 |  | 0.792 |  |  | 0.792 | 164.74 | 0 | 0 | 0 | 0 | 0
| SW 4 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 18 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 121.75 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1100) | 8 | 100 | 2 | 1 | 26 |  | 2.752 |  |  | 2.752 | 143.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X125) | 8 | 100 | 2 | 4 | 26 |  | 0.802 |  |  | 0.802 | 166.82 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| SW 5A | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0
|  | 12 |  | 4 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 270.56 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X583) | 8 | 100 | 4 | 2 | 26 |  | 1.718 |  |  | 1.718 | 357.34 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 4 | 4 | 26 |  | 0.792 |  |  | 0.792 | 329.47 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X516) | 8 | 200 | 4 | 1 | 13 |  | 1.584 |  |  | 1.584 | 82.37 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 4 | 2 | 7 |  | 0.34 |  |  | 0.34 | 19.04 | 0 | 0 | 0 | 0 | 0
| SW 6 | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 270.56 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1135) | 8 | 100 | 4 | 1 | 26 |  | 2.822 |  |  | 2.822 | 293.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X118) | 8 | 100 | 4 | 5 | 26 |  | 0.788 |  |  | 0.788 | 409.76 | 0 | 0 | 0 | 0 | 0
| SW 7A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 22 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 148.81 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X583) | 8 | 100 | 2 | 2 | 26 |  | 1.718 |  |  | 1.718 | 178.67 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 2 | 4 | 26 |  | 0.796 |  |  | 0.796 | 165.57 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X671) | 8 | 200 | 2 | 1 | 13 |  | 1.894 |  |  | 1.894 | 49.24 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 1 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
| SW 8A | 16 |  | 1 | 1 | 16 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 1 | 1 | 40 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X983) | 8 | 100 | 1 | 2 | 26 |  | 2.518 |  |  | 2.518 | 130.94 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 1 | 8 | 26 |  | 0.796 |  |  | 0.796 | 165.57 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1616) | 8 | 200 | 1 | 1 | 13 |  | 3.784 |  |  | 3.784 | 49.19 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 1 | 4 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 9 | 16 |  | 6 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 169.25 | 0 | 0
|  | 12 |  | 6 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
|  | 10 |  | 6 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 198.6 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 6 | 1 | 26 |  | 1.752 |  |  | 1.752 | 273.31 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 6 | 1 | 26 |  | 1.048 |  |  | 1.048 | 163.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 6 | 2 | 26 |  | 1.322 |  |  | 1.322 | 412.46 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 6 | 1 | 26 |  | 1.088 |  |  | 1.088 | 169.73 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 6 | 1 | 13 |  | 2.684 |  |  | 2.684 | 209.35 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 6 | 2 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 10 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 20 |  | 2.95 |  | 0.36 | 3.31 | 0 | 132.4 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X683) | 8 | 100 | 2 | 2 | 26 |  | 1.918 |  |  | 1.918 | 199.47 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X128) | 8 | 100 | 2 | 4 | 26 |  | 0.808 |  |  | 0.808 | 168.06 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 26 |  | 0.34 |  |  | 0.34 | 35.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2061) | 8 | 200 | 2 | 1 | 13 |  | 4.674 |  |  | 4.674 | 121.52 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 5 | 7 |  | 0.34 |  |  | 0.34 | 23.8 | 0 | 0 | 0 | 0 | 0
| SW 11 | 16 |  | 2 | 1 | 16 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0
|  | 12 |  | 2 | 1 | 24 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 162.34 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 20 |  | 2.95 |  | 0.36 | 3.31 | 0 | 132.4 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X983) | 8 | 100 | 2 | 2 | 26 |  | 2.518 |  |  | 2.518 | 261.87 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X124) | 8 | 100 | 2 | 8 | 26 |  | 0.8 |  |  | 0.8 | 332.8 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2081) | 8 | 200 | 2 | 1 | 13 |  | 4.714 |  |  | 4.714 | 122.56 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 5 | 7 |  | 0.34 |  |  | 0.34 | 23.8 | 0 | 0 | 0 | 0 | 0
| SW 12 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 6 |  | 2.95 |  | 0.36 | 3.31 | 0 | 39.72 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X751) | 8 | 200 | 2 | 1 | 13 |  | 2.054 |  |  | 2.054 | 53.4 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 1 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
| SW 13 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 22 |  | 2.95 |  | 0.36 | 3.31 | 0 | 145.64 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (140X583) | 8 | 100 | 2 | 2 | 26 |  | 1.638 |  |  | 1.638 | 170.35 | 0 | 0 | 0 | 0 | 0
| BE OTHER (140X133) | 8 | 100 | 2 | 4 | 26 |  | 0.738 |  |  | 0.738 | 153.5 | 0 | 0 | 0 | 0 | 0
| MID MAIN (140X2261) | 8 | 200 | 2 | 1 | 13 |  | 4.994 |  |  | 4.994 | 129.84 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 5 | 7 |  | 0.3 |  |  | 0.3 | 21 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FROM 1ST TO 2ND FLOOR LVL | [10 empty] | 4333.782 | 5516.7759 | 3872.484 | 4813.4858 | 2925.1368 | 545.16 | 22006.8245
Column From 2 Floor Lvl TO 3 FLOOR LVL (106.2-109.15))
| C 1 (300X600) | 16 |  | 28 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 394.91 | 0 | 0
|  | 12 |  | 28 | 1 | 10 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 946.96 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 28 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 770.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 407.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 485.99 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 28 | 1 | 9 |  | 1.672 |  |  | 1.672 | 421.34 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 1 | 9 |  | 0.862 |  |  | 0.862 | 217.22 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 272.97 | 0 | 0 | 0 | 0 | 0
| C 2 (300X600) | 16 |  | 12 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 423.12 | 0 | 0
|  | 12 |  | 12 | 1 | 4 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 162.34 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 12 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 330.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 174.72 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 208.28 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 12 | 1 | 9 |  | 1.672 |  |  | 1.672 | 180.58 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 1 | 9 |  | 0.862 |  |  | 0.862 | 93.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 116.99 | 0 | 0 | 0 | 0 | 0
| C 3 (300X600) | 25 |  | 4 | 1 | 4 |  | 2.95 |  | 0.9 | 3.85 | 0 | 0 | 0 | 0 | 0 | 61.6
|  | 20 |  | 4 | 1 | 10 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 146.8 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 110.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 4 (300X750) | 20 |  | 16 | 1 | 4 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 234.88 | 0
|  | 16 |  | 16 | 1 | 12 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 676.99 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 16 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 646.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 302.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 353.28 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 134.4 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 16 | 1 | 7 |  | 1.972 |  |  | 1.972 | 220.86 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.896 |  |  | 0.896 | 100.35 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 123.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.38 |  |  | 0.38 | 42.56 | 0 | 0 | 0 | 0 | 0
| C 5 (300X750) | 16 |  | 14 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 197.46 | 0 | 0
|  | 12 |  | 14 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 568.18 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 14 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 565.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 264.32 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 309.12 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 117.6 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 14 | 1 | 7 |  | 1.972 |  |  | 1.972 | 193.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.896 |  |  | 0.896 | 87.81 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 108.11 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.38 |  |  | 0.38 | 37.24 | 0 | 0 | 0 | 0 | 0
| C 6 (300X715) | 16 |  | 10 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
|  | 12 |  | 10 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 405.84 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 10 |  | 1.95 |  |  | 1.95 | 0 | 390 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 188.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 220.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 84 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 8 |  | 1.902 |  |  | 1.902 | 152.16 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.896 |  |  | 0.896 | 71.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 8 |  | 0.5516 |  |  | 0.5516 | 88.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.38 |  |  | 0.38 | 30.4 | 0 | 0 | 0 | 0 | 0
| C 7 (300X800) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 14 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 189.39 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 11 |  | 2.12 |  |  | 2.12 | 0 | 186.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.91 |  |  | 0.91 | 0 | 160.16 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.552 |  |  | 0.552 | 0 | 97.15 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 6 |  | 2.072 |  |  | 2.072 | 49.73 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.862 |  |  | 0.862 | 41.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.5516 |  |  | 0.5516 | 26.48 | 0 | 0 | 0 | 0 | 0
| C 8 (300X600) | 16 |  | 4 | 1 | 14 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 197.46 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 110.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 9 (300X600) | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0 | 32
|  | 12 |  | 4 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 81.17 | 0 | 0 | 0 | 24
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 104.96 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 55.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 94.21 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 10 |  | 1.608 |  |  | 1.608 | 64.32 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 10 |  | 0.83 |  |  | 0.83 | 33.2 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 10 |  | 0.7 |  |  | 0.7 | 56 | 0 | 0 | 0 | 0 | 0
| C 10 (300X600) | 20 |  | 10 | 1 | 8 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 293.6 | 0 | 80
|  | 16 |  | 10 | 1 | 6 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 211.56 | 0 | 0 | 60
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 262.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 139.2 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 235.52 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 10 |  | 1.608 |  |  | 1.608 | 160.8 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 10 |  | 0.83 |  |  | 0.83 | 83 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 10 |  | 0.7 |  |  | 0.7 | 140 | 0 | 0 | 0 | 0 | 0
| C 11 (300X715) | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0 | 32
|  | 12 |  | 4 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0 | 32
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 10 |  | 1.87 |  |  | 1.87 | 0 | 149.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 1.072 |  |  | 1.072 | 0 | 85.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 10 |  | 0.736 |  |  | 0.736 | 0 | 117.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 0.4 |  |  | 0.4 | 0 | 32 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.886 |  |  | 1.886 | 67.9 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 1.082 |  |  | 1.082 | 38.95 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.74 |  |  | 0.74 | 53.28 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.404 |  |  | 0.404 | 14.54 | 0 | 0 | 0 | 0 | 0
| Shear wall from 2nd floor lvl to 3rd floor lvl | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SW 1 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 52.96 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X866) | 8 | 200 | 2 | 1 | 13 |  | 2.284 |  |  | 2.284 | 59.38 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 2 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 2 | 1 | 13 |  | 2.684 |  |  | 2.684 | 69.78 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 3 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X950) | 8 | 100 | 2 | 1 | 26 |  | 2.452 |  |  | 2.452 | 127.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 2 | 4 | 26 |  | 0.792 |  |  | 0.792 | 164.74 | 0 | 0 | 0 | 0 | 0
| SW 4 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 18 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 121.75 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1100) | 8 | 100 | 2 | 1 | 26 |  | 2.752 |  |  | 2.752 | 143.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X125) | 8 | 100 | 2 | 4 | 26 |  | 0.802 |  |  | 0.802 | 166.82 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| SW 5B | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0
|  | 12 |  | 4 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 4 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 105.92 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X383) | 8 | 100 | 4 | 2 | 26 |  | 1.318 |  |  | 1.318 | 274.14 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 4 | 2 | 26 |  | 0.792 |  |  | 0.792 | 164.74 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X916) | 8 | 200 | 4 | 1 | 13 |  | 2.384 |  |  | 2.384 | 123.97 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 4 | 2 | 7 |  | 0.34 |  |  | 0.34 | 19.04 | 0 | 0 | 0 | 0 | 0
| SW 6 | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 270.56 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1135) | 8 | 100 | 4 | 1 | 26 |  | 2.822 |  |  | 2.822 | 293.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X118) | 8 | 100 | 4 | 5 | 26 |  | 0.788 |  |  | 0.788 | 409.76 | 0 | 0 | 0 | 0 | 0
| SW 7B | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X383) | 8 | 100 | 2 | 2 | 26 |  | 1.318 |  |  | 1.318 | 137.07 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 2 | 2 | 26 |  | 0.796 |  |  | 0.796 | 82.78 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1071) | 8 | 200 | 2 | 1 | 13 |  | 2.694 |  |  | 2.694 | 70.04 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 8A | 16 |  | 1 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 1 | 1 | 32 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 1 | 1 | 16 |  | 2.95 |  | 0.36 | 3.31 | 0 | 52.96 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X983) | 8 | 100 | 1 | 2 | 26 |  | 2.518 |  |  | 2.518 | 130.94 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 1 | 8 | 26 |  | 0.796 |  |  | 0.796 | 165.57 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1616) | 8 | 200 | 1 | 1 | 13 |  | 3.784 |  |  | 3.784 | 49.19 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 1 | 4 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 9 | 16 |  | 6 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 169.25 | 0 | 0
|  | 12 |  | 6 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
|  | 10 |  | 6 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 198.6 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 6 | 1 | 26 |  | 1.752 |  |  | 1.752 | 273.31 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 6 | 1 | 26 |  | 1.048 |  |  | 1.048 | 163.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 6 | 2 | 26 |  | 1.322 |  |  | 1.322 | 412.46 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 6 | 1 | 26 |  | 1.088 |  |  | 1.088 | 169.73 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 6 | 1 | 13 |  | 2.684 |  |  | 2.684 | 209.35 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 6 | 2 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 10A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 81.17 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 24 |  | 2.95 |  | 0.36 | 3.31 | 0 | 158.88 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X483) | 8 | 100 | 2 | 2 | 26 |  | 1.518 |  |  | 1.518 | 157.87 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X250) | 8 | 100 | 2 | 2 | 26 |  | 1.052 |  |  | 1.052 | 109.41 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 26 |  | 0.34 |  |  | 0.34 | 35.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2461) | 8 | 200 | 2 | 1 | 13 |  | 5.474 |  |  | 5.474 | 142.32 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 11A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 26 |  | 2.95 |  | 0.36 | 3.31 | 0 | 172.12 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X683) | 8 | 100 | 2 | 2 | 26 |  | 1.918 |  |  | 1.918 | 199.47 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X124) | 8 | 100 | 2 | 4 | 26 |  | 0.8 |  |  | 0.8 | 166.4 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 26 |  | 0.34 |  |  | 0.34 | 35.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2681) | 8 | 200 | 2 | 1 | 13 |  | 5.914 |  |  | 5.914 | 153.76 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 12 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 6 |  | 2.95 |  | 0.36 | 3.31 | 0 | 39.72 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X751) | 8 | 200 | 2 | 1 | 13 |  | 2.054 |  |  | 2.054 | 53.4 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 1 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
| SW 13A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 26 |  | 2.95 |  | 0.36 | 3.31 | 0 | 172.12 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (140X383) | 8 | 100 | 2 | 2 | 26 |  | 1.238 |  |  | 1.238 | 128.75 | 0 | 0 | 0 | 0 | 0
| BE OTHER (140X133) | 8 | 100 | 2 | 2 | 26 |  | 0.738 |  |  | 0.738 | 76.75 | 0 | 0 | 0 | 0 | 0
| MID MAIN (140X2661) | 8 | 200 | 2 | 1 | 13 |  | 5.794 |  |  | 5.794 | 150.64 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.3 |  |  | 0.3 | 25.2 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FROM 2nd TO 3rd FLOOR LVL | [10 empty] | 4084.6634 | 5698.6182 | 3692.0792 | 5281.4502 | 1661.1888 | 237.16 | 20655.1598
Column From 3 Floor Lvl TO 4 FLOOR
| C 1 (300X600) | 16 |  | 28 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 394.91 | 0 | 0
|  | 12 |  | 28 | 1 | 10 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 946.96 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 28 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 770.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 407.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 485.99 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 28 | 1 | 9 |  | 1.672 |  |  | 1.672 | 421.34 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 1 | 9 |  | 0.862 |  |  | 0.862 | 217.22 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 272.97 | 0 | 0 | 0 | 0 | 0
| C 2 (300X600) | 16 |  | 12 | 1 | 6 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 253.87 | 0 | 0
|  | 12 |  | 12 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 12 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 330.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 174.72 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 208.28 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 12 | 1 | 9 |  | 1.672 |  |  | 1.672 | 180.58 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 1 | 9 |  | 0.862 |  |  | 0.862 | 93.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 116.99 | 0 | 0 | 0 | 0 | 0
| C 3 (300X600) | 20 |  | 4 | 1 | 8 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 117.44 | 0
|  | 16 |  | 4 | 1 | 6 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 84.62 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 110.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 4 (300X750) | 16 |  | 16 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 564.16 | 0 | 0
|  | 12 |  | 16 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 16 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 646.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 302.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 353.28 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 134.4 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 16 | 1 | 7 |  | 1.972 |  |  | 1.972 | 220.86 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.896 |  |  | 0.896 | 100.35 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 123.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.38 |  |  | 0.38 | 42.56 | 0 | 0 | 0 | 0 | 0
| C 5 (300X750) | 16 |  | 14 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 197.46 | 0 | 0
|  | 12 |  | 14 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 568.18 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 14 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 565.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 264.32 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 309.12 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 117.6 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 14 | 1 | 7 |  | 1.972 |  |  | 1.972 | 193.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.896 |  |  | 0.896 | 87.81 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 108.11 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.38 |  |  | 0.38 | 37.24 | 0 | 0 | 0 | 0 | 0
| C 6 (300X715) | 16 |  | 10 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
|  | 12 |  | 10 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 405.84 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 10 |  | 1.95 |  |  | 1.95 | 0 | 390 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 188.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 220.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 84 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 8 |  | 1.902 |  |  | 1.902 | 152.16 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.896 |  |  | 0.896 | 71.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 8 |  | 0.5516 |  |  | 0.5516 | 88.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.38 |  |  | 0.38 | 30.4 | 0 | 0 | 0 | 0 | 0
| C 7 (300X800) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 14 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 189.39 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 11 |  | 2.12 |  |  | 2.12 | 0 | 186.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.91 |  |  | 0.91 | 0 | 160.16 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.552 |  |  | 0.552 | 0 | 97.15 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 6 |  | 2.072 |  |  | 2.072 | 49.73 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.862 |  |  | 0.862 | 41.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.5516 |  |  | 0.5516 | 26.48 | 0 | 0 | 0 | 0 | 0
| C 8 (300X600) | 16 |  | 4 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
|  | 12 |  | 4 | 1 | 4 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 110.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 9 (300X600) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 4 | 1 | 10 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0 | 40
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 104.96 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 55.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 94.21 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 10 |  | 1.608 |  |  | 1.608 | 64.32 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 10 |  | 0.83 |  |  | 0.83 | 33.2 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 10 |  | 0.7 |  |  | 0.7 | 56 | 0 | 0 | 0 | 0 | 0
| C 10 (300X600) | 16 |  | 10 | 1 | 14 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 493.64 | 0 | 0 | 140
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 262.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 139.2 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 235.52 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 10 |  | 1.608 |  |  | 1.608 | 160.8 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 10 |  | 0.83 |  |  | 0.83 | 83 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 10 |  | 0.7 |  |  | 0.7 | 140 | 0 | 0 | 0 | 0 | 0
| C 11 (300X715) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 4 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 162.34 | 0 | 0 | 0 | 48
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 10 |  | 1.87 |  |  | 1.87 | 0 | 149.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 1.072 |  |  | 1.072 | 0 | 85.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 10 |  | 0.736 |  |  | 0.736 | 0 | 117.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 0.4 |  |  | 0.4 | 0 | 32 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.886 |  |  | 1.886 | 67.9 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 1.082 |  |  | 1.082 | 38.95 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.74 |  |  | 0.74 | 53.28 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.404 |  |  | 0.404 | 14.54 | 0 | 0 | 0 | 0 | 0
| Shear wall from 3 floor lvl to 4 floor lvl | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SW 1 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 52.96 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X866) | 8 | 200 | 2 | 1 | 13 |  | 2.284 |  |  | 2.284 | 59.38 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 2 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 2 | 1 | 13 |  | 2.684 |  |  | 2.684 | 69.78 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 3 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X950) | 8 | 100 | 2 | 1 | 26 |  | 2.452 |  |  | 2.452 | 127.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 2 | 4 | 26 |  | 0.792 |  |  | 0.792 | 164.74 | 0 | 0 | 0 | 0 | 0
| SW 4 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 18 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 121.75 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1100) | 8 | 100 | 2 | 1 | 26 |  | 2.752 |  |  | 2.752 | 143.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X125) | 8 | 100 | 2 | 4 | 26 |  | 0.802 |  |  | 0.802 | 166.82 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| SW 5B | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0
|  | 12 |  | 4 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 4 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 105.92 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X383) | 8 | 100 | 4 | 2 | 26 |  | 1.318 |  |  | 1.318 | 274.14 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 4 | 2 | 26 |  | 0.792 |  |  | 0.792 | 164.74 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X916) | 8 | 200 | 4 | 1 | 13 |  | 2.384 |  |  | 2.384 | 123.97 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 4 | 2 | 7 |  | 0.34 |  |  | 0.34 | 19.04 | 0 | 0 | 0 | 0 | 0
| SW 6 | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 162.34 | 0 | 0 | 0
|  | 10 |  | 4 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 105.92 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1135) | 8 | 100 | 4 | 1 | 26 |  | 2.822 |  |  | 2.822 | 293.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X118) | 8 | 100 | 4 | 5 | 26 |  | 0.788 |  |  | 0.788 | 409.76 | 0 | 0 | 0 | 0 | 0
| SW 7B | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X383) | 8 | 100 | 2 | 2 | 26 |  | 1.318 |  |  | 1.318 | 137.07 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 2 | 2 | 26 |  | 0.796 |  |  | 0.796 | 82.78 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1071) | 8 | 200 | 2 | 1 | 13 |  | 2.694 |  |  | 2.694 | 70.04 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 8B | 16 |  | 1 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 1 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 67.64 | 0 | 0 | 0
|  | 10 |  | 1 | 1 | 22 |  | 2.95 |  | 0.36 | 3.31 | 0 | 72.82 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X683) | 8 | 100 | 1 | 2 | 26 |  | 1.918 |  |  | 1.918 | 99.74 | 0 | 0 | 0 | 0 | 0 | 683
| BE OTHER (180X122) | 8 | 100 | 1 | 4 | 26 |  | 0.796 |  |  | 0.796 | 82.78 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 400 | 1 | 2 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2216) | 8 | 200 | 1 | 1 | 13 |  | 4.984 |  |  | 4.984 | 64.79 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 1 | 5 | 7 |  | 0.34 |  |  | 0.34 | 11.9 | 0 | 0 | 0 | 0 | 0
| SW 9 | 16 |  | 6 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 169.25 | 0 | 0
|  | 12 |  | 6 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
|  | 10 |  | 6 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 198.6 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 6 | 1 | 26 |  | 1.752 |  |  | 1.752 | 273.31 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 6 | 1 | 26 |  | 1.048 |  |  | 1.048 | 163.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 6 | 2 | 26 |  | 1.322 |  |  | 1.322 | 412.46 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 6 | 1 | 26 |  | 1.088 |  |  | 1.088 | 169.73 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 6 | 1 | 13 |  | 2.684 |  |  | 2.684 | 209.35 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 6 | 2 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 10A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 81.17 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 24 |  | 2.95 |  | 0.36 | 3.31 | 0 | 158.88 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X483) | 8 | 100 | 2 | 2 | 26 |  | 1.518 |  |  | 1.518 | 157.87 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X250) | 8 | 100 | 2 | 2 | 26 |  | 1.052 |  |  | 1.052 | 109.41 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 26 |  | 0.34 |  |  | 0.34 | 35.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2461) | 8 | 200 | 2 | 1 | 13 |  | 5.474 |  |  | 5.474 | 142.32 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 11A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 26 |  | 2.95 |  | 0.36 | 3.31 | 0 | 172.12 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X683) | 8 | 100 | 2 | 2 | 26 |  | 1.918 |  |  | 1.918 | 199.47 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X124) | 8 | 100 | 2 | 4 | 26 |  | 0.8 |  |  | 0.8 | 166.4 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 26 |  | 0.34 |  |  | 0.34 | 35.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2681) | 8 | 200 | 2 | 1 | 13 |  | 5.914 |  |  | 5.914 | 153.76 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 12 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 6 |  | 2.95 |  | 0.36 | 3.31 | 0 | 39.72 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X751) | 8 | 200 | 2 | 1 | 13 |  | 2.054 |  |  | 2.054 | 53.4 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 1 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
| SW 13A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 26 |  | 2.95 |  | 0.36 | 3.31 | 0 | 172.12 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (140X383) | 8 | 100 | 2 | 2 | 26 |  | 1.238 |  |  | 1.238 | 128.75 | 0 | 0 | 0 | 0 | 0
| BE OTHER (140X133) | 8 | 100 | 2 | 2 | 26 |  | 0.738 |  |  | 0.738 | 76.75 | 0 | 0 | 0 | 0 | 0
| MID MAIN (140X2661) | 8 | 200 | 2 | 1 | 13 |  | 5.794 |  |  | 5.794 | 150.64 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.3 |  |  | 0.3 | 25.2 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Column From 3 Floor Lvl TO 4 FLOOR | [10 empty] | 4048.6197 | 5776.2244 | 4137.0593 | 5147.7506 | 288.9024 | 0 | 19398.5564
Column From 4 Floor Lvl TO 5 FLOOR
| C 1 (300X600) | 16 |  | 28 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 394.91 | 0 | 0
|  | 12 |  | 28 | 1 | 10 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 946.96 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 28 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 770.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 407.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 28 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 485.99 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 28 | 1 | 9 |  | 1.672 |  |  | 1.672 | 421.34 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 1 | 9 |  | 0.862 |  |  | 0.862 | 217.22 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 28 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 272.97 | 0 | 0 | 0 | 0 | 0
| C 2 (300X600) | 16 |  | 12 | 1 | 6 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 253.87 | 0 | 0
|  | 12 |  | 12 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 12 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 330.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 174.72 | 0 | 0 | 0 | 0
|  | 10 | 75 | 12 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 208.28 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 12 | 1 | 9 |  | 1.672 |  |  | 1.672 | 180.58 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 1 | 9 |  | 0.862 |  |  | 0.862 | 93.1 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 12 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 116.99 | 0 | 0 | 0 | 0 | 0
| C 3 (300X600) | 16 |  | 4 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
|  | 20 |  | 4 | 1 | 4 |  | 2.95 |  | 0.72 | 3.67 | 0 | 0 | 0 | 0 | 58.72 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 110.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 4 (300X750) | 16 |  | 16 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 564.16 | 0 | 0
|  | 12 |  | 16 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 16 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 646.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 302.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 353.28 | 0 | 0 | 0 | 0
|  | 10 | 75 | 16 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 134.4 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 16 | 1 | 7 |  | 1.972 |  |  | 1.972 | 220.86 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.896 |  |  | 0.896 | 100.35 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 123.56 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 16 | 1 | 7 |  | 0.38 |  |  | 0.38 | 42.56 | 0 | 0 | 0 | 0 | 0
| C 5 (300X750) | 16 |  | 14 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 197.46 | 0 | 0
|  | 12 |  | 14 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 568.18 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 14 | 2 | 10 |  | 2.02 |  |  | 2.02 | 0 | 565.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 264.32 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 309.12 | 0 | 0 | 0 | 0
|  | 10 | 75 | 14 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 117.6 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 14 | 1 | 7 |  | 1.972 |  |  | 1.972 | 193.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.896 |  |  | 0.896 | 87.81 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 2 | 7 |  | 0.5516 |  |  | 0.5516 | 108.11 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 14 | 1 | 7 |  | 0.38 |  |  | 0.38 | 37.24 | 0 | 0 | 0 | 0 | 0
| C 6 (300X715) | 16 |  | 10 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
|  | 12 |  | 10 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 405.84 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 10 |  | 1.95 |  |  | 1.95 | 0 | 390 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.944 |  |  | 0.944 | 0 | 188.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 10 |  | 0.552 |  |  | 0.552 | 0 | 220.8 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 10 |  | 0.42 |  |  | 0.42 | 0 | 84 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 8 |  | 1.902 |  |  | 1.902 | 152.16 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.896 |  |  | 0.896 | 71.68 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 8 |  | 0.5516 |  |  | 0.5516 | 88.26 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 8 |  | 0.38 |  |  | 0.38 | 30.4 | 0 | 0 | 0 | 0 | 0
| C 7 (300X800) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 14 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 189.39 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 11 |  | 2.12 |  |  | 2.12 | 0 | 186.56 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.91 |  |  | 0.91 | 0 | 160.16 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 11 |  | 0.552 |  |  | 0.552 | 0 | 97.15 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 6 |  | 2.072 |  |  | 2.072 | 49.73 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.862 |  |  | 0.862 | 41.38 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 6 |  | 0.5516 |  |  | 0.5516 | 26.48 | 0 | 0 | 0 | 0 | 0
| C 8 (300X600) | 16 |  | 4 | 1 | 10 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 141.04 | 0 | 0
|  | 12 |  | 4 | 1 | 4 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.72 |  |  | 1.72 | 0 | 110.08 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.91 |  |  | 0.91 | 0 | 58.24 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.5424 |  |  | 0.5424 | 0 | 69.43 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.672 |  |  | 1.672 | 60.19 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.862 |  |  | 0.862 | 31.03 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.5416 |  |  | 0.5416 | 39 | 0 | 0 | 0 | 0 | 0
| C 9 (300X600) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 4 | 1 | 10 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0 | 40
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 104.96 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 55.68 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 94.21 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 10 |  | 1.608 |  |  | 1.608 | 64.32 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 10 |  | 0.83 |  |  | 0.83 | 33.2 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 10 |  | 0.7 |  |  | 0.7 | 56 | 0 | 0 | 0 | 0 | 0
| C 10 (300X600) | 16 |  | 10 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 282.08 | 0 | 0 | 80
|  | 12 |  | 10 | 1 | 6 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 202.92 | 0 | 0 | 0 | 60
| Stirrups ZONE A | 10 | 75 | 10 | 2 | 8 |  | 1.64 |  |  | 1.64 | 0 | 262.4 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 2 | 8 |  | 0.87 |  |  | 0.87 | 0 | 139.2 | 0 | 0 | 0 | 0
|  | 10 | 75 | 10 | 4 | 8 |  | 0.736 |  |  | 0.736 | 0 | 235.52 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 10 | 1 | 10 |  | 1.608 |  |  | 1.608 | 160.8 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 1 | 10 |  | 0.83 |  |  | 0.83 | 83 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 10 | 2 | 10 |  | 0.7 |  |  | 0.7 | 140 | 0 | 0 | 0 | 0 | 0
| C 11 (300X715) | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0 | 16
|  | 12 |  | 4 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 162.34 | 0 | 0 | 0 | 48
| Stirrups ZONE A | 10 | 75 | 4 | 2 | 10 |  | 1.87 |  |  | 1.87 | 0 | 149.6 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 1.072 |  |  | 1.072 | 0 | 85.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 4 | 10 |  | 0.736 |  |  | 0.736 | 0 | 117.76 | 0 | 0 | 0 | 0
|  | 10 | 75 | 4 | 2 | 10 |  | 0.4 |  |  | 0.4 | 0 | 32 | 0 | 0 | 0 | 0
| Stirrups ZONE B | 8 | 150 | 4 | 1 | 9 |  | 1.886 |  |  | 1.886 | 67.9 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 1.082 |  |  | 1.082 | 38.95 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 2 | 9 |  | 0.74 |  |  | 0.74 | 53.28 | 0 | 0 | 0 | 0 | 0
|  | 8 | 150 | 4 | 1 | 9 |  | 0.404 |  |  | 0.404 | 14.54 | 0 | 0 | 0 | 0 | 0
| Shear wall from 3 floor lvl to 4 floor lvl | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SW 1 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 52.96 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X866) | 8 | 200 | 2 | 1 | 13 |  | 2.284 |  |  | 2.284 | 59.38 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 2 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 2 | 1 | 13 |  | 2.684 |  |  | 2.684 | 69.78 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 3 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X950) | 8 | 100 | 2 | 1 | 26 |  | 2.452 |  |  | 2.452 | 127.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 2 | 4 | 26 |  | 0.792 |  |  | 0.792 | 164.74 | 0 | 0 | 0 | 0 | 0
| SW 4 | 16 |  | 2 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 2 | 1 | 18 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 121.75 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1100) | 8 | 100 | 2 | 1 | 26 |  | 2.752 |  |  | 2.752 | 143.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X125) | 8 | 100 | 2 | 4 | 26 |  | 0.802 |  |  | 0.802 | 166.82 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| SW 5B | 16 |  | 4 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 112.83 | 0 | 0
|  | 12 |  | 4 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 4 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 105.92 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X383) | 8 | 100 | 4 | 2 | 26 |  | 1.318 |  |  | 1.318 | 274.14 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X120) | 8 | 100 | 4 | 2 | 26 |  | 0.792 |  |  | 0.792 | 164.74 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X916) | 8 | 200 | 4 | 1 | 13 |  | 2.384 |  |  | 2.384 | 123.97 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 4 | 2 | 7 |  | 0.34 |  |  | 0.34 | 19.04 | 0 | 0 | 0 | 0 | 0
| SW 6 | 16 |  | 4 | 1 | 4 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 4 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 162.34 | 0 | 0 | 0
|  | 10 |  | 4 | 1 | 8 |  | 2.95 |  | 0.36 | 3.31 | 0 | 105.92 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X1135) | 8 | 100 | 4 | 1 | 26 |  | 2.822 |  |  | 2.822 | 293.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X118) | 8 | 100 | 4 | 5 | 26 |  | 0.788 |  |  | 0.788 | 409.76 | 0 | 0 | 0 | 0 | 0
| SW 7B | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 66.2 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X383) | 8 | 100 | 2 | 2 | 26 |  | 1.318 |  |  | 1.318 | 137.07 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X122) | 8 | 100 | 2 | 2 | 26 |  | 0.796 |  |  | 0.796 | 82.78 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1071) | 8 | 200 | 2 | 1 | 13 |  | 2.694 |  |  | 2.694 | 70.04 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 2 | 7 |  | 0.34 |  |  | 0.34 | 9.52 | 0 | 0 | 0 | 0 | 0
| SW 8B | 16 |  | 1 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 28.21 | 0 | 0
|  | 12 |  | 1 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 67.64 | 0 | 0 | 0
|  | 10 |  | 1 | 1 | 22 |  | 2.95 |  | 0.36 | 3.31 | 0 | 72.82 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X683) | 8 | 100 | 1 | 2 | 26 |  | 1.918 |  |  | 1.918 | 99.74 | 0 | 0 | 0 | 0 | 0 | 683
| BE OTHER (180X122) | 8 | 100 | 1 | 4 | 26 |  | 0.796 |  |  | 0.796 | 82.78 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 400 | 1 | 2 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2216) | 8 | 200 | 1 | 1 | 13 |  | 4.984 |  |  | 4.984 | 64.79 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 1 | 5 | 7 |  | 0.34 |  |  | 0.34 | 11.9 | 0 | 0 | 0 | 0 | 0
| SW 9 | 16 |  | 6 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 169.25 | 0 | 0
|  | 12 |  | 6 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 324.67 | 0 | 0 | 0
|  | 10 |  | 6 | 1 | 10 |  | 2.95 |  | 0.36 | 3.31 | 0 | 198.6 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 6 | 1 | 26 |  | 1.752 |  |  | 1.752 | 273.31 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 6 | 1 | 26 |  | 1.048 |  |  | 1.048 | 163.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 6 | 2 | 26 |  | 1.322 |  |  | 1.322 | 412.46 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 6 | 1 | 26 |  | 1.088 |  |  | 1.088 | 169.73 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 6 | 1 | 26 |  | 0.34 |  |  | 0.34 | 53.04 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X1066) | 8 | 200 | 6 | 1 | 13 |  | 2.684 |  |  | 2.684 | 209.35 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 6 | 2 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 10A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 12 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 81.17 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 24 |  | 2.95 |  | 0.36 | 3.31 | 0 | 158.88 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X483) | 8 | 100 | 2 | 2 | 26 |  | 1.518 |  |  | 1.518 | 157.87 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X250) | 8 | 100 | 2 | 2 | 26 |  | 1.052 |  |  | 1.052 | 109.41 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 26 |  | 0.34 |  |  | 0.34 | 35.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2461) | 8 | 200 | 2 | 1 | 13 |  | 5.474 |  |  | 5.474 | 142.32 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 11A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 20 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 135.28 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 26 |  | 2.95 |  | 0.36 | 3.31 | 0 | 172.12 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X683) | 8 | 100 | 2 | 2 | 26 |  | 1.918 |  |  | 1.918 | 199.47 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X124) | 8 | 100 | 2 | 4 | 26 |  | 0.8 |  |  | 0.8 | 166.4 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 2 | 26 |  | 0.34 |  |  | 0.34 | 35.36 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X2681) | 8 | 200 | 2 | 1 | 13 |  | 5.914 |  |  | 5.914 | 153.76 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.34 |  |  | 0.34 | 28.56 | 0 | 0 | 0 | 0 | 0
| SW 12 | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 16 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 108.22 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 6 |  | 2.95 |  | 0.36 | 3.31 | 0 | 39.72 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X600) | 8 | 100 | 2 | 1 | 26 |  | 1.752 |  |  | 1.752 | 91.1 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X248) | 8 | 100 | 2 | 1 | 26 |  | 1.048 |  |  | 1.048 | 54.5 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| BE MAIN (180X385) | 8 | 100 | 2 | 2 | 26 |  | 1.322 |  |  | 1.322 | 137.49 | 0 | 0 | 0 | 0 | 0
| BE OTHER (180X268) | 8 | 100 | 2 | 1 | 26 |  | 1.088 |  |  | 1.088 | 56.58 | 0 | 0 | 0 | 0 | 0
| BE OTHER | 8 | 100 | 2 | 1 | 26 |  | 0.34 |  |  | 0.34 | 17.68 | 0 | 0 | 0 | 0 | 0
| MID MAIN (180X751) | 8 | 200 | 2 | 1 | 13 |  | 2.054 |  |  | 2.054 | 53.4 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 1 | 7 |  | 0.34 |  |  | 0.34 | 4.76 | 0 | 0 | 0 | 0 | 0
| SW 13A | 16 |  | 2 | 1 | 8 |  | 2.95 |  | 0.576 | 3.526 | 0 | 0 | 0 | 56.42 | 0 | 0
|  | 12 |  | 2 | 1 | 8 |  | 2.95 |  | 0.432 | 3.382 | 0 | 0 | 54.11 | 0 | 0 | 0
|  | 10 |  | 2 | 1 | 26 |  | 2.95 |  | 0.36 | 3.31 | 0 | 172.12 | 0 | 0 | 0 | 0
| Stirrups | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BE MAIN (140X383) | 8 | 100 | 2 | 2 | 26 |  | 1.238 |  |  | 1.238 | 128.75 | 0 | 0 | 0 | 0 | 0
| BE OTHER (140X133) | 8 | 100 | 2 | 2 | 26 |  | 0.738 |  |  | 0.738 | 76.75 | 0 | 0 | 0 | 0 | 0
| MID MAIN (140X2661) | 8 | 200 | 2 | 1 | 13 |  | 5.794 |  |  | 5.794 | 150.64 | 0 | 0 | 0 | 0 | 0
| MID OTHER | 8 | 400 | 2 | 6 | 7 |  | 0.3 |  |  | 0.3 | 25.2 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Column From 3 Floor Lvl TO 4 FLOOR | [10 empty] | 4048.6197 | 5776.2244 | 4317.4552 | 4902.6294 | 144.4512 | 0 | 19189.3799